## Slide 1: COMS Nodal Commercial Systems Project Update
COPs Meeting
July 2007
Justin Rasberry & Bill Barnes

## Slide 2: Agenda
Item | Purpose | Presenter
Deliverables Update | For Information | Bill Barnes
Delivery Schedule Update | For Information | Justin Rasberry
Questions | For Information | Bill and Justin

## Slide 3: COMS Requirements Update
ERCOT is nearly complete syncing all projects to the March 2007 Protocols and a number of NPRRs and whitepapers (termed Baseline 1).
The baseline sync is needed to make sure all projects can communicate data appropriately with one another
Baseline 2 synchronization has begun. Activities around baseline 2 should conclude by August 2007
ERCOT is anticipating at least 3 baselines before Go Live
All associated documentation (use cases, CSDs, test cases, etc) will be updated as Baselines approved
New document naming convention will in place for all baseline 1 and future baseline versions.
COPs personnel should stay abreast with COMS requirements.

## Slide 4: COMS Requirements Update
The following COMS Requirements are approved by TPTF as version 2.0:
  AIEC
  DAM, 3 documents -- Energy, AS, and Make Whole
  RUC
  Eligibility
  Statements and Invoices, 2 documents
  Financial Transfer
  Real Time Operations, 6 documents – AS, Energy, Voltage, Emergency Operations, RMR, and Black Start
  Registration
  CRR Requirements
The following COMS requirements version 1.1 were submitted at May 23 TPTF
  Data Aggregation Requirements
The following COMS requirements version 1.1 will be reviewed at the July 9 TPTF meeting
  CMM Requirements and CSD
All documents are going through the TPTF approval cycle and should be updated by July 2007

## Slide 5: COMS CSD Update
The following COMS Conceptual System Designs (CSDs) were being submitted to TPTF as version 1.1 on May 23:
  Registration
  AIEC
  CRR
  DAM
  Eligibility
  Financial Transfer
  Statements
  Invoices
  RUC
The following COMS Conceptual System Design (CSDs) will be discussed at the July 9 TPTF:
  CMM

## Slide 6: Nodal Settlements Mini Market Examples
Nodal Settlements Mini Market Examples
  Published June 29th
  SDAWG review meeting July 26th & July 27th
  Agenda
  RSVP
  Please review beforehand, bring/submit questions
    Tips: Review examples with Nodal Protocols and Requirements
Day 1 – 9:30am | Day 2 – 9:30am
DAM AIEC RUC | Carry over from Day 1 RTM Settlement Ancillary Services Black Start Voltage Support RMR Base Point Deviation RT Energy Imbalance Emergency Operations Revenue Neutrality Fees CRR Settlements

## Slide 7: Statements and Invoice – Presentation Format
Background: During summer of 2006, COPS & ERCOT discussed and agreed to design concepts impacting nodal settlement statements.
  No PRICE, QUANTITY, BILLABLE QUANTITY data.
  BILL AMOUNT calculated and shown at Operating Day/Charge Type summary level per settlement run per Statement Recipient.
    Not interval level
  Statements will not repeat previous settlement interval level data.
  Statements show settlement amounts at Operating Day/Charge Type level per settlement interval.
ERCOT staff used these design concepts with Nodal Protocols to design and build Settlement Statements
Next Step: Finalize Statement presentation format
  In other words, how the data appears on the web page
  Recommended approach: ERCOT prepares options and brings to COPs/SDAWG for discussion and eventual vote
  Review Statement Summary page and Statement Detail page
Next Next Step: Repeat the process for all Invoices

## Slide 8: Development Update
Detailed Design on task
  Should have drafts of Detailed Design documents by early 3Q2007
  Functional Decompositions completed in April 2007 on base coding
Lodestar version 4.7 successfully delivered in April 2007
  Code base which will be used to build Nodal
  Have had a number of defects and working Lodestar to correct
Lodestar metadata changes version 4 complete
  Metadata changes have been delivered to ERCOT and applied to Lodestar 4.7 schema
Should have Statements and Invoice mock displays ready for COPs/TPTF by July 2007
Plan to start unit testing as early as Summer 2007 to meet EDS timeline
  Initial testing at the Modular level and will “build up” to batch

## Slide 9: Development Update
Most build packages consists of multiple modules
  Modules aligned into business functional components (i.e. DAM Energy, DAM AS, CRR, etc.)
Target FAT completion by mid 4th quarter 2007
Target SAT completion by early 1st quarter 2008
Currently, Lodestar S&B slated for EDS 3 & 4
  Statements and Invoice format for EDS 3
  Shadow Settlements EDS 4 (requires Extracts)
Settlements Go Live with 1st CRR auction

## Slide 10: Questions ??