## Slide 1: Testing Update
Glen Wingerd
Project Manager - INT

## Slide 2: Testing Update - INT
Agenda
  Current Testing Efforts
  Testing Metrics
  Supporting information

## Slide 3: Testing Update - INT
CMM (Base Product) –7/6/07
  We have currently executed 174 of 202 total scripts.
    Pass = 141
    Fail = 33
    % Complete = 70%
  DEFECTS
    There are currently 40 Active Defects
    There have been 10 Defects addressed and Closed.
EIP3 (Loopback) – 7/9/07
  We have currently executed 127 of 132 total scripts
    Pass = 126
    Fail = 1
    % Complete = 94.45%
  DEFECTS
    There is currently 1 Active Defects
    There have been 31 Defects addressed and Closed

## Slide 4: Testing Update - INT
Excludes defects with status of “Invalid”

## Slide 5: Testing Update - INT

## Slide 6: Testing Update - INT
Only “approved” test scripts in Quality Center
No inferred traceability

## Slide 7: Testing Update - INT
Only measures closed defects, not defects that are still open

## Slide 8: Testing Update - INT
Most recent run

## Slide 9: Testing Update - INT
Most recent run

## Slide 10: Testing Update - INT
Traceability
Does not require the Script be approved

## Slide 11: Testing Update - INT
Quality measurement
Measures against approved Test Scripts
Does not include “Invalid” defects

## Slide 12: Testing Update - INT
Deferred status common with planned iterations
Severity 1 and 2 not eligible for deferral

## Slide 13: Testing Update - INT
Severity is set by Testing and verified by business

## Slide 14: Testing Update - INT
On the Horizon
  EIP3 (Backend) - August
  MIS – August
  CRR – September
  CMM (w/ ERCOT customs) – Q3
  COMS – REG2 – Q3

## Slide 15: Testing Update - INT
Questions?

## Slide 16: Testing Overview - INT
Testing Phases

## Slide 17: Testing Overview - INT
Execution of Testing by Phase

## Slide 18: Testing Overview - INT
Testing Types

## Slide 19: Testing Overview - INT
Testing Environments

## Slide 20: Testing Overview - INT
Testing Artifacts

## Slide 21: Testing Overview - INT
Traceability

## Slide 22: Testing Overview - INT
Defect Tracking Status Lifecycle
Once Defects are assigned they are tracked using the status lifecycle.