## Slide 1: RO Projects Financial Overview Retail Market Subcommittee July 10, 2007 Justin Rasberry Market Operations Division Projects Organization

## Slide 2: 2007 RO PPL
Unplanned 2006 Carry-over Projects
(Green Shaded Area)
Projects ABOVE the current Capability Line
(Orange Shaded Area)
Projects BELOW the current Capability Line
(Yellow Shaded Area)

## Slide 3: Unplanned 2006 Carry-Over Projects
Complete
PR50121_07 Retail Business Processes (SOA) moved to Complete
PR50121_08 Endpoint Services Ph II & III (SOA) moved to Complete
Other Changes
Removed Majordomo Replacement from 2007 PPL as this was cancelled in 2006.

## Slide 4: Projects ABOVE the Capability Line
TX SET 3.0 Migrated to production, Moving to Closing mid July

## Slide 5: Projects BELOW the Capability Line
PR 60007_01, Performance Measure Reporting Requirements project remains right under the capability line awaiting pending PUCT action

## Slide 6: Financial Overview as of 6/29/2007
As communicated at May RMS, the DPO fully expected that we may see the variance rise as we complete the 2008 PPL planning process and active project in Planning can more fully identify spend expectations for 2007 and carry-overs into 2008
Expect Performance Measures Project to initiate in 2007 that will be able to use funds from the variance.
RO PPL Budget Activity | Amount | Notes/comments
Approved RO Capability Line Budget Funding | $5.17M | Previously reported as $4.88M, PPL corrections Current approved RO funding allocation Designates where the capability line falls
Current Forecast Spend of projects above the Capability Line | $3.42M | Based on current expectations and run rates for active and not started projects above the capability line Budget range of $3M – $4M
Budget Variance | ~$1.74M | Budget Variance is difference between RO Capability Line Budget Funding and Current Forecast Spend of projects above the Capability Line $1.13M due to amounts forecasted into 2008 for current projects $440,000 resulting from projects running under budget Budget Variance could be applied to the funding required for the Performance Measures Reporting project CART will need to evaluate when to release the funds as other CARTS are requesting more funds.

## Slide 7: Questions / Contact
Justin Rasberry
Manager, MO DPO
Market Operations Divisional Projects Organization
ERCOT
(512) 248-3991
jrasberry@ercot.com