## TPTF Comments & Responses
Document Name: |  |  |  |  | Service Level Agreement - Nodal EDS Environments v0.92
S.No. | Issuing Entity (Name) | Page Number (Red Line Doc) | Section | Item | Description | Response Type | Reviewer | Reason / Comment
1 | Reliant (F. Trefny) |  | Title Page |  | This agreement covers EDS 1 and EDS 2 but EDS 2 overlaps EDS 3 in time. This level of service is likely OK during the EDS 1 testing but in EDS 2 the work of EDS 3 will be going on at the same time. | Accepted | R Sarasa | [ERCOT] The document structure and content changed based on meeting with TPTF (F Trefny) on 07/17/07. Service Levels are represented by time periods, and not by EDS phases.
2 | Reliant (F. Trefny) |  | Title Page |  | It seems like it may be better to have Service Level Agreements that are in place during EDS testing and are superseded at future planned dates to increase Service Levels as the need for more testing time comes into action. For example, one level for July through September, increased levels from October through February 2008 and 24 hour support by March 2008. | Accepted | R Sarasa | [ERCOT] The document structure and content changed based on meeting with TPTF (F Trefny) on 07/17/07. Service Levels are represented by time periods, and not by EDS phases.
3 | Reliant (F. Trefny) |  |  |  | § EDS 1 will involve heavy person-to-person interaction between ERCOT and each of the Transmission and Generation market participants. During Release 2, both ERCOT and market participant operators will be logged into EDS 1 systems and perform ICCP labor-intensive point-to-point verification. | Clarification Provided | R Sarasa | [ERCOT] Document structure and content changed. Sentence not used.
4 | Reliant (F. Trefny) |  |  |  | Further, EDS 2 will involve on-demand browser-based interaction from market participants, randomly accessing reports from the MIS portal or submitting NOMCR or other Change Requests for network operations model changes. | Clarification Provided* | R Sarasa | [ERCOT] Document structure and content changed. Sentence not used.
5 | Reliant (F. Trefny) |  |  |  | Support Hours: 8 AM – 5 PM CT Business Days (unless otherwise prearranged by ERCOT Operations to support off primary shift testing) | Clarification Provided | R Sarasa | [ERCOT] Document structure and content changed. Paragraph not used.
6 | Reliant (F. Trefny) |  |  |  | 98% during Support Hours (priority should be given to testing teams schedule who may be working extra hours to perform tests) | Clarification Provided | R Sarasa | [ERCOT] Document structure and content changed. Paragraph not used.
7 | Reliant (F. Trefny) |  |  |  | Scheduled maintenance windows are as follows: Business Days: 5 PM till next morning 8 AM CT Wednesdays: 9 AM – 11 AM CT Exceptions will be granted to off hours testing that has been prearranged Non-business Days: 24 hours Exceptions will be granted to off hours testing that has been prearranged | Clarification Provided | R Sarasa | [ERCOT] Document structure and content changed. Paragraph not used.
8 | Reliant (F. Trefny) |  |  |  | Scheduled maintenance will be scheduled to not interfere with scheduled testing activities of ERCOT and TSP/QSE operations | Clarification Provided | R Sarasa | [ERCOT] Document structure and content changed. Original paragraph (relevent to this comment) is not used.
9 | Reliant (F. Trefny) |  |  |  | Market Participants can may access systems via secure connection from any location that is in compliance with ERCOT Access standards and ERCOT Nodal Protocols. | Clarification Provided | R Sarasa | [ERCOT] Document structure and content changed. Sentence not used.
10 | Reliant (F. Trefny) |  |  |  | Is this right or should it be during scheduled conference called between ERCOT testing teams and MPs? | Clarification Provided | R Sarasa | [ERCOT] Document structure and content changed. Original paragraph (relevent to this comment) is not used.
11 | Reliant (F. Trefny) |  |  |  | Low: Calls seeking clarifications or requests for configuration / setup help. This may be higher is schedule for completion of testing is impacted. Medium: Problems / Issues that adversely impact part of the intended functionality, or produce incorrect results. | Clarification Provided | R Sarasa | [ERCOT] Document structure and content changed. Paragraph not used.
12 | Reliant (F. Trefny) |  |  |  | Are these the same lines used for normal zonal problems. Will there be special lines for Nodal? | Clarification Provided | R Sarasa | [ERCOT] Document structure and content changed. Section 4 addresses support contact information in the new structure. HelpDesk contact number is the same as used for Zonal production environment.
13 | Reliant (F. Trefny) |  |  |  | Is this table of response times compatiable with having testing personnel standing by for a fix? Suggest we need to have dedicated teams for Nodal. | Clarification Provided | R Sarasa | [ERCOT] Document structure and content changed. Table not used.
14 | Reliant (F. Trefny) |  |  |  | Is this table of response times compatiable with having testing personnel standing by for a fix? Suggest we need to have dedicated teams for Nodal. | Clarification Provided | R Sarasa | [ERCOT] Document structure and content changed. Table not used.

## Punch List
Document Name:
Punch List # | Punch List Description | Related TPTF Comment

## Data Entry Lists
Response | Description
Accepted | Comment accepted and requirements document updated as per the comment.
Clarification Provided* | Clarification provided and requirements document updated to clarify
Clarification Provided | Clarification provided and no updates made to the requirements document.
Pending | Issue is not resolved yet. All pending issues will be dispositioned to a punch list and resolved later. These issues need more time and coordination across multiple Nodal projects.
Rejected | Comment rejected as it does not comply with Nodal Protocols.