## Nodal Project Schedule
Texas Nodal Market Implementation Schedule
Features | Project | Readiness Criteria Measurement Begins | GO-LIVE | Performance Measured | Compliance Application | Status G/Y/R | Prev Status | Mitigation Activities | Comments
EDS 1 '- Base EMS Platform (Replication, Failover etc.,) - Base EMS Data Models - Base Alarm function - Base SCADA functions - Base State Estimator - Base Network Security Analysis (RT/ST) - Base Power Flow | EMS 1 | 2007-07-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
OAG 2.4 Base to address dual redundant ICCP from TSP and QSE | EMS 2 A | 2007-07-01 | 2007-10-01 | 2008-01-01 | 2008-04-30
EDS 2 State Estimator - State Estimator Performance Standards SCADA - Telemetry Performance Standards - RT Weather Zone calculations - Dynamic Ratings for single model - FOD – Actual Outage Detection NSA - SPS/RAP - Constraint Management (RT Tracki | EMS 2 B EDW 1 | 2007-09-01 | 2008-06-01 | 2008-08-01 | 2008-11-29
EDS 2 ' - Full CIM model - Base capability to add changes - Testing initial load from EMS - Testing NMMS to EMS functionality | NMMS 1 | 2007-11-01 | 2007-12-01 | 2008-02-01 | 2008-05-31
- PTC UI - PTC Schema - Interfaces for NOMCR, PMCR - Full Case Builder | NMMS 2 | 2008-01-01 | 2007-12-01 | 2008-04-01 | 2008-07-30
Areva NMMS to EMS model | EIP 1 | 2007-12-01 | 2007-12-01 | 2008-04-01 | 2008-07-30 |  |  | Need FAT start date from project
EDS 3 ' - Registration for MPs - Registration of CRR Account holders - Ability for MPs to submit forms on-line | REG 1 EIP2 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2008-01-29
- SCED - All MMS components used by SCED to compute LMPs - COP - Energy Offer Curves - Inc / Dec offer Curves - Output Schedules | MMS 1 | 2007-10-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
- Verifiable Costs - FIP - FOP | S&B 1 | 2008-04-01 | 2008-06-01 | 2009-02-01 | 2009-06-01
- Search - Link to EDW (MIR) - Link to public data (ERCOT.com) - Click thru screens - Links to applications as available | MIS 1 | 2008-04-01 | 2008-06-01 | 2008-08-01 | 2008-11-29
NSA - Calculation of Shift Factors - MVA to MW conversion for constraints - Constraint Direction Generation Sub-system - Resource Limit Calculator | EMS 2 C | 2008-02-01 | 2008-06-01 | 2008-12-01 | 2009-03-31
- Priority 1 External Web Services - EMS to MMS for LMP testing - MMS to EMS for LMP testing - Registration to MMS | EIP 3 | 2007-10-01 | 2007-10-01 | 2007-12-01 | 2008-03-30 |  |  | Need FAT start date from project
EDS 3 Release 6 & 7 MTLF ported from current Zonal Final Build of - State Estimator - RT NSA including Stability applications and TCM - Generation Sub-system | EMS 3 EIP 4 |  |  | 2007-10-09 | 2008-02-06
Credit Monitoring | CMM 1 | 2008-01-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
- Ability to upload Input data or enter them manually via CRR UI - All CRR components necessary to run CRR Markets - CRR Database Subsystem - CRR Calculation Engine - CRR Data Interface Subsystem - CRR Market Operator and Market Participant UI | CRR 1 EIP 5 | 2008-01-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 4 Release 8 Full MMS - RUC - SASM - DAM - CCT - Settlements Interface | MMS 2 |  |  | 2007-09-25 | 2008-01-23
Full Settlements & Billing, Statements & Invoices | S&B2 EIP6 | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
EDS 4 Release 9 Baseline 1 Baseline 2 | MMS 3 | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
Outage Scheduler | OS 1 | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
PTC Updates Time based MP editing model Case builder to create time based model Outages Contingency Editor Fully defined Model management system | NMMS 3 | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
Final Build of - MTLF - LTLF - RPP - Forecast Weather Data for LF - Study NSA - Support RT Stability Analysis - TCM - Dynamic Ratings - Forced Outage Detection | EMS 4 | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
Financial Transfer Interfaces with settlements and finance Testing of banking statements | Financial Transfer | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
| EIP 7 | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01 |  |  | Need FAT start date from project
Outage Evaluation - Multi-hour STNET - Outage Sensitivity Calculations Voltage Support | EMS 5 | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
Disputes and dispute process | Disputes | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
Real - Time Market Go- Live |  | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
Day - Ahead Market Go -Live |  | 2008-08-01 | 2008-12-07 | 2008-12-01 | 2008-12-01
Zonal Control Systems Retire |  | 2009-02-01 | 2009-02-01 | 2009-02-01 | 2009-02-01
Zonal Settlement Systems Retire |  | Never | Never | Never | Never
Formulas:
Compliance Application = [Performance Measured]+120

## Protocol Application
Section | Nodal Protocol Description |  | Nodal Dates |  |  |  | Zonal Dates
|  |  | Rediness Criteria Measurement Begins | GO-LIVE | Performance Measured | Compliance Application | Protocol Retired
1 | OVERVIEW
1.1 | Summary of the ERCOT Protocols Document
1.2 | Functions of ERCOT
1.3 | Confidentiality
1.4 | Operational Audit
1.5 | ERCOT Fees and Charges
1.6 | Open Access to the ERCOT Transmission Grid
1.7 | Rules of Construction
1.8 | Effective Date
2 | DEFINITIONS AND ACRONYMS
2.1 | Definitions |  | 2007-07-01 | 2007-07-01 | 2007-07-01 | 2007-07-01
2.2 | Acronyms And Abbreviations |  | 2007-07-01 | 2007-07-01 | 2007-07-01 | 2007-07-01
3 | MANAGEMENT ACTIVITIES FOR THE ERCOT SYSTEM
3.1 | Outage Coordination
3.2 | Analysis of Long-Term Resource Adequacy
3.3 | Management of Changes to ERCOT Transmission Grid
3.4 | Load Zones
3.5 | Hubs
3.6 | Load Participation
3.7 | Resource Parameters
3.8 | Special Considerations for Split Generation Meters
3.9 | Current Operating Plan (COP)
3.10 | Network Operations Modeling and Telemetry |  | 2007-09-01 | 2008-06-01 | 2008-08-01 | 2008-11-29
3.11 | Transmission Planning
3.12 | Load Forecasting
3.13 | Renewable Production Potential Forecasts
3.14 | Contracts for Reliability Resources
3.15 | Voltage Support
3.16 | Standards for Determining Ancillary Service Quantities
3.17 | Ancillary Service Capacity Products
3.18 | Resource Limits in Providing Ancillary Service
3.19 | Constraint Competitiveness Tests
4 | Day-Ahead Operations
4.1 | Introduction
4.2 | ERCOT Activities in the Day-Ahead
4.3 | QSE Activities and Responsibilities in the Day-Ahead
4.4 | Inputs into DAM and Other Trades
4.5 | DAM Execution and Results
4.6 | DAM Settlement
5 | Transmission Security Analysis and Reliability Unit Commitment (RUC)
5.1 | Introduction
5.2 | Reliability Unit Commitment Timeline Summary
5.3 | ERCOT Security Sequence Responsibilities
5.4 | QSE Security Sequence Responsibilities
5.5 | Security Sequence, Including RUC
5.6 | RUC Cost Eligibility
5.7 | Settlement for RUC Process
6 | Adjustment Period and Real-Time Operations
6.1 | Introduction
6.2 | Market Timeline Summary
6.3 | Adjustment Period and Real-Time Operations Timeline
6.4 | Adjustment Period
6.5 | Real-Time Energy Operations
6.6 | Settlement Calculations for the Real-Time Energy Operations
6.7 | Real-Time Settlement Calculations for the Ancillary Services
7 | Congestion Revenue Rights
7.1 | Function of Congestion Revenue Rights
7.2 | Characteristics of Congestion Revenue Rights
7.3 | Types of Congestion Revenue Rights to Be Auctioned
7.4 | Allocation of Preassigned Congestion Revenue Rights
7.5 | CRR Auctions
7.6 | CRR Balancing Account
7.7 | Congestion Management in McCamey Area
7.8 | Bilateral Trades and ERCOT CRR Registration System
7.9 | CRR Settlements
8 | Performance Monitoring and Compliance
8.1 | QSE/Resource Performance Monitoring and Compliance
8.2 | ERCOT Performance Monitoring and Compliance
8.3 | TSP Performance Monitoring and Compliance
8.4 | Non-Compliance
8.5 | Frequency Response Requirements and Monitoring
9 | SETTLEMENT AND BILLING
9.1 | General
9.2 | Settlement Statements for the Day-Ahead Market
9.3 | Settlement Invoices for the DAM
9.4 | Payment Process for the DAM
9.5 | Settlement Statements for Real-Time Market
9.6 | Settlement Invoices for the Real-Time Market
9.7 | Payment Process for the RTM
9.8 | CRR Auction Award Invoices
9.9 | Payment Process for CRR Auction Award Invoices
9.10 | CRR Auction Revenue Distribution Invoices
9.11 | Payment Process for CRR Auction Revenue Distribution
9.12 | CRR Balancing Account Invoices
9.13 | Payment Process for the CRR Balancing Account
9.14 | Settlement and Billing Dispute Process
9.15 | Settlement Charges
9.16 | Administrative Fees
9.17 | Transmission Billing Determinant Calculation
9.18 | Profile Development Cost Recovery Fee for Non-ERCOT Sponsored Load Profile Segment
10 | METERING | 4
10.1 | Overview
10.2 | Scope of Metering Responsibilities
10.3 | Meter Data Acquisition System (MDAS)
10.4 | Certification of EPS Metering Facilities
10.5 | TSP and DSP EPS Meter Inspectors
10.6 | Auditing and Testing of Metering Facilities
10.7 | ERCOT Request for Installation of EPS Metering Facilities
10.8 | Maintenance of Metering Facilities
10.9 | Standards for Metering Facilities
10.10 | Security of Meter Data
10.11 | Validating, Editing, and Estimating of Meter Data
10.12 | Communications
10.13 | Meter Identification
10.14 | Exemptions from Compliance to Metering Protocols
11* | Data Acquisition and Aggregation
11.1 | Data Acquisition And Aggregation From ERCOT Polled Settlement (EPS) Metered Entities
11.2 | Data Acquisition From TDSPs
11.3 | ESI ID Synchronization
11.4 | Load Data Aggregation
11.5 | Data Aggregation
11.6 | Unaccounted For Energy (UFE) Analysis
12 | Market Information System
12.1 | Overview
12.2 | ERCOT Responsibilities
12.3 | MIS Administrative and Design Requirements
12.4 | ERCOT Internet Website
13* | Transmission and Distribution Losses
13.1 | Overview
13.2 | Transmission Losses
13.3 | Distribution Losses
13.4 | Special Loss Calculations for Settlement and Analysis
14* | State of Texas Renewable Energy Credit Trading Program
14.1 | Overview
14.2 | Duties of ERCOT
14.3 | Duties of the PUCT
14.4 | Creation of REC Accounts and Attributes of RECs
14.5 | Registration to Become a REC Generator or REC Aggregation Company
14.6 | Reporting Requirements
14.7 | Awarding of RECs
14.8 | Transfer of RECs Between Parties
14.9 | REC Offsets
14.10 | Allocation of Statewide REC Requirement Among Competitive Retailers
14.11 | Retiring of RECs
14.12 | Penalties and Enforcement
14.13 | Maintain Public Information
14.14 | Submit Annual Report to Public Utility Commission of Texas
15* | Customer Registration
15.1 | Customer Switch of Competitive Retailer
15.2 | Database Queries
15.3 | Monthly Meter Reads
15.4 | Electric Service Identifier (ESI ID)
16 | REGISTRATION AND QUALIFICATION OF MARKET PARTICIPANTS
16.1 | Qualification, Registration, and Execution of Agreements
16.2 | Registration and Qualification of Qualified Scheduling Entities
16.3 | Registration of Load Serving Entities
16.4 | Registration of ERCOT and Non-ERCOT Transmission and Distribution Service Providers
16.5 | Registration of a Resource Entity
16.6 | Registration of Municipally Owned Utilities and Electric Cooperatives in the ERCOT Region
16.7 | Registration of Renewable Energy Credit Account Holders
16.8 | Registration and Qualification of Congestion Revenue Rights Account Holders
16.9 | Resources Providing Reliability Must-Run Service
16.10 | Resources Providing Black Start Service
16.11 | Financial Security for Counter-Parties
16.12 | User Security Administrator and Digital Certificates
17 | MARKET MONITORING AND DATA COLLECTION
17.1 | Overview
17.2 | Objectives and Scope of Market Monitoring Data Collection
17.3 | Market Data Collection and Use
17.4 | Provision of Data to Individual Market Participants
17.5 | Reports to PUCT Staff, WEMM, and the FERC
17.6 | Changes to Facilitate Market Operation
18* | Load Profiling
18.1 | Overview
18.2 | Methodology
18.3 | Posting
18.4 | Assignment of Load Profile ID
18.5 | Additional Responsibilities
18.6 | Installation and Use of Interval Data Recorders
18.7 | Supplemental Load Profiling
19* | Texas Standard Electronic Transaction (TX SET)
19.1 | Overview
19.2 | Methodology
19.3 | Texas Standard Electronic Transaction Definitions
19.4 | Texas SET Change Control Documentation
19.5 | Texas SET Acceptable Extended Character Set
19.6 | Texas SET Envelope Standards
20* | Alternative Dispute Resolution Procedure
20.1 | Applicability
20.2 | Initiation and Pursuit of ADR Process
20.3 | Informal Dispute Resolution
20.4 | Mediation Procedures
20.5 | Arbitration Procedures
20.6 | Dispute Resolution Costs
20.7 | Requests for Data
20.8 | Resolution of Disputes and Notification to Market Participants
20.9 | Settlement of Approved ADR Claims
21* | Process for Protocol Revision
21.1 | Introduction
21.2 | Submission of a Protocol Revision Request
21.3 | Protocol Revision Subcommittee
21.4 | Protocol Revision Procedure
21.5 | Urgent Requests
21.6 | Protocol Revision Implementation
21.7 | Submission of a System Change Request
21.8 | System Change Request Procedure
21.9 | Review of Project Prioritization, Review of Unfunded Project List, and Annual Budget Process
21.10 | Review of Guide Changes
21.11 | Process for Nodal Protocol Revisions
22* | Agreements
| Standard Form Black Start Agreement | 22(A)
| Standard Form Load Serving Entity Agreement | 22(B)
| Standard Form Qualified Scheduling Entity Agreement | 22(C)
| Standard Form REC Account Agreement | 22(D)
| Standard Form Resource Entity Agreement | 22(E)
| Standard Form Transmission and/or Distribution Service Provider Agreement | 22(G)
| Standard Form TCR Account Holder Agreement | 22(H)
| Notification of Suspension of Operations | 22(I)
| Standard Form Synchronous Condernser Agreement | 22(J)
22 | Nodal Agreements
| Attachment F: Standard Form Reliability Must-Run Agreement | 22F-1
| Attachment HMP: Standard Form Market Participant Agreement | 22HMP-1
23* | Texas Test Plan Team - Retail Market Testing
23.1 | Overview
23.2 | Testing Participants
23.3 | Documentation and Testing Materials
23.4 | Market Changes
23.5 | Testing Success
24* | Retail Point to Point Communications
24.1 | Maintenance Service Order Request
24.2 | Transmission Distribution Service Provider to Competitive Retailer Invoice
24.3 | Monthly Remittance
24.4 | MOU/EC TDSP to CR Monthly Remittance Advice
24.5 | Maintain Customer Information Request
24.6 | MOU/EC TDSP to CR Maintain Customer Information Request
ERCOT Fee Schedule - 2006*
* - From Zonal Protocol