## Example
QSE Name | ACME | Phone | email
QSE PM | ACME PM | 512-555-5555 | qsepm@acme.com
ERCOT Project Manager | Scott Middleton | 512-555-5555 | smiddleton@ercot.com
ERCOT Account Manager
ERCOT MMS First Line Support | Pradeep Patra
ERCOT Security Support | Greg Sutter
ERCOT Network Support | John Fisher
ERCOT MMS / SME Support | Resmi Surendran
Support Window | 2007-08-24
Testing Window Start | 2007-08-24
Test Window End | 2007-08-31
Execution Checklist / Plan
Activity | Responsible Party | Date | Status
Send and Confirm Project Plan | ACME PM + Scott Middleton | Day After email from QSE PM
Send Digital Certficate to ACME's USA | Scott Middleton | 2007-08-16
Send Testing Package to QSE PM - Script file - Resource list w/ Paramteres - Sample XML - Basic connectivity test script | Scott Middleton | 2007-08-09
Provide ERCOT Public Key | Scott Middleton | 2007-08-09
Provide ACME Target URL for Notifications | ACME PM | 2007-08-10
Confirm Resources for Phase 1 Testing | ACME PM | 2007-08-10
Configure MMS for ACME | Resmi Surendran | 2007-08-11
Configure EIP Infrastructure for ACME | Greg Sutter | 2007-08-11
Update Sample files with QSE specific data for Scenarios | ACME PM | 2007-08-11
Email Test Files to Scott Middleton | ACME PM | 2007-08-12
Pre-test Sample files: - If necessary, correct and return to QSE | Pradeep Patra | 2007-08-15
Using Validated Files, Generate Files for Remaining Scenarios | ACME PM | 2007-08-16
Setup Webex / Conf Bridge - "pre"-test window Conf Call - Support Window WebEx | Scott Middleton | 2007-08-19
Conduct "pre"-test window Conf Call - Perform network connectivity test (basic ping) - Perform basic authentication (cert) test - MMS / API | Scott Middleton, ACME PM, John Fisher, Greg Sutter, Resmi Surendran | 2007-08-23
Execute Support Window | Scott Middleton, ACME PM, Pradeep Patra, Resmi Surendran | 2007-08-24
Execute Test Window (Start) | ACME PM | 2007-08-24
Execute Test Window (End) | ACME PM | 2007-08-31
Send ACME Phase 1 Completion Report | Scott Middleton | 2007-09-01
Remove ACME Profile from LDAP | Greg Sutter | 2007-09-01
Testing Checklist
TEST CONDUCTED BY: | Scott Middleton
DATE CONDUCTED: | 2007-08-24
QSE REPRESENTATIVE: | ACME PM
Scenario ## - Description | Pass/Pass Conditionally/Fail | Comments
Basic Connectivity
ERCOT Pings QSE's Server(s)
QSE Pings ERCOT Server(s)
Authentication / Digital Certificate
QSE log's into MMS UI's
QSE Log's into WebServices via System Status Transaction
CURRENT OPERATING PLAN
3.2 COP Submit - User Interface
3.3 - COP Submit - External Webservice XML
3.4 COP Submit – Scenario Variations
3.4.1 Submit failure due to HSL limit
3.4.2 Submit failure due to LSL limit
3.4.3 Submit failure due to HEL limit
3.4.4 Submit failure due to LEL limit
3.4.5 Submit failure due to AS limits
3.4.6 Submit failure due to invalid time interval
3.4.7 Submit failure due to missing output schedule
3.4.8 Submit failure due to invalid CC configuration
3.5 COP Query & Update – User Interface
3.6 COP Query - External Webservice XML
3.7 COP Update – Scenario Variations
3.7.1 Update Rejection – User Interface
3.7.2 Update Rejection Variation – External Webservice XML
4.2 TPO Submit - User Interface
4.3 TPO Submit - External Webservice XML
4.4 TPO Submit – Scenario Variation
4.4.1 Submit failure due to FIP/FOP
4.4.2 Submit failure due to Non-Monotonically increasing
4.5 TPO Query & Update – User Interface
4.6 TPO Query - External Webservice XML
4.7 TPO Update – Scenario Variations
4.7.1 Update Rejection Variation – User Interface
4.7.2 Update Rejection Variation – External Webservice XML
4.8 TPO Cancel – User Interface
4.9 TPO Cancel – External Web Service XML
OUTPUT SCHEDULE
5.2 Output Schedule Submit - User Interface
5.3 OS Submit - External Webservice XML
5.4 OS Submit – Scenario Variation
5.4.1 Submit failure due valid Cost Curve
5.4.2 Submit failure due to MW level outside limits
5.4.3 Submit failure due to Ramp Rate
5.5 OS Query & Update – User Interface
5.6 OS Query – External Webservice XML
5.7 OS Update – Scenario Variations
5.7.1 Update Rejection Variation – User Interface
5.7.2 Update Rejection Variation – External Webservice XML
5.8 OS Cancel – User Interface
5.9 OS cancel – External Webservice XML
Incremental/Decremental
6.2 Inc/Dec Submit - User Interface
6.3 Inc/Dec Submit – External Webservice XML
6.4 Inc/Dec Submit – Scenario Variation
6.4.1 Submit failure due to first MW breakpoint
6.4.2 Submit failure due to non monotonically increasing
6.5 Inc/Dec Query & Update – User Interface
6.6 Inc/Dec Query – External Webservice XML
6.7 Inc/Dec Query – Scenario Variation
6.7.1 Update Rejection Variation – User Interface
6.7.2 Update Rejection Variation – External Webservice XML
6.8 Inc/Dec Cancel – User Interface
6.9 Inc/Dec Cancel – External Webservice XML
Additional Web Services
7.1.1 System Status
7.1.2 Get MRID
7.1.2.1 Get MRID for COP
7.1.2.2 Get MRID for TPO
7.1.2.3 Get MRID for OS
7.1.2.4 Get MRID for INC/DEC Offer Curve
Formulas:
ACME = [ACME, row above]