## Nodal Project Schedule
Texas Nodal Market Implementation Schedule
Features | Project | Readiness Criteria Measurement Begins | TNM Implementation Date | Performance Measured | Compliance Application | Status G/Y/R | Prev Status | Mitigation Activities | Comments
EDS 1 '- Base EMS Platform (Replication, Failover etc.,) - Base EMS Data Models - Base Alarm function - Base SCADA functions - Base State Estimator - Base Network Security Analysis (RT/ST) - Base Power Flow | EMS 1 | 2007-07-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
OAG 2.4 Base to address dual redundant ICCP from TSP and QSE | EMS 2 A | 2007-07-01 | 2007-10-01 | 2008-01-01 | 2008-04-30
EDS 2 State Estimator - State Estimator Performance Standards SCADA - Telemetry Performance Standards - RT Weather Zone calculations - Dynamic Ratings for single model - FOD – Actual Outage Detection NSA - SPS/RAP - Constraint Management (RT Tracki | EMS 2 B EDW 1 | 2007-09-01 | 2008-06-01 | 2008-08-01 | 2008-11-29
EDS 2 ' - Full CIM model - Base capability to add changes - Testing initial load from EMS - Testing NMMS to EMS functionality | NMMS 1 | 2007-11-01 | 2007-12-01 | 2008-02-01 | 2008-05-31
- PTC UI - PTC Schema - Interfaces for NOMCR, PMCR - Full Case Builder | NMMS 2 | 2008-01-01 | 2007-12-01 | 2008-04-01 | 2008-07-30
Areva NMMS to EMS model | EIP 1 | 2007-12-01 | 2007-12-01 | 2008-04-01 | 2008-07-30 |  |  | Need FAT start date from project
EDS 3 ' - Registration for MPs - Registration of CRR Account holders - Ability for MPs to submit forms on-line | REG 1 EIP2 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2008-01-29
- SCED - All MMS components used by SCED to compute LMPs - COP - Energy Offer Curves - Inc / Dec offer Curves - Output Schedules | MMS 1 | 2007-10-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
- Verifiable Costs - FIP - FOP | S&B 1 | 2008-04-01 | 2008-06-01 | 2009-02-01 | 2009-06-01
- Search - Link to EDW (MIR) - Link to public data (ERCOT.com) - Click thru screens - Links to applications as available | MIS 1 | 2008-04-01 | 2008-06-01 | 2008-08-01 | 2008-11-29
NSA - Calculation of Shift Factors - MVA to MW conversion for constraints - Constraint Direction Generation Sub-system - Resource Limit Calculator | EMS 2 C | 2008-02-01 | 2008-06-01 | 2008-12-01 | 2009-03-31
- Priority 1 External Web Services - EMS to MMS for LMP testing - MMS to EMS for LMP testing - Registration to MMS | EIP 3 | 2007-10-01 | 2007-10-01 | 2007-12-01 | 2008-03-30 |  |  | Need FAT start date from project
EDS 3 Release 6 & 7 MTLF ported from current Zonal Final Build of - State Estimator - RT NSA including Stability applications and TCM - Generation Sub-system | EMS 3 EIP 4 |  |  | 2007-10-09 | 2008-02-06
Credit Monitoring | CMM 1 | 2008-01-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
- Ability to upload Input data or enter them manually via CRR UI - All CRR components necessary to run CRR Markets - CRR Database Subsystem - CRR Calculation Engine - CRR Data Interface Subsystem - CRR Market Operator and Market Participant UI | CRR 1 EIP 5 | 2008-01-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 4 Release 8 Full MMS - RUC - SASM - DAM - CCT - Settlements Interface | MMS 2 |  |  | 2007-09-25 | 2008-01-23
Full Settlements & Billing, Statements & Invoices | S&B2 EIP6 | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
EDS 4 Release 9 Baseline 1 Baseline 2 | MMS 3 | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
Outage Scheduler | OS 1 | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
PTC Updates Time based MP editing model Case builder to create time based model Outages Contingency Editor Fully defined Model management system | NMMS 3 | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
Final Build of - MTLF - LTLF - RPP - Forecast Weather Data for LF - Study NSA - Support RT Stability Analysis - TCM - Dynamic Ratings - Forced Outage Detection | EMS 4 | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
Financial Transfer Interfaces with settlements and finance Testing of banking statements | Financial Transfer | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
| EIP 7 | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01 |  |  | Need FAT start date from project
Outage Evaluation - Multi-hour STNET - Outage Sensitivity Calculations Voltage Support | EMS 5 | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
Disputes and dispute process | Disputes | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
Real - Time Market Go- Live |  | 2008-06-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
Day - Ahead Market Go -Live |  | 2008-08-01 | 2008-12-07 | 2008-12-01 | 2008-12-01
Zonal Control Systems Retire |  | 2009-02-01 | 2009-02-01 | 2009-02-01 | 2009-02-01
Zonal Settlement Systems Retire |  | Never | Never | Never | Never
Formulas:
Compliance Application = [Performance Measured]+120

## Protocol Application
Nodal Section | Nodal Protocol Description |  | Nodal Dates |  |  |  | Zonal Section | Zonal Dates
|  |  | Rediness Criteria Measurement Begins | TNM Implementation Date | Performance Measured | Compliance Application |  | Zonal Protocol Description | Retire Date (Calendar Date) | Comments
1 | OVERVIEW |  | 2007-07-01 | 2007-07-01 | 2007-07-01 | 2007-07-01
2 | DEFINITIONS AND ACRONYMS |  | 2007-07-01 | 2007-07-01 | 2007-07-01 | 2007-07-01
3 | MANAGEMENT ACTIVITIES FOR THE ERCOT SYSTEM
3.1 | Outage Coordination
Note: Denny will expand Section 3.1
3.2 | Analysis of Long-Term Resource Adequacy |  | Link to ERCOT business process
3.3 | Management of Changes to ERCOT Transmission Grid |  | Assigned to Denny
3.4 | Load Zones |  | 2007-07-01 | 2007-07-01 | N/A | N/A | N/A
3.5 | Hubs |  | 2007-07-01 | 2007-07-01 | N/A | N/A |  |  |  | Zonal Hubs are applicable to zonal market.
3.6 | Load Participation |  | Link to Registration
3.7 | Resource Parameters |  | Link to Registration
3.8 | Special Considerations for Split Generation Meters |  | Link to Registration
3.9 | Current Operating Plan (COP) |  | Link to EDS3
3.10 | Network Operations Modeling and Telemetry |  | Link to EDS1 | Link to full Nodal functionality EDS4 Rel 9 | 2008-08-01 | 2008-11-29
Note: Bob and Denny will add third decimal point for Section 3.10
3.11 | Transmission Planning |  | Assigned to Denny
3.12 | Load Forecasting |  | Link to ERCOT business process
3.13 | Renewable Production Potential Forecasts |  | Link to ERCOT business process
3.14 | Contracts for Reliability Resources |  | Link to ERCOT business process
3.15 | Voltage Support |  | Assigned to Denny
3.16 | Standards for Determining Ancillary Service Quantities |  | Link to ERCOT business process | 2008-12-01
3.17 | Ancillary Service Capacity Products |  | Link to Registration
3.18 | Resource Limits in Providing Ancillary Service |  | Link to Registration
3.19 | Constraint Competitiveness Tests |  | Assigned to Bob
4 | Day-Ahead Operations |  | Link to EDS4 Rel 9
5 | Transmission Security Analysis and Reliability Unit Commitment (RUC) |  | Link to EDS4 Rel 9
6 | Adjustment Period and Real-Time Operations |  | Link to EDS3 Rel 5
7 | Congestion Revenue Rights |  | Link to EDS3 Rel 7
7.1 | Function of Congestion Revenue Rights |  | Link to EDS3 Rel 7
7.2 | Characteristics of Congestion Revenue Rights |  | Link to EDS3 Rel 7
7.3 | Types of Congestion Revenue Rights to Be Auctioned |  | Link to EDS3 Rel 7
7.4 | Allocation of Preassigned Congestion Revenue Rights |  | Link to Registration
7.5 | CRR Auctions |  | Link to EDS3 Rel 7
7.6 | CRR Balancing Account |  | Link to EDS3 Rel 7
7.7 | Congestion Management in McCamey Area |  | Link to Registration
7.8 | Bilateral Trades and ERCOT CRR Registration System |  | Link to EDS3 Rel 7
7.9 | CRR Settlements |  | Link to EDS3 Rel 7
8 | Performance Monitoring and Compliance |  | Assigned to Bob
8.1 | QSE/Resource Performance Monitoring and Compliance
8.2 | ERCOT Performance Monitoring and Compliance
8.3 | TSP Performance Monitoring and Compliance
8.4 | Non-Compliance
8.5 | Frequency Response Requirements and Monitoring
9 | SETTLEMENT AND BILLING |  | Link to EDS4 Rel 8 |  |  |  | 9 | SETTLEMENT AND BILLING |  | The dates listed below are subject to change until the official ERCOT holidays and banking holidays are posted for 2008 and 2009.
[7 empty] | 9.1 | Overview | TBD | All sections with a Retire Date = TBD are subject to Expiration of Confidentiality (section 1.3.3) as stated in section 9.5.2 of the protocols.
[7 empty] | 9.2 | Settlement Statements
[7 empty] | 9.2.3 | Initial Statements | 2008-12-10 | Last operating day 11/30/2008
[7 empty] | 9.2.4 | Final Statements | 2009-01-28 | Last operating day 11/30/2008
[7 empty] | 9.2.5 | Resettlement Statement | TBD | Dependent on whether disputes are submitted and granted. Typically run no later than 10 business days after dispute is granted. If the True-Up of the last zonal operating day (11/30/2008) is the last dispute submitted then in theory the last Resettlement statement would be posted no later than 7/10/2009.
[7 empty] | 9.2.6 | True-Up Statement | 2009-06-01 | Last operating day 11/30/2008
[7 empty] | 9.3 | Settlement Invoice | TBD
[7 empty] | 9.4 | Payment Process
[7 empty] | 9.4.2 | Invoice Payments Due ERCOT | TBD
[7 empty] | 9.4.3 | ERCOT Payment to Invoice Recipients | TBD
[7 empty] | 9.5 | Settlement and Billing Dispute Process
[7 empty] | 9.5.2 | Notice | TBD
[7 empty] | 9.5.4 | ERCOT Processing of Disputes | TBD
[7 empty] | 9.6 | Settlement Charges | TBD
[7 empty] | 9.7 | Administrative Fees | TBD
10 | METERING |  | Assigned to Denny
10.1 | Overview
10.2 | Scope of Metering Responsibilities
10.3 | Meter Data Acquisition System (MDAS)
10.4 | Certification of EPS Metering Facilities
10.5 | TSP and DSP EPS Meter Inspectors
10.6 | Auditing and Testing of Metering Facilities
10.7 | ERCOT Request for Installation of EPS Metering Facilities
10.8 | Maintenance of Metering Facilities
10.9 | Standards for Metering Facilities
10.10 | Security of Meter Data
10.11 | Validating, Editing, and Estimating of Meter Data
10.12 | Communications
10.13 | Meter Identification
10.14 | Exemptions from Compliance to Metering Protocols
11* | Data Acquisition and Aggregation |  | N/A | Nodal Market Implementation Date
12 | Market Information System |  | Link to EDS3
13 | Transmission and Distribution Losses |  | N/A | Nodal Market Implementation Date
14* | State of Texas Renewable Energy Credit Trading Program |  | N/A | Nodal Market Implementation Date
15* | Customer Registration |  | N/A | Nodal Market Implementation Date
16 | REGISTRATION AND QUALIFICATION OF MARKET PARTICIPANTS |  | Assigned to Bob
16.1 | Qualification, Registration, and Execution of Agreements
16.2 | Registration and Qualification of Qualified Scheduling Entities
16.3 | Registration of Load Serving Entities
16.4 | Registration of ERCOT and Non-ERCOT Transmission and Distribution Service Providers
16.5 | Registration of a Resource Entity
16.6 | Registration of Municipally Owned Utilities and Electric Cooperatives in the ERCOT Region
16.7 | Registration of Renewable Energy Credit Account Holders
16.8 | Registration and Qualification of Congestion Revenue Rights Account Holders
16.9 | Resources Providing Reliability Must-Run Service
16.10 | Resources Providing Black Start Service
16.11 | Financial Security for Counter-Parties
16.12 | User Security Administrator and Digital Certificates
17 | MARKET MONITORING AND DATA COLLECTION |  | Assigned to Floyd
18* | Load Profiling |  | N/A | Nodal Market Implementation Date
19* | Texas Standard Electronic Transaction (TX SET) |  | N/A | Nodal Market Implementation Date
20* | Alternative Dispute Resolution Procedure |  | N/A | Nodal Market Implementation Date
21* | Process for Protocol Revision |  | N/A | Nodal Market Implementation Date
22* | Agreements |  | Assigned to Legal
| Standard Form Black Start Agreement | 22(A)
| Standard Form Load Serving Entity Agreement | 22(B)
| Standard Form Qualified Scheduling Entity Agreement | 22(C)
| Standard Form REC Account Agreement | 22(D)
| Standard Form Resource Entity Agreement | 22(E)
| Standard Form Transmission and/or Distribution Service Provider Agreement | 22(G)
| Standard Form TCR Account Holder Agreement | 22(H)
| Notification of Suspension of Operations | 22(I)
| Standard Form Synchronous Condernser Agreement | 22(J)
22 | Nodal Agreements
| Attachment F: Standard Form Reliability Must-Run Agreement | 22F
| Attachment B: Standard Form Market Participant Agreement | 22B
23* | Texas Test Plan Team - Retail Market Testing |  | N/A | Nodal Market Implementation Date
24* | Retail Point to Point Communications |  | N/A | Nodal Market Implementation Date
ERCOT Fee Schedule - 2006* |  |  | Assigned to Legal
* - From Zonal Protocol