## Slide 1: Texas Nodal Program Update
Tim Pare

## Slide 2: Texas Nodal Program Update
Tim Pare

## Slide 3: Agenda
Item | Who | Purpose
Nodal Program Status | Tim Pare | For Information
Nodal Organization Structure | Tim Pare | For Information
Nodal Schedule Update | Tim Pare | For Information
Nodal Scorecard Demonstration | Tim Pare | For Information
Market Readiness Update | Tim Pare | For Information
Testing | Tim Pare | For Information
Budget Update | Tim Pare | For Information

## Slide 4: The program remains at overall Amber status with Scope / Quality improving following recent Change Control Baseline
Cost
Schedule
Scope / Quality
Legend
Summary
Green
The program is spending under budget through June’s actuals. Discussions with the ERCOT Executive Committee outlined possible ways to ensure we are on budget at completion.
Amber
Amber
Baseline 1 & 2 were approved by the BoD on July 17 and changes are now being incorporated
Red
Amber
Green
Estimate at Complete = <$248m
Estimate at Complete = $248 - $263m
Estimate at Complete = >$263m
Go-live = 12/1/08
Go-live = <30 days+
Go-live = >30 days+
Program is aligned with current protocols
Program is aligned to previous protocol version
Program is not aligned to protocols
There are several schedule risks in Baseline 1 & 2 which we are analyzing.
Amber
Current product quality is not sufficient for Nodal launch
Most Nodal products currently achieve quality standards
All Nodal products currently achieve quality standards
All Nodal projects have submitted Quality Assurance plans, and are in the process of completing internal Quality reviews.
Scope/
Quality
Schedule
Cost
Nodal
Delivery

## Slide 5: Nodal Organization Chart
July 2007
1 Murray Nixon assumes MMS effective July 23, and Al Hirsch retains EMS project management
2+3 Changes as a result of Steve Grendel assuming new roles in Zonal
1
2
3

## Slide 6: Market Readiness Update - Market Readiness Metrics Scorecard
Metrics scorecard development late
  Hired new analyst (C. Wilkinson)
  Moved responsibility to Program Control Office
Scorecard Iteration 1
  Lays foundation for future releases
  Provides top-level, drill-down, and individual MP results based on survey
  TPTF Beta available August 10, 2007
  Anticipated full release August 17, 2007
Scorecard Iteration 2 in-progress
  Will display status of ERCOT internal readiness metrics (E1, E8, and E9)
  Begin to display related EDS metrics
  Planned go-live end of September

## Slide 7: Market Readiness Update – Inventory Update & In-Progress and Near-Term Metrics
Current Readiness Metric Inventory to be reviewed by TPTF July 24, 2007
In Progress and Near-Term:
  ERCOT Departmental reporting
    Training and Organization Design - In progress
    Internal procedures beginning August 1, 2007
    Nodal Operating Guides beginning December 1, 2007
  ERCOT-observable metrics
    MP Engagement – In progress
    EDS 1 Telemetry Alarm Processing – In progress
      30 percent validated (30,000 points-to-points complete out of 100,000)
    MP Registration Activities – September 2007
    MP EDS-2 Trials Participation – October 2007
  MP Self Reporting
    First Self Reporting Questionnaire completed July 9, 2007
      55 responses received
      Cleansing data now to ensure consistency across responses
    Planned follow-up bi-monthly/quarterly thereafter

## Slide 8: Market Readiness Update – Wall of Shame*
The following Market Participants have not completed the Self-Reporting Questionnaire:
    APN Starfirst LP
    Barclays Bank PLC
    Pegasus Alliance Corporation DBA Onpac Energy
    Pepco Energy Services Inc
    Pre Buy Electric LLC
    Sitara Energy Inc
    Urban Energy Source LLC
    W Power And Light LP
    WCW International Inc
    Young Energy LLC
* Experience in other countries has proven the Terminology based on Hall of Fame / Wall of Shame to be effective.

## Slide 9: Market Readiness Update – Wall of Shame*
The following QSEs Without Resources have not identified their NODAL Accountable Executive (AE):
    Citadel Energy Products LLC
    Clearview Electric Inc
    DPI Energy LLC
    Duke Energy Ohio Inc
    Hwy 3 MHP LLC
    Kansas City Power and Light Company
    National Power Company Inc
    Northern States Power Company
    Texpo Power LP DBA Texpo Energy
These Market Participants have not been engaged in readiness to the degree QSEs With Resources and TSPs have been. ERCOT will increase contact with these Market Participants as the project approaches testing with QSEs Without Resources on MIS and/or API and other key activities.
* Experience in other countries has proven the Terminology based on Hall of Fame / Wall of Shame to be effective.

## Slide 10: Testing - The approach to get there…
Start simple, incrementally add complexity, and repeat the process until it becomes second nature
Testing

## Slide 11: The EDS Artifacts detailing the test effort…
EDS 1
Approach
EDS 2
Approach
EDS 3
Approach
EDS 4
Approach
SCED
Handbook
LFC
Handbook
CRR
Handbook
DAM
Handbook
ERCOT Nodal Transition Plan
_____________
Map to:
ERCOT Nodal Transition Plan Sections
Protocol Sections
Map to:
Functional Requirements
Are based on the same inputs as internal testing artifacts, but the focus of the testing is different

## Slide 12: Testing - Summary Release Schedule

## Slide 13: EDS 1 – Testing Results
EDS 1 will verify each of the approximately 90,000 ICCP points, as the scheduled MP operator manually changes a point’s status or data value.
ERCOT operations observes the update within the specified timeframe and records a pass or failure and the type of failure.
Market Participants
ESD1 Test Progress to-date
Testing Failures by Type of Failure
Start Date: 6/1/2007 End Date: 9/30/2007
Testing Schedule is on track.
Testing results and failure rate are within expectations.
Test observations
Total ICCP Points Verified = 33,040 of 90,132 ~ 40% complete, Error Rate ~ 4%

## Slide 14: Testing – EDS3 & EDS4 Test Plans
EDS4
EDS3
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
EDS 3
LMP Data Validation
Reg
Upload Offers
Rel 5
Rel 7
Rel 6
6 month LMP Posting
CRR Data Validation
Trial Ops of CRR
LFC COMs Testing
EDS
LFC Testing
EDS 4
RTM
Go-Live
DAM
Go-Live
Settlements Statements
Upload Bids
Test Settlements
Outages
DAM, RUC, SASM
Full Nodal Functionality
24*7 Operation
168 Hr Test
EDS
Go-Live
Activities
MP Interface Spec
Rel 8
Rel 9
EDS
Approach
EDS 3
Approach
SCED
Handbook
Phase
1 to 4
LFC
Handbook
Phase
1 & 2
EDS 4
Approach
CRR
Handbook
S&B
Handbook
DAM
Handbook
168 Hour Test Handbook
Nodal Cutover Handbook
Zonal Wind Down Handbook
Outage
Handbook
RUC
Handbook
SASM
Handbook
EDS 3
EDS 4
Major milestones
EDS Preparation Milestones
Approved
In progress
TPTF Submission (approximate)
Legend
http://nodal.ercot.com/docs/pd/eds/eds3/eds3dp/EDS_3_Approach_v1.0_061107.doc
http://nodal.ercot.com/docs/pd/eds/eds3/scedhdbk/EDS_SCED_MP_Handbook_V1.02.doc
Approved Documents
Summary Release Schedule
On track for milestone
Document Status
Ahead
Document Status

## Slide 15: We have made improvements from our “Early” EDS3 experience
We have proved the “Cloning” process for migrating applications
Installation of MMS SCED in the EDS environment is already complete
Migration experience of MMS applications has improved internally
Additional practice migrations were conducted to further reduce future migration durations
Cycle time for migration defect resolution has now been reduced from days to a few hours
The good news is, we are addressing these issues today before the key critical path milestones

## Slide 16: The cost impact of Baseline 1 & 2 will be negated through cost savings across the Program
Nodal Program Budget
263.0
$
Fund savings from various projects
(6.4)
All Projects - anticipated staffing reductions, being analyzed
Other reductions, being analyzed
Total
263.0
$
Nodal Program
Plan to achieve $263 Budget
($ Millions)
(3.7)
Increased costs associated with Baseline 1 & 2
10.1