## Nodal Project Schedule
Texas Nodal Market Implementation Schedule
Nodal Project Dates
Features | Project | Readiness Criteria Measurement Begins | TNM Implementation | Performance Measured | Compliance Application | Status G/Y/R | Prev Status | Mitigation Activities | Comments
EDS 1, Release 1 | EMS 1 | 2007-07-01 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 1, Release 2 | EMS 2 A | 2007-09-01 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 2, Release 3 | EMS 2 B, EDW 1 | 2007-10-01 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 2, Release 4 | NMMS 1, NMMS 2, EIP 1 | 2007-12-01 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 3, Registration | REG 1 | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 3, Release 5 | EDW 2, MMS 1, S&B 1, EIP 2, EMS 2C, MIS 1, EIP3 | 2007-10-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 3, Release 6 | EMS 3, EDW 3, | 2008-01-03 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 3, Release 7 | CRR 1, EIP 5, EDW 4 | 2008-01-03 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 4, Release 8 | MMS 2, S&B 2, EIP 6, EDW 5 | 2008-03-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 4, NOMCR |  | 2008-02-01 | 2008-04-01 | 2008-03-01 | 2008-06-29
EDS 4, Release 9, Baseline 1, 2 | OS 1, NMMS 3, EMS4, S&B 3, EIP 7, EMS 5, S&B 4, EDW 6 | 2008-05-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
ERCOT Business Processes
Load Forecasting/Adequacy |  | 2008-05-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
Renewable Production Potential Forecasts |  | 2008-06-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
Contracts for Reliability Resources |  | 2008-06-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
Standards for Determining Ancillary Service Quantities |  | 2008-10-01 | 2008-10-01 | 2008-10-01 | 2008-10-01
Real-Time Market Go-Live |  |  | 2008-12-01 | 2008-12-01 | 2009-06-01
Day-Ahead Market Go-Live |  |  | 2008-12-07 | 2008-12-08 | 2009-06-01
Zonal Control Systems Retire |  | 2009-02-01 | 2009-02-01 | 2009-02-01 | 2009-02-01
Zonal Settlement Systems Retire |  | Never | Never | Never | Never
Formulas:
Compliance Application = [Performance Measured]+92

## Protocol Application
Nodal Section | Nodal Protocol Description |  | Nodal Dates |  |  |  | Zonal Dates
|  |  | Rediness Criteria Measurement Begins | TNM Implementation Date | Performance Measured | Compliance Application | Zonal Section | Zonal Protocol Description | Comment
1 | OVERVIEW |  | 2007-07-01 | 2007-07-01 | 2007-07-01 | 2007-07-01
2 | DEFINITIONS AND ACRONYMS |  | 2007-07-01 | 2007-07-01 | 2007-07-01 | 2007-07-01
3 | MANAGEMENT ACTIVITIES FOR THE ERCOT SYSTEM
3.1 | Outage Coordination
Note: Denny will expand Section 3.1
3.2 | Analysis of Long-Term Resource Adequacy |  | 2008-05-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
3.3 | Management of Changes to ERCOT Transmission Grid |  | Assigned to Denny
3.4 | Load Zones |  | 2007-07-01 | 2007-07-01 | N/A | N/A | N/A
3.5 | Hubs |  | 2007-07-01 | 2007-07-01 | N/A | N/A |  |  | Zonal Hubs are applicable to zonal market.
3.6 | Load Participation |  | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.7 | Resource Parameters |  | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.8 | Special Considerations for Split Generation Meters |  | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.9 | Current Operating Plan (COP) |  | 2007-10-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
3.10 | Network Operations Modeling and Telemetry |  | 2007-07-01 | 2008-05-01 | 2008-07-01 | 2008-10-01
Note: Bob and Denny will add third decimal point for Section 3.10
3.11 | Transmission Planning |  | Assigned to Denny
3.12 | Load Forecasting |  | 2008-05-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
3.13 | Renewable Production Potential Forecasts |  | 2008-06-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
3.14 | Contracts for Reliability Resources |  | 2008-06-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
3.15 | Voltage Support |  | Assigned to Denny
3.16 | Standards for Determining Ancillary Service Quantities |  | 2008-10-01 | 2008-12-01
3.17 | Ancillary Service Capacity Products |  | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.18 | Resource Limits in Providing Ancillary Service |  | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.19 | Constraint Competitiveness Tests |  | Link to LFC Testing EDS3-Release 6 | Nodal Market Implementation Date | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Link to Nodal Implementation Date |  |  | The CCT implementation must be implemented in sufficient time to allow CMWG/TAC to evaluate the constraint classifications Competitive/non-competitive prior to market open.
4 | Day-Ahead Operations |  | 2008-05-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
5 | Transmission Security Analysis and Reliability Unit Commitment (RUC) |  | 2008-05-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
6 | Adjustment Period and Real-Time Operations |  | 2007-10-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
7 | Congestion Revenue Rights |  | 2008-01-03 | 2008-12-01 | 2009-02-01 | 2009-06-01
7.1 | Function of Congestion Revenue Rights |  | 2008-01-03 | 2008-12-01 | 2009-02-01 | 2009-06-01
7.2 | Characteristics of Congestion Revenue Rights |  | 2008-01-03 | 2008-12-01 | 2009-02-01 | 2009-06-01
7.3 | Types of Congestion Revenue Rights to Be Auctioned |  | 2008-01-03 | 2008-12-01 | 2009-02-01 | 2009-06-01
7.4 | Allocation of Preassigned Congestion Revenue Rights |  | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
7.5 | CRR Auctions |  | 2008-01-03 | 2008-12-01 | 2009-02-01 | 2009-06-01
7.6 | CRR Balancing Account |  | 2008-01-03 | 2008-12-01 | 2009-02-01 | 2009-06-01
7.7 | Congestion Management in McCamey Area |  | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
7.8 | Bilateral Trades and ERCOT CRR Registration System |  | 2008-01-03 | 2008-12-01 | 2009-02-01 | 2009-06-01
7.9 | CRR Settlements |  | 2008-01-03 | 2008-12-01 | 2009-02-01 | 2009-06-01
8 | Performance Monitoring and Compliance
8.1 | QSE/Resource Performance Monitoring and Compliance |  | Link to EDS3-Release 6 | Nodal Market Implementation Date | Link to EDS3-Release 6 LFC Testing | Link to EDS3-Release 6 LFC Testing |  |  | Regulation AS certification begins in EDS3 Release 6 testing. Resources not subject to certification will qualify for AS in accordance with Section 8 prior to market open.
8.2 | ERCOT Performance Monitoring and Compliance |  | Nodal Market Implementation Date | Nodal Market Implementation Date | Nodal Market Implementation Date | Link to Nodal Market Compliance Date |  |  | ERCOT performance monitoring is performed by the IMM. IMM reports are reviewed by the TAC.
8.3 | TSP Performance Monitoring and Compliance |  | Link to EDS2-Release 3 SE Verification for telemetry and NSA Link to EDS2-Release 4 for NOMCR Checkout Link to EDS4-Release 9 Full Nodal Functionality 24x7 ops | Nodal Market Implementation Date | Link to EDS4-Release 9 168 Hour Test | Link to Nodal Market Compliance Date |  |  | ERCOT must develop a TSP Monitoring Program and obtain TAC approval.
8.4 | Non-Compliance |  | NA | NA | NA | Link to Nodal Market Compliance Date
8.5 | Frequency Response Requirements and Monitoring |  | Link to EDS4-Release 9 Full Nodal Functionality 24x7 ops | Nodal Market Implementation Date | Link to EDS4-Release 9 168 Hour Test | Nodal Market Implementation Date |  |  | Frequency Response provisions must be in effect beginning with the test sequence that implements the nodal LFC as the system frequency control.
9 | SETTLEMENT AND BILLING |  | 2008-03-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
10 | METERING |  | Assigned to Denny
10.1 | Overview
10.2 | Scope of Metering Responsibilities
10.3 | Meter Data Acquisition System (MDAS)
10.4 | Certification of EPS Metering Facilities
10.5 | TSP and DSP EPS Meter Inspectors
10.6 | Auditing and Testing of Metering Facilities
10.7 | ERCOT Request for Installation of EPS Metering Facilities
10.8 | Maintenance of Metering Facilities
10.9 | Standards for Metering Facilities
10.10 | Security of Meter Data
10.11 | Validating, Editing, and Estimating of Meter Data
10.12 | Communications
10.13 | Meter Identification
10.14 | Exemptions from Compliance to Metering Protocols
11* | Data Acquisition and Aggregation |  | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
12 | Market Information System |  | 2007-10-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
13 | Transmission and Distribution Losses |  | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
14* | State of Texas Renewable Energy Credit Trading Program |  | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
15* | Customer Registration |  | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
16 | REGISTRATION AND QUALIFICATION OF MARKET PARTICIPANTS
16.1 | Qualification, Registration, and Execution of Agreements |  | 2007-10-01 | N/A | N/A | Link to Nodal Market Compliance Date |  | SFA replaces existing ERCOT/MP agreements
16.2 | Registration and Qualification of Qualified Scheduling Entities |  | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Nodal Market Implementation Date | 2008-03-08 | Link to Nodal Market Compliance Date |  |  | Hard dates presented at the last registration webex. CRR Account Holder Registration must complete 01/01/08 to support CRR testing and monthly CRR auction beginning 11/08.
16.3 | Registration of Load Serving Entities |  | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | TBA | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Link to Nodal Market Compliance Date |  |  | Hard dates presented at the last registration webex.
16.4 | Registration of ERCOT and Non-ERCOT Transmission and Distribution Service Providers |  | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Nodal Market Implementation Date | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Link to Nodal Market Compliance Date
16.5 | Registration of a Resource Entity |  | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Nodal Market Implementation Date | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Link to Nodal Market Compliance Date
16.6 | Registration of Municipally Owned Utilities and Electric Cooperatives in the ERCOT Region |  | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Nodal Market Implementation Date | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Link to Nodal Market Compliance Date
16.7 | Registration of Renewable Energy Credit Account Holders |  | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Nodal Market Implementation Date | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Link to Nodal Market Compliance Date
16.8 | Registration and Qualification of Congestion Revenue Rights Account Holders |  | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | 2008-01-01 | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Link to Nodal Market Compliance Date
16.9 | Resources Providing Reliability Must-Run Service |  | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Nodal Market Implementation Date | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Link to Nodal Market Compliance Date
16.10 | Resources Providing Black Start Service |  | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Nodal Market Implementation Date | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Link to Nodal Market Compliance Date
16.11 | Financial Security for Counter-Parties |  | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | 2008-01-01 | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Link to Nodal Market Compliance Date
16.12 | User Security Administrator and Digital Certificates |  | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Nodal Market Implementation Date | Link to EDS4-Release 9 Full Nodal Functionality 24x7 Operations | Link to Nodal Market Compliance Date
17 | MARKET MONITORING AND DATA COLLECTION |  | 2008-05-01
18* | Load Profiling |  | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
19* | Texas Standard Electronic Transaction (TX SET) |  | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
20* | Alternative Dispute Resolution Procedure |  | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
21* | Process for Protocol Revision |  | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
22* | Agreements |  | Assigned to Legal
| Standard Form Black Start Agreement | 22(A)
| Standard Form Load Serving Entity Agreement | 22(B)
| Standard Form Qualified Scheduling Entity Agreement | 22(C)
| Standard Form REC Account Agreement | 22(D)
| Standard Form Resource Entity Agreement | 22(E)
| Standard Form Transmission and/or Distribution Service Provider Agreement | 22(G)
| Standard Form TCR Account Holder Agreement | 22(H)
| Notification of Suspension of Operations | 22(I)
| Standard Form Synchronous Condenser Agreement | 22(J)
22 | Nodal Agreements
| Attachment F: Standard Form Reliability Must-Run Agreement | 22F
| Attachment B: Standard Form Market Participant Agreement | 22B
23* | Texas Test Plan Team - Retail Market Testing |  | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
24* | Retail Point to Point Communications |  | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
ERCOT Fee Schedule - 2006* |  |  | Assigned to Legal
* - From Zonal Protocol