## Slide 1: COMS Nodal Commercial Systems Project Update
COPs Meeting
August 2007
Justin Rasberry & Bill Barnes

## Slide 2: Agenda
Item | Purpose | Presenter
Deliverables Update | For Information | Bill Barnes
Delivery Schedule Update | For Information | Justin Rasberry
Questions | For Information | Bill and Justin

## Slide 3: COMS Requirements Update
Baseline 2 synchronization has begun. Activities around baseline 2 should conclude by September 2007.
  Targeting TPTF review in Sept.
ERCOT is anticipating at least 3 baselines before Go Live
All associated documentation (use cases, CSDs, test cases, etc) will be updated as Baselines approved
COPs personnel should stay abreast with COMS requirements.

## Slide 4: COMS CSD Update
The following COMS Conceptual System Designs (CSDs) have been submitted/approved as version 2.0 via TPTF
  Registration
  AIEC
  CRR
  DAM
  Eligibility
  Financial Transfer
  Statements
  Invoices
  RUC
  CMM
All COMS Conceptual System Design (CSDs) will be rolled into the v3.0(thru baseline 2) submittal to TPTF:
  Real Time not previously approved as v2.0
  Data Aggregation not previously approved as v2.0

## Slide 5: Statement Summary and Detail Page – Presentation Format
Finalize Settlement Statement presentation format
  In other words, how the data appears on the web page
  Recommended approach: ERCOT prepares options and brings to COPs/SDAWG for discussion and eventual vote
  Review Statement Summary page and Statement Detail page
    We are here
Repeat the process for all Invoices

## Slide 6: Development Update
Detailed Design on task
  Final Draft 1 complete
  Will continue to updates with “As-Built” information throughout development cycle
Lodestar version 4.7 successfully delivered in April 2007
  Corrected majority of major issues which impacted design and build strategies
  Monitoring remaining issues and enhancements to ensure we stay on schedule
  Requesting additional engagement from Lodestar Executive Management
Lodestar metadata changes nearing 90% total completion
  Metadata changes will exist throughout build cycle
Unit testing in progress
  Initial testing at the Modular level and will “build up” to batch

## Slide 7: Development Update
Most build packages consists of multiple modules
  Modules aligned into business functional components (i.e. DAM Energy, DAM AS, CRR, etc.)
Target FAT completion by mid/late 4th quarter 2007
Target SAT completion by mid/late 1st quarter 2008
Currently, Lodestar S&B slated for EDS 3 & 4
  Statements and Invoice format for EDS 3
  Shadow Settlements EDS 4 (requires Extracts)
Settlements Go Live with 1st CRR auction

## Slide 8: Questions ??
Justin Rasberry
Manager, MO DPO
Market Operations Divisional Projects Organization
ERCOT
(512) 248-3991
jrasberry@ercot.com
Bill Barnes
Manager, Settlements and Billing
ERCOT
(512) 248-6850
bbarnes@ercot.com