## Slide 1: MO Projects Financial Overview COPS August 14, 2007 Justin Rasberry Market Operations Division Projects Organization

## Slide 2: 2007 MO PPL
Projects ABOVE the current Capability Line
(Orange Shaded Area)
Projects BELOW the current Capability Line
(Yellow Shaded Area)
Unplanned 2006 Carry-over Projects
(Green Shaded Area)

## Slide 3: Unplanned 2006 Carry-Over Projects
No status change on these projects

## Slide 4: Projects ABOVE the Capability Line
Two Project Changes
  PR 70002_01 QSE Dispute Extract Cancelled with COPS vote. CART formalized cancellation 7/20/2007
  PR 40066_04 Lodestar Upgrade moved to “Planning”

## Slide 5: Projects BELOW the Capability Line
No status change on these projects

## Slide 6: Financial Overview as of 7/31/2007
DPO fully expected that we may see the variance rise as we complete the 2008 PPL planning process and active project in Planning can more fully identify spend expectations for 2007 and carry-overs into 2008
MO PPL Budget Activity | Amount | Notes/comments
Approved MO Capability Line Budget Funding | $1.33M | Current approved MO funding allocation Designates where the capability line falls
Current Forecast Spend of projects above the Capability Line | $1.09M | Based on current expectations and run rates for active and not started projects above the capability line Budget range of $1M – $2M
Budget Variance | ~$240K | Budget Variance is difference between MO Capability Line Budget Funding and Current Forecast Spend of projects above the Capability Line $150K due to carry-over amounts into 2008 for current projects $90K resulting from projects running under budget Budget Variance could be applied to the funding required for the Performance Measures Reporting project CART will need to evaluate when to release the funds.

## Slide 7: Budget Variance Allocation
At previous RMS meetings, it was requested that ERCOT present its plan for release of funds to RMS before monies are returned to SRT for potential re-allocation. Below is the same summation for COPS.
MO Release
Approx. $200k
MO/RO Budget Variance
2007; $ thousand
$1,743
$109
$314
MO Total = $243
No Concerns
Should be monitored
Should not Release
CART reviewed the MO-RO portfolio collectively and approved the release of $1.3M from the overall portfolio budget variance of approx. $2.2M.
MO Total = -$8
MO Total = $5

## Slide 8: Questions / Contact
Justin Rasberry
Manager, MO DPO
Market Operations Divisional Projects Organization
ERCOT
(512) 248-3991
jrasberry@ercot.com