External Web Services Target Availability

- Sandbox column indicates the target date that the External Web Service will be deployed to the nodal sandbox.  The Web Service is not integrated to a business system (e.g. MMS).

- Back-end column indicates the target date for the external web service to be integrated to the business application.  These dates do not include the completion of all internal testing efforts.

- EDS 3 and 4 Usage columns indicate the target date the integrated web service is used for testing purposes in the EDS environment.

| Submission Type | Sandbox (Loopback) | Back-end | EDS 3 Usage | EDS 4 Usage |
| --- | --- | --- | --- | --- |
| Offers |  |  |  |  |
| Three-Part Supply Offer | Jul 07 | Aug 07 | Aug 07 | Q1 08 |
| Inc/Dec Energy Offer | Jul 07 | Aug 07 | Aug 07 |  |
| DAM Energy-Only Offer | Aug 07 | Oct 07 |  | Q1 08 |
| AS Offer | Aug 07 | Oct 07 |  | Q1 08 |
| CRR Offer | Sep 07 | Nov 07 |  | Q1 08 |
| Bids |  |  |  |  |
| DAM Energy Bid | Aug 07 | Oct 07 |  | Q1 08 |
| PTP Obligation Bid | Sep 07 | Nov 07 |  | Q1 08 |
| Schedules |  |  |  |  |
| Output Schedule (inc. DSR) | July 07 | Aug 07 | Aug 07 |  |
| Self Schedule | Sep 07 | Nov 07 |  | Q1 08 |
| DC Tie Schedule | Oct 07 | Dec 07 |  | Q1 08 |
| Outage Cancellation | Dec 07 | Feb 08 |  | Q1 08 |
| Trades |  |  |  |  |
| Capacity Trade | Oct 07 | Dec 07 |  | Q1 08 |
| Energy Trade | Oct 07 | Dec 07 |  | Q1 08 |
| AS Trade | Aug 07 | Oct 07 |  | Q1 08 |
| Other Market Interfaces |  |  |  |  |
| COP | July 07 | Aug 07 | Aug 07 |  |
| AS Self-Arrangement | Aug 07 | Oct 07 |  | Q1 08 |
| Other Web Service Components |  |  |  |  |
| Bid Set Acceptance | July 07 | Aug 07 | Aug 07 |  |
| Bid Set Error | July 07 | Aug 07 | Aug 07 |  |
| Get MRID | July 07 | Aug 07 | Aug 07 |  |
| System Status | July 07 | Aug 07 | Aug 07 |  |
| Alert Acknowledgement | Dec 07 | Feb 08 |  |  |
| Outputs |  |  |  |  |
| Forecasted Load | Aug 07 | Oct 07 |  | Q2 08 |
| Real-Time System Load | Aug 07 | Oct 07 | Nov 07 |  |
| Market LMPs and SPPs | Aug 07 | Oct 07 | Nov 07 |  |
| Mitigated Curves | Aug 07 | Nov 07 | Nov 07 |  |
| Outage Creation | Aug 07 | Feb 08 |  | Q2 08 |
| Total Regulation | Sep 07 | Nov 07 |  | Q2 08 |
| Load Ratio Share | Sep 07 | Nov 07 |  | Q2 08 |
| Unit Availability | Sep 07 | Nov 07 | Dec 07 |  |
| Startup and Shutdown Instructions | Sep 07 | Nov 07 |  | Q2 08 |
| Proxy Curves | Sep 07 | Nov 07 | Dec 07 |  |
| Get AwardSet | Oct 07 | Dec 07 |  | Q2 08 |
| Market MCPCs | Oct 07 | Dec 07 |  | Q2 08 |
| Ancillary Service Schedule Obligations | Oct 07 | Dec 07 |  | Q2 08 |
| Load Distribution Factors | Oct 07 | Dec 07 | Dec 07 |  |
| Customer Load Profile | Oct 07 | Dec 07 |  | Q2 08 |
| Market Totals | Nov 07 | Jan 08 |  | Q2 08 |
| Binding Constraints | Nov 07 | Jan 08 | Jan 08 |  |
| Active Contingencies in SCED | Nov 07 | Jan 08 | Jan 08 |  |
| Voltage Profiles | Nov 07 | Jan 08 |  | Q2 08 |
| Competitive Constraints | Nov 07 | Jan 08 | Jan 08 |  |
| Shift Factors | Nov 07 | Jan 08 | Jan 08 |  |
| Ancillary Service System Plan | Nov 07 | Jan 08 |  | Q2 08 |
| Dynamic Ratings | Dec 07 | Feb 08 | Jan 08 |  |
| Aggregated Ancillary Service Offer Curves | Dec 07 | Feb 08 |  | Q2 08 |
| Total Ancillary Service Offers | Dec 07 | Feb 08 |  | Q2 08 |
| Total DAM Energy | Dec 07 | Feb 08 |  | Q2 08 |
| Derated CRRs | Dec 07 | Feb 08 |  | Q2 08 |
| Outage Query | Dec 07 | Feb 08 |  | Q2 08 |
| Notifications |  |  |  |  |
| Notices and Alerts | Sep 07 | Nov 07 | Nov 07 | Q2 08 |
| CRR Awards | Sep 07 | Nov 07 |  | Q2 08 |
| Outage Notifications | Sep 07 | Nov 07 |  | Q2 08 |
| Energy Offer Awards | Oct 07 | Dec 07 |  | Q2 08 |
| PTP Obligation Awards | Oct 07 | Dec 07 |  | Q2 08 |
| Pending Trade | Nov 07 | Jan 08 |  | Q2 08 |
| Energy Only Offer Awards | Nov 07 | Jan 08 |  | Q2 08 |
| Energy Bid Award | Nov 07 | Jan 08 |  | Q2 08 |
| Ancillary Service Awards | Nov 07 | Jan 08 |  | Q2 08 |