Texas Nodal:

EDS CRR Testing

Market Participant Handbook – DRAFT

This is a living document, drafted for discussion during the EDS CRR Market Participant Workshop. Based on this Workshop, ongoing planning meetings, and Nodal Project deliveries details of this document will be further refined.

Version 0.04

August 14, 2007

Revision History

| Document Revisions |  |  |  |
| --- | --- | --- | --- |
| Date | Version | Description | Author(s) |
| 2007/07/25 | 0.01 | Draft document created for EDS 3 CRR Planning Workshop w/ EDS 3 team. This version is a working draft for planning discussion. | D. Kurdy |
| 2007/07/31 | 0.02 | Updated with Phase 5 overview based on discussion with K. Sumanam; clarification edits from T. Madden; general clarification edits | D. Kurdy |
| 2007/08/01 | 0.03 | Updated with comments from the CRR Home Team and general clarification edits | D. Kurdy |
| 2007/08/14 | 0.04 | Minor consistency/clarification edits | R. Cheng |

Table of Contents

1	Introduction	5

1.1	Market Participant Handbook	6

1.2	Document Structure	7

2	Release Overview	8

2.1	Early Deliveries	8

2.2	Nodal Sandbox	9

2.3	Supporting Documents	10

3	Pre-EDS 3 Release 7 - Registration and digital certification; NOIE PCRR contract submission	11

3.1	Phase Definition	11

3.2	EDS Testing Activities	13

3.3	Market Participant Involvement	13

4	Phase 1 – UI connectivity, data upload/download	15

4.1	Phase Overview	15

4.2	EDS Testing Activities	17

4.3	Market Participant Involvement	18

5	Phase 2 – Mock monthly allocation and auction (ERCOT-provided data)	20

5.1	Phase Overview	20

5.2	EDS Testing Activities	22

5.3	Market Participant Involvement	23

6	Phase 3 – Mock Monthly Auction (MP-created data)	25

6.1	Phase Overview	25

6.2	EDS Testing Activities	27

6.3	Market Participant Involvement	28

7	Phase 4 – Mock Multi-Month Allocation and Auction (MP-created data)	30

7.1	Phase Overview	30

7.2	EDS Testing Activities	32

7.3	Market Participant Involvement	33

8	Phase 5 – Integration Testing	35

8.1	Phase Overview	35

8.2	EDS Testing Activities	37

8.3	Market Participant Involvement	38

9	EDS Communications	39

9.1	EDS Planning Workshops	39

9.2	Online Readiness Center	39

9.3	NOIE/McFRI EDS3-R7 Kickoff Session	39

9.4	Full Participant EDS3-R7 Kickoff Session	39

9.5	EDS Weekly Conference Calls	39

9.6	Weekly Status Bulletin	40

9.7	Issue Tracking Process	40

9.8	Entry / Exit Criteria	40

10	Appendix	41

10.1	Issue Submission Lifecycle	41

10.2	Draft Issue Submission Form	42

- Introduction

The ERCOT Nodal Transition Plan, approved by the Technical Advisory Committee (TAC), organizes transition activities into four tracks, which required participation from both ERCOT and market participants. The Texas Nodal Program defined four Early Delivery Systems (EDS) sequences to meet the requirements of the Systems Testing and Nodal Market Implementation track of the Transition Plan. These sequences were further refined based on the Nodal project delivery schedules to group Nodal functionality and features into nine incremental software releases that will be used to meet the requirements outlined in the Nodal Transition Plan.

The EDS sequences and releases are outlined below:

EDS 1

- Release 1  –  Alarm Processing

- Release 2  –  Point-to-Point Checkout

EDS 2

- Release 3  –  Trial Operation of State Estimator & Network Security Analysis

- Release 4  –  Trial Operation of NMMS (Network Model Validation)

EDS 3

- Release 5  –  Trial Operation of SCED, 6 month LMP posting

- Release 6  –  Trial Operation of LFC, ACE

- Release 7  –  Trial Operation of CRR (This document - CRR MP Handbook)

EDS 4

- Release 8  –  Trial Operation of RT Settlements (No Extracts)

- Release 9  –  Trial Operation of DAM, RUC, SASM, Full Settlements, EDW Extracts

- TXMACS 1.0  –  Full Nodal Functionality & 168 hour testing

The Nodal program has adopted an incremental approach for releasing functionality into the EDS environment to maximize the overall benefit of EDS, by providing system functionality to the Market Participants to begin testing as early as possible. The objective of these early deliveries is to provide MPs with sufficient tools to enable development of their systems.  The EDS environment will be updated incrementally as soon as a set of Nodal functionality has been tested internally by ERCOT.  Once the integrated set of system functionality has completed the internal ERCOT quality control testing, the EDS environment will be updated for formal milestone testing activities. This incremental approach is diagramed below:

## Market Participant Handbook

The Market Participant Handbook has been created to provide a detailed testing guide for participation in the Early Delivery System (EDS) activities. The Handbooks are one of the guiding documents to help Market Participants understand how to prepare, participate and when to engage in EDS. This Handbook will cover the details for Release 7 – Trial Operation of CRR.

The testing areas described in this document will be guided by the Nodal Transition Plan and the Nodal delivery schedule; however, the detailed testing activities and schedule will be completed by working collaboratively with ERCOT subject matter experts and Market Participant representatives.

The Early Delivery Systems are intended to:

- Provide Market Participants with the tools to complete development and testing of updated Nodal systems in as realistic environment as possible.

- Validate Nodal functionality and timelines including Day-Ahead, Adjustment Period and Real-Time activities for ERCOT, Transmission Service Providers (TSPs) and Market Participants (MPs).

- Build stakeholder confidence that Nodal design and systems adhere to Nodal Protocols and Nodal Transition Plan requirements.

- Generate Locational Marginal Prices (LMPs) for distribution to ERCOT Market Participants for at least six months prior to the Nodal Markets going live.

- Confirm through a series of structured and unstructured testing that

"stable and accurate operation of the SCADA, Network Security Analysis, Transmission Constraint Management, SCED, LFC, DAM, RUC, and real time settlement system can be declared"

## Document Structure

It is critical that all participants have a common understanding of EDS activities, start dates, and participation expectations. This document will cover the following topics to ensure that both ERCOT and Market Participants are ready for each EDS phase.

Release Overview – This section outlines the specific phases, objectives, and supporting documents for the EDS Release 7 – Trial Operation of CRR.

<For Each Phase>

- EDS Phase Overview

  - EDS Environment

  - Testing Schedule

  - Functionality Available (Available Interfaces, Validation, Functionality, Data)

- EDS Testing Activities

  - Testing Structure (Required vs. Optional Involvement, Structured vs. Unstructured Testing, etc.)

  - Test Scenarios

  - Test Data

- Market Participant Involvement

  - Target Roles (Show relevant roles w/ Participation Expectations)

  - Preparation Activities (Data, Digital Certificates, Workshop involvement, New Data, Training)

  - System Readiness (MP EDS, Tools, Capabilities)

# Release Overview

For EDS 3, CRR will be one of the last business functionalities to be released to the EDS environment. The release procedure will follow the ERCOT release mechanism described earlier in this document. The initial system delivery will provide CRR AHs with the opportunity to test connectivity to the CRR system; submission of bids and offers, nominations, retrieval of results and submission of bilateral trades. CRR AHs will also have the opportunity to ‘practice’ their bidding strategies through mock auctions.

## Early Deliveries

The Trial Operations of CRR will be executed in several phases, incrementally adding functionality until a fully integrated, internally tested product is released to the EDS environment.

Each phase and its objectives are as follows:

Pre EDS 3 Release 7 – Registration, Allocation pre-work, Training

- Market Participants wishing to participate in EDS Activities indicate their intention to do so

- Market Participants wishing to participate in EDS Activities are registered as CRR AHs and have appropriate digital certificates

- Market Participants wishing to participate in EDS Activities complete required CRR Training

- NOIEs submit PCRR entitlement forms to ERCOT

- NOIEs wishing to identify themselves as NOIE Load Zones indicate their intention to do so

- Wind Generators within the boundaries of the McCamey Area identify themselves for McFRI eligibility

- ERCOT verifies receipt of contracts/entitlements and inputs this information into the system

Phase 1 – UI connectivity, data upload/download (~2 weeks)

- CRR environment is available for CRR EDS 3 Activities

- CRR AHs are able to connect to the CRR System using a digital certificate

- CRR AHs are able to use UI to retrieve market information and submit nominations or bids/offers

Phase 2 – Mock monthly allocation and auction (ERCOT-provided data)

(~3 weeks)

- ERCOT conducts mock monthly allocation (NOIEs submits nominations as directed)

- ERCOT conducts mock monthly auction (CRR AHs submit ERCOT-provided bids and offers)

- CRR AHs understand the results of a market based on a set of inputs

- CRR AHs bilaterally trade CRRs as orchestrated by ERCOT

Phase 3 – Mock monthly auction (MP-created data) (~3 weeks)

- ERCOT conducts mock monthly auction (CRR AHs submit self-created bids and offers)

- CRR AHs bilaterally trade CRRs

Phase 4 – Mock multi-month allocation and auction (MP-created data) (~4 weeks)

- ERCOT conducts mock multi-month allocation (NOIEs submits self-created nominations)

- ERCOT conducts mock multi-month auction (CRR AHs submit self-created bids and offers)

Phase 5 – Integration testing (~1 week)

- CRR AHs retrieve/view data from other Nodal up-stream systems to CRR system

The following items must be included in one of the above phases of the EDS 3 Release 7 or must else in a new phase:

  - Additional ‘practice’ Auctions – if Market Participants wish, additional rounds of practice bidding may be possible (current phases run though April, EDS3-R7 is scheduled to end June 2007)

  - Credit – based on design decisions and detailed development timeline, the implementation and testing timeline for Credit data input module TBD

  - Training – an 8 hour training course is currently planned for Fall 2007 delivery. However, there may be additional UI training TBD

  - EDW/MIR/MER – The functionality for data extracts and reporting via the EDW (and related projects) is yet to be determined

Note 1: Settlements and Billing will produce invoices as part of EDS4. However, auction and allocation results will be available during each CRR EDS3-R7 phase through the CRR System (file download).

Note 2: An automated programmatic interface (API) / web services are not in the current CRR project scope. Therefore, reference to API or web services functionality is not currently contained in this document. If the ERCOT Board or Directors includes this functionality in scope, the EDS team will coordinate with the PMO and dependant projects to determine a timeline for implementation, internal testing and market trials.

## Nodal Sandbox

As there is no API/web service currently in scope for the CRR project, no Nodal Sandbox is necessary.

## Supporting Documents

The following documentation should be reviewed for a better understanding of the overall EDS 3 Approach, System Requirements and Conceptual System Design.

| Reference: Nodal Website | Description | Version |
| --- | --- | --- |
| EDS 3 Approach | EDS 3 Approach document | 0.91 |
| CRR Requirements | Congestion Revenue Rights (CRR) Requirement Specification | 1.0 |
| CRR Conceptual System Design | CRR system design overview document | 1.0 |
| Standard Form MP Agreement | ERCOT Standard Form Agreement for Market Participants | Protocol version 8/1/2007 |
| CRR AH Application for Registration | CRR AH Application | 1.0 |
| TBD | PCRR Entitlement Form | TBD |
| TBD | NOIE Load Zone Declaration Form | TBD |
| TBD | McFRI Eligibility Form | TBD |
| TBD | EDS3-R7 Intention to Participate Form | TBD |

# Pre-EDS 3 Release 7 - Registration and digital certification; NOIE PCRR contract submission

## Phase Definition

EDS Environment

* Note: Only the colored components will be tested during this phase.

During the period prior to the start of EDS 3 testing for CRR, Market Participants wishing to participate in the CRR EDS will have to register with ERCOT as CRR AHs through the official registration process. The registration process for CRR AHs is outlined by the ERCOT registration group and recorded at http://nodal.ercot.com/readiness/rq/index.html

Market Participants should notify ERCOT of their intention to participate in the CRR EDS activities. CRR AHs must have completed the registration process in order to participate in the first round of EDS activities.

In addition, NOIEs who desire to register for PCRRs must submit documentation to ERCOT. For a NOIE to be eligible for PCRRs the entity must:

(a) own or have a long-term (greater than five years) contractual commitment that was entered into before September 1, 1999 for annual capacity and energy from specific Generation Resources; or

(b) have a long-term (greater than five years) allocation from the federal government for annual capacity and energy produced at a federally-owned hydroelectric Generation Resource, and that allocation was in place prior to September 1, 1999.

NOIEs must submit proof of their eligibility to ERCOT prior to the date identified above. Proof will consist of a copy of the contract and ERCOT provided form (including CRR AH name and DUNS number).

NOIEs that wish to become a NOIE Load Zone as outlined in section 3.4.3 of the Nodal protocols must submit their intention to do so by completing the ERCOT provided form. This notification will not be considered binding for Nodal go-live, however the indication will allow ERCOT to appropriately form the network model for EDS activities.

Additionally, to participate in any phase of CRR testing, CRR AHs must have completed ERCOT CRR training. The details of the course(s) are to be determined.

EDS Testing Schedule

The CRR Pre-EDS 3 Release 7 Testing Schedule will consist of several dates by which activities must be met:

- December 1, 2007

  - Market Participants wishing to participate as CRR AHs (CRR AH) in the EDS3-R7 activities must submit the form with their intention to do so and expected phases of participation

  - NOIEs must submit eligible contracts and desired entitlements

  - NOIEs wishing to identify themselves as NOIE Load Zones shall indicate their intention to do so

  - Wind Generation Resources (WGRs) [or QSEs representing WGRs] within the boundaries McCamey Area must identify themselves for McFRI eligibility

  - NOIEs and WGRs [or QSEs representing WGRs] must register as CRR AHs. This will initiate the digital certification process of assigning new rights to an already existing Nodal digital certificate or assigning a new Nodal digital certificate.

- January 15, 2008

  - Market Participants wishing to participate in EDS3-R7 must have registered with ERCOT as a CRR AH. This will initiate the digital certification process of assigning new rights to an already existing Nodal digital certificate or assigning a new Nodal digital certificate.

  - Market Participants wishing to participate in Phase 1 must have registered for and completed ERCOT CRR Training.

EDS Functionality

This section outlines the system interfaces, web services, and requirements functionality that will be tested for this phase.

Network Model

- Identification of NOIE Load Zones will help identify the Network Model to be used for EDS 3 Release 7 and the possible implications for go live.

Registration

- Market Participants must register as CRR AHs according to the registration process as recorded at http://nodal.ercot.com/readiness/rq/index.html.

| Req | Req Specification Name | Description |
| --- | --- | --- |
| <Req ID> | <Title> | Partial/Full - <description> |

## EDS Testing Activities

The Pre-EDS 3 Release 7 activities will not actually require testing, it will consist of data collection from Market Participants and Market Participant interactivity with the ERCOT Registration process.

Intention to participate

- Complete the form available at https://nodal.ercot.com/TBD to indicate their intention to participate in EDS3-R7 and send to CRR@ercot.com.

Registration

- Follow process outlined at http://nodal.ercot.com/readiness/rq/index.html.

NOIE submission of desired PCRR contracts:

- Submit an electronic copy of contract and the form available at https://nodal.ercot.com/TBD to CRR@ercot.com. Hard copy submission to ERCOT may also be required.

NOIE self-identification of NOIE Load Zone

- Compete the form available at https://nodal.ercot.com/TBD to express their intention to become a NOIE Load Zone to CRR@ercot.com. This notification will not be considered binding for Nodal go-live, however the indication will allow ERCOT to appropriately form the network model for EDS activities.

McFRI eligibility

- Complete the form available at https://nodal.ercot.com/TBD to indicate their intention to receive McFRIs and generation location and send to CRR@ercot.com.

Training

- MPs wishing to participate in any testing must have completed ERCOT CRR training. The details of the course(s) are to be determined.

## Market Participant Involvement

Target Roles

The activities and functionality being tested Pre-EDS 3 Release 7 are relevant to the following groups:

CRR AHs:  Registration, NOIE contact submission and entitlement notification, NOIE load zone ID, McFRI eligibility identification

ERCOT: Contract receipt, NOIE load zone receipt, McFRI eligibility receipt, Registration (forms and Siebel)

Preparation Activities

The Pre-EDS 3 Release 7 activities consist of preparation for EDS 3 Release 7 Phase 1. No additional preparation is necessary.

EDS Involvement

All NOIEs and McCamey Area WGRs [or QSEs representing WGRs] will be expected to participate in the Pre-EDS 3 Release 7 activities. ERCOT will work with individual NOIEs as necessary to clarify options.

Additionally, any Market Participant who is not a NOIE but wishes to participate in EDS3R7 will be expected to complete the CRR AH registration process. Date of completion will determine the phase in which the CRR AH will be integrated into EDS3R7 activities.

# Phase 1 – UI connectivity, data upload/download

## Phase Overview

This intention of Phase 1 is to ensure that CRR AHs are able to connect to the CRR System, and to allow CRR AHs to familiarize themselves with the CRR Market User Interface functionality. Note: no allocations or auctions will be executed in this phase.

EDS Environment

* Note: Only the colored components will be tested during this phase.

During EDS3-R7 Phase 1, the EDS environment will be upgraded to include the CRR System. The applications deployed for this phase of EDS will be in a testing configuration rather than a production one – they are not intended to perform to production standards at this point.

These EDS systems will be available and supported from 8am to 5pm on designated “EDS Testing Days” based on the defined EDS calendar. During off hours and non-testing days the system may be unavailable due to system updates, ERCOT testing, or other testing activities. Any changes in testing schedules will be reflected in the EDS testing calendar and communicated to Market Participants.

EDS Testing Schedule

Phase 1 will consist of two weeks worth of effort to ensure that a limited number of CRR AHs are able to connect to the CRR System for upload and download of files.

- Monday Conference Call - Used to communicate with all EDS participants on

  - EDS activities planned for the week

  - Updates to online support documents & tools

  - Resolved issues or environment updates

- Workshops - The EDS team will conduct workshops during this phase. ERCOT will guide CRR AHs through the expected activities through group work activities (either via WebEx or Conf Call). CRR AHs will also have the opportunity to receive direct support from ERCOT Subject Matter Experts in one-on-one sessions as necessary. A detailed calendar of EDS workshops will be available on the Nodal Website.

- Friday Conference Call - Used to communicate with all EDS participants on

  - EDS activities accomplished during the week

  - Updates to online support documents and tools

  - Identified software or environment updates

During the workshops CRR AHs will utilize the CRR Market User Interface (MUI) to upload or retrieve the following items:

- Bid and Offer Portfolios

- Network Model Files

- Additional Market Files

- Market Result Files

EDS Functionality

This section outlines the system interfaces and requirements functionality that will be tested for this phase:

CRR Market User Interface

The following screens will be available for Market Participant testing:

- Allocation Manager (not being tested in this phase)

- Auction Portfolio Manager

- Downloads

- Bilateral Transactions (not being tested in this phase)

- Messages [CRR system only] (not being tested in this phase)

- Credit Assignment Manager (not being tested in this phase)

CRR System Functionality

* Note: Only the colored components will be tested during this phase.

| Req | Req Specification Name | Description |
| --- | --- | --- |
| <Req ID> | <Title> | Partial/Full - <description> |

## EDS Testing Activities

Phase 1 will provide connectivity validation and file upload and download verification. Specific participant actions will be defined during the EDS planning workshops.

Testing Structure

This phase will be a structured test where CRR AHs will be limited in the types of activities and can be performed. Testing will consist of workshops where EDS team members will (via WebEx or conference call) give an overview of the processes and direct guidance for downloading of network and market data, uploading provided bid and offer portfolios and downloading results. All activities will be completed within the workshops. However, there will be additional time to setup one-on-one phone support as necessary.

Test Scenarios

Below is a DRAFT list of CRR AH activities:

CRR Market User Interface

Main System Landing Page

- Verify system acceptance and recognition of CRR AH user profile

Downloads (pre-market)

- Select active market

- Download Existing CRRs

- Download Network Model

- Download Non-Thermal Constraints list

- Download Contingencies

- Download Flowgates

- Download Monitored Lines and Transformers

- Download Source/Sink list

- Download Base Loading

Auction Portfolio Manager

- Download bid/offer format

- Upload Bid/Offer Portfolio

- Edit Bid/Offer Portfolio

- Create New Bid/Offer Portfolio

- Target Portfolio to Market

Downloads (post-market)

- Download Market Results

- Download Flowgate Shadow Price

- Download Source/Sink Shadow Price

- Download Bid/Offer list

- Download Binding Constraint list

To support testing ERCOT will provide CRR AHs with step-by-step instructions for performing the required activities.

Test Data

Bid/Offer Data - ERCOT shall provide CRR AHs with the populated bid/offer portfolios for submission in .CSV or .XML format.

Registration Data - To support testing activities ERCOT shall populate the CRR system with appropriate CRR AH data.

Network Model Data - To support testing activities ERCOT shall populate the CRR system with a CRR Network Model and related files. Bids/offers created by ERCOT will relate to this set of files.

## Market Participant Involvement

Target Roles

The activities and functionality being tested in Phase 1 of EDS 3 Release 7 are relevant to the following groups:

CRR AHs: UI connectivity, bid/offer submission, file upload and download (pre and post market)

ERCOT: Monthly auction market setup, CRR Network Model and related files creation and upload to CRR System, bid/offer creation and distribution to Phase 1 participants, execution of a market

Preparation Activities

To participate in any phase of EDS3-R7 Market Participants must have completed all necessary activities relevant to their role as outlined in the previous section, Pre-EDS 3 Release 7. This includes registration, training and notification of intention to participate in each phase. It also includes NOIE Load Zone declaration by NOIEs, contract and entitlement submission for PCRR eligible NOIEs and McFRI eligibility notification by McCamey Area CRR AHs representing WGRs/QSEs.

EDS Involvement

During Phase 1 participants are required to perform all activities listed under “4.2 EDS Testing Activities”. ERCOT will work with the CRR AHs to ensure that they are sufficiently trained and will address appropriate issues to ensure proper testing.

System Readiness

For systems, participants will only require an internet connected computer, web browser and a specific digital certificate.

# Phase 2 – Mock monthly allocation and auction (ERCOT-provided data)

## Phase Overview

The intention of Phase 2 is to demonstrate the allocation, auction and bilateral trade functionality of the system. NOIEs will be guided on how and what to submit to the allocation and CRR AHs will be provided with bid/offers that they will submit to the auction. ERCOT will engage CRR AHs to explain the auction/allocation results and describe the impacts of variation in the input data (largely bids/offers). Note: ERCOT will include credit limits to constrain awards in the auction.

The reason for using ERCOT-designed bids/offers is to ensure the input data will show multiple dimensions of the CRR System optimization.

EDS Environment

* Note: Only the colored components will be tested during this phase.

During EDS3-R7 Phase 2 the EDS environment will consist of the same CRR System components as Phase 1. The applications deployed for this phase of EDS will be in a Testing configuration rather than a Production one – they are not intended to perform to production standards at this point.

The EDS systems will be available and supported from 8am to 5pm on designated “EDS Testing Days” based on the defined EDS calendar. During off hours and non-testing days the system may be unavailable for system updates, ERCOT testing, or other testing activities. Any changes in testing schedules will be reflected in the EDS testing calendar and communicated to Market Participants.

EDS Testing Schedule

Phase 2 will consist of three weeks worth of effort to conduct a mock allocation, auction and view and discuss results. There will be additional workshops for participants who did not participate in Phase 1, however the time dedicated will be limited.

- Monday Conference Call - Used to communicate with all EDS participants on

  - EDS activities planned for the week

  - Updates to online support documents & tools

  - Resolved issues or environment updates

- Workshops - The EDS team will conduct workshops during this phase. ERCOT will guide CRR AHs through the expected activities through group work activities (either via WebEx or Conf Call). CRR AHs will also have the opportunity to receive direct support from ERCOT Subject Matter Experts in one-on-one sessions as necessary. A detailed calendar of EDS workshops will be available on the Nodal Website.

- Friday Conference Call - Used to communicate with all EDS participants on

  - EDS activities accomplished during the week

  - Updates to online support documents and tools

  - Identified software or environment updates

During the workshops CRR AHs will utilize the CRR Market User Interface (MUI) to upload or retrieve the following items:

- PCRR Nominations

- Bid and Offer Portfolios

- Network Model Files

- Additional Market Files

- Market Result Files

EDS Functionality

This section outlines the system interfaces and requirements functionality that will be tested for this phase:

CRR Market User Interface

The following screens will be available for participant testing:

- Allocation Manager

- Auction Portfolio Manager

- Downloads

- Bilateral Transactions

- Messages [CRR system only] (not being tested in this phase)

- Credit Assignment Manager (not being tested in this phase)

CRR System Functionality

* Note: Only the colored components will be tested during this phase.

| Req | Req Specification Name | Description |
| --- | --- | --- |
| <Req ID> | <Title> | Partial/Full - <description> |

## EDS Testing Activities

Phase 2 will provide nomination and bid/offer validation and file upload and download verification. Specific participant actions will be defined during the EDS workshops.

Testing Structure

This phase will be a structured test where CRR AHs will be limited in the types input that can be performed. Testing will consist of workshops where EDS team members will (via WebEx or conference call) give an overview of the processes and direct guidance for creating nomination, submitting bids/offers, downloading pre-market and post-market files and conducting bilateral trades. All activities will be completed within the workshops. SMEs will be available for one-on-one phone support as necessary.

At the conclusion of the nomination and auction processes, ERCOT will engage the CRR AHs to discuss the results of the auction. This discussion will include, to the extent possible, impact of bids and offers, model sensitivities and inclusion/exclusion of modeled elements.

Test Scenarios

Below is a DRAFT list of CRR AH activities:

CRR Market User Interface

All previously identified activities

Allocation Manager

- Upload Nominations

- Download Nominations

- Modify Nominations online

Bilateral Market

- Create Trade Offers

- Create Trade Requests

- Target Trades

- Accept Trades

To support the testing ERCOT will provide CRR AHs with step-by-step instructions for performing the required activities.

Test Data

Nomination Data - ERCOT shall provide CRR AHs with directions to create online nominations and/or provide templates for submission in .CSV or .XML format. Templates can be found at https://nodal.ercot.com/TBD when they are finalized by ERCOT. A market notice will be issued when updates to the templates are available.

Bid/Offer Data - ERCOT shall provide CRR AHs with populated bid/offer portfolios for submission in .CSV or .XML format.

Bilateral Trades - ERCOT shall provide CRR AHs with directions/scripts to create and accept bilateral trades.

Registration Data - To support testing activities ERCOT shall populate the CRR system with appropriate CRR AH data.

Network Model Data - To support testing activities ERCOT shall populate the CRR system with a CRR Network Model and related files. Bids/offers created by ERCOT will relate to this set of files.

Entitlement Data - To support testing activities ERCOT shall populate the CRR system with the set of Entitlements based on NOIE eligible generation contracts.

Credit Data - To support testing activities ERCOT shall populate the CRR system with credit limits for each CRR AH or Counter Party.

## Market Participant Involvement

Target Roles

The activities and functionality being tested in Phase 2 of EDS 3 Release 7 are relevant to the following groups:

CRR CRR AHs: Nomination submission, bid/offer submission, file upload and download (pre and post market), conduct bilateral trades

ERCOT: Allocation market setup, monthly auction market setup, CRR Network Model and related files creation and upload to CRR System, bid/offer creation and distribution to Phase 2 participants, execution of market, explanation of auction market results, direct bilateral trades

Preparation Activities

To participate in Phase 2 of EDS3-R7 Market Participants must have completed all necessary activities, relevant to their role as outlined in Pre-EDS 3 Release 7. This includes registration, training and notification of intention to participate in each phase.

EDS Involvement

During Phase 2 participants are required to perform all activities listed under “5.2 EDS Testing Activities” relevant to their eligibility (eligible NOIEs will be the only participants working with Nominations).  ERCOT will work with the CRR AHs to ensure that they are sufficiently trained and will address appropriate issues to ensure proper testing.

System Readiness

For systems, participants will only require an internet connected computer, web browser and a specific Digital Certificate.

# Phase 3 – Mock Monthly Auction (MP-created data)

## Phase Overview

The intention of Phase 3 is to give CRR AHs the opportunity to better understand the intricacies of the auction by creating their own bid/offer portfolios. Because these bids and offers are created by CRR AHs themselves, ERCOT will have minimal ability to explain the auction results in detail as there may not be sufficient time to understand the impact of each individual bid.

This phase also enables CRR AHs to assign credit, which will then be a binding constraint in the optimization.

In addition, phase 3 allows CRR AHs to engage in self-directed bilateral trades.

EDS Environment

* Note: Only the colored components will be tested during this phase.

During EDS3-R7 Phase 3 the EDS environment will be consist of the same CRR System components as Phase 1 plus the credit limit assignment user interface. Market Participants planning to participate in any phase must have completed the Pre-Phase EDS3-R7 requirements.

The applications deployed for this phase of EDS will be in a Testing configuration rather than a Production one. These systems are not intended to perform to production standards at this point.

The EDS systems will be available and supported from 8am to 5pm on designated “EDS Testing Days” based on the defined EDS calendar. During off hours and non-testing days the system may be unavailable for system updates, ERCOT testing, or other testing activities. Any changes in testing schedules will be reflected in the EDS testing calendar and communicated to Market Participants.

EDS Testing Schedule

Phase 3 will consist of three weeks worth of effort to conduct a mock auction and view and discuss results. There will be additional workshops for participants who did not participate in Phase 1 or 2, but the time dedicated will be limited.

- Monday Conference Call - Used to communicate with all EDS participants on

  - EDS activities planned for the week

  - Updates to online support documents & tools

  - Resolved issues or environment updates

- Workshops - The EDS team will conduct workshops during this phase. ERCOT will guide CRR AHs through the expected activities through group work activities (either via WebEx or Conf Call). CRR AHs will also have the opportunity to receive direct support from ERCOT Subject Matter Experts in one-on-one sessions as necessary. A detailed calendar of EDS workshops will be available on the Nodal Website.

- Friday Conference Call - Used to communicate with all EDS participants on

  - EDS activities accomplished during the week

  - Updates to online support documents and tools

  - Identified software or environment updates

During the workshops CRR AHs will utilize the CRR Market User Interface (MUI) to upload, retrieve or enter the following items.

- Bid and Offer Portfolios

- Network Model Files

- Additional Market Files

- Market Result Files

- Credit Assignment

EDS Functionality

This section outlines the system interfaces and requirements functionality that will be tested for this phase:

CRR Market User Interface

The following screens will be available for Market Participant testing:

- Allocation Manager (not being tested in this phase)

- Auction Portfolio Manager

- Downloads

- Bilateral Transactions

- Messages [CRR system only]

- Credit Assignment Manager

CRR System Functionality

* Note: Only the colored components will be tested during this phase.

| Req | Req Specification Name | Description |
| --- | --- | --- |
| <Req ID> | <Title> | Partial/Full - <description> |

## EDS Testing Activities

Phase 3 will provide practice for the participants to create their own bid/offer portfolios. Specific participant actions will be defined during the EDS workshops.

Testing Structure

This phase will be a semi-structured test where CRR AHs will create their own set of bid/offer portfolios. During this phase participants will be limited to a total of 100 bids to ensure time for all ERCOT activities. Testing will consist workshops where EDS team members will (via WebEx or conference call) give an overview of the processes and direct guidance for creating nominations, creating bid/offer portfolios, assigning credit to individual markets, downloading pre-market and post market files and self directing bilateral trades. Much of Phase 3 will consist of participants creating their own strategies for bidding and then creating and submitting those bids. ERCOT SMEs will be available to support participants during the submission periods. However, ERCOT will NOT offer advice on bidding strategies.

At the conclusion of the nomination and auction processes, ERCOT will engage the CRR AHs to discuss the results of the auction. This discussion will include, to the extent possible, impact of bids and offers, model sensitivities and inclusion/exclusion of modeled elements.

Test Scenarios

Below is a DRAFT list of CRR AH activities:

CRR Market User Interface

All previously identified actions – excluding Allocation Manager

Credit Assignment Manager

- View ACL

- Distribute ACL to open markets

To support the testing ERCOT will provide CRR AHs with step-by-step instructions for performing the required activities. However, in Phases 3 and 4 the instructions will not direct the participants on bidding strategies.

Test Data

Bid/Offer Data - ERCOT shall provide CRR AHs with bid/offer templates portfolios for submission in .CSV or .XML format. Templates can be found at https://nodal.ercot.com/TBD when they are finalized by ERCOT. A market notice will be issued when updates to the templates are available.

Bilateral Trades - ERCOT shall support CRR AHs in conducting bilateral trades, however in Phase 3 participants will create, agree, target and accept trades themselves..

Registration Data - To support testing activities ERCOT shall populate the CRR system with appropriate CRR AH data.

Network Model Data - To support testing activities ERCOT shall populate the CRR system with a CRR Network Model and related files. Participants will need to create bids/offers based on this set of files.

Credit Data - To support testing activities ERCOT shall populate the CRR system with a CRR AHs ACL. Participants will need to create bids/offers based on this set of files. CRR AHs will also have to assign this credit to auction markets.

## Market Participant Involvement

Target Roles

The activities and functionality being tested in Phase 2 of EDS 3 Release 7 are relevant to the following groups:

CRR AHs: Bid/offer creation and submission, file upload and download (pre and post market), conduct bilateral trades, enter credit information

ERCOT: Monthly auction market setup, CRR Network Model and related files creation and upload to CRR System, upload ACL, execution of market, explanation of auction market results

Preparation Activities

To participate in Phase 3 of EDS3-R7 Market Participants must have completed all necessary activities, relevant to their role as outlined in Pre-EDS 3 Release 7. This includes registration, training and notification of intention to participate in each phase.

EDS Involvement

During Phase 3, participants are required to perform all activities listed under “6.2 EDS Testing Activities”. ERCOT will work with the CRR AHs to ensure that they are sufficiently trained and will address appropriate issues to ensure proper testing.

System Readiness

For systems, participants will only require an internet connected computer, web browser and a specific Digital Certificate.

# Phase 4 – Mock Multi-Month Allocation and Auction (MP-created data)

## Phase Overview

The intention of Phase 4 is to allow CRR AHs to create their own nominations and bids/offers for a multi-calendar-period allocation and auction. The allocation and auction will be at an increased level of complexity in comparison to previous phases, and CRR AHs will be given an opportunity to further practice their bidding strategies.

EDS Environment

* Note: Only the colored components will be tested during this phase.

During EDS3-R7 Phase 4 the EDS environment will be consist of the same CRR System components as Phase 3. At this point in the testing phase the CRR System will move largely to a production configuration – however, not all components of interacting systems may be on production at this point.

The EDS systems will be available and supported from 8am to 5pm on designated “EDS Testing Days” based on the defined EDS calendar. During off hours and non-testing days the system may be unavailable for system updates, ERCOT testing, or other testing activities. Any changes in testing schedules will be reflected in the EDS testing calendar and communicated to Market Participants.

EDS Testing Schedule

Phase 4 will consist of four weeks worth of effort to conduct a mock allocation, auction and view and discuss results. Much of the time of Phase 4 will consist of time for participants to determine their nomination and bidding strategies. There will be additional workshops for participants who did not participate in Phases 1, 2 or 3, but the time dedicated will be limited.

- Monday Conference Call - Used to communicate with all EDS participants on

  - EDS activities planned for the week

  - Updates to online support documents & tools

  - Resolved issues or environment updates

- Workshops - The EDS team will conduct workshops during this phase. ERCOT will guide CRR AHs through the expected activities through group work activities (either via WebEx or Conf Call). CRR AHs will also have the opportunity to receive direct support from ERCOT Subject Matter Experts in one-on-one sessions as necessary. A detailed calendar of EDS workshops will be available on the Nodal Website.

- Friday Conference Call - Used to communicate with all EDS participants on

  - EDS activities accomplished during the week

  - Updates to online support documents and tools

  - Identified software or environment updates

During the workshops CRR AHs will utilize the CRR Market User Interface (MUI) to upload, retrieve or enter the following submission items.

- PCRR Nominations

- Bid and Offer Portfolios

- Network Model Files

- Additional Market Files

- Market Result Files

- Credit Assignment

EDS Functionality

This section outlines the system interfaces and requirements functionality that will be tested for this phase:

CRR Market User Interface

The following screens will be available for Market Participant testing:

- Allocation Manager

- Auction Portfolio Manager

- Downloads

- Bilateral Transactions (not tested in this phase)

- Messages [CRR system only]

- Credit Assignment Manager

CRR System Functionality

* Note: Only the colored components will be tested during this phase.

| Req | Req Specification Name | Description |
| --- | --- | --- |
| <Req ID> | <Title> | Partial/Full - <description> |

## EDS Testing Activities

Phase 4 will provide exposure to the annual allocation and auction processes as well as practice for the participants to create their own bid/offer portfolios. Specific participant actions will be defined during the EDS workshops.

Testing Structure

This phase will be a semi-structured test where CRR AHs will create their own set of nominations and bid/offer portfolios. Testing will consist of workshop where EDS team members will (via WebEx or conference call) give an overview of the processes and direct guidance for creating nominations, bid/offer portfolios, assigning credit and downloading pre-market and post market files. Much of Phase 4 will consist of participants creating their own strategies for nominations and bidding and creating and submitting data. ERCOT SMEs will be available to support participants during the submission periods. However, ERCOT will NOT offer advice on bidding or nomination strategies.

At the conclusion of the nomination and auction processes, ERCOT will engage the CRR AHs to discuss the results of the auction. This discussion will include, to the extent possible, impact of bids and offers, model sensitivities and inclusion/exclusion of modeled elements.

Test Scenarios

Below is a DRAFT list of CRR AH activities:

CRR Market User Interface

All previously identified actions

To support the testing ERCOT will provide CRR AHs with step-by-step instructions for performing the submission activities. However, in Phases 3 and 4 the instructions will not direct the participants on bidding strategies.

Test Data

Nomination Data - ERCOT shall provide CRR AHs with the nominations templates for submission in .CSV or .XML format. Templates can be found at https://nodal.ercot.com/TBD when they are finalized by ERCOT. A market notice will be issued when updates to the templates are available.

Bid/Offer Data - ERCOT shall provide CRR AHs with bid/offer templates portfolios for submission in .CSV or .XML format. Templates can be found at https://nodal.ercot.com/TBD when they are finalized by ERCOT. A market notice will be issued when updates to the templates are available.

Registration Data - To support testing activities ERCOT shall populate the CRR system with appropriate CRR AH data.

Network Model Data - To support testing activities ERCOT shall populate the CRR system with a CRR Network Model and related files. Participants will need to create bids/offers based on this set of files.

Entitlement Data - To support testing activities ERCOT shall populate the CRR system with the set of Entitlements based on NOIE eligible generation contracts.

Credit Data - To support testing activities ERCOT shall populate the CRR system with a CRR AHs ACL. Participants will need to create bids/offers based on this set of files. CRR AHs will also have to assign this credit to auction markets.

## Market Participant Involvement

Target Roles

The activities and functionality being tested in Phase 4 of EDS 3 Release 7 are relevant to the following groups:

CRR AHs: Nomination creation and submission, Bid/offer creation and submission, file upload and download (pre and post market), enter credit information

ERCOT: Annual allocation market setup, annual auction market setup, CRR Network Model and related files creation and upload to CRR System, upload ACL, execution of market, explanation of market results

Preparation Activities

To participate in Phase 4 of EDS3-R7 Market Participants must have completed all necessary activities, relevant to their role as outlined in Pre-EDS 3 Release 7. This includes registration, training and notification of intention to participate in each phase.

EDS Involvement

During Phase 4 participants are required to perform all activities listed under “7.2 EDS Testing Activities” relevant to their eligibility (eligible NOIEs will be the only participants working with Nominations). ERCOT will work with the CRR AHs to ensure that they are sufficiently trained and will address appropriate issues to ensure proper testing.

System Readiness

For systems, participants will only require an internet connected computer, web browser and a specific Digital Certificate.

# Phase 5 – Integration Testing

## Phase Overview

This intention of Phase 5 is demonstrate the integration of CRR with other “up-stream” Nodal systems.

*Note: The timing of this phase is yet to be determined and is based on system integration activity.

EDS Environment

* Note: Only the colored components will be tested during this phase.

During EDS3-R7 Phase 5 the EDS environment will be consist of the same CRR System components as Phase 4 with the addition of the fully integrated ‘up-stream’ systems. Downstream systems will be tested in EDS4 as part of the receiving systems testing. At this point in the testing phase, CRR System will move largely to a production configuration – however, not all components of interacting systems may be on production at this point in the EDS cycle.

The EDS systems will be available and supported from 8am to 5pm on designated “EDS Testing Days” based on the defined EDS calendar. During off hours and non-testing days the system may be unavailable for system updates, ERCOT testing, or other testing activities. Any changes in testing schedules will be reflected in the EDS testing calendar and communicated to Market Participants.

EDS Testing Schedule

Phase 5 will consist of a single week to verify information that has been directly pushed via integrated upstream systems.

- Monday Conference Call - Used to communicate with all EDS participants on

  - EDS activities planned for the week

  - Updates to online support documents & tools

  - Resolved issues or environment updates

- Workshops - The EDS team will conduct workshops during this phase (either via WebEx or Conf Call). A detailed calendar of EDS workshops will be available on the Nodal Website.

- Friday Conference Call - Used to communicate with all EDS participants on

  - EDS activities accomplished during the week

  - Updates to online support documents and tools

  - Identified software or environment updates

During the workshops AHs will utilize the CRR Market User Interface (MUI) to upload and retrieve the following items.

- Network Model Files

- Additional Market Files

- Market Result Files

- Credit Assignment

EDS Functionality

This section outlines the system interfaces and requirements functionality that will be tested for this phase:

Internal ERCOT Interfaces

Information will be automatically input from the following upstream systems:

- NMMS

- Registration (Siebel)

- CMM

CRR Market User Interface

Information will be downloaded from the following screens:

- Downloads

- Credit Assignment Manager

CRR System Functionality

* Note: Only the colored components will be tested during this phase.

| Req | Req Specification Name | Description |
| --- | --- | --- |
| <Req ID> | <Title> | Partial/Full - <description> |

## EDS Testing Activities

Phase 5 will provide the opportunity for participants to verify the CRR interface functionality. Specific Market Participant actions will be defined during the EDS workshops.

Testing Structure

This phase will be a structured test where AHs will download and verify that the CRR System has received appropriate files from upstream systems. Testing will consist of workshops where EDS team members will (via WebEx or conference call) give guidance for the download of pre-market market files and review imported credit limit.

Test Scenarios

Below is a DRAFT list of AH activities:

CRR Market User Interface

Downloads (pre-market)

- Select active market

- Download Network Model

- Download Non-Thermal Constraints list

- Download Contingencies

- Download Flowgates

- Download Monitored Lines and Transformers

- Download Source/Sink list

Credit Assignment Manager

- Review ACL

To support the testing ERCOT will provide AHs with step-by-step instructions for performing the required activities.

Test Data

Registration Data - The ERCOT interface shall populate the CRR system will be with appropriate CRR AH data by ERCOT.

Network Model Data - The ERCOT interface shall populate the CRR system with a CRR Network Model and related files.

Credit Data - The ERCOT interface shall populate the CRR system with a CRR AHs ACL.

## Market Participant Involvement

Target Roles

The activities and functionality being tested in Phase 4 of EDS 3 Release 7 are relevant to the following groups:

CRR AHs: File download (pre-market) and review, validate credit

ERCOT: Market setup

Preparation Activities

To participate in Phase 4 of EDS3-R7 Market Participants must have completed all necessary activities, relevant to their role as outlined in Pre-EDS 3 Release 7. This includes registration, training and notification of intention to participate in each phase.

EDS Involvement

During Phase 4 participants are required to perform all activities listed under “8.2 EDS Testing Activities”.

System Readiness

For systems, participants will only require an internet connected computer, web browser and a specific Digital Certificate.

# EDS Communications

To ensure that Market Participants are kept abreast of the developments before and during the EDS, ERCOT has designed the following communication channels:

## EDS Planning Workshops

To ensure that both ERCOT and the Market Participants maximize the benefits of the EDS, starting May 2007 the EDS team will be scheduling monthly planning workshops and ongoing conference calls to complete the details required for EDS execution. The workshops will focus on: test preparations; testing scenarios; the detailed test procedures and schedule of the test sequences; test sequence planning at the QSE and Resource level; and a substantive list of specific entry and exit criteria for each EDS Release; and the final exit criteria that signifies the completion of all Transition Plan activities that support a declaration of readiness. The EDS planning workshops will provide input for the test plans and test scenarios to support the day-to-day testing activities.

## Online Readiness Center

Online readiness support for the ERCOT and market participant transition to the nodal market as well as supporting EDS documentation can be found in the Nodal Transition Readiness Center on the ERCOT Nodal Website: http://nodal.ercot.com/readiness/index.html

## NOIE/McFRI EDS3-R7 Kickoff Session

Channel: Meeting (Austin), WebEx

Audience: NOIEs and McCamey Area Wind Generation Resources

Timing: Early November 2007

Materials: Agenda, EDS Handbook

Notes: Cover the following:

- Contract/Entitlement submission

- NOIE Load Zone declaration

- McFRI eligibility declaration

- Registration

- Q&A

## Full Participant EDS3-R7 Kickoff Session

Channel: Meeting (Austin), WebEx

Audience: All Market Participants intending to participate

Timing: Early November 2007

Materials: Agenda, EDS Handbook

Notes: Cover the following:

- Registration

- EDS3-R7 Overview

- Q&A

## EDS Weekly Conference Calls

Channel: Conference Call

Audience: Participating MPs

Timing: Twice Weekly (Monday and Friday)

Materials: TBD

## Weekly Status Bulletin

Need to refine:

Channel: Market Notice, web

Audience: CRR AHs/participants

Timing: End of test week

Materials: Weekly status bulletin

Notes: Covers weekly status during formal testing. Interim bulletins may be sent as needed.

## Issue Tracking Process

Prior to the delivery of market systems and associated business functionality to the EDS environment each application will be run through a series of testing phases to identify and resolve as many of the defects as possible. Some of the testing phases include Pre-FAT that would be done at the vendor site, Factory Acceptance Testing (FAT) that would be executed at ERCOT and finally Integration Testing (ITest) aimed at integrate testing all Nodal applications. Defects identified during these phases would be logged and tracked internally for resolution.  Given the accelerated release of many of the systems into the EDS environment and the gradual increase in quality of systems, it is anticipated that there will be defects discovered by the Market Participants.  These defects should be reported to ERCOT using a  Market Participant Issue Reporting Form (sample in appendix).   All items will be investigated by ERCOT testing personnel and logged into the internal defect tracking system.  Defect statuses will be discussed at the end of the week wrap-up call as well as posted on the Nodal Readiness Center website which will be updated weekly (process overview in appendix- TBD)

## Entry / Exit Criteria

Entry Criteria

ERCOT Activities:

- CRR System application running in EDS environment

- FAT complete

- Security testing complete

- Limited iTest complete

Market Participant Activities:

- Complete Pre-EDS3R7 activities

Exit Criteria

ERCOT Activities:

- No unresolved system errors

Market Participant Activities:

- None

- Appendix

## Issue Submission Lifecycle

## Draft Issue Submission Form