## Nodal Project Schedule
Texas Nodal Market Implementation Schedule
Nodal Project Dates
Features | Project | Readiness Criteria Measurement Begins | TNM Implementation | Performance Measured | Compliance Application | Status G/Y/R | Prev Status | Mitigation Activities | Comments
EDS 1, Release 1 | EMS 1 | 2007-07-01 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 1, Release 2 | EMS 2 A | 2007-09-01 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 2, Release 3 | EMS 2 B, EDW 1 | 2007-10-01 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 2, Release 4 | NMMS 1, NMMS 2, EIP 1 | 2007-12-01 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 3, Registration | REG 1 | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 3, Release 5 | EDW 2, MMS 1, S&B 1, EIP 2, EMS 2C, MIS 1, EIP3 | 2007-10-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 3, Release 6 | EMS 3, EDW 3, | 2008-01-03 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 3, Release 7 | CRR 1, EIP 5, EDW 4 | 2008-01-03 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 4, Release 8 | MMS 2, S&B 2, EIP 6, EDW 5 | 2008-03-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 4, NOMCR |  | 2008-02-01 | 2008-04-01 | 2008-06-01 | 2008-10-01
EDS 4, Release 9, Baseline 1, 2 | OS 1, NMMS 3, EMS4, S&B 3, EIP 7, EMS 5, S&B 4, EDW 6 | 2008-05-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 4, Release 9, ERCOT, QSE & TSP Responsibilities |  | 2008-01-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
ERCOT Business Processes
Load Forecasting/Adequacy |  | 2008-05-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
Renewable Production Potential Forecasts |  | 2008-06-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
Contracts for Reliability Resources |  | 2008-06-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
Standards for Determining Ancillary Service Quantities |  | 2008-10-01 | 2008-10-01 | 2008-10-01 | 2008-10-01
2-Day Response for Outage (Section 3.1.5.3) |  | 2008-04-01 | 2008-07-01 | 2008-09-01 | 2008-12-01 |  |  |  | Implementation schedule pending from ERCOT
Full Nodal Functionaliy in Preparation for the 168-Hour Test Process |  | 2008-07-01 | N/A | N/A | N/A
PCRR Documentation Delivered to ERCOT |  | 2007-10-01 | 2008-09-30 | N/A | 2009-06-01
NOIE Load Zone Declaration |  | 2007-10-01 | 2008-12-01 | N/A | N/A
CRR Auction |  | 2008-01-01 | 2008-09-30 | 2008-12-01
Standard Form Agreements Completed |  | 2007-08-01 | 2007-10-15 | N/A | 2007-10-15
Real-Time Market Go-Live |  |  | 2008-12-01 | 2008-12-01 | 2009-06-01
Day-Ahead Market Go-Live |  |  | 2008-12-07 | 2008-12-08 | 2009-06-01
Zonal Control Systems Retire |  | 2009-02-01 | 2009-02-01 | 2009-02-01 | 2009-02-01
Zonal Settlement Systems Retire |  | Never | Never | Never | Never
Formulas:
Compliance Application = [Performance Measured]+92
Compliance Application = [TNM Implementation]
Performance Measured = [TNM Implementation]+62

## Nodal Protocol Application
Nodal Section Number | Nodal Section Title | Effective Date for Rediness Criteria Measurement | Texas Nodal Market Implementation Date | Performance Measured Under Nodal Section 8 Date | Nodal Compliance Application Date | Zonal Section Number | Zonal Section Title | Zonal Retirement Date | Comments
1 | Overview | 2007-07-01 | 2007-07-01 | 2007-07-01 | 2007-07-01
2 | Definitions and Acronyms | 2007-07-01 | 2007-07-01 | 2007-07-01 | 2007-07-01
3 | Management Activities for the ERCOT System
3.1 | Outage Coordination except 3.1.5.3 | 2008-01-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
3.1.5.3 | Timelines for response by ERCOT for TSP Requests | 2008-03-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
3.2 | Analysis of Long-Term Resource Adequacy | 2008-05-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
3.3 | Management of Changes to ERCOT Transmission Grid | 2008-02-01 | 2008-04-01 | 2008-06-01 | 2008-10-01
3.4 | Load Zones | 2007-07-01 | 2007-07-01 | N/A | N/A | N/A
3.5 | Hubs | 2007-07-01 | 2007-07-01 | N/A | N/A |  |  |  | Zonal Hubs are applicable to zonal market.
3.6 | Load Participation | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.7 | Resource Parameters | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.8 | Special Considerations for Split Generation Meters | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.9 | Current Operating Plan (COP) | 2007-10-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
3.10 | Network Operations Modeling and Telemetry
3.10.1 | Time Line for Network Model Change Requests | 2008-02-01 | 2008-04-01 | 2008-06-01 | 2008-10-01
3.10.2 | ERCOT Annual Planning Model | 2008-01-01 | 2008-09-30 | 2008-12-01 | 2008-12-01
3.10.3 | CRR Network Model | 2008-01-03 | 2008-09-30 | 2008-12-01 | 2009-06-01
3.10.4 | ERCOT Responsibilities | 2008-01-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
3.10.5 | TSP Responsibilities | 2008-01-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
3.10.6 | Resource Entity Responsibilities | 2008-01-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
3.11 | Transmission Planning | 2008-01-01 | 2008-09-30 | 2008-12-01 | 2008-12-01
3.12 | Load Forecasting | 2008-05-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
3.13 | Renewable Production Potential Forecasts | 2008-06-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
3.14 | Contracts for Reliability Resources | 2008-06-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
3.15 | Voltage Support | 2008-01-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
3.16 | Standards for Determining Ancillary Service Quantities | 2008-10-01 | 2008-12-01
3.17 | Ancillary Service Capacity Products | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.18 | Resource Limits in Providing Ancillary Service | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.19 | Constraint Competitiveness Tests | 2008-01-03 | 2008-12-01 | 2008-05-01 | 2008-12-01 |  |  |  | The CCT implementation must be implemented in sufficient time to allow CMWG/TAC to evaluate the constraint classifications Competitive/non-competitive prior to market open.
4 | Day-Ahead Operations | 2008-05-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
5 | Transmission Security Analysis and Reliability Unit Commitment (RUC) | 2008-05-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
6 | Adjustment Period and Real-Time Operations | 2007-10-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
7 | Congestion Revenue Rights
7.1 | Function of Congestion Revenue Rights | 2008-01-03 | 2008-09-30 | 2008-12-01 | 2009-06-01
7.2 | Characteristics of Congestion Revenue Rights | 2008-01-03 | 2008-09-30 | 2008-12-01 | 2009-06-01
7.3 | Types of Congestion Revenue Rights to Be Auctioned | 2008-01-03 | 2008-09-30 | 2008-12-01 | 2009-06-01
7.4 | Allocation of Preassigned Congestion Revenue Rights | 2008-09-30 | 2008-09-30 | 2008-12-01 | 2008-10-01
7.5 | CRR Auctions | 2008-01-03 | 2008-09-30 | 2008-12-01 | 2009-06-01
7.6 | CRR Balancing Account | 2008-01-03 | 2008-09-30 | 2008-12-01 | 2009-06-01
7.7 | Congestion Management in McCamey Area | 2008-09-30 | 2008-09-30 | 2008-12-01 | 2008-10-01
7.8 | Bilateral Trades and ERCOT CRR Registration System | 2008-01-03 | 2008-09-30 | 2008-12-01 | 2009-06-01
7.9 | CRR Settlements | 2008-01-03 | 2008-09-30 | 2008-09-30 | 2008-09-30
8 | Performance Monitoring and Compliance
8.1 | QSE/Resource Performance Monitoring and Compliance | 2008-01-03 | 2008-12-01 | 2008-01-03 | 2009-06-01 |  |  |  | Regulation AS certification begins in EDS3 Release 6 testing. Resources not subject to certification will qualify for AS in accordance with Section 8 prior to market open.
8.2 | ERCOT Performance Monitoring and Compliance | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2009-06-01 |  |  |  | ERCOT performance monitoring is performed by the IMM. IMM reports are reviewed by the TAC.
8.3 | TSP Performance Monitoring and Compliance | 2008-02-01 | 2008-12-01 | 2008-07-01 | 2009-06-01 |  |  |  | ERCOT must develop a TSP Monitoring Program and obtain TAC approval.
8.4 | Non-Compliance | NA | NA | NA | 2009-06-01
8.5 | Frequency Response Requirements and Monitoring | 2008-07-01 | 2008-12-01 | 2008-07-01 | 2009-06-01 |  |  |  | Frequency Response provisions must be in effect beginning with the test sequence that implements the nodal LFC as the system frequency control.
9 | Settlement and Billing | 2008-03-01 | 2008-12-01 | 2008-12-01 | 2008-12-01 | 9 | Settlement and Billing
[6 empty] | 9.1 | Overview | TBD | All sections with a Retire Date = TBD are subject to Expiration of Confidentiality (section 1.3.3) as stated in section 9.5.2 of the protocols.
[6 empty] | 9.2 | Settlement Statements
[6 empty] | 9.2.3 | Initial Statements | 2008-12-10 | Last operating day 11/30/2008
[6 empty] | 9.2.4 | Final Statements | 2009-01-28 | Last operating day 11/30/2008
[6 empty] | 9.2.5 | Resettlement Statement | TBD | Dependent on whether disputes are submitted and granted. Typically run no later than 10 business days after dispute is granted. If the True-Up of the last zonal operating day (11/30/2008) is the last dispute submitted then in theory the last Resettlement statement would be posted no later than 7/10/2009.
[6 empty] | 9.2.6 | True-Up Statement | 2009-06-01 | Last operating day 11/30/2008
[6 empty] | 9.3 | Settlement Invoice | TBD
[6 empty] | 9.4 | Payment Process
[6 empty] | 9.4.2 | Invoice Payments Due ERCOT | TBD
[6 empty] | 9.4.3 | ERCOT Payment to Invoice Recipients | TBD
[6 empty] | 9.5 | Settlement and Billing Dispute Process
[6 empty] | 9.5.2 | Notice | TBD
[6 empty] | 9.5.4 | ERCOT Processing of Disputes | TBD
[6 empty] | 9.6 | Settlement Charges | TBD
[6 empty] | 9.7 | Administrative Fees | TBD
10 | Metering | Assigned to Bob
10.1 | Overview
10.2 | Scope of Metering Responsibilities
10.3 | Meter Data Acquisition System (MDAS)
10.4 | Certification of EPS Metering Facilities
10.5 | TSP and DSP EPS Meter Inspectors
10.6 | Auditing and Testing of Metering Facilities
10.7 | ERCOT Request for Installation of EPS Metering Facilities
10.8 | Maintenance of Metering Facilities
10.9 | Standards for Metering Facilities
10.10 | Security of Meter Data
10.11 | Validating, Editing, and Estimating of Meter Data
10.12 | Communications
10.13 | Meter Identification
10.14 | Exemptions from Compliance to Metering Protocols
11* | Data Acquisition and Aggregation | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
12 | Market Information System | 2007-10-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
13 | Transmission and Distribution Losses | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
14* | State of Texas Renewable Energy Credit Trading Program | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
15* | Customer Registration | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
16 | Registration and Qualification of Market Participants
16.1 | Qualification, Registration, and Execution of Agreements | 2007-08-01 | 2007-10-15 | N/A | 2007-10-15 |  |  |  | Standard Form Agreement replaces existing ERCOT/MP agreements
16.2 | Registration and Qualification of Qualified Scheduling Entities | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.3 | Registration of Load Serving Entities | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.4 | Registration of ERCOT and Non-ERCOT Transmission and Distribution Service Providers | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.5 | Registration of a Resource Entity | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.6 | Registration of Municipally Owned Utilities and Electric Cooperatives in the ERCOT Region | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.7 | Registration of Renewable Energy Credit Account Holders | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.8 | Registration and Qualification of Congestion Revenue Rights Account Holders | 2008-07-01 | 2008-09-30 | 2008-09-30 | 2008-09-30
16.9 | Resources Providing Reliability Must-Run Service | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.10 | Resources Providing Black Start Service | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.11 | Financial Security for Counter-Parties | 2008-07-01 | 2008-09-30 | 2008-12-01 | 2008-12-01 |  |  |  | 9/30/08 date in place for Market Participants who will participate in the CRR Auction
16.12 | User Security Administrator and Digital Certificates | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
17 | Market Monitoring and Data Collection | 2008-05-01 | 2008-07-01 | N/A | N/A
18* | Load Profiling | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
19* | Texas Standard Electronic Transaction (TX SET) | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
20* | Alternative Dispute Resolution Procedure | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
21* | Process for Protocol Revision | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
22 | Agreements |  |  |  |  | 22 | Agreements
| Attachment F: Standard Form Reliability Must-Run Agreement | [5 empty] | Standard Form Reliability Must-Run Agreement
| Standard Form Black Start Agreement | [5 empty] | Standard Form Black Start Agreement
| Attachment B: Standard Form Market Participant Agreement | 2007-10-15 |  |  |  |  | Standard Form Load Serving Entity Agreement | 2007-10-15
[7 empty] | Standard Form Qualified Scheduling Entity Agreement | 2007-10-15
| Standard Form REC Account Agreement | [5 empty] | Standard Form REC Account Agreement
[7 empty] | Standard Form Resource Entity Agreement | 2007-10-15
[7 empty] | Standard Form Transmission and/or Distribution Service Provider Agreement | 2007-10-15
| Standard Form TCR Account Holder Agreement | [5 empty] | Standard Form TCR Account Holder Agreement
| Notification of Suspension of Operations | [5 empty] | Notification of Suspension of Operations
Standard Form Synchronous Condenser Agreement
23* | Texas Test Plan Team - Retail Market Testing | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
24* | Retail Point to Point Communications | N/A | 2008-12-01 | 2008-12-01 | 2008-12-01
ERCOT Fee Schedule - 2006* |  | Assigned to Legal
* - From Zonal Protocol
Formulas:
Texas Nodal Market Implementation Date = [Texas Nodal Market Implementation Date, row above]
Nodal Compliance Application Date = [Nodal Compliance Application Date, row above]
Nodal Compliance Application Date = [Texas Nodal Market Implementation Date]

## Section by Section Disposition
Zonal Section Number | Zonal Section Title | Retirement Date
1 | Overview
1.1 | Summary of the ERCOT Protocols Document
1.2 | Functions of ERCOT
1.3 | Confidentiality
1.4 | Operational Audit
1.5 | ERCOT Fees and Charges
1.6 | Rules of Construction
1.7 | Effective Date
2 | Definitions and Acronyms
2.1 | Definitions
2.2 | Acronyms
3 | Open Access to the ERCOT Transmission Grid
3.1 | Overview
3.2 | Eligibility for Transmission Service
3.3 | Nature of Transmission Service
3.4 | Payment for Transmission Access Service
3.5 | Interconnection of New Generation
4 | Scheduling
4.1 | Overview of the Scheduling Process
4.2 | Scheduling-Related Duties of ERCOT
4.3 | Scheduling-Related Duties of Qualified Scheduling Entities
4.4 | Day Ahead Scheduling Process
4.5 | Adjustment Period Scheduling Process
4.6 | Operating Period Process
4.7 | Validation and Correction of Schedule Data
4.8 | Temporary Deviations from Scheduling Procedures
4.9 | Dynamic Schedules
4.10 | Resource Plan Performance Metrics
5 | Dispatch
5.1 | ERCOT Control Area Authority
5.2 | North American Electric Reliability Corporation/ERCOT Tagging Procedures
5.3 | Routine Dispatch Duties of ERCOT
5.4 | Dispatch Instructions
5.5 | Changes in ERCOT System Status
5.6 | Emergency and Short Supply Operation
5.7 | Block Load Transfers between ERCOT and Non-ERCOT Control Areas
5.8 | BtB Ties and BLTs with the CFE Control Area
5.9 | Frequency Response Requirements and Monitoring
6 | Ancillary Services
6.1 | Ancillary Services Required by ERCOT
6.2 | Providers of Ancillary Services
6.3 | Responsibilities of ERCOT and Qualified Scheduling Entities
6.4 | Standards and Determination of the Control Area Requirements for Ancillary Services
6.5 | Ancillary Services Selection and Requirements
6.6 | Selection Methodology
6.7 | Deployment Policy
6.8 | Compensation for Services Provided
6.9 | Settlement for ERCOT-Provided Ancillary Services
6.10 | Ancillary Service Qualification, Testing and Performance Standards
6.11 | System-Wide Offer Caps
7 | Congestion Management
7.1 | Overview of ERCOT Congestion Management
7.2 | CSC Zone Determination Process
7.3 | Congestion Management for CSCs/Zonal Congestion
7.4 | Congestion Management for Local Congestion
7.5 | Transmission Congestion Rights
7.6 | Incorporation of Reliability Must-Run and Out of Merit Order Resources
7.7 | Remedies to Congestion Through Transmission Expansion
7.8 | Congestion Management in McCamey Area
7.9 | Trading Hubs
8 | Planned Outages and Maintenance Outages of Transmission and Resource Facilities
8.1 | Outage Coordination
8.2 | Communications Regarding Resource Facility and Transmission Facility Outages
8.3 | ERCOT Approval of Transmission System Outages
8.4 | Acceptance of Proposed Planned Outages of Resources other than Reliability Resources
8.5 | Approval of RMR Unit, Synchronous Condenser Unit or Black Start Resource Outages
8.6 | Management of Resource Outages other than Reliability Resources
8.7 | Long-Term-Demand Forecasts
8.8 | Coordination for System Topology Modifications
9 | Settlement and Billing
9.1 | Overview | TBD
9.2 | Settlement Statements
9.2.3 | Initial Statements | 2008-12-10
9.2.4 | Final Statements | 2009-01-28
9.2.5 | Resettlement Statement | TBD
9.2.6 | True-Up Statement | 2009-06-01
9.3 | Settlement Invoice | TBD
9.4 | Payment Process
9.4.2 | Invoice Payments Due ERCOT | TBD
9.4.3 | ERCOT Payment to Invoice Recipients | TBD
9.5 | Settlement and Billing Dispute Process
9.5.2 | Notice | TBD
9.5.4 | ERCOT Processing of Disputes | TBD
9.6 | Settlement Charges | TBD
9.7 | Administrative Fees | TBD
9.8 | Transmission Billing Determinant Calculation
9.9 | Profile Development Cost Recovery Fee for a Non-ERCOT Sponsored Load Profile Segment
10 | Metering
10.1 | Overview
10.2 | Scope of Metering Responsibilities
10.3 | Meter Data Acquisition System (MDAS)
10.4 | Certification of ERCOT Polled Settlement Metering Facilities
10.5 | TDSP ERCOT Polled Settlement Meter Inspectors
10.6 | Auditing and Testing of Metering Facilities
10.7 | ERCOT Request for Installation of ERCOT Polled Settlement Metering Facilities
10.8 | Maintenance of Metering Facilities
10.9 | Standards for Metering Facilities
10.10 | Security of Meter Data
10.11 | Validating, Editing, and Estimating of Meter Data
10.12 | Communications
10.13 | Meter Identification
10.14 | Exemptions from Compliance to Metering Protocols
11 | Data Acquisition and Aggregation
11.1 | Data Acquisition And Aggregation From ERCOT Polled Settlement (EPS) Metered Entities
11.2 | Data Acquisition From TDSPs
11.3 | ESI ID Synchronization
11.4 | Load Data Aggregation
11.5 | Data Aggregation
11.6 | Unaccounted For Energy (UFE) Analysis
12 | Market Information System
12.1 | Overview
12.2 | ERCOT Obligation to Provide Information
12.3 | Transmission-Related Information
12.4 | Market-Related Information
12.5 | Applicable Reliability Standards
13 | Transmission and Distribution Losses
13.1 | Overview
13.2 | Transmission Losses
13.3 | Distribution Losses
13.4 | Special Loss Calculations for Settlement and Analysis
14 | State of Texas Renewable Energy Credit Trading Program
14.1 | Overview
14.2 | Duties of ERCOT
14.3 | Duties of the PUCT
14.4 | Creation of REC Accounts and Attributes of RECs
14.5 | Registration to Become a REC Generator or REC Aggregation Company
14.6 | Reporting Requirements
14.7 | Awarding of RECs
14.8 | Transfer of RECs Between Parties
14.9 | REC Offsets
14.10 | Allocation of Statewide REC Requirement Among Competitive Retailers
14.11 | Retiring of RECs
14.12 | Penalties and Enforcement
14.13 | Maintain Public Information
14.14 | Submit Annual Report to Public Utility Commission of Texas
15 | Customer Registration
15.1 | Customer Switch of Competitive Retailer
15.2 | Database Queries
15.3 | Monthly Meter Reads
15.4 | Electric Service Identifier (ESI ID)
16 | Registration and Qualification of Market Participants
16.1 | Registration and Execution of Agreements
16.2 | Registration and Qualification of Qualified Scheduling Entities
16.3 | Registration of Load Serving Entities
16.4 | Registration of ERCOT and Non-ERCOT Transmission and Distribution Service Providers (TDSP)
16.5 | Registration of Generation Resources, Loads Acting as a Resource and Emergency Interruptible Load Service Resources
16.6 | Registration of Municipally Owned Utilities and Electric Cooperatives in the ERCOT Region
16.7 | Registration of REC Account Holders
16.8 | Registration of TCR Account Holders
16.9 | Resources Providing Reliability Must Run Service or Synchronous Condenser Service
16.10 | Resources Providing Black Start Service
16.11 | User Security Administrator and Digital Certificates
17 | Market Data Collection and Use
17.1 | Objectives and Scope
17.2 | Data Collection and Retention
17.3 | Types of Data Made Available to the PUCT
17.4 | Provision of Data to Individual Market Participants
17.5 | Reports to the PUCT and the FERC
17.6 | Changes to Facilitate Market Operation
18 | Load Profiling
18.1 | Overview
18.2 | Methodology
18.3 | Posting
18.4 | Assignment of Load Profile ID
18.5 | Additional Responsibilities
18.6 | Installation and Use of Interval Data Recorders
18.7 | Supplemental Load Profiling
19 | Texas Standard Electronic Transaction (TX SET)
19.1 | Overview
19.2 | Methodology
19.3 | Texas Standard Electronic Transaction Definitions
19.4 | Texas SET Change Control Documentation
19.5 | Texas SET Acceptable Extended Character Set
19.6 | Texas SET Envelope Standards
20 | Alternative Dispute Resolution Procedure
20.1 | Applicability
20.2 | Initiation and Pursuit of ADR Process
20.3 | Informal Dispute Resolution
20.4 | Mediation Procedures
20.5 | Arbitration Procedures
20.6 | Dispute Resolution Costs
20.7 | Requests for Data
20.8 | Resolution of Disputes and Notification to Market Participants
20.9 | Settlement of Approved ADR Claims
21 | Process for Protocol Revision
21.1 | Introduction
21.2 | Submission of a Protocol Revision Request
21.3 | Protocol Revision Subcommittee
21.4 | Protocol Revision Procedure
21.5 | Urgent Requests
21.6 | Protocol Revision Implementation
21.7 | Submission of a System Change Request
21.8 | System Change Request Procedure
21.9 | Review of Project Prioritization, Review of Unfunded Project List, and Annual Budget Process
21.10 | Review of Guide Changes
21.11 | Process for Nodal Protocol Revisions
22 | Agreements
22(A) | Standard Form Black Start Agreement
22(B) | Standard Form Load Serving Entity Agreement | 2007-10-15
22(C) | Standard Form Qualified Scheduling Entity Agreement | 2007-10-15
22(D) | Standard Form REC Account Agreement
22(E) | Standard Form Resource Entity Agreement | 2007-10-15
22(F) | Standard Form Reliability Must-Run Agreement
22(G) | Standard Form Transmission and/or Distribution Service Provider Agreement | 2007-10-15
22(H) | Standard Form TCR Account Holder Agreement
22(I) | Notification of Suspension of Operations
22(J) | Standard Form Synchronous Condernser Agreement
22(K) | Standard Form Emergency Interruptible Load Service (EILS) Agreement
22(L) | Standard Form Market Participant Agreement
23 | Texas Test Plan Team – Retail Market Testing
23.1 | Overview
23.2 | Testing Participants
23.3 | Documentation and Testing Materials
23.4 | Market Changes
23.5 | Testing Success
24 | Retail Point to Point Communications
24.1 | Maintenance Service Order Request
24.2 | Transmission Distribution Service Provider to Competitive Retailer Invoice
24.3 | Monthly Remittance
24.4 | MOU/EC TDSP to CR Monthly Remittance Advice
24.5 | Maintain Customer Information Request
24.6 | MOU/EC TDSP to CR Maintain Customer Information Request
ERCOT Fee Schedule - 2006
Nodal Section Number | Nodal Section Title | Implementation Date
1 | Overview | 2007-07-01
2 | Definitions and Acronyms | 2007-07-01
3 | Management Activities for the ERCOT System
3.1 | Outage Coordination | 2008-07-01
3.1.5.3 | Timelines for response by ERCOT for TSP Requests | 2008-07-01
3.2 | Analysis of Long-Term Resource Adequacy | 2008-10-01
3.3 | Management of Changes to ERCOT Transmission Grid
3.4 | Load Zones | 2007-07-01
3.5 | Hubs | 2007-07-01
3.6 | Load Participation | 2008-12-01
3.7 | Resource Parameters | 2008-12-01
3.8 | Special Considerations for Split Generation Meters | 2008-12-01
3.9 | Current Operating Plan (COP) | 2008-12-01
3.10 | Network Operations Modeling and Telemetry | 2008-04-01
3.10.1
Note: Bob and Denny will add third decimal point for Section 3.10
3.11 | Transmission Planning
3.12 | Load Forecasting | 2008-10-01
3.13 | Renewable Production Potential Forecasts | 2008-10-01
3.14 | Contracts for Reliability Resources | 2008-10-01
3.15 | Voltage Support
3.16 | Standards for Determining Ancillary Service Quantities | 2008-12-01
3.17 | Ancillary Service Capacity Products | 2008-12-01
3.18 | Resource Limits in Providing Ancillary Service | 2008-12-01
3.19 | Constraint Competitiveness Tests | 2008-12-01
4 | Day-Ahead Operations | 2008-12-01
5 | Transmission Security Analysis and Reliability Unit Commitment (RUC) | 2008-12-01
6 | Adjustment Period and Real-Time Operations | 2008-12-01
7 | Congestion Revenue Rights
7.1 | Function of Congestion Revenue Rights | 2008-09-30
7.2 | Characteristics of Congestion Revenue Rights | 2008-09-30
7.3 | Types of Congestion Revenue Rights to Be Auctioned | 2008-09-30
7.4 | Allocation of Preassigned Congestion Revenue Rights | 2008-09-30
7.5 | CRR Auctions | 2008-09-30
7.6 | CRR Balancing Account | 2008-09-30
7.7 | Congestion Management in McCamey Area | 2008-09-30
7.8 | Bilateral Trades and ERCOT CRR Registration System | 2008-09-30
7.9 | CRR Settlements | 2008-09-30
8 | Performance Monitoring and Compliance
8.1 | QSE/Resource Performance Monitoring and Compliance | 2008-12-01
8.2 | ERCOT Performance Monitoring and Compliance | 2008-12-01
8.3 | TSP Performance Monitoring and Compliance | 2008-12-01
8.4 | Non-Compliance | NA
8.5 | Frequency Response Requirements and Monitoring | 2008-12-01
9 | Settlement and Billing | 2008-12-01
10 | Metering
10.1 | Overview
10.2 | Scope of Metering Responsibilities
10.3 | Meter Data Acquisition System (MDAS)
10.4 | Certification of EPS Metering Facilities
10.5 | TSP and DSP EPS Meter Inspectors
10.6 | Auditing and Testing of Metering Facilities
10.7 | ERCOT Request for Installation of EPS Metering Facilities
10.8 | Maintenance of Metering Facilities
10.9 | Standards for Metering Facilities
10.10 | Security of Meter Data
10.11 | Validating, Editing, and Estimating of Meter Data
10.12 | Communications
10.13 | Meter Identification
10.14 | Exemptions from Compliance to Metering Protocols
11* | Data Acquisition and Aggregation | 2008-12-01
12 | Market Information System | 2008-12-01
13 | Transmission and Distribution Losses | 2008-12-01
14* | State of Texas Renewable Energy Credit Trading Program | 2008-12-01
15* | Customer Registration | 2008-12-01
16 | Registration and Qualification of Market Participants
16.1 | Qualification, Registration, and Execution of Agreements | 2007-10-15
16.2 | Registration and Qualification of Qualified Scheduling Entities | 2008-12-01
16.3 | Registration of Load Serving Entities | 2008-12-01
16.4 | Registration of ERCOT and Non-ERCOT Transmission and Distribution Service Providers | 2008-12-01
16.5 | Registration of a Resource Entity | 2008-12-01
16.6 | Registration of Municipally Owned Utilities and Electric Cooperatives in the ERCOT Region | 2008-12-01
16.7 | Registration of Renewable Energy Credit Account Holders | 2008-12-01
16.8 | Registration and Qualification of Congestion Revenue Rights Account Holders | 2008-09-30
16.9 | Resources Providing Reliability Must-Run Service | 2008-12-01
16.10 | Resources Providing Black Start Service | 2008-12-01
16.11 | Financial Security for Counter-Parties | 2008-09-30
16.12 | User Security Administrator and Digital Certificates | 2008-12-01
17 | Market Monitoring and Data Collection | 2008-07-01
18* | Load Profiling | 2008-12-01
19* | Texas Standard Electronic Transaction (TX SET) | 2008-12-01
20* | Alternative Dispute Resolution Procedure | 2008-12-01
21* | Process for Protocol Revision | 2008-12-01
22 | Agreements
Attachment F: Standard Form Reliability Must-Run Agreement
Standard Form Black Start Agreement
| Attachment B: Standard Form Market Participant Agreement | 2007-10-15
Standard Form REC Account Agreement
Standard Form TCR Account Holder Agreement
Notification of Suspension of Operations
23* | Texas Test Plan Team - Retail Market Testing | 2008-12-01
24* | Retail Point to Point Communications | 2008-12-01
ERCOT Fee Schedule - 2006*
* - From Zonal Protocol