## Nodal Project Schedule
Texas Nodal Market Implementation Schedule
Nodal Project Dates
Features | Project | Readiness Criteria Measurement Begins | TNM Implementation | Performance Measured | Compliance Application | Status G/Y/R | Prev Status | Mitigation Activities | Comments
EDS 1, Release 1 | EMS 1 | 2007-07-01 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 1, Release 2 | EMS 2 A | 2007-09-01 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 2, Release 3 | EMS 2 B, EDW 1 | 2007-10-01 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 2, Release 4 | NMMS 1, NMMS 2, EIP 1 | 2007-12-01 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 3, Registration | REG 1 | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
EDS 3, Release 5 | EDW 2, MMS 1, S&B 1, EIP 2, EMS 2C, MIS 1, EIP3 | 2007-10-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 3, Release 6 | EMS 3, EDW 3, | 2008-01-03 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 3, Release 7 | CRR 1, EIP 5, EDW 4 | 2008-01-03 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 4, Release 8 | MMS 2, S&B 2, EIP 6, EDW 5 | 2008-03-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 4, NOMCR |  | 2008-02-01 | 2008-04-01 | 2008-06-01 | 2008-10-01
EDS 4, Release 9, Baseline 1, 2 | OS 1, NMMS 3, EMS4, S&B 3, EIP 7, EMS 5, S&B 4, EDW 6 | 2008-05-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
EDS 4, Release 9, ERCOT, QSE & TSP Responsibilities |  | 2008-01-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
ERCOT Business Processes
Load Forecasting/Adequacy |  | 2008-05-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
Renewable Production Potential Forecasts |  | 2008-06-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
Contracts for Reliability Resources |  | 2008-06-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
Standards for Determining Ancillary Service Quantities |  | 2008-10-01 | 2008-10-01 | 2008-10-01 | 2008-10-01
2-Day Response for Outage (Section 3.1.5.3) |  | 2008-04-01 | 2008-07-01 | 2008-09-01 | 2008-12-01 |  |  |  | Implementation schedule pending from ERCOT
Full Nodal Functionaliy in Preparation for the 168-Hour Test Process |  | 2008-07-01 | N/A | N/A | N/A
PCRR Documentation Delivered to ERCOT |  | 2007-10-01 | 2008-09-30 | N/A | 2009-06-01
NOIE Load Zone Declaration |  | 2007-10-01 | 2008-12-01 | N/A | N/A
CRR Auction |  | 2008-01-01 | 2008-09-30 | 2008-09-30 | 2008-09-30
Standard Form Agreements Completed |  | 2007-08-01 | 2007-10-15 | N/A | 2007-10-15
Real-Time Market Go-Live |  |  | 2008-12-01 | 2008-12-01 | 2009-06-01
Day-Ahead Market Go-Live |  |  | 2008-12-08 | 2008-12-08 | 2009-06-01
ERCOT and Market Participant Zonal Control Systems Retire |  |  | 2009-02-01 | 2009-02-01 | 2009-02-01
Zonal Settlement Systems Retire |  |  | Never | Never | Never |  |  |  | Legal to provide specific language describing "Never" or an accronym.
Formulas:
Compliance Application = [Performance Measured]+92
Compliance Application = [TNM Implementation]
Performance Measured = [TNM Implementation]+62
Performance Measured = [TNM Implementation]

## Nodal Protocol Application
Nodal Section Number | Nodal Section Title | Effective Date for Readiness Criteria Measurement | Texas Nodal Market Implementation Date | Performance Measured Under Nodal Section 8 Date | Nodal Compliance Application Date | Comments
1 | Overview | 2007-07-01 | 2007-07-01 | 2007-07-01 | 2007-07-01
2 | Definitions and Acronyms | 2007-07-01 | 2007-07-01 | 2007-07-01 | 2007-07-01
3 | Management Activities for the ERCOT System
3.1 | Outage Coordination except 3.1.5.3 | 2008-01-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
3.1.5.3 | Timelines for response by ERCOT for TSP Requests | 2008-03-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
3.2 | Analysis of Long-Term Resource Adequacy | 2008-05-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
3.3 | Management of Changes to ERCOT Transmission Grid | 2008-02-01 | 2008-04-01 | 2008-06-01 | 2008-10-01
3.4 | Load Zones |  | 2007-07-01
3.5 | Hubs |  | 2007-07-01 |  |  | Zonal Hubs are applicable to zonal market.
3.6 | Load Participation | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.7 | Resource Parameters | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.8 | Special Considerations for Split Generation Meters | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.9 | Current Operating Plan (COP) | 2007-10-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
3.10 | Network Operations Modeling and Telemetry
3.10.1 | Time Line for Network Model Change Requests | 2008-02-01 | 2008-04-01 | 2008-06-01 | 2008-10-01
3.10.2 | ERCOT Annual Planning Model | 2008-01-01 | 2008-09-30 | 2008-09-30 | 2008-09-30
3.10.3 | CRR Network Model | 2008-01-03 | 2008-09-30 | 2008-09-30 | 2008-09-30
3.10.4 | ERCOT Responsibilities | 2008-01-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
3.10.5 | TSP Responsibilities | 2008-01-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
3.10.6 | Resource Entity Responsibilities | 2008-01-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
3.11 | Transmission Planning | 2008-01-01 | 2008-09-30 | 2008-09-30 | 2008-09-30
3.12 | Load Forecasting | 2008-05-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
3.13 | Renewable Production Potential Forecasts | 2008-06-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
3.14 | Contracts for Reliability Resources | 2008-06-01 | 2008-10-01 | 2008-07-01 | 2008-10-01
3.15 | Voltage Support | 2008-01-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
3.16 | Standards for Determining Ancillary Service Quantities | 2008-10-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
3.17 | Ancillary Service Capacity Products | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.18 | Resource Limits in Providing Ancillary Service | 2007-09-04 | 2008-12-01 | 2008-07-01 | 2008-10-01
3.19 | Constraint Competitiveness Tests | 2008-01-03 | 2008-12-01 | 2008-05-01 | 2008-12-01 | The CCT implementation must be implemented in sufficient time to allow CMWG/TAC to evaluate the constraint classifications Competitive/non-competitive prior to market open.
4 | Day-Ahead Operations | 2008-05-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
5 | Transmission Security Analysis and Reliability Unit Commitment (RUC) | 2008-05-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
6 | Adjustment Period and Real-Time Operations | 2007-10-01 | 2008-12-01 | 2009-02-01 | 2009-06-01
7 | Congestion Revenue Rights
7.1 | Function of Congestion Revenue Rights | 2008-01-03 | 2008-09-30 | 2008-09-30 | 2008-09-30
7.2 | Characteristics of Congestion Revenue Rights | 2008-01-03 | 2008-09-30 | 2008-09-30 | 2008-09-30
7.3 | Types of Congestion Revenue Rights to Be Auctioned | 2008-01-03 | 2008-09-30 | 2008-09-30 | 2008-09-30
7.4 | Allocation of Preassigned Congestion Revenue Rights | 2007-10-01 | 2008-09-30 | 2008-09-30 | 2008-09-30
7.5 | CRR Auctions | 2008-01-03 | 2008-09-30 | 2008-09-30 | 2008-09-30
7.6 | CRR Balancing Account | 2008-01-03 | 2008-09-30 | 2008-09-30 | 2008-09-30
7.7 | Congestion Management in McCamey Area | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30
7.8 | Bilateral Trades and ERCOT CRR Registration System | 2008-01-03 | 2008-09-30 | 2008-09-30 | 2008-09-30
7.9 | CRR Settlements | 2008-01-03 | 2008-09-30 | 2008-09-30 | 2008-09-30
8 | Performance Monitoring and Compliance
8.1 | QSE/Resource Performance Monitoring and Compliance | 2008-01-03 | 2008-12-01 | 2008-01-03 | 2009-06-01 | Regulation AS certification begins in EDS3 Release 6 testing. Resources not subject to certification will qualify for AS in accordance with Section 8 prior to market open.
8.2 | ERCOT Performance Monitoring and Compliance | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2009-06-01 | ERCOT performance monitoring is performed by the IMM. IMM reports are reviewed by the TAC.
8.3 | TSP Performance Monitoring and Compliance | 2008-02-01 | 2008-12-01 | 2008-07-01 | 2009-06-01 | ERCOT must develop a TSP Monitoring Program and obtain TAC approval.
8.4 | Non-Compliance | NA | NA | NA | 2009-06-01
8.5 | Frequency Response Requirements and Monitoring | 2008-07-01 | 2008-12-01 | 2008-07-01 | 2009-06-01 | Frequency Response provisions must be in effect beginning with the test sequence that implements the nodal LFC as the system frequency control.
9 | Settlement and Billing | 2008-03-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
10 | Metering
10.1 | Overview | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
10.2 | Scope of Metering Responsibilities | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
10.3 | Meter Data Acquisition System (MDAS) except 10.3.2.3 | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
10.3.2.3 | Generation Netting for EPS Meters | 2008-01-03 | 2008-12-01 | 2008-12-01 | 2008-12-01
10.4 | Certification of EPS Metering Facilities | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
10.5 | TSP and DSP EPS Meter Inspectors | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
10.6 | Auditing and Testing of Metering Facilities | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
10.7 | ERCOT Request for Installation of EPS Metering Facilities | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
10.8 | Maintenance of Metering Facilities | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
10.9 | Standards for Metering Facilities | 2007-12-01 | 2008-07-01 | 2008-09-15 | 2008-12-01
10.10 | Security of Meter Data | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
10.11 | Validating, Editing, and Estimating of Meter Data | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
10.12 | Communications | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
10.13 | Meter Identification | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
10.14 | Exemptions from Compliance to Metering Protocols | 2008-12-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
11* | Data Acquisition and Aggregation |  | 2008-12-01 | 2008-12-01 | 2008-12-01
12 | Market Information System | 2007-10-01 | 2008-12-01 | 2008-12-01 | 2008-12-01 | ERCOT shall post CRR auction notices in accordance with Section 7.5.3.2 to MIS for the first monthly auction.
13 | Transmission and Distribution Losses |  | 2008-12-01 | 2008-12-01 | 2008-12-01
14* | State of Texas Renewable Energy Credit Trading Program |  | 2008-12-01 | 2008-12-01 | 2008-12-01
15* | Customer Registration |  | 2008-12-01 | 2008-12-01 | 2008-12-01
16 | Registration and Qualification of Market Participants
16.1 | Qualification, Registration, and Execution of Agreements | 2007-08-01 | 2007-10-15 | 2007-10-15 | 2007-10-15 | Standard Form Agreement replaces existing ERCOT/MP agreements
16.2 | Registration and Qualification of Qualified Scheduling Entities | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.3 | Registration of Load Serving Entities | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.4 | Registration of ERCOT and Non-ERCOT Transmission and Distribution Service Providers | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.5 | Registration of a Resource Entity | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.6 | Registration of Municipally Owned Utilities and Electric Cooperatives in the ERCOT Region | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.7 | Registration of Renewable Energy Credit Account Holders | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.8 | Registration and Qualification of Congestion Revenue Rights Account Holders | 2008-07-01 | 2008-09-30 | 2008-09-30 | 2008-09-30
16.9 | Resources Providing Reliability Must-Run Service | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.10 | Resources Providing Black Start Service | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
16.11 | Financial Security for Counter-Parties | 2008-07-01 | 2008-09-30 | 2008-12-01 | 2008-12-01 | 9/30/08 date in place for Market Participants who will participate in the CRR Auction
16.12 | User Security Administrator and Digital Certificates | 2008-07-01 | 2008-12-01 | 2008-12-01 | 2008-12-01
17 | Market Monitoring and Data Collection | 2008-05-01 | 2008-07-01
18* | Load Profiling |  | 2008-12-01 | 2008-12-01 | 2008-12-01
19* | Texas Standard Electronic Transaction (TX SET) |  | 2008-12-01 | 2008-12-01 | 2008-12-01
20* | Alternative Dispute Resolution Procedure |  | 2008-12-01 | 2008-12-01 | 2008-12-01
21* | Process for Protocol Revision |  | 2008-12-01 | 2008-12-01 | 2008-12-01
22 | Agreements
| Attachment F: Standard Form Reliability Must-Run Agreement | 2008-07-01 | 2008-12-01 | 2008-07-01 | 2008-07-01
Standard Form Black Start Agreement
| Attachment B: Standard Form Market Participant Agreement | 2007-10-15 | 2007-10-15 | 2007-10-15 | 2007-10-15
Standard Form REC Account Agreement
Standard Form TCR Account Holder Agreement
Notification of Suspension of Operations
23* | Texas Test Plan Team - Retail Market Testing |  | 2008-12-01 | 2008-12-01 | 2008-12-01
24* | Retail Point to Point Communications |  | 2008-12-01 | 2008-12-01 | 2008-12-01
Indicates areas not appropriate to transition matrix.
* - From Zonal Protocol
Formulas:
Texas Nodal Market Implementation Date = [Texas Nodal Market Implementation Date, row above]
Nodal Compliance Application Date = [Nodal Compliance Application Date, row above]
Nodal Compliance Application Date = [Texas Nodal Market Implementation Date]

## Zonal Protocol Retirement
Zonal Section Number | Zonal Section Title | Retirement Date | Comment
1 | Overview | 2008-11-30
2 | Definitions and Acronyms | 2008-11-30
3 | Open Access to the ERCOT Transmission Grid | 2008-11-30
4 | Scheduling | 2008-11-30
5 | Dispatch | 2008-11-30
6 | Ancillary Services | 2008-11-30
7 | Congestion Management | 2008-11-30
7.9 | Trading Hubs | 2008-11-30
8 | Planned Outages and Maintenance Outages of Transmission and Resource Facilities
8.1 | Outage Coordination | 2008-03-31
8.2 | Communications Regarding Resource Facility and Transmission Facility Outages | 2008-03-31
8.3 | ERCOT Approval of Transmission System Outages | 2008-03-31
8.4 | Acceptance of Proposed Planned Outages of Resources other than Reliability Resources | 2008-03-31
8.5 | Approval of RMR Unit, Synchronous Condenser Unit or Black Start Resource Outages | 2008-03-31
8.6 | Management of Resource Outages other than Reliability Resources | 2008-03-31
8.7 | Long-Term-Demand Forecasts | 2008-11-30
8.8 | Coordination for System Topology Modifications | 2008-03-31
9 | Settlement and Billing | Never | All sections with a Retire Date = TBD are subject to Expiration of Confidentiality (section 1.3.3) as stated in section 9.5.2 of the protocols.
9.2.3 | Initial Statements | 2008-12-10
9.2.4 | Final Statements | 2009-01-28
9.2.6 | True-Up Statement | 2009-06-01
10 | Metering | 2008-11-30
11 | Data Acquisition and Aggregation | 2008-11-30
12 | Market Information System
12.1 | Overview | 2009-03-02 | Requirements to post zonal offers per PUC rule requirement.
12.2 | ERCOT Obligation to Provide Information | 2009-03-02
12.3 | Transmission-Related Information | 2009-03-02
12.4 | Market-Related Information | 2009-03-02
12.5 | Applicable Reliability Standards | 2009-03-02
13 | Transmission and Distribution Losses | 2008-11-30
14 | State of Texas Renewable Energy Credit Trading Program | 2008-11-30
15 | Customer Registration | 2008-11-30
16 | Registration and Qualification of Market Participants | 2008-11-30
17 | Market Data Collection and Use | 2008-11-30
18 | Load Profiling | 2008-11-30
19 | Texas Standard Electronic Transaction (TX SET) | 2008-11-30
20 | Alternative Dispute Resolution Procedure | Never
21 | Process for Protocol Revision | 2008-11-30
22 | Agreements
22(A) | Standard Form Black Start Agreement
22(B) | Standard Form Load Serving Entity Agreement | 2007-10-15
22(C) | Standard Form Qualified Scheduling Entity Agreement | 2007-10-15
22(D) | Standard Form REC Account Agreement
22(E) | Standard Form Resource Entity Agreement | 2007-10-15
22(F) | Standard Form Reliability Must-Run Agreement | 2008-11-30
22(G) | Standard Form Transmission and/or Distribution Service Provider Agreement | 2007-10-15
22(H) | Standard Form TCR Account Holder Agreement | 2009-02-01
22(I) | Notification of Suspension of Operations
22(J) | Standard Form Synchronous Condernser Agreement | 2008-11-30
22(K) | Standard Form Emergency Interruptible Load Service (EILS) Agreement | 2008-11-30
22(L) | Standard Form Market Participant Agreement
23 | Texas Test Plan Team – Retail Market Testing | 2008-11-30
24 | Retail Point to Point Communications | 2008-11-30