## MCT 7_13_07
Lesson Learned | Category | Source | Submitter | Very | Somewhat | Not Very | Not at All | Comments | Future Corrective Action
Consider holding Market Information "Pre-Release Workshop" after Market Requirements are defined and before testing begins in future Texas SET releases. This should be a mandatory "in person" meeting for all MPs. This will provide more awareness of changes and it will ensure a detailed understanding of the market requirements. | Communications | MCT | MCT
MPs bring to MCT their validation criteria (i.e. rejection criteria) during Design phase, perhaps as a standing agenda item at MCT since all MPs will be at different phases in Design. Create a template as a guideline for what is expected in discussions. How much extra effort is this? | Requirements | MCT | Suzette Sondag/EC-Power | [5 empty] | Suzette to draft a template for 8/29 meeting
Consolidated change controls (i.e. Ts & Cs, Mass Transition) vs. Multiple single change controls | Requirements | MCT | MCT
Document Market Requirements differently: separate sections for System changes (ex. What the system should do to support the business processes) and Business Process changes. | Requirements | MCT | MCT
Concerted effort to challenge assumptions during Market Requirements definition process. ERCOT should more actively challenge the market's assumptions. | Requirements | MCT | Jennifer Frederick/ERCOT, Cary Reed/AEP
Sub-groups to be assigned redline Implementation Guides to review against Market Requirements and Change controls prior to MCT review of redline guides. | Requirements | MCT | Jennifer Garcia/Direct Energy
Make goal to have a solid draft of Business Requirements done prior to redlining Implementation Guides. Take more time to get Requirements firmed up. TX SET to come up with a date and/or % complete with Requirements prior to starting the redline Guides (this will be dependent on mandatory dates by Rulemakings). | Requirements | MCT | Rob Bevill/Green Mountain
Meet more frequently during Requirements definition phase. | Requirements | MCT | Cary Reed/AEP
Market to request of PUCT fewer the 4 flight tests per year during version release years | Testing | MCT | Susan Munson/ERCOT
How to communicate transaction shutdowns better within the market? Some MPs did not receive market notices and were not on the conference calls | Communications | MCT | Susan Munson/ERCOT | [5 empty] | RCS to check for confirmations that MPs are aware of shutdowns and receive communications
Prepare and send out questionnaire to MPs for Lessons Learned session preparation. This will enable more candid feedback. | Project Closing | MCT | Cary Reed/AEP | [5 empty] | Cary to provide sample questionnaire.
Add TTPT Lessons Learned to TX SET/MCT Lessons Learned for 3.0 | Project Closing | MCT | Kathy Scott/Centerpoint
RMGRRs should be written and sent through the governance process after PRRs, SCRs, and Market Requirements are written. | Requirements |  | Susan Munson/ERCOT
Testing of 867_03 IDRs should be Required to verify if sender and receiver are able to successfully translate and it could also determine receiver validation processes |  | Email | Kathy Scott/Centerpoint
867_03 should be tested to include each type of 867_03 being communicated in the market - Metered, Unmetered (Streetlight), and Interval. |  | Email | Kathy Scott/Centerpoint
In response to "Pre-Release Workshop" - Workshop would be early enough to allow time for issues and requirements to be modified to include additional details where needed and opportunity for Questions and Answers prior to Market developing their own internal design and requirements, not a week before testing. |  | Email | Kathy Scott/Centerpoint
Pre-Release Workshop would be mandatory for participation from all Market Participants because it would be tied to MP Certification, similar to new release testing certification. |  | Email | Kathy Scott/Centerpoint
Testing requirement need to have time to verify complete transaction and not just what was expected in test script. |  | Email | Kathy Scott/Centerpoint
ERCOT's involvement as Test Administrator -should include updating documentation and managing of scripts. |  | Email | Kathy Scott/Centerpoint
Flight Administrator should be involved with TX SET and MCT when requirements are developed for version release |  | Email | Kathy Scott/Centerpoint
Clearly document and detail requirements/design instructions |  | Email | Kathy Scott/Centerpoint
Testing should include minimum of 2 weeks for version release regression testing at the end of all test scripts and prior to blackout/implementation weekend. This would allow time to test old and new code prior to production implementation |  | Email | Kathy Scott/Centerpoint
Version Release should always include as the Market Coordination Team, TX SET, and TTPT team developing test scripts. |  | Email | Kathy Scott/Centerpoint
What is the role of TDTWG during a Release because of issues identified by TDTWG during Version 3.0 and the Customer Billing Contact Information File. |  | Email | Kathy Scott/Centerpoint

## TTPT
Lesson Learned | Category | Source | Submitter | Very | Somewhat | Not Very | Not at All | Comments | Future Corrective Action
When resends are requested, need to indicate the reason why. | Testing | TTPT | Service Provider | n/a | n/a | n/a | n/a | Original file sometimes fails for reason not mentioned.
Mention in test script instructions on sending a transaction late. | Testing | TTPT | Service Provider | n/a | n/a | n/a | n/a | When getting caught up on sending transactions, they would fail due to testing date being too old now.
Establish report on Retail Testing website so MPs do not have to count their numbers up on the daily call. | Testing | TTPT | Service Provider | n/a | n/a | n/a | n/a
Proper procedures should be used by TDSPs when resending point-to-point transactions. | Testing | TTPT | Service Provider | n/a | n/a | n/a | n/a | Hard to remove a transaction from a billing system without a cancellation transaction or 824.
Resend request needs to include all relevant information. | Testing | TTPT | Service Provider | n/a | n/a | n/a | n/a | Ex. What date needs to be used in DTM segment.
MPs and ERCOT need to follow script details. | Testing | TTPT | Service Provider | n/a | n/a | n/a | n/a | Ex. Transactions missing necessary segments that script calls for.
Email should be sent to MPs prior to conference call for important issues. | Testing | TTPT | Service Provider | n/a | n/a | n/a | n/a
Testing has to start on scheduled date | Testing | TTPT | TDSP | n/a | n/a | n/a | n/a |  | All system changes should be complete and the test environment ready to go by the kick-off call. This will give ERCOT the weekend in the event they run into a technical issue.
Clearly defined process on how to address an issue when a script is not working or a process is not working as expected | Testing | TTPT | TDSP | n/a | n/a | n/a | n/a
Clear explanation of testing processes needs to be given. | Testing | TTPT | TDSP | n/a | n/a | n/a | n/a | This will achieve realistic expectations and help stay on schedule. Testing resources may be different for MPs than those whom have previously managed testing.
Backdated transactions should not be sent after 5:00 PM | Testing | TTPT | TDSP | n/a | n/a | n/a | n/a |  | ERCOT should validate that the date wanted is an acceptable date. All testing resources should be educated about the time requirements for transactions that go through ERCOT. Add communication to the kick-off call. TDSPs should inform testing partners when their batch process begins on the kick-off call. Create a Tip Sheet for Testing on back-dated transactions.
Better organized Saturday work days | Testing | TTPT | TDSP | n/a | n/a | n/a | n/a |  | The MP that is behind needs to provide a plan for catching up to the Flight Admin this should be communicated to the impacted MPs.
Internal testers need to be aware of all script checkpoints and verify they are correct | Testing | TTPT | ERCOT | n/a | n/a | n/a | n/a
SIM transactions for MOU ESI IDs need to be checked for added segments/values associated with MOU territories | Testing | TTPT | ERCOT | n/a | n/a | n/a | n/a
Test Bed Loader Tool (internal tool for ERCOT) needs to be updated so that all service instances are set up for new TS scripts | Testing | TTPT | ERCOT | n/a | n/a | n/a | n/a