## TPTF Comments
Comment ID | Comment Location | Comment | NPRR047 | NPRR059 | Other | Status | Status - Restructured | NOTES - Restructured | NOTES
R2 | p.7 | Deleted 'in' |  |  | X | Deferred | Rejected |  | Deferred to Restructured version (v2.1). This deletion is incorrect and appears to have been inadvertently included as a comment.
R3 | p.7 | ERCOT shall also settle PCRRs. |  |  | X | Deferred | Addressed | Incorporated verbiage in Scope section which covers entire document. | Deferred to Restructured version (v2.1); Addressed in Scope section
R4 | p. 9, FR4 | What is the naming convention? It should be specified in this document as this is the “requirements document.”] |  |  | X | Deferred | Rejected | Naming convention really means all data elements deemed necessary to uniquely identify a CRR. These are being defined through interface documentation with affected systems. | Deferred to Restructured version (v2.1)
R5 | p.10, FR5 | , including PCRRs, |  |  | X | Deferred | Response Provided | See R3 | Deferred to Restructured version (v2.1); Addressed in Scope section
R7 | p.11, FR8 | added "monthly" |  |  | X | Deferred | Addressed | Restructuring split into two requirements and incorporated the word monthly. | Deferred to Restructured version (v2.1)
R8 | p.11, FR8 | [Reliant: what does this mean? Protocol language from 8-1-07 Protocols is below. What is the point that requires clarification? If a CRR Account holder offers a block into an auction and it ‘clears’ the result is that it is considered ‘reconfigured.’ The owner would be provided with the proceeds from the auction corresponding to the value of the transmission capacity that the CRR “freed up” and correspondingly “cleared” in the auction. It would be useful to have a description (in this document) of how the value of the auction clearing from the offered CRR(s) would be determined. ] (Inserted Protocol 7.5.1 Nature and Timing) |  |  | X | Deferred | Deferred to Business Process Clarification |  | Deferred to Restructured version (v2.1)
R9 | p.13 FR9 | Change existing language: o Create, validate and manage nominations for CRRs for allocations - to - o Create, validate and manage nominations for PCRRs allocations |  |  | X | Deferred | Response Provided | See R3 | Deferred to Restructured version (v2.1)
R11 | p.14, FR10 | Change existing language: Assumption: The CRR hedge type, with MWs will be posted. - to - Assumption: The CRR hedge type, with MWs will also be posted. |  |  | X | Deferred | Rejected |  | Deferred to Restructured version (v2.1)
R12a | p.14, FR10 | Added language to the ASSUMPTION: It also includes the assumptions of the transmission capability for dynamically rated elements (including temperature assumptions), |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: The CRR System will allow posting of information deemed necessary and appropriate. | Deferred to Restructured version (v2.1)
R12b | p.14, FR10 | Added language to the ASSUMPTION: It also includes the assumptions of the peak load, |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: Peak load is not an input for the CRR market process. | Deferred to Restructured version (v2.1)
R12c | p.14, FR10 | Added language to the ASSUMPTION: It also includes the assumptions of scaled TTC to reflect limits by impact of outages, to be used in each TOU block and month of the auction |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: The CRR System will allow posting of information deemed necessary and appropriate. | Deferred to Restructured version (v2.1)
R12d | p.14, FR10 | Added language to the ASSUMPTION: Additionally, it includes the same contingencies and operating procedures that are enforced in the Network Model along with outages from the Outage Scheduler. This means that if there are RAPs or SPSs, they are, to the extent practicable, to be modeled in the CRR model. This information must be posted along with other commercially significant data. |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: Contingency lists are part of the CRR Network Model. | Deferred to Restructured version (v2.1)
R13 | p.15, FR12 | a. PTP Options and PTP Options with Refund – the source and sink, time of use block, effective dates and total MWs; [Reliant: this information actually also must be posted before the CRR auction—because the allocations remove transmission capacity from the model and the network model for the auction is required to reflect available transmission capacity. The transmission capacity is not available if it has been “preassigned.” This assumption is inherent in FR 15 but it should be clearly set forth here.] |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: Requirement is addressed in FR10. | Deferred to Restructured version (v2.1)
R14 | p.15, FR12 | a. PTP Obligations and PTP Obligations with Refund – the source and sink , time of use block, effective dates, and total MWs; [Reliant: this information actually also must be posted before the CRR auction—because the allocations remove transmission capacity from the model and the network model for the auction is required to reflect available transmission capacity. The transmission capacity is not available if it has been “preassigned.” This assumption is inherent in FR 15 but it should be clearly set forth here.] |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: Requirement is addressed in FR10. | Deferred to Restructured version (v2.1)
R15a | p.16, FR15 | § PCRR PTP Allocation (Allocation Stage 1) [Reliant: Where are the validation processes set forth for the PCRR allocation? |  |  | X | Deferred | Response Provided | Covered in FR35 | Deferred to Restructured version (v2.1)
R15b | p.16, FR15 | § PCRR PTP Allocation (Allocation Stage 1) [Reliant: Where is the discussion of the pro-rata allocation for PCRR requests that cannot be accommodated? --7.4.2(a)] |  |  | X | Deferred | Response Provided | Covered in FR35 | Deferred to Restructured version (v2.1)
R16 | p.16, FR15 | MCFRI Allocation (Allocation Stage 2) [Reliant: Where are the validation processes set forth for the MCFRI allocation?] |  |  | X | Deferred | Response Provided | Covered in FR38 | Deferred to Restructured version (v2.1)
R17 | p.18, FR17 | [Reliant: Where are the rest of the conditions—on outages, dynamic ratings, peak load conditions, that are set forth in 7.5.1(2)—excerpted from 8/1/07 nodal protocols below? As far as we can tell, this section of the requirements is the only one that references 7.5.1(2). However, FR20 appears to cover (2)(b). (Included excerpt of 7.5.1(2) of Protocols) |  |  | X | Deferred | Addressed | Adding Protocol reference in FR16 | Deferred to Restructured version (v2.1)
R18 | p.20, FR49 | [Reliant: what is a “Label?” What is a “Type?” What is a “Class?”] | X |  |  | Addressed | NA | Covered in NPRR047 & NPRR059 | RESPONSE: The terms in question are system terms, and do not necessarily reflect Protocol language. Label=Descriptive name of CRR Type=(Baseload, PreAward, Refund, Standard, Capacity) Class=Time of Use (PeakWD, PeakWE, OffPeak)
R19 | p.20, FR49 | The system shall allow the CRR Market Operator to create a new CRR. [Reliant: What does this mean?] | X |  |  | Response Provided | NA | Covered in NPRR047 & NPRR059 | RESPONSE: This is a capability necessary to allow a CRR Market Operator the flexibility to handle a repossessed or forfeited CRR.
R20 | p.21, FR19 | § Load distribution factors for Load Zone definition [Reliant: What about hub distribution factors?] |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: covered under FR20. | Deferred to Restructured version (v2.1)
R21 | p.22, FR50 | Assumption: The CRR Network Model input into the CRR System shall be a CIM compliant file converted to PSS/E RAWD format file following the requirements noted below. The CIM compliant file will be posted as the CRR Network Model. [Reliant: ERCOT should also post the PSS/E RAWD file since this is the one that will be used in the auction.] |  |  | X | Deferred | Deferred to Business Process Clarification | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: The posting of the Network Model files is a Business Process and not a CRR System requirement. | Deferred to Restructured version (v2.1)
R22 | p.22, FR50 | § The CRR System shall import the CRR Network Model for CRR markets a maximum (previously said "minimum") of two months in advance of the effective month. |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: Business Process not a CRR System requirement. | Deferred to Restructured version (v2.1)
R23 | p.22, FR50 | § . [Reliant: The CRR Network Model shall also be posted in the PSS/E RAWD format that is being used for the auction.] |  |  | X | Deferred | Deferred to Business Process Clarification | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: The posting of the Network Model files is a Business Process and not a CRR System requirement. | Deferred to Restructured version (v2.1)
R24a | p.22, FR50 | Information in the CRR Network Model shall include the effective period of the auction (monthly for monthly auctions, each month for annual auctions), Contingencies Reliant: (including RAPs and SPSs), |  |  | X | Deferred | Response Provided | Addressed in FR17 | Deferred to Restructured version (v2.1)
R24b | p.22, FR50 | Information in the CRR Network Model shall include Reliant: Outage information, |  |  | X | Deferred | Addressed | While out of scope for the restructuring effort, review indicates this only covered indirectly in FR16. Therefore, updates made to FR10 and FR50. | Deferred to Restructured version (v2.1)
R24c | p.22, FR50 | Information in the CRR Network Model shall include the impact of existing (outstanding) CRRs, as well as Source/Sinks and Flowgates to be auctioned for time of use as described in FR3. |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: The impact of existing CRRs is not required to be provided. However, existing CRRs are posted per FR10. | Deferred to Restructured version (v2.1)
R25 | p.23, FR21 | Assumption: PTP Obligations between every combination of sources and sinks shall only be available in the first month of an auction. Subsequent to Board action, if any, PTP Obligations between a selected subset sources and sinks for all months could be made available. The CRR System shall only accommodate one subset of selected sources and sinks for any given auction. [Reliant: does this mean by calendar period or Time of Use block or both?] |  |  | X | Deferred | Response Provided | By calendar period | Deferred to Restructured version (v2.1)
R26 | p.23, FR21 | An NPRR is needed to clarify section 7.5.1 (5). [Reliant: what exactly requires clarification?] |  |  | X | Deferred | Deferred to Business Process Clarification | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: | Deferred to Business Process Clarification version
R27 | p.25, FR25 | [Reliant: the time of use period for the optimization should be specified here.] |  | X |  | Rejected | NA |  | Covered in FR3 (excerpt below): The CRR System shall enable ERCOT to distribute CRRs in the following time of use blocks:  Weekday peak (5x16) time of use blocks for hours ending 0700-2200, Monday through Friday (excluding NERC holidays),  Weekend peak (2x16) time of use blocks for hours ending 0700-2200, Saturday and Sunday, and NERC holidays  Off-peak (7x8) time of use blocks for hours ending 0100-0600 and hours ending 2300-2400 Sunday through Saturday
R28 | p.25, FR25 | [Reliant: To be clear, does this mean that the Account Holder determines the allocation of credit through the CMM system and the CRR system will retrieve the information from the CMM system?] | X |  |  | Response Provided | NA |  | RESPONSE: The CRR System will obtain a credit constraint for each Counterparty from the CMM System. It will be the responsibility of the Counterparty to decide how much of the Counterparty ACL will be applied to each CRR market. A Counterparty’s CRR Auction credit limit is equal to the lesser of the Counterparty’s Auction Credit Limit or, if provided, the CRR Account Holder’s (Counterparty’s) self-imposed credit limit per CRR market.
R29 | p.25, FR25 | [Reliant: Condition iii above should be enforced after the auction clearing. Meaning that if an Account Holder is cleared for PTP Obligations, then after they have paid for them, they are immediately liable for the forward liability from an ERCOT credit perspective through standard ERCOT evaluation of these instruments. This ‘forward condition’ should not be a constraint in the auction, it is enforced by credit after the CRRs are placed in the Account Holders account---which does not occur until they are paid for after the auction clears (see condition d immediately below).] | X |  |  | Rejected | NA |  | RESPONSE: Condition iii is enforced as part of the optimization. The Protocols require that all three factors be summed and be included as a constraint in the Auction clearing, not as an after fact call for additional credit. The CRR team anticipates using factors similar to ACPE as described in Section 16.11.4.6
R30 | p.26, FR25 | [Reliant: does this mean the shadow price of the most limiting element of the bundle of elements that comprise the flowgate?] |  |  | X | Response Provided | NA |  | RESPONSE: Yes
R31 | p.26, FR25 | [Reliant: this doesn’t make sense. If the Obligations are reconfigured in the auction (meaning they are sold) then they don’t exist any more. So why wouldn’t the offering party be ‘relieved’ of the obligations? The issue you are trying to protect against is default in payment by the entity that won them in the auction. It is not fair to penalize the initial holder of the instruments for such a condition which it didn’t cause. The reasoning is that they original obligation products no longer exist---so why would that entity be liable for them? This issue needs to be handled in auction defaults.] | X |  |  | Response Provided | NA |  | RESPONSE: The requirement is correct as written. Selling at a negative price means that the seller is paying money to have someone take over the CRR. Until the seller pays that money, the CRR (and expected obligation) remains with the seller. If the seller doesn’t pay, repossession and/or forfeiture process(es) are applied. Sections 16.11.6.1.4 and 16.11.6.1.5
R32 | p.27, FR52 | · [Reliant: what does this mean? Does this mean that CRRs of the same type and amount from A to B and B to C cannot be offered as CRRs from A to C? If so, this is what should be stated.] |  |  | X | Deferred | Response Provided | Yes | Deferred to Restructured version (v2.1)
R33a | p.27, FR52 | [Reliant: If a monthly product must always be auctioned for the whole month, this should be explicitly stated. |  |  | X | Deferred | Addressed | Covered under FR52.2. | Deferred to Restructured version (v2.1)
R33b | p.27, FR52 | Also, given that in FR 49 ERCOT envisions “creating” CRRs, why couldn’t ERCOT ‘create’ a CRR so that a Party that has cobbled together a product for a whole month, has a product to offer? If this is not the intent of FR 49, what is the intent of ERCOT “creating” a CRR?] |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: It is unlikely that MPs want ERCOT staff to be adjusting their financial hedges. | Deferred to Restructured version (v2.1)
R34 | p.27, FR52 | § [Reliant: it seems like all offers and bids require source and sink information.] |  |  | X | Deferred | Response Provided | Covered earlier than where comment appeared in FR52 | Deferred to Restructured version (v2.1)
R35 | p.28, FR52 | § [Reliant: is it possible to create 10 single one-MW offers between source A and sink B for a CRR holder that has 10 MW between points A and B? If not, does this mean that the minimum amount of an offer is what was previously cleared between A and B for a specified CRR Account Holder?] |  |  | X | Response Provided | NA |  | RESPONSE: Yes.
R36 | p.28, FR52 | (for one tenth of a MW?) |  |  | X | Response Provided | NA |  | RESPONSE: Yes.
R37 | p.28, FR52 | for the Time of Use Block |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: The comment appears to address duration. TOU is not duration. | Deferred to Restructured version (v2.1)
R38 | p.28, FR52 | [Reliant: isn’t this redundant now that the offers are by time of use blocks (rather than hours as originally envisioned in the protocols)?] |  |  | X | Response Provided | NA |  | RESPONSE: No. It clarifies that all hours are treated the same.
R39 | p.29, FR26 | , adjusted to reflect outstanding P/CRRs and outages (and system upgrades), and scaled, if required, for feasibility, |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: Addressed in FR16. | Deferred to Restructured version (v2.1)
R40 | p.30, FR35 | § Refund option – The eligible NOIE may nominate up to 100% of the lesser of the net unit capacity or contractual amount for those Resources. PCRRs allocated under the refund option are not transferable and may only be used by the NOIE to which they are allocated. |  |  | X | Deferred | Addressed | While outside scope of restructuring document (and NPRRs 047 & 059), the deletions are appropriate as they refer to other system requirements. | Deferred to Restructured version (v2.1)
R41 | p.30, FR35 | Capacity option – The eligible NOIE may nominate up to 100% of the lesser of the net unit capacity or contractual amount for those Resources at a capacity factor of no greater than 40% over each calendar year. |  |  | X | Deferred | Addressed | Covered a few lines below comment insertion in restructured version. | Deferred to Restructured version (v2.1)
R42 | p.31, FR35 | § Reliant: This is also limited by the amount of transmission capability designated to be available in any auction.] |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: The capacity factor limit for capacity option PCRRs has nothing to do with the amount of transmission capability designated to be available. | Deferred to Restructured version (v2.1)
R43 | p.31, FR35 | [Reliant: is this really a deletion process? Or is the intent to make the capacity available to the auction—and to enforce a zero injection at a Resource location known to be offline. It seems like we should potentially consider a process where the ‘unusable’ PCRRs are offered into the next auction and a zero injection is enforced at the location of the source. Similarly the ‘reallocation’ is also subject to SFT and allocation prior to the next auction, assuming the network configuration for the next auction—taking into account the updated information from the NOIE about the offline status of the applicable Resources. New CRRs can’t be ‘invented’ without running an allocation and auction process (unless it is the concatenation process described above for ‘creating’ a new instrument). The auction is needed for pricing the PCRRs.] |  |  | X | Deferred | Response Provided | Yes. The PCRRs still have value and are not considered unusable. Force Majeure events will be an offline business process. | Deferred to Restructured version (v2.1)
R44 | p.32, FR39 | § [Reliant: this condition is the basis for the staged release that is set forth in the Protocols in 7.4.2(c). The fact that NOIEs are allowed to request 100 percent of transmission capability, when only a fraction of the grid capacity is being auctioned off, means that the staged release process is required to make the system parallel the capacity available to other participants.] |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: The Nexant CRR System has another way of ensuring that allocations based on 100% network capacity do not over shadow the capacity made available during auctions. | Deferred to Restructured version (v2.1)
R45 | p.36, FR40 | Reliant: Additionally, PTP Obligations and PTP Options that are allocated as PCRRs are not tradable; the system shall enforce this condition.] |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: The refund options are the ones that are not tradable. | Deferred to Restructured version (v2.1)
R46 | p.36, FR40 | [Reliant: define bandwidth for X.] |  |  | X | Deferred | Response Provided | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: FR40 indicates the cutoff time is configurable. The assumption states some bounds. The specific number of days will be specified by the Business Process. | Deferred to Restructured version (v2.1)
R47 | p.42, SR24 | [Reliant: what about hub and load zone bus designations? What about LDFs? What about the list of WGRs in McCamey?] |  |  | X | Deferred | Response Provided | Hub and Load Zone bus designations are included in the Source/Sink file. LDFs are included as part of the Load Flow database, which contains the CRR Network Model. The list of WGRs is not provided by another system, but is uploaded by CRR Market Operators. | Deferred to Restructured version (v2.1)
R48 | p.42, SR25 | § [Reliant: what does this mean in terms of what is available for DAM settlement and RT settlement? At the end of any given day, both sets of data will be required. Also, if the bilateral trading closes at 0600, this means that a snapshot will need to occur then.] |  |  | X | Deferred | Response Provided | There will be no changes in CRR ownership captured by the CRR System between DAM and RT, so there is only one set of data. Agreed that the snapshot of daily ownership will be taken after the bilateral trading cutoff. | Deferred to Restructured version (v2.1)
R49 | p.43, SR26 | Added: o PCRR designation [Reliant: note that NOIE CRR Account Holders can hold PCRRs and CRRs and only the CRRs are tradable. There are PCRRs that don’t have refunds, so the distinction between a PCRR and a CRR is an important distinction that seems to be somewhat overlooked in this document.] |  |  | X | Deferred | Rejected | Outside scope of restructuring document (and NPRRs 047 & 059). NOTE: PCRRs, with the exception of those with refund, are tradable. | Deferred to Restructured version (v2.1)
R50 | p.44, SR28 | Outage Scheduler / Same as NMMS |  |  | X | Deferred | Rejected | Outage Scheduler information comes to the CRR System via NMMS. | Deferred to Restructured version (v2.1)
R51a | p.53, SR30 | [Reliant: What about the load requirements, by zone that are set forth in 7.4(2)(e) and 7.4(2)(f)? Won’t ERCOT need to get this from the NOIEs? Or does ERCOT intend to use tie meter information for this purpose? |  |  | X | Deferred | Response Provided | The ERCOT CRR Team will validate submissions received from NOIEs. | Deferred to Restructured version (v2.1)
R51b | p.53, SR30 | [Reliant: What about the unit fuel types? Will ERCOT CRR team retrieve this from planning or registration, or will it be required from the NOIEs? |  |  | X | Deferred | Response Provided | The ERCOT CRR Team will validate submissions received from NOIEs. | Deferred to Restructured version (v2.1)
R51c | p.53, SR30 | [Reliant: What about the Resource “net unit capacity” information? Will the ERCOT CRR team retrieve this from Operations from seasonal testing data and then compare station load provided by the NOIEs or will the NOIEs have to demonstrate testing and station load (to achieve the “net station load” to ERCOT CRR team?] |  |  | X | Deferred | Deferred to Business Process Clarification | Questions were asked during the July 27th TPTF meeting. The upcoming Business Process Clarification NPRR will resolve. | Deferred to Restructured version (v2.1)
L1 | p.23, FR51 | {Note is not correct per August 1, 2007 Section 7 Protocol.} |  | X |  | Accepted | NA |  | Incorporated into v1.91
L2 | p.30, FR46 | Deleted Protocol reference, and added: Section 7.4.2(h) |  |  | X | Deferred to Restructure | Addressed | Incorporated more detailed reference. | Deferred to Restructured version (v2.1)
[7 empty] | 20 | Rejected
[7 empty] | 8 | Addressed
[7 empty] | 5 | Deferred to Business Process Clarification
[7 empty] | 11 | NA
[7 empty] | 15 | Response Provided
[7 empty] | 60 | Total