Texas Nodal Market

Active Readiness Metric Inventory

Version 0.90

August 27, 2007

Table of Contents

Revision History	2

Introduction	2

EDS Timeline Cross Reference for all Metrics (Approved and Future)	4

Market Participant Metrics	11

MP1 - MP Engagement	11

MP2 – QSE with Resources Connectivity to EDS Environment	12

MP3 – QSE with Resources Upload of SCED Offers to EDS	12

MP5 – ICCP Point to Point Telemetry Test	14

MP11 - MP Registration Activities	15

MP14 - MP EDS-2 Trials Participation	17

Commercial Operations MetricsCongestion Revenue Rights MetricsERCOT Internal Metrics	19

Congestion Revenue Rights MetricsERCOT Internal Metrics	20

ERCOT Internal Metrics	21

E1 - ERCOT Staff Completes Training	21

E6 - Develop Nodal Operating Guides	22

E8 - ERCOT Staffed for Texas Nodal Operations	23

E9 - Develop TN Procedures	24

Energy Management Operations MetricsNetwork Model Management Metrics	25

Network Model Management Metrics	26

N1 - ERCOT Telemetry Alarm Processing	26

Market Operations Metrics	27

Contingency Metrics	28

IMM Metrics	29

Overall Readiness Metrics	30

# Revision History

| Date | Author | Description of Revision |
| --- | --- | --- |
| 8/27/2007 | Chris Wilkinson | Initial Version The intent of this document is to inventory all Texas NODAL Market Readiness Metrics that the NODAL PMO is actively measuring. These metrics have been reviewed and approved by TPTF and TAC. This version picks up where 17a_Metric_Inventory_metric_descriptions_V24.doc left off, which was the last consolidated view of metrics presented to TPTF. Going forward, al TPTF future metrics will be housed in the Future Metric Inventory document. This document is different than 17a_Metric_Inventory_metric_descriptions_V24.doc in that it covers the following active metrics only: - MP1 - MP2 - MP3 - MP5 - MP11 - MP14 - E1 - E6 - E8 - E9 - N1 |

# Introduction

The Readiness Metric Inventory is a detailed report of all readiness metrics.  The following table outlines the information provided per metric. The intent of this document is to inventory all Texas NODAL Market Readiness Metrics that the NODAL PMO is actively measuring.  These metrics have been reviewed by TPTF and TAC and will be governed by a change control process going forward once approved.

Metric Number – Metric Name

| Reported By: Indicates if the metric is discoverable by ERCOT, Market Participants, WEMM or any combination thereof. |  |  | EDS: Indicates the related Early Delivery System, if applicable. |
| --- | --- | --- | --- |
| Target Completion: Indicates the time period that the metric result will be published. |  |  |  |
| Category: Indicates how the data will roll up functionally in the Readiness Dashboard tool. |  |  |  |
| Metric Description: Provides a description of the metric. |  |  |  |
| Background: Indicates the intent of the metric. |  |  |  |
| Criteria: Outlines the criteria used to determine if the metric has been successfully completed. Provides a concrete measurement standard to evaluate the metric against |  |  |  |
| Reporting Data Sources: Indicates the source of the data to be used when evaluating the measurement standard and or the individual or team responsible for reporting status. |  |  |  |
| References | TP: Cross reference to the Transition Plan | TNP: Cross reference to the Texas Nodal Protocols |  |

The Metric Map is a time based graphical representation of the Metrics.

Sample Metric Map

# EDS Timeline Cross Reference for all Metrics (Approved and Future)

| Metric | Milestone Target Completion | Owner | Date |
| --- | --- | --- | --- |
| MP7 – MP Use of MIS - REMOVED | Deleted |  | Deleted |
| MP1 – MP Engagement | 6-month LMP posting – Start less 45 days, TBD, TBD | MP self report | June 1, 2007 |
| MP1 – MP Engagement | 6-month LMP posting – Start less 45 days June 1, TBD, TBD | MP self report | TBD |
| MP1 – MP Engagement | 6-month LMP posting – Start less 45 days June 1, TBD, TBD | MP self report | TBD |
| N1 – ERCOT Telemetry Alarm Processing | EDS 1 – Release 1 Complete plus 14 days | EDS 1 PM | July 15, 2007 |
| E1 - ERCOT Staff Completes Training | Start of EDS 2 | ERCOT Readiness PM | August 6, 2007 |
| MP11 – MP Registration Activities | EDS 3 – Registration EDS Trial Preparation Milestone plus 14 days | ERCOT Manager of Wholesale Client Services | September 17, 2007 |
| MP14 – MP EDS-2 Trials Participation | EDS 2 – Start of Release 4 plus 14 days | EDS 2 PM | October 1, 2007 |
| MO5 – Generate LMPs for 6 months | Test 1- 6 Month LMP Posting minus 90 days | EDS 3 PM | October 15, 2007 |
| MP5 – ICCP Point to Point Telemetry Test | EDS 1 - Release 2 Complete plus 14 days | EDS 2 PM | October 15, 2007 |
| N2 – ERCOT Telemetry/ICCP System Failover | EDS 1 – Release 2 Complete plus 14 days | EDS 1 PM | October 15, 2007 |
| MP4 – QSE Test Digital Certificates Obtained - Removed | 6-month LMP posting major milestone less60 days |  | November 15, 2007 |
| MP2 – QSE with Resources Connectivity to EDS Environment | LMP Data Validation Milestone less 30 days | EDS 3 PM | September 1, 2007 |
| MP3 – QSE with Resources Upload of SCED Offers to EDS | LMP Data Validation Milestone | EDS 3 PM | October 1, 2007 |
| E1 - ERCOT Staff Completes Training | Start of EDS 3 | ERCOT Readiness PM | October 1, 2007 |
| MO5 – Generate LMPs for 6 months | Test 2 – 6 Month LMP Posting minus 90 days | EDS 3 PM | October 15, 2007 |
| E6 – Develop Nodal Operating Guides | Go Live Less 360 days | ERCOT Readiness PM | December 1, 2007 |
| E3 – Validate Telemetry/SE-EDW/MIS Access & Data Accuracy | EDS 2 – Release 3 complete | EDS 2 PM | December 3, 2007 |
| EMO9 – Validate Zonal and Nodal Common Constraints | EDS 2 Release 3 complete | EDS 2 PM | December 3, 2007 |
| N3 – Validate SE performance and Accuracy | EDS 2 – Release 3 complete | EDS 2 PM | December 3, 2007 |
| MP6 – QSE and TSP Telemetry/ICCP System Availability | EDS 2 – Release 3 plus 14 days | EDS 1 & 2 PM | December 17, 2007 |
| MP12 – MP Completes EDS-3 Related Training | First – EDS 3 – 6 Month LMP Posting Major Milestone less 30 days Second – Market Open less 30 days | MP Self Reported | December 17, 2007 |
| E1 - ERCOT Staff Completes Training | Start of EDS 4 | ERCOT Readiness PM | January 1, 2008 |
| MO5 – Generate LMPs for 6 months | First – 6 Month LMP Posting plus 14 days | EDS 3 PM | January 28, 2008 |
| MO4 – Verify Base Point Generation | 6 Month LMP Posting plus 14 days | EDS 3 PM | January 28, 2008 |
| EMO5 – Verify ACE performance | EDS-3 LFC Major Milestone Start + 30 days | EDS 3 PM | February 4, 2008 |
| CRR1 – Develop CRR Test Plan | 180 days prior to the first monthly CRR auction | EDS 3 PM | March 3, 2008 |
| CRR2 – Develop TCR to CRR Transition Plan | Go Live Activities less 270 days | CRR PM | March 3, 2008 |
| MO5 – Generate LMPs for 6 months | Second – 6 Month LMP Posting plus 45 days | EDS 3 PM | March 17, 2008 |
| MP16 – MP EDS-4 Trials Participation | EDS 4 Release 9 – DAM, RUC, SASM less 14 days | EDS 4 PM | March 28, 2008 |
| MO5 – Generate LMPs for 6 months | Third – 6 Month LMP Posting plus 90 days | EDS 3 PM | April 10, 2008 |
| MP15 – MP EDS-3 Trials Participation | EDS 3 trials Start plus 14 days | EDS 3 PM | April 29, 2008 |
| E8 – ERCOT Staffed for Texas Nodal Operations | EDS 4 – Full Nodal Functionality 24*7 Operations Major Milestone less 60 days | ERCOT Readiness PM | May 1, 2008 |
| EMO7 – Verify Load Forecast Accuracy | EDS-4 Release 9 Start + 120 days | EDS 4 PM | May 1, 2008 |
| E7 – Validate EDW WEMM Access & Accuracy | EDW 6 FAT Milestone plus 90 days | EDS 4 PM | June 2, 2008 |
| E10 – Validate EDW Commercial Systems Access & Accuracy | EDW 6 FAT Milestone plus 90 days | EDS 4 PM | June 2, 2008 |
| E11 – Validate EDW Compliance Data Access | EDW 6 FAT Milestone plus 90 days | EDS 4 PM | June 2, 2008 |
| EMO6 – QSE Response to Dispatch | EDS-3 Major Milestone LFC Testing + 60 days | EDS 3 PM | June 2, 2008 |
| MP13 – MP Completes EDS-4 Related training | First – EDS 4 – Full Nodal Functionality 24*7 Operations less 20 days Second – Market Open less 30 Days | MP Self Reported | June 5, 2008 |
| MO5 – Generate LMPs for 6 months | Fourth – 6 Month LMP Posting plus 135 days | EDS 3 PM | June 16 2008 |
| CO9 – Verify Financial Transfer and Processing | EDS-4 Full Nodal Functionality Major Milestone | EDS 4 PM | July 1, 2008 |
| E9 – Develop TN Procedures | Go-Live less 60 days | ERCOT Readiness PM | July 1, 2008 |
| EMO2 – Verify Voltage Support Functionality | EDS-4 Full Nodal Functionality Milestone | EDS 4 PM | July 1, 2008 |
| MO3 Verify Supplemental Ancillary Services market (SASM) | Full Nodal Functionality 24*7 Operations | EDS 4 PM | July 1, 2008 |
| MP8 – QSE, AP & RTM MIS and Web Service Transactions | EDS-4 Release 9 – 24*7 Operations plus 7 days | EDS 3 & 4 PM | July 8, 2008 |
| MP9 – QSE, DAM MIS and Web Service Transactions | EDS-4 Release 9 – 24*7 Operations plus 7 days | EDS 4 PM | July 9, 2008 |
| MO5 – Generate LMPs for 6 months | Fifth – 6 Month LMP Posting plus 180 days | EDS 3 PM | July 10, 2008 |
| CO5 Verify RTM Settlement Statements | EDS-4 Release 8 complete plus 14 days | EDS 4 PM | July 14, 2008 |
| CO6 – Verify RTM Settlement Invoices | EDS-4 Release 8 complete plus 14 days | EDS 4 PM | July 14, 2008 |
| CRR3 – Trial operation of Monthly CRR Auction | EDS-3 – Release 7 complete milestone | EDS 3 PM | July 20, 2008 |
| CRR5 – Trial Operation of Annual CRR Auction during Trials | EDS-3 – Release 7 Completion | EDS 3 PM | July 21, 2008 |
| CRR4 – Implement TCR to CRR Transition Plan | Go Live Activities less 120 days | CRR PM | August 1, 2008 |
| CO3 – Verify DAM Settlement Statements | EDS-4 Full Nodal Functionality Major Milestone plus 30 days | EDS 4 PM | August 4, 2008 |
| CO7 – Verify DAM Invoices | EDS-4 Full Nodal Functionality Major Milestone plus 30 days | EDS 4 PM | August 4, 2008 |
| E2 – Verify ERCOT Performance Monitoring Test Plan | EDS 4 - 168 Hour Test major Milestone less 30 days | ERCOT Readiness PM | August 4, 2008 |
| E4 – Price Protection Mechanisms | Go Live Activities less 90 days | ERCOT Readiness PM | August 4, 2008 |
| E12 MIS Compliance Test | EDS-4 Full Nodal Functionality Major Milestone plus 30 | MIS PM | August 4, 2008 |
| E14 – Verify QSE Performance Monitoring Test Plan | EDS 4 – 168 Hour Test Major Milestone less 30 days | ERCOT Readiness PM | August 4, 2008 |
| E15 – Verify TSP Performance Monitoring Test Plan | EDS 4 – 168 Hour Test Major Milestone less 30 days | ERCOT Readiness PM | August 4, 2008 |
| EMO8 – Conduct EECP Test | EDS 4 – 168 Hour Test Major Milestone less 30 days | EDS 2 PM | August 4, 2008 |
| MP17 – MP Qualification Activities | EDS 4 168 Hour Testing Major Milestone less 90 days , less 30 days, less 14 days | ERCOT Manager of Wholesale Client Services | June 2, 2008 August 4, 2008 August 18, 2008 |
| C010 – Verify Credit Calculations | EDS-4 168-Hour Test Major Milestone less 14 days | EDS 4 PM | August 18, 2008 |
| CO8 – Verify CRR Auction Invoices | EDS-3 End of Trial Operations of CRR Major Milestone plus 30 days | EDS 4 PM | August 20, 2008 |
| CO4 – Zonal/Nodal Coordinated Settlement Operations | EDS 4 168 Hour Test Major Milestone | EDS 4 PM | September 1, 2008 |
| MO1 – Operate DA market for 7 Days | Full Nodal Functionality 24*7 Operations plus 60 days | EDS 4 PM | September 1, 2008 |
| MO2 Operate 7 Day Market with RUC | Full Nodal Functionality 24*7 Operations plus 60 days | EDS 4 PM | September 1, 2008 |
| MO6 - Verify DAM Ancillary Services | Full Nodal Functionality 24*7 Operations plus 60 days | EDS 4 PM | September 1, 2008 |
| R2 – Develop Texas Nodal Market Launch Plan | Go Live Activities less 90 days | ERCOT Readiness PM | September 1, 2008 |
| E13 – Standard Form Agreements Executed | Go Live Activities less 120 days | Manager of Wholesale Client Services | September 2, 2008 |
| C1 – Contingency Plan for Weekly, Daily and Hourly RUC Failure | Go Live Activities less 60 days | EDS 4 PM | October 1, 2008 |
| C2 – Contingency Plan for DAM/LMP Failure | Go Live Activities less 60 days | EDS 4 PM | October 1, 2008 |
| C3 – Contingency Plan for ICCP Data Failure | Go Live Activities less 60 days | EDS 2 PM | October 1, 2008 |
| C4 – Contingency Plan for SCED Failure | Go Live Activities less 60 days | EDS 3 PM | October 1, 2008 |
| C5 – Contingency Plans for Key Settlement and Financial Transfer Processes | Go Live Activities less 60 days | EDS 4 PM | October 1, 2008 |
| C6 – Develop Plan for SE Failure | Go Live Activities less 60 days | EDS 2 PM | October 1, 2008 |
| C7 – Contingency Plan for a Backup Facility | Go Live Activities less 60 days | EDS 4 PM | October 1, 2008 |
| C8- Contingency Plan for Portal/API Failure | Go Live Activities less 60 days | EDS 4 PM | October 1, 2008 |
| R1 – Nodal Readiness declaration | Go Live less 60 days | ERCOT NODAL Program Executive Director | October 1, 2008 |
| C9 – Contingency Plan for Site Unavailability | Go Live Activities less 60 days | EDS 4 PM | October 6, 2008 |
| C10 – Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS | Go Live Activities less 60 days | EDS 4 PM | October 6, 2008 |
| E5 – Nodal SAS 70 Preparedness | Go Live Activities less 45 days | ERCOT Readiness PM | October 15, 2008 |
| CO1 – Settle market for 7 Days and provide appropriate extracts | EDS-4 Release 9 Complete | EDS 4 PM | November 3, 2008 |
| CO2 Verify Dispute Process of 168 Hour Test | EDS-4 Release 9 Complete | EDS 4 PM | November 3, 2008 |
| EMO3 – Verify Outage Evaluation System Functionality | EDS-4 Release 9 Complete | EDS 4 PM | November 3, 2008 |
| EMO4 – Run 7 Day Stability Test | Go live Less 30 days | EDS 4 PM | November 3, 2008 |
| IMM1 | EDS 4 – Release 9 Complete | ERCOR PMO PM | November 3, 2008 |
|  | Go Live Activities less 14 days |  | November 17, 2008 |
| EMO1 – Network Security Analysis & Transmission Constraint Management | EDS 2 – Release 3 complete plus 60 days | EDS 2 PM | February 2, 2009 |
| MP10 – Mapping of Resources to Resource Nodes and Resources to Revenue Quality Meters is Complete | Start Go Live Activities less 120 days | ERCOT Manager of Wholesale Client Services | March 2, 2009 |

# Market Participant Metrics

### MP1 - MP Engagement

| Reported By: MP (Accountable Executive) & ERCOT |  |  | EDS: Registration |
| --- | --- | --- | --- |
| Target Completion: Periodic: June 1, TBD, TBD |  |  |  |
| Category: Engagement |  |  |  |
| Metric Description: MP are actively participating in Nodal preparation to include the assignment of an Accountable Executive, a Program Manager,the allocation of a budget, Program Charter and have indicated an intent to participate in the Nodal Market. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants are engaged in Nodal preparations. |  |  |  |
| Criteria: The Readiness Team will review self reporting from each Market Participant indicating their level of engagement in Nodal preparation, mobilization and delivery. Readiness will be achieved when MP Accountable Executives have submitted Completion Review Documents outlining their status related to defined activities. Target 1 – Preparation AE Response Accountable Exec Nominated Project Manager Assigned Project Brief/Initiation Document Completed Project Plan Completed Project Budget Allocated Target 2 Mobilization AE Response Project Staffed and mobilized to meet the EDS Testing Requirements Project Vendor(s) Selected (if Appropriate) Training Plan completed Training Budget allocated Testing Plan completed Business Impact Assessment Completed Target 3 Delivery AE Response Planned Completion Date for Registration <= yyyy/mm/dd Planned Completion Date Qualification <= yyyy/mm/dd Plan Completion Date for Business Requirements <= yyyy/mm/dd Plan Completion Date for Conceptual Systems Designs <= yyyy/mm/dd Plan Completion Date for Detailed Designs <= yyyy/mm/dd Planned Date Systems will be available to test interfaces with ERCOT System <= yyyy/mm/dd |  |  |  |
| Reporting Data Sources: MP Self Reported |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### MP2 – QSE with Resources Connectivity to EDS Environment

| Reported By: QSE with Resource & ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: 6-month LMP posting major milestone less 45 days |  |  |  |
| Category: Connectivity |  |  |  |
| Metric Description: QSEs with resources have confirmed their ability to connect to the MIS and/or an External Web Service in the early Early Delivery System (EDS) environments. |  |  |  |
| Background: The intent of this metric is to ensure that QSEs with Resources can successfully connect to the eEDS allowing ERCOT to provide better support to the MPs facilitating trials completion. |  |  |  |
| Criteria: The Readiness Team will review documentation providing connectivity statistics for the EDS3 environment by Market Participant. Readiness will be met when the MP successfully submits a three part offer, incremental/decremental offer, current operating plan or a output schedule via either web services or the MIS that is logged in the Enterprise Integration Framework (EIF) transaction database as successfully passing the proxy server. EIF entry per QSE with resources >=1 RAG Rules - Red – Failure to meet 10/2/07 execution deadline - Amber – Failure to sign-up by 8/15/07 - Green – Meeting Plan |  |  |  |
| Reporting Data Sources: EIF log table entry in EDS / ERCOT EDS 3 PM EDS 3 team will track registration and execution by QSE with Resources |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### MP3 – QSE with Resources Upload of SCED Offers to EDS

| Reported By: QSE with Resources & ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: 6-month LMP posting major milestone less 45 days |  |  |  |
| Category: Connectivity |  |  |  |
| Metric Description: QSEs with Resources shall demonstrate their ability to successfully submit a 3 part offer and if applicable a dynamic output schedule to the MIS and/or an External Web Service in the Early Delivery System (EDS) environment and successfully pass validation with the MMS system. |  |  |  |
| Background: The intent of this metric is to ensure that QSEs with Resources can successfully submit a 3 part offer and if applicable a dynamic output schedule to the EDS. |  |  |  |
| Criteria: The Readiness Team will review documentation providing transaction statistics by Market Participant. Readiness will be met when the MP successfully submits a request that is logged in the Enterprise Integration Framework (EIF) transaction database. EIF entry with transaction status of Passed per QSE with resources >=1 - RAG Rules - Red – Failure to meet 10/2/07 execution deadline - Amber – Failure to sign-up by 8/15/07 - Green – Meeting Plan |  |  |  |
| Reporting Data Sources: EIF log table entry in EDS as verified by the ERCOT EDS Test Team / ERCOT EDS 3 PM EDS 3 team will track SCED offers by QSE with Resources. |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### MP5 – ICCP Point to Point Telemetry Test

| Reported By: QSEs, TDSPs & ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 1 - Release 2 Complete plus 14 days |  |  |  |
| Category: Telemetry |  |  |  |
| Metric Description: ERCOT shall coordinate a test with TSPs and QSEs with resources to verify that the equipment point mapping, value, and status are correctly transmitted within an acceptable scan rate. |  |  |  |
| Background: The intent of this metric is to ensure that TSP, QSE and ERCOT telemetry ICCP representations are in synch with one another. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the accuracy of telemetry points mapping, station topology diagrams, values and status within an acceptable scan rate. Readiness will be achieved when MPs have added all required points to meet Nodal Protocols, Point to Point Verification has occurred, Telemetry issues documented and communicated to MPs, ERCOT has ICCP database under change control and MPs have submitted service requests to resolve ICCP issues. Number of points missing from Nodal Protocol Requirement <= 5% Number of Point to Point Verification = 95% of Points within a 10 second scan rate Number of Telemetry issues identified = Number of Telemetry issues documented and communicated to MPs. Number of MP service request submitted >= 90% of Number of Telemetry issues documented and communicated to MPs RAG Rules Red – Failure to meet above criteria Amber – Behind point to point schedule Green – Meeting above criteria |  |  |  |
| Reporting Data Sources: ICCP Database / Network Operations Model & the EDS 1 status report located on the Nodal Readiness Center: EDS 1 Status MMDDYYYY.xls / ERCOT EDS 2 PM |  |  |  |
| References | TP: 5.4.1 (2)(a) | TNP: 3.10.7, 6.5.7.6.1(8) & 8.1.2.2(6)(b) |  |

### MP11 - MP Registration Activities

| Reported By: MP & ERCOT |  |  | EDS: Registration |
| --- | --- | --- | --- |
| Target Completion: EDS 3 - Registration EDS Trial Preparation Milestone plus 14 days |  |  |  |
| Category: Registration and Qualification |  |  |  |
| Metric Description: This metric shall measure whether Market Participants have performed the tasks outlined in the Registration & Qualification Guide . |  |  |  |
| Background: The intent of this metric is that ERCOT has all registration related data for all market participants intending to participate in the Nodal Market on record. |  |  |  |
| Criteria: The Readiness Team will review data provided by the Registration and Qualification Coordinator tracking the ERCOT/MP registration activities. MP Readiness will be achieved when the Registration checklist is completed by Client Services and the market participant Accountable Executive and Authorized Representative are notified by ERCOT via email. MP Registration Checklists Completed = Number of MPs Intending to Participate in Nodal Market September 2007 Targets: - measure completion of the Resource Asset Registration Form (RARF) by Resource Entities. - Individual Resource Entities will be measured on their successful completion of the RARF for their generation resources - Market will be measured by percent received % of Generation Participation >= 95% RAG Rules - MPs Red – Failure to submit documentation Amber – Incomplete form Green – All forms received RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria - measure completion of the Ancillary Service Attestation by QSEs with Resources. - Individual QSEs will be measured on their successful completion of the Attestation. Since this is voluntary at this time, QSEs will not be assessed ‘red’ - Market Segment will be measured by percent received % of Ancillary Generation >= 95% RAG Rules - MPs Amber – Incomplete form Green – All forms received RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria Note: additional targets will be added as registration and qualification deadlines arise. These targets will be added via the change control process. |  |  |  |
| Reporting Data Sources: Registration Checklists / ERCOT Manager of Wholesale Client Services |  |  |  |
| References | TP: N/A | TNP: 16.2 thru 16.8 & 3.7.1 |  |

### MP14 - MP EDS-2 Trials Participation

| Reported By: QSE with Resource, TSP & ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 – Start of Release 4 plus 14 days |  |  |  |
| Category: Trials Participation |  |  |  |
| Metric Description: This metric evaluates the level of TSP and QSE market participant participation in the EDS 2 Trial. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants have the ability to access telemetry and State Estimator performance reports and are actively participating in the NOMCR process. |  |  |  |
| Criteria: The Readiness Team will review documentation that an adequate number of MPs by market segment representing an adequate percent of overall load have reviewed performance reports on MIS and confirmed ability to access those reports and submitted modifications through the NOMCR process. # of TSP and QSE MPs Participating in Trial >=95% of TSP and QSE MPs intending to participate in Nodal Market % of Load and Generation Participation >= 95% AND % of Load Serving Entities and Resource Entities Participation >= 95% # of TSP and QSE MPs Participating in Trial accessing Telemetry SE Performance Report >= 75% # of TSP and QSE MPs Participating in Trial participating in the NOMCR process >= 75% RAG Rules - MPs Red - Not participating in trials Amber –Participating, but not in NOMCR Green – Meeting criteria RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: EDS 2 Trials Log / ERCOT EDS 2 PM |  |  |  |
| References | TP: 5.4.1 | TNP: 3.10.8, 3.3.2.1, 3.10.7 |  |

# Commercial Operations Metrics

# Congestion Revenue Rights Metrics

# ERCOT Internal Metrics

### E1 - ERCOT Staff Completes Training

| Reported By: ERCOT |  |  | EDS: 2,3,4 |
| --- | --- | --- | --- |
| Target Completion: Start of EDS 2,3,4, Go Live Activities less 14 days |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT Staff Completes required training modules by area of expertise and job responsibilities. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT staff has the ability to facilitate the Nodal Market. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT Staff have completed the required training. Readiness will be achieved when ERCOT staff have completed required training. Actual Passing Participation by Course for Required Training by EDS/Go Live = 100% - This metric will be measure continuously with updates published in conjunction with planned EDS milestones. - Measurement will include: - Division and Department Head approval of plan - Progress against plan - Division and Department Head sign-off of training accomplishments for each EDS RAG Rules Red – Failure to meet plan Amber – Behind Training Schedule Green – Meeting Plan |  |  |  |
| Reporting Data Sources: Learning Management System / ERCOT Readiness PM - ERCOT will plan which training modules individuals are required to take and will track progress against the plan. - ERCOT will publish accomplishments against the plan. |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E6 - Develop Nodal Operating Guides

| Reported By: ERCOT |  |  | EDS: 3,4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Less 360 days |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT shall develop Nodal Operating Guides to direct Market Participants on the daily operation of the Texas Nodal Market and Grid. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has provided the Market Participants with the information required to operate the Texas Nodal Market and Grid. |  |  |  |
| Criteria: The Readiness Team will receive documentation that the creation and posting of approved Nodal Operating Guides has occurred. Readiness will be met when the Operating Guides have been posted to the MIS and approved by ROS and TAC. - Traceability of Operating Guidelines to Protocols (50 percent) - Progress against plan (50 percent) - August 22nd – OWG Review of additional comments - September 12th – Impact Analyses due - September 13th – ROS Meeting to consider NOGRR001-017 and IAs - October 5th – TAC Meeting to consider NOGRR001-017 and IAs RAG Rules Red – Failure to Meet Plan and Provide Full Traceability by February, 2008 Amber – Meeting Either Schedule or Traceability, but Not Other Green – On Schedule and Traceability Targets |  |  |  |
| Reporting Data Sources: Operating Guides / ERCOT Readiness PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E8 - ERCOT Staffed for Texas Nodal Operations

| Reported By: ERCOT |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - Full Nodal Functionality 24*7 Operations Major Milestone less 60 days |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT will ensure the appropriate staffing levels required to execute the nodal market. In addition, the roles and responsibilities have been appropriately defined for nodal personnel. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT is appropriately staffed to support Nodal Operations as approved by the PUCT. |  |  |  |
| Criteria: Each impacted Director or VP is responsible for conducting a sizing and alignment analyses for their area as a part of the overall ERT project. Each department will develop their respective supporting documentation and readiness assessment. The Readiness Team will view the analysis results for each department and verify completion of the sizing and alignment analysis and the development of the corresponding staffing plan. Readiness will be achieved upon the completion of Sizing and Alignment Analysis for each Department and Departmental Staffing Plans and the execution of those plans. ERCOT will publish accomplishments against the plan. This metric will be measure continuously with updates published in conjunction with planned EDS milestones. - Sizing and Alignment Analysis completed for each impacted department - Creation of Org. Charts (Q22007) - Division and Department Head approval of deliverables - Allocation of appropriate funding to staff the organization (Q12008) - Staffing to plan (Q42008) |  |  |  |
| Reporting Data Sources: Sizing and Alignment Analysis for each Department / Departmental Staffing Plans / ERCOT Readiness PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E9 - Develop TN Procedures

| Reported By: ERCOT |  |  | EDS: 2,3,4 |
| --- | --- | --- | --- |
| Target Completion: Go-Live less 60 days |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT shall develop it’s internal processes and procedures supporting the Texas Nodal Market. |  |  |  |
| Background: It is the intent of this metric to have ensure that the processes and procedures necessary to run the Nodal market are in place. |  |  |  |
| Criteria: The Readiness Team will review documentation that ERCOT has created the processes and procedures necessary for operating the Texas Nodal Market. Readiness will be achieved when the processes supporting the Nodal Market have been completed. - Traceability of procedures to Protocols (50 percent) - Progress against plan (50 percent) RAG Rules Red – Failure to Meet Plan and Provide Full Traceability Amber – Meeting Either Schedule or Traceability, but Not Other Green – On Schedule and Traceability Targets |  |  |  |
| Reporting Data Sources: ERCOT Process/ Procedure Inventory / ERCOT Readiness PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

# Energy Management Operations Metrics

# Network Model Management Metrics

### N1 - ERCOT Telemetry Alarm Processing

| Reported By: MP & ERCOT(EDS 1 Team) |  |  | EDS: 1 |
| --- | --- | --- | --- |
| Target Completion: EDS 1 - Release 1 Complete plus 14 days |  |  |  |
| Category: Network Model Management |  |  |  |
| Metric Description: ERCOT initiates alarms for Limit Violations,& Status Changes. |  |  |  |
| Background: The intent of this metric is to ensure that control operators are aware of relevant EMS alarms. |  |  |  |
| - Criteria: The Readiness Team will review the results of the Limit, Status and other EMS Alarm Tests. Readiness will be achieved when alarms are generated from the Limit, Status and other EMS Tests and the attributes of the alarms are correct. . Load / Rating > Alarm set point Change of Status inititiates a Status Alarm RAG Rules Red – Failure to meet criteria Amber – Within 10 percent of meeting criteria Green – Meeting criteria |  |  |  |
| Reporting Data Sources: Alarm Log / ERCOT EDS 1 PM |  |  |  |
| References | TP: 5.4.1 (2)(f),(g) | TNP: |  |

# Market Operations Metrics

# Contingency Metrics

# IMM Metrics

# Overall Readiness Metrics