## Slide 1: Role of Account Management at ERCOT
Market Engagement and Readiness (MER)
Training Update
TPTF Meeting
August 29th, 2007
Market Education
Notes: <number>

## Slide 2: Agenda
    Training Development
      Progress report
      Upcoming Courses
    Training Delivery
      Progress Report
      New Releases
      Scheduled Training
Market Training
ERCOT Nodal Market Transition

## Slide 3: Training Development – Progress Report
Course | Length | Initiated | Training Sub-Group Review | Beta Course | Class Room Training |  | Web-Based Training | 
 |  |  |  |  | Due Date | Status | Due Date | Status
ERCOT Nodal 101: The Basics | 1 - Day |  |  |  | Done |  | Feb – 07 | 
Economics of LMP | 1 - Day |  |  |  | Done |  | N/A | N/A
Transition To Nodal Markets | Web-Based |  |  | N/A | N/A | N/A | May – 07 | 
Load Serving Entity 201 | 2 - Days |  |  |  | Done |  | Aug – 07 | 90%
Basic Training Program | 5 - Days |  |  | Sept – 07 | Oct – 07 | 90% | Dec – 07 | 30%
NOIE QSE Operations | 1 - Day |  |  | Oct – 07 | Oct – 07 | 30% | Dec – 07 | 0%
Network Model Management | 2 - Days |  |  | Oct – 07 | Nov – 07 | 40% | Dec – 07 | 0%
Congestion Revenue Rights | 2 - Days |  |  | Oct – 07 | Oct – 07 | 30% | Dec – 07 | 0%
Market Settlement 301 | 2 - days |  |  | Oct – 07 | Nov – 07 | 30% | Jan – 08 | 0%
Notes: <number>

## Slide 4: Training Development – Progress Report
Course | Length | Initiated | Training Sub-Group Review | Beta Course | Class Room Training |  | Web-Based Training | 
 |  |  |  |  | Due Date | Status | Due Date | Status
Generation 101 | 1 - Day |  | Aug – 07 | Oct – 07 | Nov – 07 | 30% | Dec – 07 | 0%
Generation 201 | 1 - Day |  | Nov – 07 | Jan – 08 | Feb – 08 | 20% | Mar – 08 | 0%
Generation 301 | 1 - Day |  | Jan – 08 | Feb – 08 | Mar – 08 | 10% | Apr – 08 | 0%
Market Information System | 2 - Days |  | TBD | N / A | N/A | 10% | Mar – 08 | 10%
Notes: <number>

## Slide 5: Training Development – Upcoming Courses
Course | Length | Delivery Date
Transmission 101 | 2 ½ – Days | Feb-08
ERCOT 101 for Wind Generation | 1 - Day | Mar-08

## Slide 6: Training Development – New Releases
  Basic Training Program
    Beta Course Scheduled for September
    First delivery of course scheduled for October in Austin
    5 day course
      Day 1 – (Course Introduction, Fundamentals of the Nodal Market, Day-Ahead Market)
      Day 2 – (Day-Ahead Market , Transmission Security Analysis & RUC )
      Day 3 – (Transmission Security Analysis & RUC, Adjustment Period)
      Day 4 – (Adjustment Period , Operating Period)
      Day 5 – (Operating Period, Abnormal Emergency Operations)
    Will be delivered once a month

## Slide 7: Training Delivery – Progress Report
Course | Delivery | No. of Instructor Led sessions | Passed |  | 
 |  |  | MP | ERCOT | Total
ERCOT Nodal 101: The Basics | Instructor Led Web Based Test Only | 46 | 1616/1756 | 482/531 | 2098/2287 92%
Economics of LMP | Instructor Led | 16 | 430 | 175 | 605*
Transitions to Nodal Markets | Web | N/A | 158 | 105 | 147/263**
LSE 201 | Instructor Led | 3 | 127 | 3 | 124/130
* ILT - No exam
** WBT – No exam – Completed reviewing 75% or more of the slides

## Slide 8: Training Delivery – Scheduled Training
ERCOT Nodal 101: The Basics | 
Date | Location
Sept 11, 2007 | ERCOT Austin (Austin)
The Economics of LMP | 
Sept 17, 2007 | ERCOT Austin (Austin)
Sept 24, 2007 | Suez Energy (Houston)
Oct 8, 2007 | Suez Energy (Houston)
Oct 29, 2007 | Stream Energy (Dallas)
Load Serving Entity 201 | 
Sept 27-28, 2007 | CenterPoint Energy (Houston)
Oct 2-3, 2007 | Atrium (Dallas)
Basic Training Program | 
October 22-26, 2007 | The Commons Center (Austin)
Market Training
ERCOT Nodal Market Transition
Notes: <number>

## Slide 9: Questions
Questions ??
Market Training
ERCOT Nodal Market Transition
Notes: <number>