## Meeting Schedule
Month | Date | Location
March (3) | 12 | ERCOT Austin 206B
April (4) | 21 & 22 | AmeriSuites/AmeriSuites
May (5) | 12 & 13 | ERCOT Austin 206A/ERCOT Austin 206B
June (6) | 10 & 11 | ERCOT Austin 206A/ComfortSuites
July (7) | 15 & 16 | AmeriSuites/AmeriSuites
August (8) | 12 & 13 | ERCOT Austin 206A/ComfortSuites
September (9) | 16 & 17 | AmeriSuites/AmeriSuites
October (10) | 13 & 14 | ERCOT Austin 206B/ERCOT Austin 206B
November (11) | 10 & 11 | ERCOT Austin 206B/ERCOT Austin 206B
December (12) | 8 & 9 | ERCOT Austin 206B/ERCOT Austin 206B

## Membership & Attendance
Officer | Name | Company | E-Mail Address | Phone | Alternate Phone | 2003-03-01 | 2003-04-01 | 2003-05-01 | 2003-06-01 | 2003-07-01 | 2003-08-01 | 2003-09-01 | 2003-10-01 | 2003-11-01 | 2003-12-01
| Bergman, Karen | ERCOT | kbergman@ercot.com | 512-248-3171
| Bratton, Charlie | TXU Energy | cbratto1@txu.com | 214-875-3703 | bar: 2003-03-01
| Brubaker, Wendy | Systrends | wendy.brubaker@systrends.com | 562-693-9856
| Dawson, Bernie | Envision Utility Software | bernardd@envworld.com | 512-266-7787
| Eddleman, Neil | TEAM | neil@txteam.org
| Flowers, BJ | TXU Energy | bj.flowers@txu.com | 214-812-4330
| Hayden, Leeanne | Republic Power | leighannmc@att.net | 214-906-7680
| Hermes, Connie | STEC | connie@stec.org | 361-485-6173 | bar: 2003-03-01
| Hurdle, Angela | PUC | Angela.hurdle@puc.state.tx.us | 512-936-7397
| Jackson, Tom | Austin Energy | Tom.Jackson@austinenergy.com | 512-322-6324 | bar: 2003-03-01
| Klimitchek, Darrell | STEC | Darrell@stec.org | 361-485-6275 | bar: 2003-03-01
| Moore, Elizabeth | TXU Energy | emoore2@txu.com | 214-812-3406
| Mullins, David | Republic Power | David.mullins@ngwi.com | 832-615-0233
| Odle, Dave | ERCOT | dodle@ercot.com | 512-658-4716 | bar: 2003-03-01
| Ohrt, Wendy | STEC | wendyjo.stec.org | 361-485-6172 | bar: 2003-03-01
2003 VC | Patrick, Kyle | Reliant Resources | kpatrick@reliant.com | 713-497-3396 | bar: 2003-03-01
| Pell, Vera | AEP Retail | vpell@aep.com | 918-493-9529
| Reed, Cary | AEP | careed@aep.com | 918-260-0093 | bar: 2003-03-01
2003 Chair | Rehfeldt, Diana | TNMP/First Choice Power | drehfeldt@tnpe.com | 817-377-5580 | bar: 2003-03-01
| Reily, Bill | Oncor | breily1@txu.com | 214-875-2520 | bar: 2003-03-01
2003 VC | Robertson, Johnny | TXU | jrobert1@txu.com | 214-875-1565 | bar: 2003-03-01
| Robeson, Dave | Entergy | drobe90@entergy.com | 504-576-2571
| Rodriguez, Robert | Constellation New Energy | Robert.Rodriguez@constellation.com | 281-793-6339
| Santhhappan, Geetha | Constellation New Energy | geetha.santhappan@constellation.com | 713-646-5464 | bar: 2003-03-01
| Scott, Kathy | CenterPoint Energy | Kathy.d.scott@centerpointenergy.com | 713-945-6630 | bar: 2003-03-01
| Skiba, Ed | Entergy | edskiba@us.ibm.com | 504-576-5246
| Taylor, Revis | Simplified Data Solutions | rtaylor@simplified.net
| Waters, Garry | Competitive Assets | garrywaters@bluebon.net | 512-321-3703
| Wilburn, Suzette M. | ERCOT | swilburn@ercot.com | 512-248-3991 | bar: 2003-03-01
| Zake, Diana | Reliant Resources | dzake@reliant.com | 512-494-3004 | bar: 2003-03-01

## 2003 Action Items
Meeting | Sponsor | Issue | Action Item | Resolution
February | Charlie Bratton/ Ed Skiba | 814_PC Changes | Ed Skiba will be asked to draft a change control for review. Changes which impact both the PC and PD will be submitted (i.e., on the PD there is the Reject for “invalid zip code” which may need to be removed). Johnny Robertson will send the updated verbiage to Ed for his use. | OPEN
February | Tom Jackson | MC/TDSP Bi-Directional Use of 814_PC | Bernie Dawson will follow up on this. | OPEN
February | BJ Flowers | Missing 867s, missing 810s and missing 867s & 810s. These three actions may be brought back to RMS depending on what is found out. Findings from the TDSP will be sent to Diana Rehfeldt nlt 28 Feb 2003 to see if this needs to go to RMS. | There are three Actions:ACTION 1: CRs will identify which ESIs are missing consumption and/or invoices. All CRs are asked to send ESIs to the TDSPs for analysis related to missing consumption and invoices. If TDSP needs more then contact the TDSP and request more. Send data to TDSPs ASAP. ACTION 2: ERCOT will also do an analysis. Karen Bergman believes ERCOT provides some type of report related to missing usage/867s…she will look into this and let SET know. ACTION 3: TDSPs will do analysis for issues related to 867s and 810s. | CRs who sent their data to TDSPs were responded to by the TDSPs.
February | Dave Odle | Negative Consumption on 867_03 | ACTION: MPs are requested to do an analysis on whether or not a negative number is a valid value for the PTD PP (IDR) or PTD SU (non-IDR): QTY02 and/or MEA03. Do you send a negative number???? Is this valid per Ts&Cs and/or other???? This will be submitted for the next Market Change Control call. | OPEN
February | Kathy Scott | Change Controls 2003-483 & 484 | ACTION: Kathy Scott to update and send to Ed Skiba and Dave Robeson to review before they go to David Odle for sending for market change control. The examples need to be looked over also. ACTION: David Odle will update status of these in the log as WITHDRAWN. | OPEN
February | Kyle Patrick | Visio Process Flows | ACTION: ERCOT to work with Visio group and get all visios including new ones official and posted to the WEB Site. | OPEN
February | Dave Odle | Duplicate 814_20 Issue when Current CR and New CR are SAME | ACTION: David Odle to write this up and submit for change control conference call. | Yes we need to make the adjustments and one 814_20 will be sent to the CRs from ERCOT in the situation that they are both the old and the new CR. Visios will need to be adjusted aswell.
February | Dave Odle | 867_04 MEAo7 = 51 Issue | ACTION: David Odle to research and clarify what specifically is being requested. Then will submit for change control conference call if needed. | OPEN
February | Robert Rodriguez | Timeframe for TDSP to send read information on Standard Monthly On Cycle Read not associated with Disconnect/Termination | ACTION: Diana Rehfeldt to submit an RMS Issues form to RMS for resolution. | OPEN
February | Dave Odle | Reject reasons. | ACTION: DAVID ODLE TO SUBMIT THIS LIST FOR INCLUSION IN THE MINUTES. ACTION: Reject reasons-each market participant to review Dave Odle’s analysis plus review their own companys receipt and sending of the A13 codes to see if we can develop a specific code to identify the reject and/or proper use of the reject codes by your specific company. ACTION: A large number of “008” reject codes are being used on the 814_07 with the reject text of “esi id exists but is not active” and “esi id not active for this esp on the period of end date”. CRs are being asked to see who is sending and the specific reason why. | OPEN
February | TX SET | Business Application Overviews | 814_28 & 814_29 ACTION: DAVID ODLE, CAREY REED AND CHARLIE BRATTON ARE GOING TO TAKE A LOOK AT THESE AND REWORK. ISSUES OF HOW MUCH DETAIL ARE TO BE IN ALL OF THESE WAS DISCUSSED…… 824 ACTION: BILL REILLY AND KYLE PATRICK WILL TAKE THIS AND LOOK IT OVER. ACTION: TDSPS ARE REQUESTED TO DETERMINE WHAT THEY DO IF THEY RECEIVE THE BGN08 = EV. 810_02 ACTION: TOM JACKSON AND BERNIE DAWSON WILL LOOK OVER THIS. 810_03 ACTION: BILL REILLYAND CAREY REED WILL LOOK OVER THIS. 650_01 650_02, 650_04, 650_05 ACTION: TOM JACKSON AND BERNIE DAWSON WILL LOOK OVER THIS. SO WILL DARRELL KLIMICHEK. | OPEN
February | Diana Rehfeldt | 650_02 change control 2003-485; Withdrawn. | DIANA REHFELDT WILL SEND THE WITHDRAWN CHANGE CONTROL WITH QUESTIONS/CHANGES TO ED SKIBA AND DAVE ROBESON. DAVID ODLE WILL UPDATE THE CHANGE CONTROL LOG TO SHOW THIS ONE AS WITHDRAWN. THIS WILL COME UP ON A CHANGE CONTROL CALL FOR APPROVAL. ONLY NEED TO DISCUSS THE ITEMS WHICH WERE CHANGED. | OPEN
February | Kathy Scott | Outage Transactions | ACTION: KATHY SCOTT TO SEND THESE TRANSACTIONS TO DAVID ODLE TO POST TO THE WEB SITE. | OPEN
February | Kyle Patrick | New POLR Rule | ACTION: The CR should not send the 1MW or greater to the AREP. The PUCT is supposed to send a message to the market requesting them to not do this. ERCOT is going to look and see if they can do something to keep this from happening if the CR does send this in. ERCOT will look into possibly doing validation via 814_10, if customer is large C&I, greater than 1MW then Reject. Possibly take this to RMS. | PUCT to send email out.
February | Dave Odle | SET V1.5 Baseline to EDI Guides | ACTION: David Odle will baseline the V1.5 EDI guides and post them to the WEB Site (i.e, accept the Redlines which are for V1.5). Looking for SET folks to review these after he gets this done to ensure they are accurate. | OPEN
February | Jennifer Teel | Noticed the REF*BLT segment is missing from the 814_10 example in the guideline. ************************************************************************************************ 814_10 Examples #1 of 1 Drop to AREP Request - Current CR to ERCOT Current CR sends Drop to AREP Request to ERCOT Current CR is dropping the customer to the Affiliated Retail Electric Provider (AREP) ST~814~000000001 Transaction Type, Control Number BGN~13~200105010800001~20010501~~~~~10 Request, Unique Transaction Number, Transaction Date, SET Transaction Number N1~8R~CUSTOMER NAME Customer Name N2~D/B/A ABC COMPANY~C/O JANE SMITH Customer Name Overflow N3~123 N MAIN ST~ANY ADDITIONAL INFO Customer Service Address N4~ANYTOWN~TX~781110001 Customer Service Address PER~IC~NAME~TE~8005551212 Customer Contact Name and Telephone number(s) N1~8S~TDSP COMPANY~1~007909411 TDSP Name and DUNS Number N1~AY~ERCOT~1~183529049~~40 ERCOT Name and DUNS Number, Receiver N1~BT~ACCOUNTS PAYABLE DIVISION Customer Billing Name N2~D/B/A ABC COMPANY~C/O JANE SMITH Customer Billing Name Overflow N3~123 N MAIN ST~ANY ADDITIONAL INFORMATION Customer Billing Address N4~ANYTOWN~TX~78111 Customer Billing Address N1~ SJ~CR COMPANY~9~007909422CR51~~41 CR Name and DUNS Number, Sender LIN~1~SH~EL~SH~CE Cycle Switch ASI~7~002 Drop Request REF~Q5~~10111111234567890ABCDEFGHIJKLMNOPQRS ESI ID REF~SU~Y Special Needs Indicator SE~19~000000001 Number of Segments, Control Number | Change Control to be written | Kyle Patrick wrote and submitted a change control for this
February | Dave Odle | I would like for TX SET to examine the 650_04 (and any other transaction where this occurs) for clarity in regards to the DTM~139 and 215. The guide currently says Required if BGN.08 = 'S2' and this isn't completely accurate. It is actually supplied if the TDSP can estimate, therefore it is technically OPTIONAL. This is causing some confusion on what validation should be placed on the maps. | The sentence referring to the condition based on the BGN should be removed. A change controls should be written to remove this sentence. These DTM's are OPTIONAL based on if the TDSP can estimate. There should be no reference to the BGN08. | OPEN
March | Jennifer Teel | Option 1 CR's don't need to do the 814_PC. I even went back to the version 1.4 guidelines and the wording was the same. I wonder how many CR's (I know I have some) who have been doing the 814_PC and are option 1. To me though this leads to the question of how a CR updates "Critical Care Information" - this was one of the tests with the 814_PC. And for Muni/Coop's it is used to update Bill Type Information. I think there may need to be some Version 1.6 changes in the front matter to cover these two scenarios. I would advise that if CR's are prepared to test the SG312 we let them. If TXU does not have coding, than maybe they code be exempt on a one off. | None | Option 1 CRs do not use 814_PCs. The reason is that in 1.5 contact information is provided on the enrollment transactions. Option 1 CRs do not update special needs, the TDSP updates Special Needs for these customers to the CR on the 814_20.
March | Cary Reed, Bill Reily, Kyle Patrick, Wendy Ohrt | 810 820 Issues | Subgroup to discuss and design 810 820 Workshop. Workshop has a target date of April to be held. | OPEN
APRIL | Dave Odle | Myself as a CR along with 2 other cases hit a situation this test flight where the N1*SJ DUNS number had to be the same as the CR GS code. This is an ERCOT requirement. ERCOT caught some of these fixes in the last couple of weeks, but in my case we had started sending Frame 1 and had to make a change and communicate to the TDSP. I don't know of any documentation in the TX market that states that the GS and the N1*SJ DUNS have to be exactly the same. Maybe I am missing something. If this is not documented does it make sense to document this somewhere so we can avoid issues with New CR's or service providers entering the market and making the same mistake. Any feedback on if this is already documented or if not - where should it be documented would be much appreciated. | ERCOT to bring documenttion to further discuss this issue. | OPEN
March | Diana Rehfeldt, Kyle Patrick, Johnny Robertson | To document workgroup voting procedures document. This should cover TX SET Officer Elections, TX SET Change Controls, and Ad Hoc Votess. | SET leadership to distribute to SET membership for discussion. | OPEN
March | MIMO | 814_24 Cancellation Reason | TX SET to add codes | OPEN
March | MIMO | 814_08 Cancellation Reason | TX SET to add codes | OPEN

## Agenda Item Request Form
Meeting | Sponsor | Agenda Item | Issue | Time Request
ex: April | ex: Kyle Patrick (Reliant Resources) | ex: 814_05 Discussion | ex: CR is receiving inproper code in the 814_05 transaction. | ex: 30 Minutes
April | Charlie Bratton | TXU agreed with Entergy and Ercot on CC 499. However I would like to have a Agenda item to address this. Discuss that all Business Application Overviews approvals must be done on a Change Control that is specific to the BAO. |  | 30 Minutes
April | Diana Rehfeldt | Voting Procedures | RMS request that each sub Work Group produce their formal voting procedures. | 30 Minutes
April | Diana Rehfeldt | Cancel/Rebill Process Review | Market requested through RMS Chair that TX SET review the current cancel/rebill process to determine if the number of cancel/rebills can be reduced in the market. | 30 Minutes--Maybe initial discussion with assignment to Task Force
April | Diana Rehfeldt | Release Project Plan |  | 30 Minutes
April | Johnny Robertson | 810_02 COMET WG changes add SAC04 code CRE020 for Meter Owner Credit 814_20 changes may require an code 38 to be added to the N1 loop at N105 for CR,TDSP, Customer, and Third party authorized by the customer. Add an N1 loop for N101=53 (Registered Owner) third party N105 =38 in all N1 loops for owner. | TDSP needs a code to allow credit to be passed to the customer who authorized the change of meter ownership.. Second is notify all parties the meter change was complete and who the meter owner is CR, TDSP, Customer, or third party, | 1 hour , COMNET WG will meet next week and talk about this and I may have a change control to discuss at the April TX SET meeting.
April | Dave Odle | Myself as a CR along with 2 other cases hit a situation this test flight where the N1*SJ DUNS number had to be the same as the CR GS code. This is an ERCOT requirement. ERCOT caught some of these fixes in the last couple of weeks, but in my case we had started sending Frame 1 and had to make a change and communicate to the TDSP. I don't know of any documentation in the TX market that states that the GS and the N1*SJ DUNS have to be exactly the same. Maybe I am missing something. If this is not documented does it make sense to document this somewhere so we can avoid issues with New CR's or service providers entering the market and making the same mistake. Any feedback on if this is already documented or if not - where should it be documented would be much appreciated. | ERCOT to bring documenttion to further discuss this issue. | 1 Hour

## Next Release Project Plan
Project Plan for Next Release
Activity | Time Frame | Start Date | End Date | Membership
Identify all changes required for version 1.6. Submit all change controls to be applied to version 1.6. Discussion and approval/denial of all change control design documents. | As determined | Ongoing Effort
Update current version 1.5 to a clean baseline with all change controls applied | 3 weeks | February |  | See 1.5 Baseline Matrix Assignments Worksheet
Review all change controls and prepare any SCRs and PRRs as needed | 1 week
Build SEF and Word docs. With all 1.6 change controls applied. | 3 weeks
Publish v1.6 first draft redline | 1 day
Tx SET committee will review and compare Visio's, change controls and implementation guides. All market participants will start design and technical analysis. | 6 weeks
Resolve issues | 1 week
Apply resolved issues and any change controls approved since the redline publication | 1 week
Publish final v1.6 redline | 1 day
TxSET committee will review and compare Visio's, change controls and implementation guides. Any identified gaps or errors will be sent to TxSET | 2 weeks
Resolve issues | 1 week
Apply resolved issues | 1 week
Update Transaction Scenario Inventory. Clean up any identified errors. | 2 weeks
Publish official version 1.6 | 1 day
Minimum time needed for TxSET to publish a new version of implementation guides after the design requirements have been given to TxSET. | 21 weeks'**
Delivered to TTPT

## 1.5 Baseline Matrix (3-12-03)
Transaction | TX SET Volunteer | Analysis Results | Changes to be applied | Baselined?
650_01 | Charlie Bratton | Ready | None | Y
650_02 | Charlie Bratton | (2002-305) - 650_02 RD Read (Out of Cycle) still inserted?? | None - it appears that the changes from CC 2002-305 are applied to redline correctly - may need clarification on this one | Y
650_04 | Charlie Bratton | (2002-346) - Not fixed in Example 2 | Update ST/SE segment count in example 2 | Y
650_05 | Charlie Bratton | Ready |  | Y
814_PC | Diana Rehfeldt | (2001-188) Examples 1 - 3 not updated to remove the PER02 Name from the PER*IC of the N1*FJ and N1*VA (2003-477) Summary Page not updated to remove 2002-405 change control and Examples as listed above still not updated (2002-267) Listed this transaction to remove the 9 DUNS Qualifier in the N1*AY, but does not apply. Also was not listed in the Summary of pages. (2002-331) listed on summary of changes page and examples cleaned up by replacing the F5 code with the proper FJ code, but this change control does appear on the list as an approved change control for v1.5 (2002-405) listed on Summary of changes page, but does not appear as approved change control for v1.5. Also see reference in 2003-477 above. | Will update the guide to reflect these changes Will remove change control 405 from the summary of changes as it was withdrawn None, change does not apply to this transaction This CC was approved as an emergency for both 1.4 and 1.5. It's located on the 1.4 tab of the CC Log. Should we add it to the 1.5 as well? Will remove reference to the CC in the summary of changes as it was withdrawn | Y
814_PD | Diana Rehfeldt | 2002-267 Listed this transaction to remove the 9 DUNS Qualifier in the N1*AY, but does not apply. Also was not listed in the Summary of pages. | None, change does not apply to this transaction | Y
814_01 | Diana Rehfeldt | Ready |  | Y
814_02 | Diana Rehfeldt | Ready |  | Y
814_03 | Cary Reed | (2002-444) - missing from Change Control page as approved on 10/25/02. The gray box information on the REF~BLT. Required | Will update Summary of Changes and guide to reflect the information from CC444 | Y
814_04 | Cary Reed | (2002-246) - ok,although it really applies to 814_05 and is listed there also. |  | Y
814_05 | Cary Reed | (2001-161) - not marked at V1.5 on Change Control Log, otherwise, ok. (2002-266) - missing from Summary of changes page-The information on the cc log would be nice to include in the change summary | Will update the change control log to reflect this CC in the 1.5 section Will update the summary of changes to reflect the information from CC266 | Y
814_06 | Cary Reed | Ready |  | Y
814_07 | Kyle Patrick | Ready |  | Y
814_08 | Kyle Patrick | (2002-231) - 2002-293 is in place so 2001- 231 does not need to be applied. (2002-317) - 2002-362 reapplies this change control correctly. | None, both change controls are listed correctly None, both change controls are listed correctly | Y
814_09 | Kyle Patrick | Ready |  | Y
814_10 | Kyle Patrick | (2002-450) - Still Required if Available in the REDLINE (2002-261) - example 2 of 2 is not included in the REDLINE it appears to me that the latest CC in this transaction "428" was not written from the latest REDLINE so some of the changes that previous CCs initiated were not captured in the last one. So whomever overlayed "428" in fact overlayed the old document...wiping out some of the changes. Thats just a guess...whatever the case 231, and 317 just need to be applied. Thanks KP | Update verbiage in the guide to 'Required' - Added CC 450 to Summary of Changes Add example to the guide Need some clarification on this one. 428 was applied correctly, the redlines changes in the guide do not exactly match the redline changes in the change control, however, this is because of how the Track Changes Feature works. Content is correct. Also, CC 231 and 317 do not apply to the 814_10, only the 814_08. | Y
814_11 | Johnny Robertson | (2002-394) - Does not match the Change control in REDLINE | Update the summary of changes to reflect CC 2002-394 | Y
814_12 | Johnny Robertson | (2002-349) - Does not match the Change control in REDLINE (2002-354) - Does not match the Change control in REDLINE | Update the summary of changes to reflect CC 2002-349 Update the summary of changes to reflect CC 2002-354 | Y
814_13 | Johnny Robertson | Ready |  | Y
814_14 | Johnny Robertson | Correct Examples for (2002-261) | Example needs the REF~BLT added to reflect CC 2002-261 | Y
814_15 | Bernie Dawson | Ready |  | Y
814_16 | Bernie Dawson | (2002-257) - All Change controls are included, but there are some differences in the way CC 2002-257 was originally approved. | 2002-257 was approved, but put into the wrong N1 loop. CC 2002-430 was then written to correct CC257. The gray box in the 814_16 refects the example in CC 430. Because this was the latest CC approved, the gray box in the 814_16 will reference this example. Summary of changes will be updated to indicate that 430 was written to correct 257 | Y
814_17 | Bernie Dawson | (2002-382) - see graybox, whch should have used the word "witihn" instead of "with"; (2002-354) - DTM segment was removed from standard ANSI ASC structure section on page 6 in error. | Will update the guide to reflect these changes Will update the guide to reflect these changes | Y
814_18 | Bernie Dawson | Ready |  | Y
814_19 | Robert Rodriguez | Ready |  | Y
814_20 | Robert Rodriguez | (2002-258) Did not see that it had been implemented to the 814_20 transaction. (2002-325) Did not see that it had been implemented to the 814_20 transaction. | Reviewed the implementation guide and it appears that all CCs have been updated appropriately. No changes will be made. Reviewed the implementation guide and it appears that all CCs have been updated appropriately. No changes will be made. | Y
814_21 | Robert Rodriguez | Ready |  | Y
814_22 | Robert Rodriguez | Ready |  | Y
814_23 | Kathy Scott | (2002-267) - Remove code in the N103 that allows DUNS +4 for ERCOT.Add CC #2002-267 to Summary of Changes for this Change Control date 4/1/2002 | Will update summary of changes | Y
814_24 | Kathy Scott | (2002-267) - Remove code in the N103 that allows DUNS +4 for ERCOT.Add CC #2002-267 to Summary of Changes for this Change Control date 4/1/2002 (2002-326) - Correct the spelling of the word -" Investigate" shown in the Summary of Changes for this transaction (2002-353) - Need to align or line-up the bullets and information on the Summary of Changes so all will look uniformed as all previous changes noted in the Summary, please see this change control. If any questions call me on this one - 713-582-8654 (2002-354) - Correct the Note in the Summary of Changes for this Change Control - to Modified gray ox of the "N402" in the N1~BT currently shows "N4.02" | Will update summary of changes Will update summary of channges I believe the bullets relating to this CC were intended to be indented to reflect the CCs that were cleaned up with the the approval of CC 353. With this said, no updates will be made to the summary of changes. x12 elements can be written as either N402 or N4.02. Both examples describe the same thing. No updates are necessary | Y
814_25 | Kathy Scott | (2002-281) - This Change Control is listed twice in the Summary of Changes for this transaction. Not sure if it needed to be twice, if not , does it being listed this many times cause confusion. (2002-290) - This Change Control appears to documented/worded correctly on the 814_25 transaction according to this Change Control, however these changes are not red-lined on the v1.5 814_25 transaction. (2002-353) - This Change Control is listed twice in the Summary of Changes for this transaction. Not sure if it needed to be twice, if not , does it being listed this many times cause confusion. Need to align or line-up the bullets and information on the Summary of Changes so all will look uniformed as all previous changes noted in the Summary, please see this change control. If any questions call me on this one - 713-582-8654 (2002-417) - According to this change control Reject Reason ANK "Invalid Source Information" was added to the 814_25 transaction, however the v1.5 does not have this new code in the REF~7G | I believe the structure of this listing in the summary of changes was done as a part of CC 353's effort to clean up the Summary of Changes. With this said, no updates will be made. CC wasn't redlined in the summary of changes, but reflected correctly. No updates will be made I believe the structure of this listing in the summary of changes was done as a part of CC 353's effort to clean up the Summary of Changes. With this said, no updates will be made. Will update the guide to reflect this change | Y
814_26 | Kathy Scott | Ready |  | Y
814_27 | Bill Reily | Ready |  | Y
814_28 | Bill Reily | Ready |  | Y
814_29 | Bill Reily | Ready |  | Y
810_02 | Bill Reily | (2002-416) page 3 example does not match the current IG examples on page 23. | Will update the guide with ONLY the change which changes the DSC001 to DSC005 | N
810_03 | Tom Jackson | Ready |  | Y
820_02 | Tom Jackson | Page 6 of the Guide, a word is missing. (2002-296) Transaction notes pertain to a cross-reference number on the 810_02? These transaction notes do not appear on change control 2002-296 which added the How To Use This Document section to the Guide. | Will update the guide with these findings | N
820_03 | Tom Jackson | (2002-310) - Add the 820_03 Muni/Co-op Remittance Advice to the approved list of TX SET EDI transactions. | CC 310 was reviewed at the June 4th TX SET meeting, where the changes discussed were approved. These changes were never reflected in CC 310. The guide is correct as it exists, and an update to CC 310 will be made to reflect this information. Will add another sentence to CC 310 which says that at the SET meeting on 06/04/02, CC 310 was modified to reflect the agreement of the group | N
867_02 | Tom Jackson | (2002-333) Change control has not been applied to the implementation guide | Will update the gray box appropriately | N
867_03 | Dave Odle | Ready |  | Y
867_04 | Dave Odle | Ready |  | Y
824 | Dave Odle | Ready |  | Y