## SPRs with Impact to MP
# | Status | Problem | Description | Work Around | System
1 | Open | Does not work with Internet Explorer version 7.0 | Works with IE6 and JRE 1.5x | Make sure your client workstation has Internet Explorer 6.0 | MMS UI
2 | Open | Issues with Java version on MMS UI | Works with IE6 and JRE 1.5x | Make sure your client workstation has JRE1.5x | MMS UI
3 | Open | Internet Explorer stops working | When using the MPI, windows stops painting the display for all Internet Explorer windows. Workaround is to quit IE and restart IE. Looks like a memory leak type of problem. | Restart Internet Explorer on your client workstation. | MMS UI
4 | Open | Validating an OS submission of DSR resource | A QSE will be prevented from submitting an Output Schedule for the remainder of the current hour due to the "QSE must submit an OS/EOC for all remaining intervals of the Operating day" rule. For OS, this rule should only check the FUTURE five-minute intervals of the current hour. It currently checks ALL intervals of the current hour. Since OS for past intervals are never valid, the QSE is prevented from submitting for the rest of the hour and they should be able to for DSR resources. | None | MMS
5 | Open | Download of Reports to Desktop does not work | Pressing the 'Download to Desktop' button doesn't appear to do anything, except the IE status bar shows 'Error in page" message. | None | MMS UI
6 | Open | Two Hour Notification Messages | Two hour notification of missing EOC/OS is issued only for resources in "ON" status and not for other on-line statuses. | None | MMS
7 | Open | MMS Output Schedule must be full day | If an MP desires to have a combo of TPO and OS they should submit the TPO first for the hours they want then submit the OS for the remaining hours. Note that if the COP has some hours as off-line the MP will still need to submit an OS for the hours not covered by the TPO. MMS will be enahanced to accept OSs for periods that do not cover the full day and will generate a warning | See description | MMS
8 | Complete | Notification Service doesnt send Notification Message to configured listener. | Listener information is configured in Market_Participant table. Create BidSet is executed by populated 'Source' element with QSE Name. Notification service doesnt send notification message to configured listener. When the Create BidSet is executed by populating 'DUNS' number then Notification Service returns the notification message to the configured listener. | Configure the listener in the market_participant table. Populate DUNS number in RequestMessage->Header->Source element to receive notifications. | EIP
9 | Open | in a TPO a QSE can't submit a price over 9999.99 even if they have verified it to be their cost | in a TPO a QSE can't submit a price over 9999.99 even if they have verified it to be their cost | Submit prices lower than 9999.99 until resolved. | EIP
10 | Open | submitting multiple OS schedule gets translated incorrectly | if an MP submits an output schedule with more than 1 break point without submitting an <ending> element to indicate the end of each output schedule interval, the system defaults the ending as the beginning of the next start interval or the end of the whole schedule. This is incorrect because the ending of the previous schedule and the beginning of the next schedule overlaps and gets rejected by MMS | None | EIP
11 | Complete | <externalID> tag is giving an error when populating in an offer | <externalID> tag is giving an error when populating in an offer | Omit <externalID> from COP submissions | EIP
12 | Complete | Query OS Not Functioning | start hr and start interval is getting populated incorrectly in OS MMS queries. Consequently, it is not returning any data. | Use MMS UI until resolved. | EIP
13 | Complete | output schedule is inconsistant with other offers, and element fields | the MMS (ABB) XML use the fields start_hr_ending and end_hr_ending for the hour fields but to populate first interval of the day, the XML want the first interval to be hr 0 and interval 5; in hour ending, there is no such hour as 0 for hour ending. Also, COP, three part offer, and Inc/Dec, the first hour is hour_ending 1. | None | EIP
14 | New | allowable end time within the EIP webservices | the current implementation of endtime need to include the first second of the next hour please see external interface specs for details on implementation so start time <startTime>2007-08-10T00:00:00-05:00</startTime> end time should be <endTime>2007-08-10T00:59:59-05:00</endtime> | in order to work around this we minus a second from all the end times | EIP
15 | Complete | the mRID returned as a reply is inconsistant with the External Interface document | According to the Exteranl Interface Document, when a user submits an offer for an hour the reply mRID should be hour ending, if the user submits an offer for a day, the return mRID should not include the hour. Currently when submitting for the day it's returning 0, which is confusing; it should not return the hour field Also, the hours should be 1-24 not 0-23 | None
16 | New | Submitting muliple transaction types within a bidset is causing issue with data | when a user submits a BidSet with 24 <ThreePartOffer> the startup data elements and the minimum load cost is not showing up in the database for hours 1-23, it shows up for hour 24 the problem also occurs when submitting 24 <OutputSchedule>; the deleteTPOs seems to be getting ignored for hour 24, and if you try to submit an Output Schedule above a TPO it's getting rejected.

## Outstanding SPRs-22Aug2007
# | Test Cycle | Severity | Defect ID | Component | Problem | Description
1 | FAT | 2-Major | 93104 | SYS - Platform | Internet Explorer stops working | When using the MPI, windows stops painting the display for all Internet Explorer windows. Workaround is to quit IE and restart IE. Looks like a memory leak type of problem.
2 | FAT | 3-Medium | 93034 | MI RPRT - Reports | Download to Desktop does not work | Pressing the 'Download to Desktop' button doesn't appear to do anything, except the IE status bar shows 'Error in page" message.
3 | FAT | 3-Medium | 93034 | MI RPRT - Reports | Download to Desktop does not work | In MPI, Market Reports -> Fetch Reports List shows one report: MP_S_OUTSCHED_EndAdjPeriod_17 The report does not seem to be obviously selectable. Pressing the 'Download to Desktop' button doesn't appear to do anything, except the IE status bar shows 'Error on page'. No report is downloaded to the Desktop. Tester: Jeff/Guang The SPR was re-tested by Zhidong Song & Guang Li on 06/11/07. The reports are selectable and can be down loaded to the Desktop properly. See the video copy in the attachement.
4 | FAT | 3-Medium | 93244 | SYS - Platform | HDL/LDL message too complicated | 1. Message rejecting manual HDL < LDL is too complicated. It should read: "Manual HDL < Final LDL" see screen shot 2. When manual input is rejected, the operator should not have to press the "refresh" to see the previous valid values.
5 | FAT | 3-Medium | 93328 | MOI - MI Operator Interface | MOI does not work with Internet Explorer version 7.0 | Works with IE6 and JRE 1.5x
6 | FAT | 3-Medium | 93329 | SYS - Platform | RSH/SSH issue is preventing failover testing
7 | FAT | 3-Medium | 93330 | MOI - MI Operator Interface | Issues with Java version | Works with IE6 and JRE 1.5x
8 | FAT | 3-Medium | 94039 | SCED | Proxy Offer Cureve for WInd Resources | Please generate wind type proxy offer curve for only Resources with Resource type “Wind Generation” and not “RENEW”
9 | FAT | 3-Medium | 94115 | MOI - MI Operator Interface | “DSP Suggestion Plan” Display problem. | The subject change has not been implemented.
10 | FAT | 3-Medium | 94127 | MOI - MI Operator Interface | Tab “Trading Day” and “Operational” switch displays during clicking tabs | 7.3 Test Case 59 - Adhoc Report Manager - Operational. When click on the tab "Audit", the tab "Operational" turns into "Trading Day". When click on the tab "Trading Day" turn into "Operational". This is the duplication of SPR # 92018. (Z.Song, 07/26/07).
11 | FAT | 3-Medium | 94243 | MOI - MI Operator Interface | Adhoc Rpt Manager display does not work as designed. | There are two frames on this display. Test Case instructions do not call out which frame is being referred to. Issues found are as follows: 3b: Description column is not in the botton frame, but does appear in the
12 | FAT | 3-Medium | 94264 | MOI - MI Operator Interface | Personalization of Work Environment cannot be saved under the user tree | Users are able to save views to a user tree and personalize them, but if the user logs completely off the system, the view under the user tree is erased. System does not save views as designed.
13 | FAT | 4-Minor | 92955 | MI RULE - Validation Rules | Curve submission of more than ten points results in cryptic XML type error | The error message resulting from submitting a Three-Part Supply Offer of more than ten points results in an error relative to XML format ("<point> not allowed") which does not clearly convey the validation error.
14 | FAT | 4-Minor | 93032 | MI MPI - Market Participant Interface | Two Hour Notification Messages | The two hour notification of missing EOC/OS does not cover all Resources of the QSE.
15 | FAT | 4-Minor | 93103 | MOI - MI Operator Interface | Displayed data fields are not in the test case list | Displayed data fields are not in the test case list. Test case listed fields are not in the MOI display.
16 | FAT | 4-Minor | 93118 | MOI - MI Operator Interface | Document errors for MOI trees | Market > Monitoring > Market Status > "SCED" Market > Monitoring > Interface Control (purpose?) Missing "Energy Types" for Test Case 14-16
17 | FAT | 4-Minor | 93120 | MOI - MI Operator Interface | Must click on edge of Participant Name & Report Type to get drop down list | Must click on edge of Participant Name and Report Type to get the dropdown list to drop down. It's very hard to hit just the edge and not the body of the dropdown list. Tester: Guang Li
18 | FAT | 4-Minor | 93130 | DSI-SCED | Update test case documentation | Update documentation for: 3.2.18 Test Case 18 (pg 55) 3.2.19 Test Case 19 (pg 57-58) 3.2.20 Test Case 20 (pg 59) Test Case 22 (DSI_TC21) Test Case 25 (DSI_TC24)
19 | FAT | 4-Minor | 93185 | MOI - MI Operator Interface | Need link to reports in report manager display | Should be able to click on the individual report name or an icon next to it to display the selected report. This capability is needed in Adhoc Report Manager and Periodical Report Manager. Tester: Guang Li
20 | FAT | 4-Minor | 93576 | SYS - Platform | Abort Message in SCED workflow messages | Abort message is displayed only on system messages. Please display the message in SCED workflow messages.
21 | FAT | 4-Minor | 94005 | MOI - MI Operator Interface | User Guide does not open up in Help Menu | The User Guide under Help menu does not open up the User Guide. The Help Topics link under Help in Display Editor does not open the topics.
22 | FAT | 4-Minor | 94102 | DSP-SCED | Add “Resource Status” to DSP Base Point Summary (MI) display | Add “Resource Status” to DSP Base Point Summary (MI) display.
23 | FAT | 4-Minor | 94218 | MOI - MI Operator Interface | Tree Node misnamed | Test Case states tree node name should read "List of Report Types". Actually reads "Master Report Catalog"
24 | FAT | 4-Minor | 94239 | MOI - MI Operator Interface | Sorting Issues | Lower case letters do not sort with upper case letters. For example, "spp" comes after "This" "End of Hour" comes before "End Of Adjustment" This should be checked in all displays.
25 | FAT | 4-Minor | 94240 | MOI - MI Operator Interface | File Export | When exporting files from MOI, users can create a new folder, but cannot rename them. Also, when saving a file, the previous file name entered appears in teh File Name text box. The user is not warned that another
26 | FAT | 4-Minor | 94241 | MOI - MI Operator Interface | column header missspelled | The Location column is spelled incorrectly.
27 | FAT | 4-Minor | 94245 | MOI - MI Operator Interface | Old Resrouce Status show number (ex 1) instead of ON, OFF | Old Resrouce Status show number (ex 1) instead of ON, OFF This is the same problem as the closed SPR#092057.
28 | FAT | 4-Minor | 94246 | DSP-SCED | Add some column to display | Add Resource status to Base Point Summary display. Also add Resource status to Suggestion plan. This is the same problem as the closed SPR#092363.
29 | Integration Test | 3-Medium | 91714 | SYS - System | All workflow messages go to the ONLINE message display | All workflow messages go to the ONLINE message display, which is not correct.
30 | Integration Test | 3-Medium | 91749 | DSI-SCED | All scripts supporting the DSI test procedures were missing from the host. | All scripts supporting the DSI test procedures were missing from the host. All scripts were copied manually into the /bin directory on the application server so that the testing can continue. These can be included in the system build.
31 | Integration Test | 3-Medium | 91990 | MOI - MI Operator Interface | The MOI displays frequently require a refresh to bring the display in. | Frequently the MOI displays require a refresh after navigation to see the tables. This is the case between the operational and audit tabs. It was observed on the Resource Caps and Floors display in particular.
32 | Integration Test | 3-Medium | 94004 | MOI - MI Operator Interface | Resource names in the Drop-down list shows "...." | Report Specific Caps and Floors display: Shows incomplete list of Resource names in the Drop-down list. It shows "...." after few names.
33 | Integration Test | 4-Minor | 91755 | SYS - Platform | "MF Business Associate Delivery Point" display data entry problems. | "MF Business Associate Delivery Point" display has data entry problems. It generates error messages when Data is entred in a an Empty cell for both the QF column as well as when Yes/No is selected under AS dispatch columns.
34 | Integration Test | 4-Minor | 92018 | MOI - MI Operator Interface | Adhoc Report Manager -Audit | Several items are mismatched between Test Procedure and Display
35 | Integration Test | 4-Minor | 92058 | MOI - MI Operator Interface | Participant Messages Trading day | Need to click "Refresh Display" button to get the complete list in Participant Name Drop Down Menu
36 | Pre-FAT | 3-Medium | 92448 | SYS - Platform | Validation when both HDL and LDL values are manually entered : accept HDL>LDL | When Operator manually enters both HDL and LDL values system should verify and accept the data only if HDL>LDL
37 | Pre-FAT | 3-Medium | 92453 | DSP-SCED | Production cost calculation offset for -250 region below LSL | The production cost calculated should be offseted for the -$250 region of Energy Offer Curev extened by the system below LSL.
38 | Pre-FAT | 3-Medium | 92701 | MI RULE - Validation Rules | Validating an OS submission of DSR resource with an invalid combination of trading date and hour against system time failed | Validating an OS submission of DSR resource with an invalid combination of starting date and hour agianst the current system time failed.
39 | Pre-FAT | 3-Medium | 92967 | MI PRCS - Background Process | Add Code for "Default Mitigated Offer Cap Curve using FIP only" | Add code in MOCF application to support following function: "MMS calculates a set of default Mitigated Offer Cap curv
40 | Pre-FAT | 4-Minor | 92193 | MOI - MI Operator Interface | Non Business Days - Operational | Edit took time to complete and display after COMMIT.
41 | Pre-FAT | 4-Minor | 92363 | DSP-SCED | Add Resource status to Base Point Summary display | Add Resource status to Base Point Summary display. Also add Resource status to Suggestion plan.
42 | Pre-FAT | 4-Minor | 92761 | MI PRCS - Background Process | Mitigated Offer Floor Formulation | For Mitigated Offer Floor Formulation, the mapping between the Resource Category (as defined in Requirement specs) and Resource Types (from data provided by ERCOT) is missing for following Resource Categories: QF WIND The mapping defined so far are: Res
43 | Pre-FAT | 4-Minor | 92762 | MI PRCS - Background Process | Mitigated Offer Floor values should be User Enterable | The Mitigated Offer Floor values should be user enterable via an MI display.
44 | Pre-FAT | 4-Minor | 92763 | MI PRCS - Background Process | Need Operator Message for Invalid "Generator Verifiable Cost" data from Settlements | When an invalid Verifiable Cost Curve data is entered for a Resource, and Mitigated Offer Cap and Floor Application (MOCF) is run, the application should write a Warning in Operator Message log for the invalid Verifiable Cost Curve. e.g GEN1 Verifiable