## Sheet1
Responses to Questions and Comments for Version 1.02 of External Interface Specification
Submitter | Question | Response
Reliant | The protocols (section 4) show Energy Trades to be scheduled according to the settlement interval (15min). The interface spec for Energy Trades (p. 77) is currently shown as hourly. | Clarification added to version 1.03
Reliant | I would like to see the samples bundled with the API document and xsd/wsdl to which they are related, and additionally someway to know which version of this bundle is running on the sandbox and EDS. And the name space we need to use in the XML. | This will be done on future releases. We plan to post release information on a web page.
Reliant | Why was deleteos removed from tpo but deletetpo remains in the outputschedule | This was done to be consistent with the functionality provided by MMS.
PCI | There is no way to query notifications. If a notification is sent, but the market participant’s system fails to receive it or process the message, there should be a way to query for the missed messages. The capability to query notifications was listed in Sec. 5.1 of previous versions if the EIS document with the note, “currently it is proposed that this interface not be provided for reasons of performance, in order to avoid periodic polling.” However, participants should need to poll only when there is some failure, not routinely; so performance is less of an issue. | We would request that a change request be provided.
Luminant | The API Doc for a DC Tie trade looks like it requires a buying and selling QSE. I think it just looks like an injection (generator) or extraction (load) from the ERCOT grid, and it is deemed delivered (I think). But the counterpart is the DC Tie itself… at least in the current zonal market (I think). But there is probably not 2 QSEs unless the QSE counterparty is a “made-up” QSE for the DC Tie. I’m not sure how ABB’s MMS handles it. This is a detail that should probably be worked out if you get a chance. | MMS requires both a buyer and a seller. We designed the interface to be consistent with that.
Structure | Notices and Alerts: It seems are though more detail (structure, XML examples) is needed for the Notices and Alert types depiceted in Figure 113. When will the detail be available? | An example will be added to version 1.03
Structure | We still don't have a clear understanding of how intervals will get represented in the Hour tag of the Error message. What are valid values for the interval on an error. I'm interested in how hours, minutes and seconds will be represented. For the example below, if I submit the following Output Schedule which has invalid data for value1 beginning at 01:10, how does the resulting error message look? | Good question, as there are two ways we could do it, using a time or an interval. The error in your example occurs for during the time interval between 1:10 and 1:15. This corresponds to the 'hour ending interval' 0215. I believe in past discussions the interval format was requested. The error structure returned would use the following XML: <error><severity>error</severity> <area>EnergySchedule</area><interval>0215</interval><text>string provided by MMS</text></error>
Luminant | Need some of the sample XML files to include the ExternalID for Clarity. | Added to examples in version 1.03
Luminant | The Document “Market Management Systems (MMS) Requirement Specification for Day-Ahead Market (DAM) and Supplemental Ancillary Service Market (SASM) section 3.3.10 describes part of the payload for AS offers from same capacity of Resource for the energy offer curve. This is not a part of the API and probably shouldn’t be but wanted to check what the MMS system is expecting. | The interface is consistent with what MMS is expecting based on the latest release from MMS. Please advise if this is incorrect.
Luminant | The ASData values on AS Offers for REGDN need to be a one to many relationship. | Corrected in version 1.03
Luminant | Protocol 4.4.7.2 (4) and MMS validation document state a multi-hour block indicator flag should be available for non-controllable Load resources. | Added to version 1.03
Luminant | How is the Expiration Time treated by MMS on the A/S Trade and Energy Trade transactions? | expiration times are not used in latest interface provided by ABB. Corrected in version 1.03 to remove expirationTime for ASTrade.
Luminant | Please provide an XSD example for WS-Notifications. | An example will be added to version 1.03.
Luminant | REQUIREMENT: Must have fully formatted XML examples for every transaction, beginning with Bid Set acceptance and Bid Set errors? | Examples have been posted on the sharepoint. Full examples for a request, reply and a notification will be added to an appendix in version 1.03.
Luminant | Instead of examples which only display the payload, can you provide an example with the complete fully formatted XML? | Examples have been posted on the sharepoint. Full examples for a request, reply and a notification will be added to an appendix in version 1.03.
Luminant | Please provide the XML examples INCLUDUING all the wrappers, the headers, all layers of the transaction. | Examples have been posted on the sharepoint. Full examples for a request, reply and a notification will be added to an appendix in version 1.03.