## Slide 1: Texas Nodal Program Nodal Testing Overview
August 31, 2007
Chairman’s Briefing
Jeyant Tamby
Notes: <number>

## Slide 2: We have recently appointed a Testing Tsar to provide oversight of all Nodal testing activities
<number>
Texas Nodal Program Update
August 22, 2007
Responsibilities of the Testing Tsar:
  Ensure testing strategies and practices are well coordinated to deliver effective results for the Nodal program.
  Ensure that products, applications and systems are in compliance with Texas Nodal Protocols and ERCOT Standards.
  Ensure that entry and exit criteria are determined and met for each testing phase.
  Ensure that use cases, test cases, test scripts are developed for each project and that they meet the requirements of the Business and Market Participants.
  Coordinate the production and re-use of test data across projects to realize synergies.
  Introduce automation into the process where appropriate.
  Coordinate the prioritization of defects for resolution across test cycles.
  Produce reports to indicate teams’ performance, status of testing by project/environment, defects, continuous improvement metrics, etc.
This briefing expands on the status of, and plans for, each of these responsibilities
Notes: <number>

## Slide 3: Ensure testing strategies and practices are well coordinated to deliver effective results for the Nodal program (1/2)
<number>
Texas Nodal Program Update
August 22, 2007
Who | Enterprise Integration Project team (EIP)
What | iDev is special case of pre-FAT, used to demonstrate that the system fulfills contractual obligations and that it fulfills the requirements, including preliminary performance and security requirements. They should also demonstrate that the system conforms to the overall system architecture.
When | One or more code drops, as specified in the contracts to support the Nodal Transition Plan.
Where | Testing is done at ERCOT in the iDev (idevnodal) environment.
Who | Vendor or project team (for internal development only)
What | Testing is done to demonstrate that the system fulfills contractual obligations and that it fulfills the requirements. They should also demonstrate that the system conforms to the overall system architecture.
When | One or more code drops, as specified in the contracts to support the Nodal Transition Plan.
Where | Testing is done on at the developer’s site.
Pre-Functional Acceptance Test (Pre-FAT)
Integration Development Test (iDEV)
Who | EIP team and their delegates
What | iFAT is a special case of FAT for the EIP. Testing is done to demonstrate that the integration software fulfills contractual obligations and that it fulfills the requirements, including security requirements. They should also demonstrate that the system conforms to the overall system architecture. Testing is done with versions of the source and sync systems that have passed FAT.
When | One or more code drops, as specified in the contracts to support the Nodal Transition Plan and EIP iteration plan.
Where | Testing is done at ERCOT in the iFAT environment.
Who | “Product” project team (e.g. EMS, MMS) and their delegates
What | Testing is done to demonstrate that the system fulfills contractual obligations and that it fulfills the requirements, including preliminary performance and security requirements. They should also demonstrate that the system conforms to the overall system architecture.
When | One or more code drops, as specified in the contracts to support the Nodal Transition Plan and the project iteration plan.
Where | Testing is done on at ERCOT in the project’s FAT environment.
Functional Acceptance Test (FAT)
Integration Functional Acceptance Test (iFAT)
Pre-FAT
FAT
iDEV
iFAT
EDS
iTEST
Notes: <number>

## Slide 4: Ensure testing strategies and practices are well coordinated to deliver effective results for the Nodal program (2/2)
<number>
Texas Nodal Program Update
August 22, 2007
Who | Integration Test project team (INT)
What | Testing is done to demonstrate that the system fulfills end to end requirements, including performance and security requirements. They should also demonstrate that the system conforms to the overall system architecture.
When | One or more code drops, as specified in the contracts to support the Nodal Transition Plan.
Where | Testing is done at ERCOT in the iTest environment.
Integration Test (iTEST)
Who | Qualified market participants and ERCOT personnel
What | Testing is done to demonstrate availability of staged parts of the functionality of the system and compliance with the Nodal protocols.
When | Four deliveries to support the Nodal Transition Plan.
Where | Testing is done using software in the EDS environment.
Early Delivery System Test (EDS)
Pre-FAT
FAT
iDEV
iFAT
EDS
iTEST
Notes: <number>

## Slide 5: Ensure that products, applications and systems are in compliance with the current Texas Nodal Protocols and ERCOT Standards
<number>
Texas Nodal Program Update
August 22, 2007
Focus to date has been on requirements coverage of the Protocols.
Emphasis is shifting to the testing artifacts.
Measurements are lagging actuals
The traceability effort is a major program-level effort, well under-way, underpinned by integrated tools
Approved
Requirement
Documents
Approved
Use Cases
Approved
Test Cases
Approved
Test Scripts
Traced From
Traced From
Traced From
Traced From
Protocols
In Requisite Pro
In Quality Center
Test Results
Traced From
1,989 subsections
3,005 requirement statements
363 Total Use Cases
4,290 Total Test Cases
940 Total Test Scripts
488 Passed Test Results
Status of all Protocols:
Status of all Protocols (Nodal and Not Nodalized):
1,421 traced subsections
1,960 traced requirements
195 traced use cases
333 traced test cases
Notes: <number>

## Slide 6: Ensure that entry and exit criteria are determined and met for each testing phase
Entry and exit criteria for each EDS are drawn from the ERCOT Nodal Transition Plan owned by TPTF
EDS 1
  Release 1 – Alarm Processing
  Release 2 – Point-to-Point Checkout
EDS 2
  Release 3 – State Estimator & Network Security Analysis
  Release 4 – NMMS (Network Model Validation)
EDS 3
  Release 5 – Trial Operation of SCED, 6 month LMP posting
  Release 6 – Trial Operation of LFC, ACE
  Release 7 – Trial Operation of CRR, sample Settlement Statements
EDS 4
  Release 8 – Trial Operation of RT Settlements (No Extracts)
  Release 9 – Trial Operation of DAM, RUC, SASM, Full Settlements, EDW Extracts
TXMACS 1.0 – Full Nodal Functionality & 168 hour testing
Each release is incremental to the last and thereby brings the system closer to full capability
Measurability needs to be enhanced
Need to develop Entry and Exit Criteria for each Test Phase, recognizing the ultimate goals of the Transition Plan and reconciling the demands of the schedule
Notes: <number>

## Slide 7: Ensure that use cases, test cases, test scripts are developed for each project and that they meet the requirements of the Business and Market Participants
Each project identifies key work products and their expected status through each RUP phase
Project and program review requirements are defined for each phase gate
Need to develop Mapping to Program Level Milestones
Notes: <number>

## Slide 8: Coordinate the production and re-use of test data across projects to realize synergies
<number>
Texas Nodal Program Update
August 22, 2007
The various sources…
… must be optimized…
… to fit the various needs
Manually created data
Zonal production systems
Mini Market application
Stub-in to application
-xml
-csv
-SQL insert
-temporary queue
-etc.
Application A
Application A
Application A
Application B
Temporary
data stores
Data Files
Need to review and optimize from program perspective
Notes: <number>

## Slide 9: Introduce automation into the process where appropriate
<number>
Texas Nodal Program Update
August 22, 2007
Each test phase has different emphases of testing type - and automation potential
Test type | Description | Applicable test phases | Automation potential
Smoke testing | Smoke testing is intended to reveal simple failures in both functionality and connectivity that are severe enough to reject a prospective software release. | All | 20%
Usability testing | Usability testing is designed to measure how well people can use the user interface for its intended purpose. Usability testing involves measuring how well test subjects respond in four areas: time, accuracy, recall and emotional response. | DEV, FAT, eEDS, EDS | 0%
Input value testing | Input Value testing is designed to test boundary conditions and invalid input values for a given domain. | FAT | 90%
Functional testing | Functional testing verifies that the system behaves correctly from the user / business perspective and functions according to the requirements, models, specifications, or any other artifact used to document the application. | Pre-FAT, FAT, iDev, iFAT, eEDS, EDS | 50%
Integration testing | Integration testing identifies problems that occur when systems are combined. | iDev, iFAT, iTest | 60%
Security testing | Security testing will be conducted to evaluate the compliance of a system or component with specified security requirements. Security testing will also compare the system against regulatory standards and best practices. | iTest | 100%
Regression testing | Regression testing is initiated any time an implementation of a system changes. | All | 70%
Performance testing | The goal of performance testing is to eliminate bottlenecks and establish a baseline for future regression testing. | iTest | 100%
Load testing | Load testing is the process of exercising the system by supplying the largest load that it can accommodate and still function properly. The goal of Load testing is not to break the system, but to keep the system constantly running at maximum load as defined in business requirements. | iTest | 100%
Stress testing | Stress testing is the process of loading a system until its resources are overwhelmed or by taking resources away until the system fails. The main purpose is to make sure that the system fails and recovers gracefully, which will be testing the systems recoverability. | iTest | 100%
WORK IN PROGRESS
Notes: <number>

## Slide 10: Coordinate the prioritization of defects for resolution across test cycles
<number>
Texas Nodal Program Update
August 22, 2007
Defect Tracking Status Lifecycle
Once Defects are assigned they are tracked using the status lifecycle.
Process and Roles/Responsibilities under review and negotiation
WORK IN PROGRESS
Notes: <number>

## Slide 11: Produce reports to indicate teams’ performance, status of testing by project/environment, defects, continuous improvement metrics, etc
<number>
Texas Nodal Program Update
August 22, 2007
Quality Center Dashboard
Overall dashboard required
Need to develop additional metrics that clearly lead to mitigating actions
Notes: <number>