## Slide 1: Texas Nodal Program Update
Jerry Sullivan

## Slide 2: Agenda
Item | Who | Purpose
Nodal Program Status | Jerry Sullivan | For Information
Nodal Schedule Update | Jerry Sullivan | For Information
Nodal Training Update | Jerry Sullivan | For Information
Network Telemetry and State Estimator Standards | Trip Doggett | To request TAC review

## Slide 3: Overall program status remains amber
Cost
Schedule
Scope / Quality
Legend
Summary
Green
Savings being identified to mitigate additional cost in Release Management and additional MMS design costs needs being assessed.
Baseline 1 and 2 costs are being rolled into forecast.
Potential increased costs for internal allocations.
Amber
Amber
Currently fully aligned with protocols.
Impact Analysis in progress for 30 items (2 draft NPRRs and 16 minor changes with no impact).
Red
Amber
Green
Estimate at Complete = <$263m
Estimate at Complete = < $263m + 10%
Estimate at Complete = >$263m + 10%
Go-live = 12/1/08
Go-live = <30 days+
Go-live = >30 days+
Program is aligned with current protocols
Program is aligned to previous protocol version
Program is not aligned to protocols
Current EDS 1-3 milestones being achieved / on track.
Significant amount of work taking place in next 3 months.
EDS 4 milestones at risk due to MMS schedule.
Plan to track NMMS integration with EMS/MMS.
Scope/
Quality
Schedule
Cost
Nodal
Delivery
Nodal Delivery
Amber
Current product quality is not sufficient for Nodal launch
Most Nodal products currently achieve quality standards
All Nodal products currently achieve quality standards
Significant design issues still open with MMS solution.
Design reviews ongoing with ERCOT/MMS staff

## Slide 4: Tactical deliverables and actions
Topic | Solution/Action
MMS | Vendor high-level schedule puts the Nodal Program schedule at risk. Critical design issues need to be resolved rapidly by ERCOT/vendor – 60% “high” category items resolved by 8/24 Commercial implications to follow – target to resolve 9/7 MMS UI development in-house Closer inter-working of ERCOT design, integration and testing teams at ABB starting Sept. 2007
Staffing | Priority staffing needs identified and initiated in consultation with Resource Managers to address gaps in EDS, MMS, and EMS
Sandbox (8/31) Priority 2 Web Services | Confidence in achieving the milestone is High Integration Testing of 6 critical SCED interfaces 84% complete as at 8/24. Will make date with few minor defects. The rest of the priority 2 web services interfaces will be incrementally delivered in Sept 2007.
EDS 2 (9/4) State Estimator and Telemetry | Confidence in achieving the milestone is High EMS Release 2 – State Estimator and Telemetry FAT test execution 40% complete, 0 severity 1 defects, as at 8/24 Currently investigating calculated points for SE Interim solution for delivery of SE Reports – looking at MIS solution
EDS 1 (10/1) Complete | Confidence in achieving the milestone is High All QSEs will be completed and tested by 10/1, except for Austin Energy (currently upgrading their EMS) Fail-over test to occur in September
EDS 3 (11/1) EMS interfacing with SCED | Confidence in achieving the milestone is Medium EMS delivery of interfaces, confidence is High MMS delivery of interfaces, confidence is Medium Delivery of SCED reports, confidence is being assessed– cross-project effort launched to expedite delivery Effort launched to develop interim solution for data consistency between EMS and MMS (prior to final solution through NMMS)
EDS2 R4 (11/1) NMMS NOMCR | Confidence in achieving the milestone is Medium, with known challenges (data reconciliation and validation, AREVA load capabilities, MP availability) NMMS 1b delivery from Siemens failed FAT initially, retest successful (8/23), Phase 1c delivery at end of Sept 2007 Plan to start testing activities with CNP in November (confirmed)
8/24 eEDS MILESTONE ACHIEVED
Austin Energy, Reliant, CPS San Antonio completed testing by 8/29 with 100% Success Rate

## Slide 5: Initiatives to achieve / adhere to schedule
MMS project
  On site teams for integration and development
  On site manager to ensure effectiveness of work force (ERCOT and vendor)
  Helping on User Interfaces
  Taking on more test procedure efforts
  Assisting in updating pertinent documents
Testing Tsar
  Appointing a testing tsar to coordinate / oversee / report and motivate actions concerning migration.
    Synergies in development projects, testing, integration, release management, and various early delivery systems (EDS)
Release Management
  Increasing effort in this area.

## Slide 6: Nodal Training Update
  Market Participant Training and the Nodal Transition
  Project Requirements
  Development Process
  Delivery Process
  Progress Report

## Slide 7: Market Participant Training and the Nodal Transition
Market Participant Training is an integral part of the transition to the Nodal Market
The Texas Nodal Transition Plan
  Transition Planning Principles
  “Market Participant training is very important, and ERCOT shall establish early and comprehensive training programs for Market Participants that will be completed in a timely manner”
Market Training
ERCOT Nodal Market Transition

## Slide 8: Market Participant Training and the Nodal Transition
The Texas Nodal Transition Plan
  Transition Plan Tracks

## Slide 9: Market Participant Training and the Nodal Transition
The Texas Nodal Transition Plan
  Market Training Track
  ERCOT:
    Develop a training program for MPs and ERCOT
    Timed in conjunction with System Testing and Market Implementation
    Follow a standard format for training development
  Market Participants:
    Must require their personnel to attend training when appropriate
Notes: <number>
<footer>
<header>
<date/time>
Track Three—the Market Training track—is the basis for the creation of this and other courses. It dictates that ERCOT must develop a training program for Market Participants and that ERCOT can require Market Participants to attend training.
For more details about training, including courses and projected course dates, please go to the Nodal Training website.

## Slide 10: Market Participant Training and the Nodal Transition
The Texas Nodal Transition Plan
  Nodal Market Training Courses

## Slide 11: Training Project Requirements
A curriculum of Nodal Market concept courses developed by TPTF
Delivery format
Test
NERC Certification
Duration
Frequency
Course Description
Target Audience
Timing

## Slide 12: Training Development Process
Standard development process
Training development team
  Subject Matter Experts
  Learning Specialists
Stakeholder engagement
  TPTF Training Subgroup
  ERCOT Business Areas
  Nodal Project Staff
Qualify Assurance / Continuous Improvement
  Issue logging and tracking
  Surveys

## Slide 13: Training Delivery Process
Trainers
  Training development team delivers beta course
  Train The Trainer
Locations
  Austin, Dallas, Houston
  Future plans for out of state locations
  ERCOT and Market Participant Facilities
Delivery Method
  Instructor Led
  Web Based
Learning Management System
  Registration
  Tracking and Reporting

## Slide 14: Training Delivery Progress Report – Completed Courses
Course | Length | Instructor Led | Web Based Training
ERCOT Nodal 101: The Basics | 1 - Day | X | X
Economics of LMP | 1 - Day | X | 
Transition To Nodal Markets | N/A |  | X
Load Serving Entity 201 | 2 - Days | X | X* *Available 9/14/07
Notes: <number>
<footer>
<header>
<date/time>
<number>

## Slide 15: Training Delivery Progress Report – In development
Course | Length | Initiated | Training Sub-Group Review | Beta Course | Class Room Training |  | Web-Based Training | 
 |  |  |  |  | Due Date | Status | Due Date | Status
Basic Training Program | 5 - Days |  |  | Sept – 07 | Oct – 07 | 90% | Dec – 07 | 30%
NOIE QSE Operations | 1 - Day |  |  | Oct– 07 | Oct – 07 | 30% | Dec – 07 | 0%
Network Model Management | 2 - Days |  |  | Oct – 07 | Nov – 07 | 40% | Dec – 07 | 0%
Congestion Revenue Rights | 2 - Days |  |  | Oct – 07 | Oct – 07 | 30% | Dec – 07 | 0%
Market Settlement 301 | 2 - days |  |  | Oct – 07 | Nov – 07 | 30% | Jan – 08 | 0%
Generation 101 | 1 - Day |  | Aug – 07 | Oct – 07 | Nov – 07 | 30% | Dec – 07 | 0%
Generation 201 | 1 - Day |  | Nov – 07 | Jan – 08 | Feb – 08 | 20% | Mar – 08 | 0%
Generation 301 | 1 - Day |  | Jan – 08 | Feb - 08 | Mar – 08 | 10% | Apr – 08 | 0%
Market Information System | 2 - Days |  | TBD | N/A | N/A | 10% | Mar – 08 | 10%
Notes: <number>
<footer>
<header>
<date/time>
<number>

## Slide 16: Training Delivery Progress Report – To be developed
Course | Length | Delivery Date
Transmission 101 | 2 ½ – Days | Feb-08
ERCOT 101 for Wind Generation | 1 - Day | Mar-08
Course | Length | Delivery Date
Extended Training - System Dynamics | 1 - Day | Once a month within the first 12 months of full Texas Nodal Market Operations
Scenario-Based Training for QSEs with Generation Resources | 1 - Day | Once a Quarter 2009 only
Scenario-Based Training for Load Serving Entities | 1 - Day | Once a Quarter 2009 only
Scenario-Based Training for TSPs and DSPs | 1 - Day | Once a Quarter 2009 only
Deliver in 2008
Deliver after go-live

## Slide 17: Training Delivery Progress Report - Statistics
Course | No. of Instructor Led sessions | Passed |  | 
 |  | MP | ERCOT | Total
ERCOT Nodal 101: The Basics | 46 | 1616/1756 | 482/531 | 2098/2287
Economics of LMP | 16 | 430 | 175 | 605*
Transitions to Nodal Markets | N/A | 80/158 | 67/105 | 147/263**
LSE 201 | 3 | 121/127 | 3/3 | 124/130
* ILT - No exam
** WBT – No exam – Completed reviewing 75% or more of the slides

## Slide 18: Training Delivery Progress Report – Nodal 101 Surveys
4 – Strongly Agree
3 - Agree
2 - Disagree
1 - Strongly Disagree

## Slide 19: Network Telemetry and State Estimator Standards
The Nodal Program and ERCOT staff request that TAC consider the proposed changes included in the attached Network Telemetry Standard and State Estimator Standard
Notes: <number>
<footer>
<header>
<date/time>
<number>