## Slide 1: Texas Nodal Market Implementation MMS FAT Testing for Accelerated SCED
Mark Patterson, Manager Market Operations Support

## Slide 2: Purpose
Communicate the recent testing efforts on the MMS team
  Coverage Approach
  Process
  Scenarios
Correlate the FAT testing effort to market requests for EDS 3 SCED testing Phase 2
Propose mechanism to increase transparency

## Slide 3: Chronology of Testing
Quality
Time
Environment Location; Vendor
Primary Executor: Vendor
Observer: N/A
Script: Proposed Set
Environment Location; Vendor
Primary Executor: Vendor
Observer: ERCOT
Script: Agreed Set+ Ad Hoc
Environment Location; ERCOT
Primary Executor: ERCOT
Observer: Vendor
Script: Agreed Set + Ad Hoc
System Test
Pre-FAT
FAT

## Slide 4: Test Scenario Creation
Derived from protocols/requirement
  Specific to the scope of this release
Developed scenarios and scripts
Line by Line assessment of Test cases vs. Protocols/Reqs
Requirement traceability/mapping review by Test Coordinator
During Pre-FAT and FAT, additional ad-hoc scenarios created

## Slide 5: Test Case Categories
Module | Number of Cases
Market Participant Interface | 11
SCED Validation Rules (160+ rules) | 17
SCED Application Processes | 81
Market Operator Interface | 64
Background Processes (Open and Close of Market, Notifications, Consistency checks and SPP Calculations) | 8
End-to-End Processes | 10
MMS Fail-over | 6
Total | *197
Note* : Does not include ad-hoc test scenarios
Summary of Test Cases provided in Appendix

## Slide 6: MMS Testing Process
Each test done by a Tester and a Witness
  Execute pre-defined test case
  Identify alternate scenarios to exercise potential failure modes
  Suggest additional ad hoc tests
  Execute additional ad hoc tests
Results Recorded
  Notes in the Binders
  Defects entered in a tracking system (including problem conditions, symptoms, expected correct results as needed)
  Scanned images of the binders

## Slide 7: EDS Scenario to FAT Scenario Mapping
EDS Scenario | SCED FAT Scenario
Economic Scheduling - Base case | 3.3.4- Resource are dispatched economically
Overlapping Offer Curves | 3.3.10- Ties among marginal resources broken by prorating.
Resource telemetry value above HSL or below LSL | 3.3.3 SCED dispatches a resource between LDL and HDL. (RLC determines HDL and LDL based on telemetry)
Output Schedule | 3.2.27 SCED creates a valid proxy EOC for resources with Output Schedule
Combined Cycle | 3.3.8 SCED uses the telemetered configuration of a CC resource to dispatch it as a single resource subject to the aggregated parameters of the components.

## Slide 8: EDS Scenario to FAT Scenario Mapping (cont)
EDS Scenario | FAT Scenario
Capped and Bounded Offer Curves Non-competitive Constraint | 3.3.11/3.3.12/3.3.13 SCED Step 1 calculates the Reference LMPs using the EOCs while observing only the Competitive Constraints. Verify that between 1st and 2nd SCED steps, SCED creates the capped and bounded EOCs. SCED Step 2 calculates Base Points, Shadow Prices and LMPs using capped and bounded EOCs while observing Competitive and Non-Competitive security constraints.
Proxy Curve –Extension to LSL and/or HSL | 3.2.26/3.2.29 SCED creates proxy offer curves using the following configurable parameters: System-wide Offer Floor, System-wide Offer Floor plus $0.01 for Output Schedule, System-wide Offer Cap minus $0.01 for Output Schedule MW plus an epsilon MW, and System-wide Offer Cap for HSL

## Slide 9: EDS Scenario to FAT Scenario Mapping (cont)
EDS Scenario | FAT Scenario
Proxy Curve with output schedule | 3.2.28 SCED creates a valid proxy EOC for resources with OS and Inc/Dec offer.

## Slide 10: Economic Scheduling – Base case
Verify that a resource is dispatched economically based on EOC

## Slide 11: Overlapping Offer Curves (Tie-Breaking)
Verify that the SCED optimization breaks a tie among marginal resources by prorating the dispatch schedules among them.
  Pro-ration is based on the size of the MW block with equal price offers.
  Only the part of price curves within resources’ available region is used.
  For multiple segment EOCs, only the marginal segments are used.

## Slide 12: Capped and Bounded Offer Curves

## Slide 13: Proxy Curve- Extension to LSL and/or HSL

## Slide 14: Test Results/SPRs
Test cycle | # of test cases | % Pass | Software Problem Reports (SPRs) |  |  | 
 |  |  | Reported | Major | Medium | Minor
SCED Integ. Test by ABB | 180 | 55% | 86 | 6 | 43 | 37
Pre-FAT | *240 | 75% | 69 | 1 | 42 | 26
FAT | *240 | 86% | 72 | 2 | 41 | 29
Totals | ---- | ---- | 227 | 9 | 128 | 90
Note*: Ad-hoc test scenarios and additional elaborate sub-test included

## Slide 15: SPR Status (as of 8/24/2007)
Test cycle | Reported | Closed | Ready for Retest | In progress
Integration Test | 86 | 79 | 3 | 4
Pre-FAT | 69 | 60 | 1 | 8
FAT | 72 | 44 | 2 | 26
All 3 Cycles | 227 | 183 | 6 | 38

## Slide 16: SPR Criticality (as of 8/14/2007)
Criticality | Major | Medium | Minor | Total
Documentation |  |  | 6 | 6
Modifications (Displays/messages) |  | 8 | 16 | 24
Client Config (works IE6.0, JRE1.5x) |  | 2 |  | 2
Must Fix |  | 10 | 1 | 11
Memory Leaks /Crashes (work around exists) | 1 |  |  | 1
Total | 1 | 20 | 23 | 44

## Slide 17: What’s Next
Review the Appendix
Submit Requests for additional scenarios to be executed
  ERCOT MMS team to execute the scenarios in the FAT environment
Invite MPS to observe future MMS FAT execution

## Slide 18
Appendix

## Slide 19: SCED Market Participant Interface (MPI)
Test Case 1 – Submit COP
Test Case 2 – Submit Incremental/Decremental Offer Curve
Test Case 3 – Submit Three-Part Energy Offer
Test Case 4 – Web Service – Trading Data
Test Case 5 – Web Service – MI Reports
Test Case 6 – Messaging
Test Case 7 – Submit Output Schedule in Adjustment Period/Real-Time
Test Case 8 – Submit Energy Offer in Adjustment Period
Test Case 9 – Submit File Exchange Request
Test Case 10 – Query/Retrieve a Market Report
Test Case 11 – Submit for Invalid Date older than Seven Days

## Slide 20: MI SCED Validation Rules
Test Case 1 – COP Data Submission Template Validation
Test Case 2 – COP Data Query Template Validation
Test Case 3 – Incremental/Decremental Offer Data Submission Template Validation
Test Case 4 – Incremental/Decremental Offer Data Query Template Validation
Test Case 5 – Incremental/Decremental Offer Data Cancel Template Validation
Test Case 6 –Three-part Supply Offer Data Submission Template Validation
Test Case 7 – Three-part Supply Offer Data Query Template Validation
Test Case 8 – Three-part Supply Offer Data Cancel Template Validation
Test Case 9 – Output Schedule Data Submission Template Validation
Test Case 10 – Output Schedule Data Query Template Validation
Test Case 11 – Output Schedule Data Cancel Template Validation
Test Case 12 – Energy Offer Data Submission Template Validation
Test Case 13 – Energy Offer Data Query Template Validation
Test Case 14 – Energy Offer Data Data Cancel Template Validation
Test Case 15 – Partial Day Submission
Test Case 16 – Multiple Submissions in one XML file
Test Case 17 – Cancellation of COP

## Slide 21: MMS SCED Application Processes: Work flow Control
Test Case 1 – WKF_TC1 Automatic Trigger SCED Execution
Test Case 2 – WKF _TC2 Manually Trigger SCED Execution
Test Case 3 – WKF _TC3 External Systems Trigger SCED Execution
Test Case 4 – WKF _TC4 Non-manual Trigger SCED Execution
Test Case 5 – WKF _TC5 Manually Trigger When SCED is Running
Test Case 6 – WKF _TC6 Execution Speed

## Slide 22: MMS SCED Application Processes: DSI Test Procedure
Test Case 1 – DSI _TC1 Retrieve Registration Data
Test Case 2 – DSI _TC2 Retrieve Resource Parameters
Test Case 3 – DSI _TC3 Retrieve CC Unit Data
Test Case 4 – DSI _TC4 Retrieve Split Resource Data
Test Case 5 – DSI _TC5 Retrieve COP Information
Test Case 6 – DSI _TC6 Retrieve EOC Data
Test Case 7 – DSI _TC7 Retrieve Output Schedule Data
Test Case 8 – DSI _TC8 Retrieve Mitigated Offer Cap
Test Case 9 – DSI _TC9 Retrieve Mitigated Offer Floor
Test Case 10 – DSI_TC10 Retrieve Telemetry Information
Test Case 11 – DSI_TC10-1 Retrieve Telemetry Information at the End of Adj. Period
Test Case 12 – DSI_TC11 Retrieve RLC Data
Test Case 13 – DSI_TC12 Retrieve DSR Data
Test Case 14 – DSI_TC13 Retrieve Gen Subsystem Data
Test Case 15 – DSI_TC14 Retrieve SE Data
Test Case 16 – DSI_TC15 Retrieve TCM Data
Test Case 17 – DSI_TC16 Retrieve CCT Data
Test Case 18 – DSI_TC17 DSR Identification
Test Case 19 – DSI_TC18 DSR Telemetry Output Schedule
Test Case 20 – DSI_TC19 Output Schedule Validation

## Slide 23: MMS SCED Application Processes : DSI Test Procedure (Cont’)
Test Case 21 – DSI_TC20 DSR Load Telemetry Loss
Test Case 22 – DSI_TC21 DSR Dispatched Outside Output Schedule
Test Case 23 – DSI _TC22 DSR Output Schedule Filling
Test Case 24 – DSI_TC23 Non-DSR Output Schedule Filling
Test Case 25 – DSI _TC24 Output Schedule Adjustment
Test Case 26 – DSI _TC25-0 Proxy Offer Curve Parameters
Test Case 27 – DSI _TC25 Proxy Offer Curve for Resources with Output Schedule
Test Case 28 – DSI _TC26 Proxy Offer Curve for DSR with INC/DEC
Test Case 29 – DSI _TC27 Proxy Offer Curve for Resources without Full Range EOC
Test Case 30 – DSI _TC28 Proxy Offer Curve for Wind Power Resources
Test Case 31 – DSI_TC29 Constraint Flow Calibration
Test Case 32 – DSI_TC30 Constraint Limit Linearization
Test Case 33 – DSI_TC31 Manually Offset Demand
Test Case 34 – DSI_TC32 Manually Set Resources to Output Schedule
Test Case 35 – DSI_TC33 ONTEST Resources
Test Case 36 – DSI_TC34 ONRR Resources
Test Case 37 – DSI_TC35 Operator Manual Override HDL and LDL
Test Case 38 – DSI_TC36 Telemetry Resource Status
Test Case 39 – DSI_TC37 DC-Tie
Test Case 40 – DSI_TC38 Manually Set CCT Flags
Test Case 41 – DSI_TC39 Re-run the Same Input Data Set

## Slide 24: MMS SCED Application Processes : SCED Calculation Module Test Procedure 107
Test Case 1 – SCED_TC1 SCED Demand
Test Case 2 – SCED_TC2 Resource Status
Test Case 3 – SCED_TC3 Operating Limit
Test Case 4 – SCED_TC4 Energy Offer Curve
Test Case 5 – SCED_TC5 Transmission Constraints
Test Case 6 – SCED_TC6 Maximum Shadow Price
Test Case 7 – SCED_TC7 Report Constraint Violations
Test Case 8 – SCED_TC8 CC Unit Dispatch Aggregation/Disaggregation
Test Case 9 – SCED_TC9 Constraint Violation Hierarchy
Test Case 10 – SCED_TC10 Tie Breaking
Test Case 11 – SCED_TC11 SCED Step1: with Competitive Constraints
Test Case 12 – SCED_TC12 Capped and Bounded Energy Offer Curve Process
Test Case 13 – SCED_TC13 SCED Step2: Competitive and Non-competitive Constraints
Test Case 14 – SCED_TC14 LMP Calculation with Constraint Violations
Test Case 15 – SCED_TC15 Movement Limit by Ramp Rate
Test Case 16 – SCED_TC16 Movement Limit by Providing Ancillary Services

## Slide 25: MMS SCED Application Processes : DSP Test Procedure
Test Case 1 – DSP_TC1 Base Point Adjustment with Pseudo Resource Deployment
Test Case 2 – DSP_TC2 Data Publish to EMS
Test Case 3 – DSP_TC2-0 Data Publish to MI
Test Case 4 – DSP_TC2-1 Emergency Electric Curtailment Plan
Test Case 5 – DSP _TC3 Resource Parameter Violation
Test Case 6 – DSP _TC4 Dispatch Outside Output Schedule
Test Case 7 – DSP_TC5 Enable/Disable Data Publish to EMS
Test Case 8 – DSP _TC6 CC Unit Base Point Disaggregation
Test Case 9 – DSP_TC7 Suggestion Plan
Test Case 10 – DSP_TC8 Base Point Summary
Test Case 11 – DSP_TC9 Timestamp of Dispatching Outside Output Schedule

## Slide 26: MMS SCED Application Processes : Save Case and Study Environment Test Procedure
Test Case 1 – SAVE_TC1 SCED Data Archive
Test Case 2 – SAVE_TC2 Study Mode
Test Case 3 – SAVE_TC3 Data Retrieve in Study Mode
Test Case 4 – SAVE_TC4 Data Modification in Study Mode
Test Case 5 – SAVE_TC5 Export MOI Data to Excel

## Slide 27: MMS SCED Application Processes : SCED Background Process Test Procedure
Test Case 1 – BACK_TC1 Bus MW Injection
Test Case 2 – BACK_TC2 Bus Shift Factors

## Slide 28: Market Operator Interface: User interface features
Test Case 1 – Navigation Tree Structure
Test Case 2– Navigation Menu Structure
Test Case 3 – Standard Function Search and Filter
Test Case 4 – Standard Function Sorting
Test Case 5 – Standard Function Save and Print
Test Case 6 – Standard Function SQL Query
Test Case 7 – Standard Function Exit

## Slide 29: Market Operator Interface: Physical Market
Test Case 8 – COP – Trading Day
Test Case 9 – COP – Operational
Test Case 10 –COP – Audit
Test Case 11 – Three-Part Supply Energy offers – Trading Day
Test Case 12 – THREE-PART SUPPLY ENERGY OFFERS – Operational
Test Case 13 – THREE-PART SUPPLY ENERGY OFFERS – Audit
Test Case 14 – Incremental/Decremental Offer Curve – Trading Day
Test Case 15 – Incremental/Decremental Offer Curve – Operational
Test Case 16 – Incremental/Decremental Offer Curve – Audit
Test Case 17 – Output Schedule– Trading Day
Test Case 18 – Output Schedule– Operational
Test Case 19 – Output Schedule – Audit
Test Case 20 – Real Time SPP– Trading Day
Test Case 21 – Real Time SPP– Operational
Test Case 22 – Real Time SPP – Audit
Test Case 23 – Global Parameters – Operational
Test Case 24 – Global Parameters – Audit
Test Case 25 – Non Business Days – Operational
Test Case 26 – Non Business Days – Audit

## Slide 30: Market Operator Interface: Data Submissions
Test Case 27–MI_TC47: RMR Offers– Trading Day
Test Case 28– MI_TC47: RMR Offers– Operational
Test Case 29 – MI_TC47: RMR Offers– Audit
Test Case 30 – MI_TC53: COP Monitor
Test Case 31 – MI_TC69: Consistency Check: COP vs. Telemetered Resource Status
Test Case 32 – MI_TC73: Resource Specific Caps and Floors – Operational
Test Case 33 – MI_TC: Resource Specific Caps and Floors – Audit

## Slide 31: Market Operator Interface: Monitoring
Test Case 34 – SCED Market Status – Trading Day
Test Case 35 – SCED Market Status – Operational
Test Case 36 – SCED Market Status – Audit
Test Case 37 – Events – Trading Day
Test Case 38 – Events – Operational
Test Case 39 – Events – Audit
Test Case 40 – Event Templates – Operational
Test Case 41 – Event Templates – Audit
Test Case 42 – Interface Control – Trading Day
Test Case 43 – Interface Control – Operational
Test Case 44 – Interface Control – Audit
Test Case 45 – Application Messages – Trading Day
Test Case 46 – Application Messages – Operational
Test Case 47 – Application Messages – Audit
Test Case 48 – Invalid Participant Submission – Trading Day
Test Case 49 – Invalid Participant Submission – Operational
Test Case 50 – Invalid Participant Submission – Audit
Test Case 51 – Participant Activity – Trading Day
Test Case 52 – Participant Activity – Operational
Test Case 53 – Participant Activity – Audit
Test Case 54 – Participant Messages – Trading Day
Test Case 55– Participant Messages – Operational
Test Case 56 – Participant Messages – Audit

## Slide 32: Market Operator Interface: Tools
Test Case 57 – Master Report Catalog – Operational
Test Case 58 – Master Report Catalog – Audit
Test Case 59 – Adhoc Report Manager – Operational
Test Case 60 – Adhoc Report Manager – Audit
Test Case 61 – Periodical Report Manager – Trading Day
Test Case 62 – Periodical Report Manager – Operational
Test Case 63 – Periodical Report Manager – Audit
Test case 64 – Personalizing Work Environment

## Slide 33: MMS MI Background Processes Test Procedure
Test Case 1: Master File
Test Case 2: Open and Close of Market
Test Case 3: Consistency Check
Test Case 4: Two-Hour-Ahead Notification for Missing OS/EOC and OS Validation
Test Case 5: End of Adjustment Period Validations for Output Schedules
Test Case 6: SPP Calculation
  Resource Node SPP Calculation
  Load Zone SPP Calculation
  Time-weighted Trading Hub SPP Calculation
  Hub Average 345kV Trading Hub SPP Calculation
  Bus Average 345kV Trading Hub SPP Calculation
  Correct Retrieval of Load Zone and Hub data
Test Case 7: Mitigated Offer Cap and Floor Calculations
  Mitigated Offer Cap and Floor Calculations before DRUC Execution
  Mitigated Offer Cap and Floor Calculations after DRUC Execution
  Non-decreasing Mitigated Offer Cap Curve Validation
  FIP% + FOP% is not equal to 100
  Default Mitigated Offer Cap Curve using FIP only
Test Case 8: Telemetered Output Schedule Notification

## Slide 34: MMS End-To-End Process Test Procedure
Test Case 1 - Registration Data to Master file (DataFlows 2,18)
Test Case 2 – Market Participant Integration Test (DataFlow 1)
Test Case 3 – MPI – Masterfile Integration Test (DataFlow 1)
Test Case 4 – Settlements-MI Interface Test (DataFlow 9)
Test Case 5 – NMMS-MI Interface Test (DataFlow 11)
Test Case 6 – GEN-SCED Interface Test (DataFlows 31,32,33,34)
Test Case 7 – SE-SCED Interface Test (DataFlow 35)
Test Case 8 – TCM-SCED Interface Test (DataFlow 36,37)
Test Case 9: Mitigated Offer Cap and Floor Calculations
  Mitigated Offer Cap and Floor Calculation before DRUC Execution
  Mitigated Offer Cap and Floor Calculation after DRUC Execution
  Non-decreasing Mitigated Offer Cap Curve Validation
  FIP% + FOP% is not equal to 100
  Default Mitigated Offer Cap Curve using FIP only

## Slide 35: MMS End-To-End Process Test Procedure (Cont’)
Test Case 10: SPP Calculation
  Resource Node SPP Calculation
  Load Zone SPP Calculation
  Time-weighted Trading Hub SPP Calculation
  Hub Average 345kV Trading Hub SPP Calculation
  Bus Average 345kV Trading Hub SPP Calculation
  Correct Retrieval of Load Zone and Hub data

## Slide 36: MMS Failover Processes Test Procedure
Test Case 1 – Database Node A Failover
Test Case 2 – Database Node B Failover
Test Case 3 – Node A and Node B Database Failure
Test Case 4 – MA Application Server (System Level) Test
Test Case 5 – MA Application Server (Application Level) Test
Test Case 6 – MI Application Server Failover