## Slide 1: Texas Nodal Program Update
Jerry Sullivan

## Slide 2: Tactical deliverables and actions
Topic | Solution/Action
MMS | ABB high-level schedule put the Nodal Program schedule at risk. Critical design issues need to be resolved rapidly by ERCOT/ABB – 60% “high” category items resolved 8/24 Commercial implications to follow – target to resolve 9/7 MMS UI development in-house Closer inter-working of ERCOT design, integration and testing teams at ABB starting Sept. 2007
Staffing | Priority staffing needs identified and initiated in consultation with Resource Managers to address gaps in EDS, MMS, and EMS
Sandbox (8/31) Priority 2 Web Services | Confidence in achieving the milestone is High Integration Testing of 6 critical SCED interfaces 84% complete as at 8/24. The rest of the priority 2 web services interfaces will be incrementally delivered in Sept 2007.
EDS 2 (9/4) State Estimator and Telemetry | Confidence in achieving the milestone is High EMS Release 2 – State Estimator and Telemetry FAT test execution 40% complete, 0 severity 1 defects, as at 8/24 Currently investigating calculated points for SE Interim solution for delivery of SE Reports – looking at MIS solution
EDS 1 (10/1) Complete | Confidence in achieving the milestone is High All QSEs will be completed and tested by 10/1, except for one market participant (currently upgrading their EMS)
EDS 3 (11/1) EMS interfacing with SCED | Confidence in achieving the milestone is Medium EMS delivery of interfaces, confidence is High MMS delivery of interfaces, confidence is Low Delivery of SCED reports, confidence is Low – cross-project effort launched to expedite delivery Effort launched to develop interim solution for data consistency between EMS and MMS (prior to final solution through NMMS)
EDS2 R4 (11/1) NMMS NOMCR | Confidence in achieving the milestone is Medium, with known challenges (data reconciliation and validation, AREVA load capabilities, MP availability) NMMS 1b delivery from Siemens failed FAT initially, retest successful (8/23), Phase 1c delivery at end of Sept 2007 Plan to start testing activities with CNP in November (confirmed)
8/24 eEDS MILESTONE ACHIEVED (Austin Energy completed initial testing 8/22)

## Slide 3: Time line update
Energy Management System (EMS)
EDS
Market Management System (MMS)
Congestion Revenue Rights (CRR)
Market Information System (MIS)
Network Model Management System (NMMS)
Commercial Systems (COMS)
ERCOT / MP Readiness & Implementation
Enterprise Integration (EIP)
Enterprise Data Warehouse (EDW)
Infrastructure (INF)
CIM
RT FAT
FAT
CMM
S&B Build
S&B FAT
FAT
EDS 1
EDS 3
EDS 4
Single Entry Model
3/31/
RT Market
12/01
DA Market
12/08
168 Hour Trials
DAM, RUC, SASM S&B Interfaces Build and FAT
SCED, CRR Interfaces Build and FAT
Currently re-planning
Currently re-planning
Readiness
Metrics
Start MP
Registration
Build Dev Environments
Build ITest & EDS1/2
Build EDS 3
Build ITest
Build EDS 4 and Fail-Over Env
SCED Interfaces, RLC
LFC
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
RPP, LF
Study Apps
SE & Telemetry
ICCP Upgrade
DAM, RUC, SASM Build and BL 1 & 2 changes
DAM, RUC, SASM , CIM FAT
VDI, DC Tie
Financial Transfer FAT
Disputes FAT
UI, NOMCR
EDS 2 FAT
CIM Importer
EDS 2
CRR Auction
11/01
Today
Key | 
FAT Start | 
FAT end | 
EDS Start | 
EDS End | 
Go-Live | 
Acronym Key
FAT – Factory Acceptance Testing
EDS – Early Delivery System
I test – Integration Testing