## Slide 1: RO Projects Financial Overview Retail Market Subcommittee September 12, 2007 Justin Rasberry Market Operations Division Projects Organization

## Slide 2: 2007 RO PPL
Projects BELOW the current Capability Line
(Yellow Shaded Area)
Projects ABOVE the current Capability Line
(Orange Shaded Area)
Unplanned 2006 Carry-over Projects
(Green Shaded Area)

## Slide 3: Unplanned 2006 Carry-Over Projects
No status change on these projects.

## Slide 4: Projects ABOVE the Capability Line
PR 70005_01: EIS Siebel to L* Data Comparison moved to “Planning” and approved a name Changed to MO SAS 70 Procedures Optimization
PR 70007_01: Market Trak Enhancements moved into “Planning”
PR 60007_01: PUCT Performance Measures Reporting Requirements moved above the cut line
Notes: 50061_01 Moved to ON Hold: Freed up approx. $120k, however not recommended for release by CART

## Slide 5: Projects BELOW the Capability Line
No status change on these projects
Notes: ERCOT will continue to evaluate the projects under the line to determine if we can move anything up. Currently the items just below the line are funded with the 2008 PPL

## Slide 6: Financial Overview as of 8/31/2007
DPO fully expects that we may see the variance rise as we continue throughout 2007 and get better accuracy with projects gating from Initiation to Planning and from Planning to Execution
RO PPL Budget Activity | Amount | Notes/comments
Approved RO Capability Line Budget Funding | $4.88M | Current approved RO funding allocation Designates where the capability line falls Updated $5.17 budget to $4.88 to reflect accurate funding
Current Forecast Spend of projects above the Capability Line | $2.76M | Based on current expectations and run rates for active and not started projects above the capability line Budget range of $3M – $4M
Budget Variance | ~$2.12M | Budget Variance is difference between RO Capability Line Budget Funding and Current Forecast Spend of projects above the Capability Line $427k resulting from projects running under budget $1.98M due to amounts forecasted into 2008 for current projects -$287k resulting from project budget corrections

## Slide 7: Budget Variance Allocation
Below is the updated view of under spend categories. These categories will be monitored throughout the year to assess potential reallocations.
RO Released
Approx. $1.1M
MO/RO Budget Variance
2007; $ thousand
$1,985
$461
$420
RO Total = $1568
No Concerns
Should be monitored
Should not Release
CART, COPS, and RMS have all reviewed the MO-RO portfolio and acknowledged the release of $1.3M from the overall portfolio budget variance of approx. $3M.
RO Total = $130
RO Total = $420

## Slide 8: Questions / Contact
Justin Rasberry
Manager, MO DPO
Market Operations Divisional Projects Organization
ERCOT
(512) 248-3991
jrasberry@ercot.com