## Texas SET 3.0 Lessons Learned
Item | Source | Topic | Phase | Process | Comments/Action Items (Next Steps) | Responsible Party | Survey Response: Very | Survey Response: Somewhat | Survey Response: Not Very | Survey Response: Not at All
1 | 7/13 MCT Brainstorm Meeting | Consider holding Market Information "Pre-Release Workshop" after Market Requirements are defined and before testing begins in future Texas SET releases. This should be a mandatory "in person" meeting for all MPs. This will provide more awareness of changes and it will ensure a detailed understanding of the market requirements. | Planning | Communication |  | MCT
2 | 7/13 MCT Brainstorm Meeting | MPs bring to MCT their validation criteria (i.e. rejection criteria) during Design phase, perhaps as a standing agenda item at MCT since all MPs will be at different phases in Design. Create a template as a guideline for what is expected in discussions. How much extra effort is this? | Planning | Requirements | Action Item: Draft a template Texas SET discussions | Suzette Sondag/Texas SET
3 | 7/13 MCT Brainstorm Meeting | Consolidated change controls (i.e. Ts & Cs, Mass Transition) vs. Multiple single change controls | Planning | Risk Management
4 | 7/13 MCT Brainstorm Meeting | Document Market Requirements differently: separate sections for System changes (ex. What the system should do to support the business processes) and Business Process changes. | Planning | Requirements |  | MCT
5 | 7/13 MCT Brainstorm Meeting | Concerted effort to challenge assumptions during Market Requirements definition process. ERCOT should more actively challenge the market's assumptions. | Planning | Requirements |  | ERCOT
6 | 7/13 MCT Brainstorm Meeting | Sub-groups to be assigned redline Implementation Guides to review against Market Requirements and Change controls prior to MCT review of redline guides. | Planning | Requirements |  | MCT/Texas SET
7 | 7/13 MCT Brainstorm Meeting | Make goal to have a solid draft of Business Requirements done prior to redlining Implementation Guides. Take more time to get Requirements firmed up. TX SET to come up with a date and/or % complete with Requirements prior to starting the redline Guides (this will be dependent on mandatory dates by Rulemakings). | Planning | Requirements |  | MCT/Texas SET
8 | 7/13 MCT Brainstorm Meeting | Meet more frequently during Requirements definition phase. | Planning | Requirements |  | MCT
9 | 7/13 MCT Brainstorm Meeting | Market to request of PUCT fewer the 4 flight tests per year during version release years | All | n/a | Action Item: Ask RMS to sponsor request to reduce number of flight tests from PUCT | Kathy Scott/RMS
10 | 7/13 MCT Brainstorm Meeting | How to communicate transaction shutdowns better within the market? Some MPs did not receive market notices and were not on the conference calls | Execution | Communication | Action Item: RCS to check for confirmations that MPs are aware of shutdowns and receive communications | ERCOT
11 | 7/13 MCT Brainstorm Meeting | RMGRRs should be written and sent through the governance process after PRRs, SCRs, and Market Requirements are written. | Planning | Requirements |  | MCT/Texas SET
1 | 7/13 MCT Brainstorm Meeting (follow-up email) | Testing of 867_03 IDRs should be Required to verify if sender and receiver are able to successfully translate and it could also determine receiver validation processes | Planning | Test Plan
2 | 7/13 MCT Brainstorm Meeting (follow-up email) | 867_03 should be tested to include each type of 867_03 being communicated in the market - Metered, Unmetered (Streetlight), and Interval. | Planning | Test Plan
3 | 7/13 MCT Brainstorm Meeting (follow-up email) | In response to "Pre-Release Workshop" - Workshop would be early enough to allow time for issues and requirements to be modified to include additional details where needed and opportunity for Questions and Answers prior to Market developing their own internal design and requirements, not a week before testing. | Planning | Communication
4 | 7/13 MCT Brainstorm Meeting (follow-up email) | Pre-Release Workshop would be mandatory for participation from all Market Participants because it would be tied to MP Certification, similar to new release testing certification. | Planning | Communication
5 | 7/13 MCT Brainstorm Meeting (follow-up email) | Testing requirement need to have time to verify complete transaction and not just what was expected in test script. | Execution | Quality Control (Testing)
6 | 7/13 MCT Brainstorm Meeting (follow-up email) | ERCOT's involvement as Test Administrator -should include updating documentation and managing of scripts. | Execution | Quality Control (Testing) |  | ERCOT
7 | 7/13 MCT Brainstorm Meeting (follow-up email) | Flight Administrator should be involved with TX SET and MCT when requirements are developed for version release | Planning | Requirements |  | ERCOT
8 | 7/13 MCT Brainstorm Meeting (follow-up email) | Clearly document and detail requirements/design instructions | Planning | Requirements
9 | 7/13 MCT Brainstorm Meeting (follow-up email) | Testing should include minimum of 2 weeks for version release regression testing at the end of all test scripts and prior to blackout/implementation weekend. This would allow time to test old and new code prior to production implementation | Execution | Quality Control (Testing)
10 | 7/13 MCT Brainstorm Meeting (follow-up email) | Version Release should always include as the Market Coordination Team, TX SET, and TTPT team developing test scripts. | Planning | Test Plan
1 | ERCOT Lessons Learned | The timing of the project was dictated by outside influences and ERCOT adjusted well and was able to deliver on time. | All | n/a
2 | ERCOT Lessons Learned | Requirements were clearly defined. | Planning | Requirements
3 | ERCOT Lessons Learned | Testing went smoothly. | Execution | Quality Control (Testing)
4 | ERCOT Lessons Learned | Testing was able to write test scripts from the requirements without much clarification needed. | Execution | Quality Control (Testing)
5 | ERCOT Lessons Learned | Project went in on time and under budget | All | n/a
6 | ERCOT Lessons Learned | Implementation weekend went very smoothly for a market project of this magnitude. | Execution | Implementation
7 | ERCOT Lessons Learned | ERCOT teams responded to market questions/issues willingly and with suggested solutions. | All | Communication
8 | ERCOT Lessons Learned | Milestone dates were met. | All | n/a
9 | ERCOT Lessons Learned | Liked that business was available and willing to hash out problems | All | Risk Management
10 | ERCOT Lessons Learned | At the beginning of stabilization, the process of using a spreadsheet to capture issues was good | Execution | Implementation, Quality Control
11 | ERCOT Lessons Learned | The implementation was good considering the size of the project | Execution | Implementation
12 | ERCOT Lessons Learned | Good coordination with AIX | Execution | Risk Management
13 | ERCOT Lessons Learned | On a major version change, limit system changes that could negatively impact flight test occur (i.e. Domain Optimization the weekend prior to Day 1 of Flight Test caused delays). | Execution | Risk Management
14 | ERCOT Lessons Learned | Sending of the Customer Billing Contact Information file (CBCI) via NAESB was new for the market (sending a .csv file using NAESB flat file protocol). | Planning | Requirements | Action Item: Make sure when any new or changed file transmissions are part of the requirements of a market project that this is vetted through the TDTWG workgroup. | MCT
15 | ERCOT Lessons Learned | MCT/TX Set did not do as thorough a job of comparing IGs to market requirements and external change controls during MCT review sessions as they should, causing gaps in requirements | Planning | Requirements | Need to find a more effective way of doing this analysis rather than in an MCT/TX Set meeting.
16 | ERCOT Lessons Learned | Market Requirements not in synch with ERCOT; RMGRRs approved before design; unclear implementation guides; unclear CBCI process; unclear governance process for change controls; test timeline too tight with flight. | Planning | Requirements
17 | ERCOT Lessons Learned | Gap in requirements with market and RMGRRs. | Planning | Requirements
18 | ERCOT Lessons Learned | Involve technical teams from companies and ERCOT in market requirements and design phases of the project to provide how they will be performing validations. | Planning | Requirements/ Design
19 | ERCOT Lessons Learned | Review ERCOT internal business requirements with the market at MCT | Planning | Requirements
20 | ERCOT Lessons Learned | RMGRRs should be written and sent through the governance process after Market requirements are complete. | Planning | Requirements/ Communication
21 | ERCOT Lessons Learned | Frequent periodic reviews of internal ERCOT Requirements document to external Market Requirements document needed during Requirements gathering phase to ensure they stay in sync. | Planning | Requirements
22 | ERCOT Lessons Learned | In the calendar year of a major version release, request through RMS/PUCT 3 test flights during the year and not the usual 4 flights. | Execution | Quality Control (Testing)
23 | ERCOT Lessons Learned | Use cases with market; merge market and ERCOT requirements and review approve with market; confirm requirements, RMGRR, PRR, and SCR are all in synch. | Planning | Requirements
24 | ERCOT Lessons Learned | Project was put into planning before the DPO was assigned | Concept & Initiation | Resource Planning
25 | ERCOT Lessons Learned | More details on ERCOT UAT test scripts were needed | Execution | Quality Control (Testing)
26 | ERCOT Lessons Learned | Dedicate resources to support testing environments | Execution | Resource Management/ Communication
27 | ERCOT Lessons Learned | Make sure RMGRRs are not approved prior to the design | Planning | Communication
28 | ERCOT Lessons Learned | Have a response to the notification email be mandatory. If no response, RCS follow up with a phone call. (Problem caused by some CRs/service providers not being aware of shutdown timelines and continuing to send transactions). | All | Communication
29 | ERCOT Lessons Learned | More effective way of comparing the Market requirements, change controls, etc. | Planning | Requirements
1 | Market Lessons Learned Survey | 1. How clearly defined were the Scope and Objectives for this project? | Concept & Initiation | Scope Definition | Positive: Our market group created a PowerPoint presentation to bridge the gap of ERCOT requirements. This PP defined each change control and functional requirement. This PP was used by the technical group and the business. |  | 4 | 2 | 1 | 0
2 | Market Lessons Learned Survey | 1. How clearly defined were the Scope and Objectives for this project? | Concept & Initiation | Scope Definition | Negative: A lot of difficulty interpreting the info provided in the initial docs (more specifically, the detailed requirements) – not clearly spelled out in initial docs. A lot of internal time was used to create what was happening and impacted transactions. We had to work internally (see positive above) to bridge the gap. Additional follow up was needed with the TDSPs for details and specific actions they would toward scenarios such as DOA, Friday Disconnects and reconnects etc. |  | 4 | 2 | 1 | 0
3 | Market Lessons Learned Survey | 1. How clearly defined were the Scope and Objectives for this project? | Concept & Initiation | Scope Definition | No real issues with either the scope or objective, though managing scope creep was at an all time high. |  | 4 | 2 | 1 | 0
4 | Market Lessons Learned Survey | 1. How clearly defined were the Scope and Objectives for this project? | Concept & Initiation | Scope Definition | It was varied based upon timeframes required to implement project. Terms and Conditions and POLR rule approval greatly impacted and reduced the amount of time needed for detailed requirements gathering and provided a clear definition for scope and objectives for this project. In this project the scope and objectives at times were unclear and if identified became a moving target. |  | 4 | 2 | 1 | 0
5 | Market Lessons Learned Survey | 2. Were the Scope and Objectives communicated effectively? | Concept & Initiation | Communication | Negative: Hard to get updated requirements, no track changes. Time was lost constantly referencing older documents. Possible list for version document upgrades i.e. ERCOT requirements version 1.12, 1.13, 1.14, etc. Regarding internal communication and meetings, it would have benefited to provide any discussion that took place to the market participants. |  | 3 | 2 | 1 | 0
6 | Market Lessons Learned Survey | 2. Were the Scope and Objectives communicated effectively? | Concept & Initiation | Communication | We will always have issues with those market participants that do not participate in development or attend meetings on a regular basis. Perhaps the suggestion of a mandatory attendance for the requirements overview will help to lessen this issue, but only if the right players attend the meetings and communicate back within their own company. |  | 3 | 2 | 1 | 0
7 | Market Lessons Learned Survey | 2. Were the Scope and Objectives communicated effectively? | Concept & Initiation | Communication | Communications of what was known at the time was communicated effectively and provided in a timely manner to Market participants. |  | 3 | 2 | 1 | 0
8 | Market Lessons Learned Survey | 3. What communication, organization, or other issues were encountered during the Concept and Initiation Phase? What could have been done to prevent this? | Concept & Initiation | Communication | Reference number 2. Getting a grasp on communication would have made things a lot smoother. Scope & objectives could be set better. |  | n/a | n/a | n/a | n/a
9 | Market Lessons Learned Survey | 3. What communication, organization, or other issues were encountered during the Concept and Initiation Phase? What could have been done to prevent this? | Concept & Initiation | Communication | We seem to always encounter issues with Third party service providers that do not attend any of the meetings during development of the requirements resulting in not totally understanding the requirements. See above. |  | n/a | n/a | n/a | n/a
10 | Market Lessons Learned Survey | 3. What communication, organization, or other issues were encountered during the Concept and Initiation Phase? What could have been done to prevent this? | Concept & Initiation | Communication | Communications can always be improved in all areas of the concept and initiation. Also, if and when applicable allowing more time for gathering requirements and scheduling market meetings for ‘Pre-Release Workshop” would create a better end product. |  | n/a | n/a | n/a | n/a
11 | Market Lessons Learned Survey | 3. What communication, organization, or other issues were encountered during the Concept and Initiation Phase? What could have been done to prevent this? | Concept & Initiation | Communication | None. |  | n/a | n/a | n/a | n/a
12 | Market Lessons Learned Survey | 3. What communication, organization, or other issues were encountered during the Concept and Initiation Phase? What could have been done to prevent this? | Concept & Initiation | Communication | The concept of the customer billing file was a bit vague. |  | n/a | n/a | n/a | n/a
13 | Market Lessons Learned Survey | 3. What communication, organization, or other issues were encountered during the Concept and Initiation Phase? What could have been done to prevent this? | Concept & Initiation | Communication | Too many version of the TX SET V3.0 Business Requirements (14) |  | n/a | n/a | n/a | n/a
14 | Market Lessons Learned Survey | 1. How effective was the Market Requirement defining process? | Planning | Requirements | Negative: ERCOT didn’t do a good job capturing meeting minutes. Internal meetings weren’t communicated out to the appropriate external contacts and a lot of “understood” statements were not documented. Meeting minutes would have been an additional asset for the rest of the groups. |  | 2 | 4 | 1 | 0
15 | Market Lessons Learned Survey | 1. How effective was the Market Requirement defining process? | Planning | Requirements | CR’s and TDSP’s worked closely to define market requirements, however, our documentation was lacking. |  | 2 | 4 | 1 | 0
16 | Market Lessons Learned Survey | 1. How effective was the Market Requirement defining process? | Planning | Requirements | The managing of the versions of the document should be examined to determine if there is a better way to communicate and handle changes to requirements and how the updates are communicated. |  | 2 | 4 | 1 | 0
17 | Market Lessons Learned Survey | 1. How effective was the Market Requirement defining process? | Planning | Requirements | This is tough to do with 3 different entities participating. I think we do the best we can each time and are continuing to look for ways to improve. |  | 2 | 4 | 1 | 0
18 | Market Lessons Learned Survey | 1. How effective was the Market Requirement defining process? | Planning | Requirements | Some gaps existed in the CBCI file requirements, and file format. Market participants had varied understanding of requirements. |  | 2 | 4 | 1 | 0
19 | Market Lessons Learned Survey | 2. How clear were the market requirements? | Planning | Requirements | The requirement for the REF~5I segment on 867_03 documents was initially too general and had to be revised mid test flight |  | 0 | 6 | 1 | 0
20 | Market Lessons Learned Survey | 2. How clear were the market requirements? | Planning | Requirements | Negative: A lot of questions over the requirements weren’t answered. We constantly had to go back to our Market team asking for more detail of change. At some point it appeared as downstream impacts were not taken as a factor. This resulted in uncovering these gaps in testing and flight. |  | 0 | 6 | 1 | 0
21 | Market Lessons Learned Survey | 2. How clear were the market requirements? | Planning | Requirements | Positive: The PowerPoint presentation (again) bridged the gap to a point. Additional documentation would be beneficial from ERCOT. |  | 0 | 6 | 1 | 0
22 | Market Lessons Learned Survey | 2. How clear were the market requirements? | Planning | Requirements | Although those of us developing the requirements understood them, we lacked in clear concise communications and documentation. |  | 0 | 6 | 1 | 0
23 | Market Lessons Learned Survey | 2. How clear were the market requirements? | Planning | Requirements | The requirements in many areas should have been more detailed to minimize areas of misinterpretation and assumptions, example new REG~5I segment in the 867_03 – when it would be provided or not provided in the estimated 867_03 transaction- what are the qualifiers. Testing requirements should always include IDR ESI IDs to determine if ESI IDs were negatively impacted with the change to 867_03 and/or 810 transactions, especially with a change to include new functionality in these transactions. Requirements gathering are very critical because of the design and system validation processes are developed by both ERCOT and MPs based upon the requirements. |  | 0 | 6 | 1 | 0
24 | Market Lessons Learned Survey | 2. How clear were the market requirements? | Planning | Requirements | Some more clear than others. The CIBC file requirement stands out as the main item that was undefined. Additionally, we had an issue related to the PMVI requirement, and were fortunate to discuss it in an internal meeting. So where the requirement was silent, we were not impacted. |  | 0 | 6 | 1 | 0
25 | Market Lessons Learned Survey | 2. How clear were the market requirements? | Planning | Requirements | They were as clear as they could be. Processes were documented very well through all the market Guides. This is always something that can be improved on. |  | 0 | 6 | 1 | 0
26 | Market Lessons Learned Survey | 3. Was a clear test plan defined? | Planning | Test Plan | No issues with identifying test plans. |  | 4 | 2 | 1 | 0
27 | Market Lessons Learned Survey | 3. Was a clear test plan defined? | Planning | Test Plan | TTPT does a fine job of developing and defining the test plan |  | 4 | 2 | 1 | 0
28 | Market Lessons Learned Survey | 3. Was a clear test plan defined? | Planning | Test Plan | IDR ESI IDs were not included in the test scripts/plan to reveal any issues with this transaction for both sender and receiver, especially where there is additional functionality or changes to the 867_03 and 810 transactions. Allow additional time (prefer 2-weeks) after all scripts have been successfully completed to regression test in Test Flights that include new TX SET release. This will allow MP to fully test old and new code together prior to moving to a production environment. |  | 4 | 2 | 1 | 0
29 | Market Lessons Learned Survey | 3. Was a clear test plan defined? | Planning | Test Plan | No. I really think MCT/TX SET needs to do a better job of defining what needs to be tested and giving that to TTPT to create rather than expecting TTPT to come up with the test plans. |  | 4 | 2 | 1 | 0
30 | Market Lessons Learned Survey | 4. Was a clear Timeline defined? | Planning | Risk Management | Yes. Certification timelines and phases were clear. Process was simple, straightforward. Timeline was clear. |  | 6 | 1 | 0 | 0
31 | Market Lessons Learned Survey | 4. Was a clear Timeline defined? | Planning | Risk Management | No surprise on dates/timelines because the project date was determined by rule implementation, however due to date requirement did not allow time for “Pre-Release Workshop”, more time was needed for requirements gathering, no room for error or major problems identified during testing, and non-emergency/urgent corrections. |  | 6 | 1 | 0 | 0
32 | Market Lessons Learned Survey | 4. Was a clear Timeline defined? | Planning | Risk Management | It was very clear when this needed to be implemented! |  | 6 | 1 | 0 | 0
33 | Market Lessons Learned Survey | 5. Was sufficient time allotted for Requirements and Design? | Planning | Risk Management | Yes. |  | 4 | 2 | 1 | 0
34 | Market Lessons Learned Survey | 5. Was sufficient time allotted for Requirements and Design? | Planning | Risk Management | Yes. We started on the requirements year ago giving ample time to work through internal issues. We should begin all implementations in this manner. |  | 4 | 2 | 1 | 0
35 | Market Lessons Learned Survey | 5. Was sufficient time allotted for Requirements and Design? | Planning | Risk Management | Frequent changing of the requirements, we need to develop more detailed requirements to remove any gray areas where there is room for interpretation or assumptions. Also, assumptions were drawn which should have been discussed as a team to determine the correct process to develop the first time without making emergency changes. Time was a huge issue due to rule implementation dates for Terms and Conditions and POLR changes. |  | 4 | 2 | 1 | 0
36 | Market Lessons Learned Survey | 5. Was sufficient time allotted for Requirements and Design? | Planning | Risk Management | The timeline was a bit compressed, but the rulemaking required the compressed timeline. |  | 4 | 2 | 1 | 0
37 | Market Lessons Learned Survey | 5. Was sufficient time allotted for Requirements and Design? | Planning | Risk Management | I think so. We spent months going over the mass transition process and the TDSPs spent HOURS in meetings on the Ts & Cs. Requirements were clear – it’s getting those down to a systems level that is the struggle. |  | 4 | 2 | 1 | 0
38 | Market Lessons Learned Survey | 6. How effective was the Market Coordination Team during this process? | Planning | All | Too many conversations during meetings; decisions were reached that were part of the requirements. Meeting notes weren’t documented properly and not communicated out. |  | 3 | 3 | 1 | 0
39 | Market Lessons Learned Survey | 6. How effective was the Market Coordination Team during this process? | Planning | All | MCT seemed to work in a crisis mode. We did not do a good job of making sure the requirements documentation was clear and concise and that everyone understood them. MCT leadership was new to the position and can use this learning opportunity as a stepping stone for future implementations. MCT leadership should be 100% dedicated to MCT. Susan was stretched because of other pressing NAESB responsibilities. |  | 3 | 3 | 1 | 0
40 | Market Lessons Learned Survey | 6. How effective was the Market Coordination Team during this process? | Planning | All | This was a significant release that included as many changes to functionality and processes as MIMO Version 2.0 for ERCOT and some MPs and at times it seemed to be overwhelming to some individuals that were not aware of steps needed for a new version release or changes required to implementation guides, and developing the requirements needed, which may have created some issues in the market of what was communicated or questions to ask to whom and when. There were areas where questions that needed to be asked were not to challenge the team when developing the requirements, therefore some assumptions where drawn internally that were incorrect creating delays and cost with changing code via change controls. Question: What role does Texas Data Transport Working Group (TDTWG) play in a version release? Should all future version releases include TDTWG representation on the Market Coordination Team along with TTPT and TX SET representation to ensure all aspects of technical design, communications technology, testing, data and business requirements are covered to reduce or eliminate Market issues early in the design phase of the project, instead of post implementation or at the development phase? |  | 3 | 3 | 1 | 0
41 | Market Lessons Learned Survey | 6. How effective was the Market Coordination Team during this process? | Planning | All | MCT was always extremely helpful and attentive and clarifying any questions around the requirements. |  | 3 | 3 | 1 | 0
42 | Market Lessons Learned Survey | 7. How clear were Implementation Guide, RMGRRs, PRRs redlined in regards to the Market Requirements? | Planning | Requirements | Negative: The communication in itself was a problem rather than the implementation. One huge change control made it more confusing. |  | 1 | 6 | 0 | 0
43 | Market Lessons Learned Survey | 7. How clear were Implementation Guide, RMGRRs, PRRs redlined in regards to the Market Requirements? | Planning | Requirements | Too many changes had to be made after the requirements had been finalized, due to unclear documentation of discussions. MPs should use both implementation guides and requirements document. MCT should make sure that there is consistency across all market documents. |  | 1 | 6 | 0 | 0
44 | Market Lessons Learned Survey | 7. How clear were Implementation Guide, RMGRRs, PRRs redlined in regards to the Market Requirements? | Planning | Requirements | Needs room for improvement, question: Can we change the order in which these items are done to support RMGRR and PRR changes after detailed requirements are completed and signed-off? This may have been the reason that RMGRR and PRRs were revisited more than once. |  | 1 | 6 | 0 | 0
45 | Market Lessons Learned Survey | 7. How clear were Implementation Guide, RMGRRs, PRRs redlined in regards to the Market Requirements? | Planning | Requirements | Certain processes such as the NASEB file were not clear at all. When asked for clarification on Requirements we were told by ERCOT that what was there was sufficient. Long delays (in flight testing and during the file due in July) were seen market wide as a result of these gaps. |  | 1 | 6 | 0 | 0
46 | Market Lessons Learned Survey | 7. How clear were Implementation Guide, RMGRRs, PRRs redlined in regards to the Market Requirements? | Planning | Requirements | They were as clear as they could be. These documents get created by people who are very well versed in the Texas market and I think sometimes we forget to bring it down to a level where all people can understand. |  | 1 | 6 | 0 | 0
47 | Market Lessons Learned Survey | 8. Was a clear communication process defined during this phase? Was it effective? | Planning | Communication | There were lots of struggle in this area. It was not effective at all. |  | 4 | 2 | 0 | 1
48 | Market Lessons Learned Survey | 8. Was a clear communication process defined during this phase? Was it effective? | Planning | Communication | There is still confusion on what constitutes an “emergency” change control. MCT leadership needs to communicate what constitutes an “emergency” change control and enforce it. |  | 4 | 2 | 0 | 1
49 | Market Lessons Learned Survey | 8. Was a clear communication process defined during this phase? Was it effective? | Planning | Communication | It was as clear as it could be. Since Service Providers are involved throughout the development and requirements phase of the project are they expected to be the responsible party to communicate with their client (CR)? |  | 4 | 2 | 0 | 1
50 | Market Lessons Learned Survey | 8. Was a clear communication process defined during this phase? Was it effective? | Planning | Communication | It was very clear how to get questions answered. The email address ERCOT set up was a great addition, although I always used Susan! |  | 4 | 2 | 0 | 1
51 | Market Lessons Learned Survey | 8. Was a clear communication process defined during this phase? Was it effective? | Planning | Communication | Flight test Market Calls were great. |  | 4 | 2 | 0 | 1
52 | Market Lessons Learned Survey | 9. What communication, organization, or other issues were encountered during the Planning Phase? What could have been done to prevent this? | Planning | All | Reference the lack of documentation in meeting minutes (number 6). Market participants weren’t given any information. The discussions were not reflected accurately in these meetings. |  | n/a | n/a | n/a | n/a
53 | Market Lessons Learned Survey | 9. What communication, organization, or other issues were encountered during the Planning Phase? What could have been done to prevent this? | Planning | All | Same as response to #6 |  | n/a | n/a | n/a | n/a
54 | Market Lessons Learned Survey | 9. What communication, organization, or other issues were encountered during the Planning Phase? What could have been done to prevent this? | Planning | All | Communications needs to be better to ensure all Market Participants are involved or aware of the changes being developed. This may improve with implementing mandatory (tie present to CR certification just like testing is tied to CR certification) Pre-Release Workshop |  | n/a | n/a | n/a | n/a
55 | Market Lessons Learned Survey | 1. How well was the Flight Test 0407 Coordinated? | Execution | Quality Control (Testing) | There seemed to be a lot of initial set-up issues on the Ercot side – many resends were requested for perfectly good transactions because of these issues. Entire batches/days for certain scripts were delayed by Ercot, causing the need for entire scripts to be adjusted, leading to much confusion. It’s hard enough to keep track of this extremely high amount of testing volume without having to deal with flaws in the test procedure itself. |  | 1 | 2 | 3 | 1
56 | Market Lessons Learned Survey | 1. How well was the Flight Test 0407 Coordinated? | Execution | Quality Control (Testing) | No big issue with it and it was unambiguous. |  | 1 | 2 | 3 | 1
57 | Market Lessons Learned Survey | 1. How well was the Flight Test 0407 Coordinated? | Execution | Quality Control (Testing) | The role of the market test flight administrator needs to be defined and reviewed with the market participants. TDSPs look to the flight administrator when market participants fall behind in testing, to ensure the participants are getting their transactions in timely. This did not happen during 3.0. TDSP’ had to spend excessive time working with individual participants to get their transactions in. Question the amount of time the flight admin., was gone during this implementation. There was inaccurate and in-appropriate comments made about us holding up the process. |  | 1 | 2 | 3 | 1
58 | Market Lessons Learned Survey | 1. How well was the Flight Test 0407 Coordinated? | Execution | Quality Control (Testing) | Flight Administrator was on vacation in week 1 of flight and also was periodically unavailable throughout the entire Flight. Flight Administrator assigned back-ups were inexperienced in the position creating market concerns with test results, resolution outstanding issues, and if Flight 0407 schedule would be met. |  | 1 | 2 | 3 | 1
59 | Market Lessons Learned Survey | 1. How well was the Flight Test 0407 Coordinated? | Execution | Quality Control (Testing) | This flight did not seem as coordinated as others. Seemed like we were always behind schedule. We were always waiting on ERCOT of the TDSP to pass us information – sometimes not finishing week 1 until 3-4 weeks later. At least one weekend of work was required due to this gap. |  | 1 | 2 | 3 | 1
60 | Market Lessons Learned Survey | 1. How well was the Flight Test 0407 Coordinated? | Execution | Quality Control (Testing) | Flight was rough this year. We spent the first two weeks having our CIS partners regenerate and resend initiating transactions just to get the test scenarios set up because of the orders already existing in ERCOT’s system. It seemed like we had a lot of test script clarification emails being sent out throughout the flight. |  | 1 | 2 | 3 | 1
61 | Market Lessons Learned Survey | 1. How well was the Flight Test 0407 Coordinated? | Execution | Quality Control (Testing) | Spent too much time waiting for transactions from other CRs. Checklist was very useful in tracking transactions. |  | 1 | 2 | 3 | 1
62 | Market Lessons Learned Survey | 2. How clear were Market Test Scripts defined? | Execution | Quality Control (Testing) | Some of the checklist entries contained no associated DUNs #’s or invalid Duns numbers. Again, if we’re going to do this HIGH VOLUME testing, the applications that we use to track everything must be accurate. |  | 3 | 3 | 1 | 0
63 | Market Lessons Learned Survey | 2. How clear were Market Test Scripts defined? | Execution | Quality Control (Testing) | There were delayed responses. There were some issues with the script on the incumbent/POLR side. |  | 3 | 3 | 1 | 0
64 | Market Lessons Learned Survey | 2. How clear were Market Test Scripts defined? | Execution | Quality Control (Testing) | Scripts were created based upon requirements, however defining detailed requirements better in the future should result in better test scripts. TTPT should include test scripts for 867_03 and 810’s for IDR, Non-Meter, and Metered services to determine if there are transactional issues for Sender and/or Receiver of these transactions, especially where changes have been made to the 867_03/810 transactions in the event of a version release. |  | 3 | 3 | 1 | 0
65 | Market Lessons Learned Survey | 3. To what degree did testing cover certification of TX SET 3.0 changes? | Execution | Quality Control (Testing) | Significant issues on the CDCI files were missed. Significant issues getting them sent in; more issues around the estimation region codes that should have been caught during “flight”. There was a difference of understanding in what ERCOT thought. |  | 1 | 5 | 1 | 0
66 | Market Lessons Learned Survey | 3. To what degree did testing cover certification of TX SET 3.0 changes? | Execution | Quality Control (Testing) | The test scripts specifically designed to test the TX Set 3.0 changes could have integrated Business and EDI processes more robustly. |  | 1 | 5 | 1 | 0
67 | Market Lessons Learned Survey | 3. To what degree did testing cover certification of TX SET 3.0 changes? | Execution | Quality Control (Testing) | Again more time to develop detailed requirements could improve testing and a longer time to test for evaluation of results, and include test script specific to IDR, non-metered, and metered ESI IDs. |  | 1 | 5 | 1 | 0
68 | Market Lessons Learned Survey | 3. To what degree did testing cover certification of TX SET 3.0 changes? | Execution | Quality Control (Testing) | Feel like there was a gap in certain functionality. Would have like to have seen more testing with the TDSPs as it relates to 650s. |  | 1 | 5 | 1 | 0
69 | Market Lessons Learned Survey | 3. To what degree did testing cover certification of TX SET 3.0 changes? | Execution | Quality Control (Testing) | The test scripts covered the main points of the version release, however there were a few that had to be altered because of system limitations. |  | 1 | 5 | 1 | 0
70 | Market Lessons Learned Survey | 3. To what degree did testing cover certification of TX SET 3.0 changes? | Execution | Quality Control (Testing) | Need to test all transaction functionality being changed ie. Sending of the 814_PC for option one CRs. Test script for the PC and PD both need to be developed. |  | 1 | 5 | 1 | 0
71 | Market Lessons Learned Survey | 4. How well was the implementation plan defined? Was this effective? | Execution | Implementation | From the ERCOT perspective: timeline was met during transition. |  | 5 | 2 | 0 | 0
72 | Market Lessons Learned Survey | 4. How well was the implementation plan defined? Was this effective? | Execution | Implementation | CRs continued to send in transactions to us after the cut-over schedule and we had to accept and process them because TDSPs could not close down their NAESB service until late Friday afternoon. |  | 5 | 2 | 0 | 0
73 | Market Lessons Learned Survey | 4. How well was the implementation plan defined? Was this effective? | Execution | Implementation | Implementation Plan showed transactions will not be transmitted after a certain time; however those same transactions were still communicated in the market after the shut-off time. Since Service Providers are involved throughout the development and requirements phase of the project are they expected to be the responsible party to communicate with their client (CR)? |  | 5 | 2 | 0 | 0
74 | Market Lessons Learned Survey | 4. How well was the implementation plan defined? Was this effective? | Execution | Implementation | We as a Market are getting good at the implementation process. |  | 5 | 2 | 0 | 0
75 | Market Lessons Learned Survey | 5. Was sufficient time allotted for Development, Testing, and Implementation? | Execution | Resource Management | Enough time was provided. |  | 5 | 0 | 2 | 0
76 | Market Lessons Learned Survey | 5. Was sufficient time allotted for Development, Testing, and Implementation? | Execution | Resource Management | Insufficient time based on number of CR’s to be tested. Suggestion for future is to limit the number of trading partners we are required to test with and consider the 3 flights a year instead of 4. |  | 5 | 0 | 2 | 0
77 | Market Lessons Learned Survey | 5. Was sufficient time allotted for Development, Testing, and Implementation? | Execution | Resource Management | No time for regression testing with new version release changes in test environment. Testing phase completed only a week prior to implementation weekend conversion. Development was accelerated to meet testing timeline specified in Flight 0407. |  | 5 | 0 | 2 | 0
78 | Market Lessons Learned Survey | 6. Was a communication plan defined for the Execution Phase? Was this effective? | Execution | Communication | Market didn’t come to an agreement on the transitional model; if it were defined earlier, it would have made the process a lot more smoothly. ERCOT could have used more development time as well. |  | 4 | 2 | 1 | 0
79 | Market Lessons Learned Survey | 6. Was a communication plan defined for the Execution Phase? Was this effective? | Execution | Communication | Only effective if everyone is aware, reads it and follows the plan. When CR’s shut-down sending transactions to ERCOT, all MPs should shut down, regardless. |  | 4 | 2 | 1 | 0
80 | Market Lessons Learned Survey | 6. Was a communication plan defined for the Execution Phase? Was this effective? | Execution | Communication | Implementation Plan showed transactions will not be transmitted after a certain time; however those same transactions were still communicated in the market after the shut-off time. Since Service Providers are involved throughout the development and requirements phase of the project are they expected to be the responsible party to communicate with their client (CR)? |  | 4 | 2 | 1 | 0
81 | Market Lessons Learned Survey | 6. Was a communication plan defined for the Execution Phase? Was this effective? | Execution | Communication | The only communication plan was market calls and occasional email about missing transactions. And instruction to review the check list. |  | 4 | 2 | 1 | 0
82 | Market Lessons Learned Survey | 7. Was a Change Control Process defined to manage necessary changes? Was this effective? | Execution | Risk Management | We appear to operate in a crisis mode. In reality we should not need a change control process until after the product is implemented and should not be making changes once the requirements are deemed final. (if we do a good job on requirements, which was lacking). |  | 1 | 2 | 3 | 0
83 | Market Lessons Learned Survey | 7. Was a Change Control Process defined to manage necessary changes? Was this effective? | Execution | Risk Management | Change control process was defined; however the process for approval may have delayed the emergency implementation of system changes for the last two changes required for market transactions to flow. It was good that the issues were identified quickly enough where only about 300 transactions were impacted for the entire Market. |  | 1 | 2 | 3 | 0
84 | Market Lessons Learned Survey | 7. Was a Change Control Process defined to manage necessary changes? Was this effective? | Execution | Risk Management | There was some dispute over gaps in the ERCOT requirement documents that we were involved in. The ERCOT documents did not cover certain gaps in device facts between the 814_04/05/14. When this gap was identified during testing, we were asked to make it work even though what we were doing was not supported in the Market Guidelines for our transaction (814_14). We had to argue our point just to get a waive on the test. The gap for this requirement was at the ERCOT level. The matter, when it came up, should have been made a change control for a later set and the back and forth should not have occurred. In conclusion, when the gap is at the ERCOT level, ERCOT should support both parties concerns and write any necessary change controls to improve the process instead of trying to make on party change to support something not in the SET. |  | 1 | 2 | 3 | 0
85 | Market Lessons Learned Survey | 7. Was a Change Control Process defined to manage necessary changes? Was this effective? | Execution | Risk Management | There were items found in the guidelines that were blatantly wrong with how we implemented, which continued to cause confusion that we would not fix. Then there were other changes that seemed to get implemented which – based on the guideline it could be interpreted both ways. So as a result we knowingly implemented guidelines that are wrong. We need to get better at this because the more we do this the more out of synch and ineffective our guidelines are going to become. |  | 1 | 2 | 3 | 0
86 | Market Lessons Learned Survey | 8. Were stabilization issues addressed appropriately? | Execution | Quality Assurance | Not sure what this means |  | 4 | 2 | 0 | 1
87 | Market Lessons Learned Survey | 8. Were stabilization issues addressed appropriately? | Execution | Quality Assurance | There are no issues that came up that weren’t addressed immediately. |  | 4 | 2 | 0 | 1
88 | Market Lessons Learned Survey | 8. Were stabilization issues addressed appropriately? | Execution | Quality Assurance | We had very little external and internal stabilization issues to deal with. |  | 4 | 2 | 0 | 1
89 | Market Lessons Learned Survey | 8. Were stabilization issues addressed appropriately? | Execution | Quality Assurance | We are still in a stabilization mode therefore we cannot truly provide an answer at this time, which could be reduced or eliminated with a period of time allotted to regression testing during the Market testing phase. |  | 4 | 2 | 0 | 1
90 | Market Lessons Learned Survey | 9. To what degree to you feel the project was successful? | Execution | All | Transactions were flowing, and everything went fairly well, compared to other Texas Sets (minor hiccups only) |  | 5 | 1 | 0 | 0
91 | Market Lessons Learned Survey | 9. To what degree to you feel the project was successful? | Execution | All | For us, this was one of the most successful implementations yet. |  | 5 | 1 | 0 | 0
92 | Market Lessons Learned Survey | 9. To what degree to you feel the project was successful? | Execution | All | Based upon the number of changes to processes and functionality this was a very successful implementation; however there are areas where improvements are needed and have been identified throughout this document. |  | 5 | 1 | 0 | 0
93 | Market Lessons Learned Survey | 9. To what degree to you feel the project was successful? | Execution | All | The market is still working! |  | 5 | 1 | 0 | 0
94 | Market Lessons Learned Survey | 1. To what degree to you feel the project was successful? | Closing | All | In the end, everything worked out although a bit more experience in key roles throughout the market could have made things smoother. |  | 5 | 2 | 0 | 0
95 | Market Lessons Learned Survey | 1. To what degree to you feel the project was successful? | Closing | All | Everything went fairly well, compared to other Texas Sets. |  | 5 | 2 | 0 | 0
96 | Market Lessons Learned Survey | 1. To what degree to you feel the project was successful? | Closing | All | Seems like there were several gaps in requirements that required either rework (ex: NAESB) or emergency change controls (ex: DOA final read processing). Flight took longer than it should have, cutover weekend took longer than it should have. All in all, risk could have been mitigated if some of these gaps had been covered more efficiently from project conception. |  | 5 | 2 | 0 | 0
97 | Market Lessons Learned Survey | 2. Overall, what Market processes worked well? | Closing | All | There were not many issues with the transaction flow. Everything went well. Transaction standpoint went well. Customer files and responses didn’t have the corresponding IDs but it was fixed fairly quickly. |  | n/a | n/a | n/a | n/a
98 | Market Lessons Learned Survey | 2. Overall, what Market processes worked well? | Closing | All | Having market meetings with companies represented in the meetings and the representatives communicating the requirements, changes and issues internally to their companies. Sufficient time was given to define market requirements and identify individual system changes. |  | n/a | n/a | n/a | n/a
99 | Market Lessons Learned Survey | 2. Overall, what Market processes worked well? | Closing | All | Providing a single point of contact for Market to discuss, resolve issues and draft recommended changes via Market Coordination Team meetings worked well. Implementation plan and schedules were very good; however improvement is needed in communicating the information to appropriate parties for all companies to abide. |  | n/a | n/a | n/a | n/a
100 | Market Lessons Learned Survey | 2. Overall, what Market processes worked well? | Closing | All | MCT is vital to successful implementations. |  | n/a | n/a | n/a | n/a
101 | Market Lessons Learned Survey | 3. Overall, what ERCOT processes worked well? | Closing | All | Testing and migration went ok. Shut down / Communication went well also. |  | n/a | n/a | n/a | n/a
102 | Market Lessons Learned Survey | 3. Overall, what ERCOT processes worked well? | Closing | All | ERCOT processes worked well when it was necessary to make changes quickly when an emergency Market issue was identified and approved via the governance process. |  | n/a | n/a | n/a | n/a
103 | Market Lessons Learned Survey | 3. Overall, what ERCOT processes worked well? | Closing | All | Implementation of the project as a whole. |  | n/a | n/a | n/a | n/a
104 | Market Lessons Learned Survey | 4. Overall, what recommendations for improvements are there for future TX SET implementations? | All | All | I think testing partners should focus more on communicating through the notes area on the checklist and also pay closer attention to keeping it updated and up to the minute. It might make sense to eliminate email notifications and just standardize a couple of guidelines to communicate notifications through the check list. – ie date/time stamp – initial as many are doing anyway. We must stress to Market participants that the scenarios must be executed in a very timely manner. They must be sending outbound transactions on the exact day which they are scripted to be sent otherwise unnecessary confusion begins to ensue. When scripts fall behind, we run into timing issues for business processes. I believe participants must be made to explain in more detail the reasons that they may not reaching daily transaction requirements. Ercot needs improve their systems for creating simulated Muni-Coop compliant test files. I’m not sure how difficult it would be to put in validations for certain EDI elements that are unique to Muni-Coops, but it would definitely eliminate the need for many resends due to human error. If an unsuccessful attempt to verify and inbound transaction has been made, the checklist should be notated with that information. I noticed that many sent transactions were left unchecked as received until follow up was initiated by us. We all know that things happen on both ends that prevent successful transmission however we need to communicate initial research results to our partners so that problems can be diagnosed and corrected more quickly. |  | n/a | n/a | n/a | n/a
105 | Market Lessons Learned Survey | 4. Overall, what recommendations for improvements are there for future TX SET implementations? | All | All | Scope and objectives weren’t as detailed, which led to the creation of additional internal analysis of the changes to communicate what is changes. Market requirements weren’t set clearly also. Cycle time was lost in the process. Priority disconnect policy was not as detailed either more detail of the changes was needed, in addition feedback from the TDSP was lacking which resulted in numerous questions going back and forth to the TDSPs. Availability of the Meeting Minutes is needed; documentation on meeting decisions is needed. Utilization of tracked changes for documentation that had been updated by ERCOT. For example the ERCOT requirements kept changes and what changed from the previous version was not available. This resulted in the entire document having to be analyzed again rather the specific change from the previous version. We also needed more standardization across the TDSPs especially around the safety net processes, DOA, & DNP. Also some customer communication would have been helpful for example around the close of market for a couple of days so couldn't do move ins as well as around DOA. |  | n/a | n/a | n/a | n/a
106 | Market Lessons Learned Survey | 4. Overall, what recommendations for improvements are there for future TX SET implementations? | All | All | Need active participation from the ERCOT employees that attend market meetings. MCT had several ERCOT members present in each meeting, but participation was either lacking or non-existent. Need more attention and responsiveness from the Flight administration when issues are raised by either ERCOT or MPs. Address problems before they become issues. Mandated meeting with all market participants to review draft of final requirements. For future flight tests, reduce overhead in the execution of the script. Each script does not need to start with demonstrating the market can effectuate a switch or move-in. In addition, we are demonstrating 'production systems execution'. With that, if billing is to be completed, then both usage and invoice would be sent to market participants. If the participant does not want to take into their test system, they can parse it out. |  | n/a | n/a | n/a | n/a
107 | Market Lessons Learned Survey | 4. Overall, what recommendations for improvements are there for future TX SET implementations? | All | All | Texas SET changes require adjustment to not only EDI formats but also market participants' business processes. Integration of these two important functions should be the goal of script development. Emphasis should not be on one or the other. This integration would provide more comprehensive certification and relieve some of the burden of internal testing by all market participants. Texas SET specific scripts should focus on Texas SET changes and the scripting sub-team should work to remove script actions that are not related to critical Texas SET changes. All MPs (CRs ERCOT and TDSPs) should stop sending and receiving transactions including 997when the CRs cease sending initiating transactions to ERCOT. Customer transactions such as 650.01s and 814.03s have a work around so as not to impact the customers. The 820.02 transactions do not involve money so there is no direct financial impact to the TDSPs by stopping the 820.02 transaction for one day (ie Friday, June 22 for SET 3.0). All other transactions that were sent and received on the Friday before cutover (ie Friday June 22) were to maintain the synchronization between trading partners. This approach will place a hard stop on transactions coming into a trading partner after the cutoff time. For our company, some CRs continued to send transactions beyond the cutoff time, but we had to receive and process these transactions because the cutoff time for 820.02s was as late as 5pm CPT. This stagger stopping time caused TDSPs NAESB service to be operational until the very last transaction type (820.02s) could be received. This approach will place a hard stop on transactions coming into a trading partner after the cutoff time. For our company, some CRs continued to send transactions beyond the cutoff time, but we had to receive and process these transactions because the cutoff time for 820.02s was as late as 5pm CPT. This stagger stopping time caused TDSPs NAESB service to be operational until the very last transaction type (820.02s) could be received. In addition, ERCOT sent 2.1 formatted transactions until early afternoon but would not accept back the 2.1 formatted 814.04. Therefore, we had to redo all the ERCOT sent transactions into 3.0 format that were received just before ERCOT stopped sending. By having an early Friday morning hard stop, we will reduce the number of companies involved in repairing transaction from 6 to only 1 and ensure other trading partners are respecting the agreed upon cutoff times. |  | n/a | n/a | n/a | n/a
108 | Market Lessons Learned Survey | 4. Overall, what recommendations for improvements are there for future TX SET implementations? | All | All | Better communications which could also help in developing more detailed business requirements |  | n/a | n/a | n/a | n/a
109 | Market Lessons Learned Survey | 4. Overall, what recommendations for improvements are there for future TX SET implementations? | All | All | Longer timeframe to gather requirements to include all the details and schedule Pre-Release workshops |  | n/a | n/a | n/a | n/a
110 | Market Lessons Learned Survey | 4. Overall, what recommendations for improvements are there for future TX SET implementations? | All | All | Two week “Regression” testing phase included in the flight schedule for a TX SET release. |  | n/a | n/a | n/a | n/a
111 | Market Lessons Learned Survey | 4. Overall, what recommendations for improvements are there for future TX SET implementations? | All | All | Include in the 867_03 testing scripts to test IDR, Metered and Unmetered services for both 810 and 867_03 transactions to determine ERCOT and MPs validation points and their ability to process these transactions that are communicated on a daily basis. |  | n/a | n/a | n/a | n/a
112 | Market Lessons Learned Survey | 4. Overall, what recommendations for improvements are there for future TX SET implementations? | All | All | Document detailed requirements in TX SET Implementation guide graybox clearly instructing Market of the proper use of data elements and/or segments. |  | n/a | n/a | n/a | n/a
113 | Market Lessons Learned Survey | 4. Overall, what recommendations for improvements are there for future TX SET implementations? | All | All | Detailed Business requirements should be completed and signed off prior to developing Technical change are made to Implementation Guides and supporting changes are made to Retail Market Guides and Protocol Revisions documents. It is the “what” is needed and “why” before the how it should be communicated that should be created for future releases |  | n/a | n/a | n/a | n/a
114 | Market Lessons Learned Survey | 4. Overall, what recommendations for improvements are there for future TX SET implementations? | All | All | If putting something like the NAESB file together, involve more technical ERCOT resources so that the requirements are clearer and there is not so much confusion during flight testing or when we have to produce the file for the first time. |  | n/a | n/a | n/a | n/a
115 | Market Lessons Learned Survey | 4. Overall, what recommendations for improvements are there for future TX SET implementations? | All | All | A requirements document that is not separated by business processes. It makes it difficult to reference requirements when developing internal designs. I think we spend a lot of time philosophizing on how things should work instead of staying focused on how things will work. If we did this it would not eat up as much time on the front end and may help us get to a more detailed level in defining requirements. |  | n/a | n/a | n/a | n/a
116 | Market Lessons Learned Survey | 4. Overall, what recommendations for improvements are there for future TX SET implementations? | All | All | The only communication plan was market calls and occasional email about missing transactions. And instruction to review the check list. |  | n/a | n/a | n/a | n/a
1 | 8/29 MCT Lessons Learned Meeting | 1. How clearly defined were the Scope and Objectives for this project? | Concept & Initiation | Scope Definition | We did have scope & objectives defined - scope creep was the issue
2 | 8/29 MCT Lessons Learned Meeting | 1. How clearly defined were the Scope and Objectives for this project? | Concept & Initiation | Scope Definition | Emergency change controls were the issue
3 | 8/29 MCT Lessons Learned Meeting | 1. How clearly defined were the Scope and Objectives for this project? | Concept & Initiation | Scope Definition | Lack of scope on safety net and estimation process - late getting those in Texas SET.
4 | 8/29 MCT Lessons Learned Meeting | 1. How clearly defined were the Scope and Objectives for this project? | Concept & Initiation | Scope Definition | Was it really scope creep or going through so many revisions of requirements?
5 | 8/29 MCT Lessons Learned Meeting | 1. How clearly defined were the Scope and Objectives for this project? | Concept & Initiation | Scope Definition | Depth of experience in market worked well.
6 | 8/29 MCT Lessons Learned Meeting | 1. How clearly defined were the Scope and Objectives for this project? | Concept & Initiation | Scope Definition | Action Item: Clearly define project scope. Review scope throughout the project lifecycle. | MCT
7 | 8/29 MCT Lessons Learned Meeting | 1. How clearly defined were the Scope and Objectives for this project? | Concept & Initiation | Scope Definition | Action Item: Add reference to the Working Groups that should be consulted during the project (i.e. defining or reviewing requirements) in the scope document if they are known. | MCT
8 | 8/29 MCT Lessons Learned Meeting | 2. Were the Scope and Objectives communicated effectively? | Concept & Initiation | Communication | Lacked documentation. If you were in the meetings, you should have gotten it. | n/a
9 | 8/29 MCT Lessons Learned Meeting | 3. What communication, organization, or other issues were encountered during the Concept and Initiation Phase? What could have been done to prevent this? | Concept & Initiation | Scope Definition | All MPs made assumptions. | n/a
10 | 8/29 MCT Lessons Learned Meeting | 3. What communication, organization, or other issues were encountered during the Concept and Initiation Phase? What could have been done to prevent this? | Concept & Initiation | Communication | Always struggled with involvement of others than the core group in the room. | n/a
11 | 8/29 MCT Lessons Learned Meeting | 1. How effective was the Market Requirement defining process? | Planning | Requirements | This should include the effectiveness of TCTF in defining requirements. These were defined by a small group of SET participants. | n/a
12 | 8/29 MCT Lessons Learned Meeting | 1. How effective was the Market Requirement defining process? | Planning | Requirements | Short timeline to get information together. This will always happen with the PUCT rulemakings. | n/a
13 | 8/29 MCT Lessons Learned Meeting | 1. How effective was the Market Requirement defining process? | Planning | Requirements | Action Item: More time toward MCT. More meetings and longer ones (1.5 – 2 days). | MCT
14 | 8/29 MCT Lessons Learned Meeting | 1. How effective was the Market Requirement defining process? | Planning | Requirements | Action Item: Consider using the Use Case Requirements methodology in defining requirements (currently being used in MarkeTrak project). | MCT
|  | 1. How effective was the Market Requirement defining process? | Planning | Requirements | Action Item: Assign one person to draft and separate person to review. | MCT
|  | 1. How effective was the Market Requirement defining process? | Planning | Requirements | Action Item: When reviewing at meeting, don’t have network access (too much multi-tasking, not enough focus on task at hand). | MCT
15 | 8/29 MCT Lessons Learned Meeting | 2. How clear were the market requirements? | Planning | Requirements | We did OK with the requirements; we didn’t document them well enough. | n/a
16 | 8/29 MCT Lessons Learned Meeting | 2. How clear were the market requirements? | Planning | Requirements | Not always sure what needs to be changed when dealing with a rulemaking. | n/a
17 | 8/29 MCT Lessons Learned Meeting | 2. How clear were the market requirements? | Planning | Requirements | Conversations and small group meetings were not documented. | n/a
18 | 8/29 MCT Lessons Learned Meeting | 2. How clear were the market requirements? | Planning | Requirements | CRs & TDSPs worked closely to define changes. | n/a
19 | 8/29 MCT Lessons Learned Meeting | 2. How clear were the market requirements? | Planning | Requirements | Ability to find documents on website was good. | n/a
20 | 8/29 MCT Lessons Learned Meeting | 2. How clear were the market requirements? | Planning | Requirements | Action Item: Need better documentation. Make point to document more detail in Requirements and meeting minutes. | ERCOT
21 | 8/29 MCT Lessons Learned Meeting | 2. How clear were the market requirements? | Planning | Requirements | Action Item: Review meeting minutes to make sure they are accurate and details make it to requirements. | MCT
22 | 8/29 MCT Lessons Learned Meeting | 2. How clear were the market requirements? | Planning | Requirements | Action Item: Document Assumptions at Requirements stage | Market
23 | 8/29 MCT Lessons Learned Meeting | 2. How clear were the market requirements? | Planning | Requirements | Action Item: Post both redline and clean documents on website. Add more comprehensive change history. | ERCOT
24 | 8/29 MCT Lessons Learned Meeting | 2. How clear were the market requirements? | Planning | Requirements | Action Item: Document conversations, emails, and small group meetings | MCT/ERCOT
25 | 8/29 MCT Lessons Learned Meeting | 2. How clear were the market requirements? | Planning | Requirements | Action Item: Assign (and post) action items and decisions made at MCT | ERCOT
26 | 8/29 MCT Lessons Learned Meeting | 3. Was a clear test plan defined? | Planning | Test Plan | Action Item: Do a better job of reviewing TTPT’s proposal for tests | MCT
27 | 8/29 MCT Lessons Learned Meeting | 3. Was a clear test plan defined? | Planning | Test Plan | Action Item: Add testing request to applicable requirement in Requirements Document | MCT
28 | 8/29 MCT Lessons Learned Meeting | 3. Was a clear test plan defined? | Planning | Test Plan | Action Item: Share ERCOT UAT test scripts | ERCOT
29 | 8/29 MCT Lessons Learned Meeting | 4. Was a clear Timeline defined? | Planning | Risk Management | A mandated date works against us. All releases without a mandated date have worked better. | n/a
|  | 4. Was a clear Timeline defined? | Planning | Risk Management | The mandated date added a risk to the project automatically. | n/a
30 | 8/29 MCT Lessons Learned Meeting | 5. Was sufficient time allotted for Requirements and Design? | Planning | Risk Management | With any release, we seem to miss it when we get down to the detail from the requirements. | n/a
31 | 8/29 MCT Lessons Learned Meeting | 6. How effective was the Market Coordination Team during this process? | Planning | All | What role does TDTWG play in a version release and at what point do they need to be involved? | n/a
32 | 8/29 MCT Lessons Learned Meeting | 6. How effective was the Market Coordination Team during this process? | Planning | All | Action Item: Involve early on when other working groups are involved and reach out. Once MCT reaches out, that working group should review the detail requirements. Define expectations of working groups' responsibilities. | MCT/Working Groups
33 | 8/29 MCT Lessons Learned Meeting | 6. How effective was the Market Coordination Team during this process? | Planning | All | Action Item: For each requirement ask question of what working group(s) should be consulted (ex. TDTWG for CBCI file, DEWG for extracts, Advanced metering for Retail metering work group) | MCT
34 | 8/29 MCT Lessons Learned Meeting | 6. How effective was the Market Coordination Team during this process? | Planning | All | Action Item: MCT Leadership Role to be dedicated to MCT Team during a version release. Competing priorities need to be managed by ERCOT / or responsible entity to allow this role to be dedicated to the Market Coordination during a version release. | ERCOT
35 | 8/29 MCT Lessons Learned Meeting | 7. How clear were Implementation Guide, RMGRRs, PRRs redlined in regards to the Market Requirements? | Planning | Requirements | One change control enabled developers to see cross impacts on transactions – developers could go one place and see all information. Mixed feelings among group as to the benefits or one Change Control vs. many. | n/a
36 | 8/29 MCT Lessons Learned Meeting | 7. How clear were Implementation Guide, RMGRRs, PRRs redlined in regards to the Market Requirements? | Planning | Requirements | Problem with having so many RMGRRs and with filing them so early. | n/a
37 | 8/29 MCT Lessons Learned Meeting | 7. How clear were Implementation Guide, RMGRRs, PRRs redlined in regards to the Market Requirements? | Planning | Requirements | More feedback needed from RMS on PRRs/RMGRRs | n/a
38 | 8/29 MCT Lessons Learned Meeting | 7. How clear were Implementation Guide, RMGRRs, PRRs redlined in regards to the Market Requirements? | Planning | Requirements | Action Item: In October, 2007 MCT presentation to RMS, discuss the problems encountered with PRRs and RMGRRs. Emphasize to RMS that comment period for PRRs and RMGRRs isn’t beneficial if MPs don’t review and provide comments. RMS action to follow? | MCT Lead/RMS
39 | 8/29 MCT Lessons Learned Meeting | 7. How clear were Implementation Guide, RMGRRs, PRRs redlined in regards to the Market Requirements? | Planning | Requirements | Action Item: Texas SET Review benefits of having one large change control vs. many smaller change controls for a project | Texas SET
40 | 8/29 MCT Lessons Learned Meeting | 8. Was a clear communication process defined during this phase? Was it effective? | Planning | Communication | What is the responsibility of a service provider to their clients? It depends on what services are contracted between the CR and the service provider. | n/a
41 | 8/29 MCT Lessons Learned Meeting | 8. Was a clear communication process defined during this phase? Was it effective? | Planning | Communication | Action Item: Mandatory Pre-release workshop. Need to build rules around the workshop. Can service providers represent their clients? | MCT/Texas SET
42 | 8/29 MCT Lessons Learned Meeting | 8. Was a clear communication process defined during this phase? Was it effective? | Planning | Communication | Action Item: Mid-Requirements gathering; include IT Staff & Developers. Have ERCOT developers provide interpretation | MCT/ERCOT/MPs
43 | 8/29 MCT Lessons Learned Meeting | 1. How well was the Flight Test 0407 Coordinated? | Execution | Quality Control (Testing) | Action Item: Set up more deadlines and checkpoints during testing. Define what happens if these are missed. | TTPT
44 | 8/29 MCT Lessons Learned Meeting | 1. How well was the Flight Test 0407 Coordinated? | Execution | Quality Control (Testing) | Action Item: Define role of ERCOT Flight Administrator | ERCOT
45 | 8/29 MCT Lessons Learned Meeting | 2. How clear were Market Test Scripts defined? | Execution | Quality Control (Testing) | There was confusion on the calls and following test scripts | n/a
46 | 8/29 MCT Lessons Learned Meeting | 2. How clear were Market Test Scripts defined? | Execution | Quality Control (Testing) | Action Item: MCT should determine what needs to be tested, more actively review scripts, and provide feedback to TTPT. | MCT
47 | 8/29 MCT Lessons Learned Meeting | 2. How clear were Market Test Scripts defined? | Execution | Quality Control (Testing) | Action Item: Define relationship between MCT & TTPT | MCT/TTPT
48 | 8/29 MCT Lessons Learned Meeting | 4. How well was the implementation plan defined? Was this effective? | Execution | Implementation | Detailed discussions of rollback plan were very effective. | n/a
49 | 8/29 MCT Lessons Learned Meeting | 4. How well was the implementation plan defined? Was this effective? | Execution | Implementation | Action Item: Better definition of cut-off plan is needed. Communicate this plan to the market (possibly at the Pre-Release workshop). | MCT
50 | 8/29 MCT Lessons Learned Meeting | 4. How well was the implementation plan defined? Was this effective? | Execution | Implementation | Action Item: Make sure transactions are not accepted or sent after cut-offs. | ERCOT/MPs
51 | 8/29 MCT Lessons Learned Meeting | 5. Was sufficient time allotted for Development, Testing, and Implementation? | Execution | Resource Management | Action Item: TTPT is addressing round-robin testing and planning for it. | TTPT
52 | 8/29 MCT Lessons Learned Meeting | 5. Was sufficient time allotted for Development, Testing, and Implementation? | Execution | Resource Management | Action Item: 3 test flights a year instead of 4 has been proposed to RMS; TTPT is planning for 3 flights. | TTPT/RMS
53 | 8/29 MCT Lessons Learned Meeting | 5. Was sufficient time allotted for Development, Testing, and Implementation? | Execution | Resource Management | Action Item: Consider adding regression testing into timelines. | TTPT
54 | 8/29 MCT Lessons Learned Meeting | 7. Was a Change Control Process defined to manage necessary changes? Was this effective? | Execution | Risk Management | There should not be change controls until after implementation. However, how should gaps be handled if discovered prior to implementation? Who knows when the next Texas SET release will go in to fix things – you could live with broken functionality for 2 years or so until the next release. | n/a
55 | 8/29 MCT Lessons Learned Meeting | 7. Was a Change Control Process defined to manage necessary changes? Was this effective? | Execution | Risk Management | There was no risk management document – how do you handle the risks? | n/a
56 | 8/29 MCT Lessons Learned Meeting | 7. Was a Change Control Process defined to manage necessary changes? Was this effective? | Execution | Risk Management | Action Item: MCT to reinforce Texas SET definition of emergency change control. (Texas SET is currently working on a clearer definition of emergency change control.) | MCT/Texas SET
57 | 8/29 MCT Lessons Learned Meeting | 7. Was a Change Control Process defined to manage necessary changes? Was this effective? | Execution | Risk Management | Action Item: Texas SET to look into feasibility of small release to catch fall-out from main implementation. | Texas SET
58 | 8/29 MCT Lessons Learned Meeting | 8. Were stabilization issues addressed appropriately? | Execution | Quality Assurance | Use of IT resources on next flight test was hard; this did not provide for proper stabilization. | n/a
59 | 8/29 MCT Lessons Learned Meeting | 1. To what degree to you feel the project was successful? | Closing | All | 3.0 went more smoothly then 2.1 | n/a
60 | 8/29 MCT Lessons Learned Meeting | 1. To what degree to you feel the project was successful? | Closing | All | It will be interesting to see how well everything worked when a mass transition actually happens | n/a
61 | 8/29 MCT Lessons Learned Meeting | 1. To what degree to you feel the project was successful? | Closing | All | Experienced people in the market and in our shop helped this go well | n/a
62 | 8/29 MCT Lessons Learned Meeting | 2. Overall, what Market processes worked well? | Closing | All | When project is approved by BOD, assign ERCOT project team to initiate project processes | ERCOT

## TTPT Lessons Learned
Lesson Learned | Category | Source | Submitter | Very | Somewhat | Not Very | Not at All | Comments | Future Corrective Action
When resends are requested, need to indicate the reason why. | Testing | TTPT | Service Provider | n/a | n/a | n/a | n/a | Original file sometimes fails for reason not mentioned.
Mention in test script instructions on sending a transaction late. | Testing | TTPT | Service Provider | n/a | n/a | n/a | n/a | When getting caught up on sending transactions, they would fail due to testing date being too old now.
Establish report on Retail Testing website so MPs do not have to count their numbers up on the daily call. | Testing | TTPT | Service Provider | n/a | n/a | n/a | n/a
Proper procedures should be used by TDSPs when resending point-to-point transactions. | Testing | TTPT | Service Provider | n/a | n/a | n/a | n/a | Hard to remove a transaction from a billing system without a cancellation transaction or 824.
Resend request needs to include all relevant information. | Testing | TTPT | Service Provider | n/a | n/a | n/a | n/a | Ex. What date needs to be used in DTM segment.
MPs and ERCOT need to follow script details. | Testing | TTPT | Service Provider | n/a | n/a | n/a | n/a | Ex. Transactions missing necessary segments that script calls for.
Email should be sent to MPs prior to conference call for important issues. | Testing | TTPT | Service Provider | n/a | n/a | n/a | n/a
Testing has to start on scheduled date | Testing | TTPT | TDSP | n/a | n/a | n/a | n/a |  | All system changes should be complete and the test environment ready to go by the kick-off call. This will give ERCOT the weekend in the event they run into a technical issue.
Clearly defined process on how to address an issue when a script is not working or a process is not working as expected | Testing | TTPT | TDSP | n/a | n/a | n/a | n/a
Clear explanation of testing processes needs to be given. | Testing | TTPT | TDSP | n/a | n/a | n/a | n/a | This will achieve realistic expectations and help stay on schedule. Testing resources may be different for MPs than those whom have previously managed testing.
Backdated transactions should not be sent after 5:00 PM | Testing | TTPT | TDSP | n/a | n/a | n/a | n/a |  | ERCOT should validate that the date wanted is an acceptable date. All testing resources should be educated about the time requirements for transactions that go through ERCOT. Add communication to the kick-off call. TDSPs should inform testing partners when their batch process begins on the kick-off call. Create a Tip Sheet for Testing on back-dated transactions.
Better organized Saturday work days | Testing | TTPT | TDSP | n/a | n/a | n/a | n/a |  | The MP that is behind needs to provide a plan for catching up to the Flight Admin this should be communicated to the impacted MPs.
Internal testers need to be aware of all script checkpoints and verify they are correct | Testing | TTPT | ERCOT | n/a | n/a | n/a | n/a
SIM transactions for MOU ESI IDs need to be checked for added segments/values associated with MOU territories | Testing | TTPT | ERCOT | n/a | n/a | n/a | n/a
Test Bed Loader Tool (internal tool for ERCOT) needs to be updated so that all service instances are set up for new TS scripts | Testing | TTPT | ERCOT | n/a | n/a | n/a | n/a