Texas Nodal:

TCR to CRR Transition Plan

This is a living document.  Its contents have been drafted for discussion with relevant parties and for approval from WMS and TPTF. Based on discussions/feedback, details of this document may be further refined.

Version 0.06

Sep 12th, 2007

Revision History

| Document Revisions |  |  |  |
| --- | --- | --- | --- |
| Date | Version | Description | Author(s) |
| 7/31/2007 | 0.01 | Drafted from Terry’s initial thoughts. | CRR |
| 8/7/2007 | 0.02 | After feedback from Terry/Beth. | CRR |
| 8/21/2007 | 0.03 | After discussion meetings with Rich Carey (TCR), Cheryl Yager/Srini S/Vanessa Spells (Credit). | CRR |
| 9/6/2007 | 0.04 | After comments from Bill Barnes (Settlements) and Finance | CRR |
| 9/7/2007 | 0.05 | After comments from Shawna. | CRR |
| 9/12/2007 | 0.06 | After final comments from Beth/Terry, Bill Barnes, Cheryl Yager. | CRR |

Table of Contents

1	Overview	4

1.1	Objectives	4

1.2	Schedule	4

1.3	Supporting documentation	4

2	Proposed Plans	5

2.1	Plan A – go live 12/1/08	6

2.2	Plan B – go live after 1/1/09	7

2.3	Plan C – go live after 1/1/09; run monthly auctions only	8

3	Proposed method of refunding annual TCR/PCR revenues	9

3.1	Alternative (option 2)	9

4	Appendix	10

4.1	Market Readiness Criteria	10

# Overview

## Objectives

This document is intended to describe the plan(s) for transitioning from the Zonal TCR market to the Nodal CRR market.  In particular, it includes the proposed method(s) for refunding annual TCR/PCR auction revenues and contingency plans.

Development of this plan will involve Nodal projects CRR, CMM and Settlements, and relevant members of the Zonal TCR/Settlements departments. This plan will be presented for approval to the WMS group, TPTF, and the Nodal Readiness Team.

This document will fulfill the Market Readiness Criteria “CRR2 – Develop TCR to CRR Transition Plan” (see appendix for details).

## Schedule

Schedule and next steps for this plan is as follows:

- Sep 19th 2007: 	Present plan; vote of approval from WMS

- Oct 8th 2007: 	Present plan to TPTF

- Oct 28th 2007: 	Vote of approval from TPTF

- Nov 14th 2007: 	Post 2008 TCR Annual Auction notice

(The notice will include refund methodology as agreed in this plan)

## Supporting documentation

Supporting documents include, but not limited to:

- Program Schedule (Nodal website; request latest version from Nodal PMO, Kalyan Sumanam)

- Protocols: Nodal and Zonal, Section 7 (ERCOT and Nodal websites)

- Market Readiness Criteria Metrics (request latest version from Nodal PMO, Chris Wilkerson)

- CRR EDS 3 handbook (Nodal EDS website or CRR Sharepoint)

- CRR requirements (Nodal website or CRR Sharepoint)

# Proposed Plans

Several plans are proposed: one of which supports the current go-live date, and two other contingency plans in preparation for circumstances that may cause the Nodal market go-live date to be later than 12/1/08:

- Plan A – go live 12/1/08

- Plan B – go live after 1/1/09

- Plan C – go live after 1/1/09; run monthly TCR auctions only (no refund)

Details of each plan are in the following subsections.

Important: the contingency plans (B and C) were developed with the following assumptions:

- Nodal go-live date is later than 12/1/08

- New go-live date is determined at least 5 months in advance of the new Nodal go-live date

- New go-live date will be the first day of the month

## Plan A – go live 12/1/08

Plan A is based upon the current nodal go-live date of 12/1/08.

The plan is to run an annual TCR Auction in Dec 07 for all of 2008 and run monthly TCR Auctions in 2008 up to December (i.e. no monthly TCR auction for Dec). After go-live on 12/1/08, annual TCR/PCR owners will be refunded for the month of Dec 08.

The proposed timeline is as below:

Assumptions/dependencies in Plan A:

- Nodal will go-live in 12/1/08

- CRR and COMS (Settlements & Billing) successfully pass EDS testing

- Should CMM-CRR interface not be completed  as expected, manual process for 1st auction

- TCR/PCR owners will be refunded for the month of Dec as described in Section 3 of this plan

## Plan B – go live after 1/1/09

Plan B is a contingency plan and may be executed should the Nodal market go-live date be postponed until after Jan 1st 2009. This contingency plan is to run an annual TCR Auction in Dec 07 for all of 2008, and also run an annual TCR Auction in Dec 08 for all of 2009, and run monthly TCR Auctions up to go live month.

Annual TCR/PCR owners will be refunded for the remaining months in 2009 after new Nodal go-live date.

The proposed timeline is as below:

Assumptions/dependencies in Plan B:

- Nodal go-live date is after 1/1/09

- CRR, NMMS, COMS (S&B) successfully pass EDS testing

- Should CMM-CRR interface not be completed  as expected, manual process for 1st auction

- TCR/PCR owners will be refunded for remaining months after Nodal go-live as described in Section 3 of this plan

- Able to run an annual TCR auction in Dec 2008

## Plan C – go live after 1/1/09; run monthly auctions only

Plan C is another contingency plan should the Nodal market go-live date be postponed until after Jan 1st 2009. The plan is to run an annual TCR Auction in Dec 07 for all of 2008, but starting Dec 09, run only monthly TCR Auctions until the new Nodal go-live date.

Under this plan no refund of auction revenues to TCR owners will be necessary.

PCRs will be allocated monthly.

The proposed timeline is as below:

Assumptions/dependencies in Plan C:

- CRR, NMMS, COMS (S&B) successfully pass EDS testing

- Should CMM-CRR interface not be completed  as expected, manual process for 1st auction

- Able to allocate PCRs monthly

- Able to run monthly auctions without holding an annual auction (will need Zonal PRR to allow only TCR monthly auctions after 2008)

# Proposed method of refunding annual TCR/PCR revenues

Every month from Jan to Nov 08, ERCOT will, as usual, divide the 2008 annual auction TCR/PCR revenues into monthly revenues in the same proportion as ERCOT’s monthly energy forecast (see graph below) and distribute them to QSEs based on their Load Ratio Share (LRS).

In Dec 08 (when TCRs/PCRs are no longer in effect), ERCOT proposes to refund remaining 2008 TCR/PCR annual auction revenue to TCR/PCR owners based on TCR/PCR purchase allocation % (see formula below).

* Note: For PCRs, purchase allocation % is based on $ amount paid, not equivalent TCR clearing price

## Alternative (option 2)

An alternative would be to calculate TCR/PCR revenue for Dec (based on formula below) and refund that amount to TCR/PCR owners.

Because this alternative calculation is greater than the remaining 2008 TCR/PCR annual auction revenue, ERCOT will first need to collect back some revenue previously allocated to QSEs based on LRS before being able to refund TCR/PCR owners.

* Note: For PCRs, purchase allocation % is based on $ amount paid, not equivalent TCR clearing price

# Appendix

## Market Readiness Criteria

Metric CRR2 - Develop TCR to CRR Transition Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 270 days |  |  |  |
| Metric Description: ERCOT will provide detailed TCR to CRR plan describing each step of the transition. |  |  |  |
| Background: The intent of this metric is to verify the existence and publication of the TCR to CRR transition Plan. |  |  |  |
| Criteria: The Readiness Team will review, from a public source, the TCR to CRR transition plan including rebate, timing and other CRR details of interest. Readiness will be achieved when the Readiness Team will be provided with documentation that verifies that the TCR to CRR transition plan has been created. TCR to CRR Transition Plan exists |  |  |  |
| Reporting Data Sources: TCR to CRR Transition Plan / ERCOT CRR PM |  |  |  |
| References | TP: N/A | TNP: |  |