## Slide 1: PMO Update to PRS
Troy Anderson
Program Management Office
September 20, 2007

## Slide 2: PMO Update
Agenda
  2008 Project Prioritization and Funding
    Approval Status and Funding Update
  Recent Project Developments
    Project that have been implemented – August
  Cost Benefit Analysis Review Board
    No activity
  NPRR Status
    Next Baseline

## Slide 3: PMO Update
2008 Project Prioritization Approval Status
  Approved by PRS on 6/21
  Approved by TAC on 6/28
  To be considered for approval by the Board on 9/18
2008 Project Funding Status
  Original 2008 project budget submission $27.5M (Zonal)
    $ 5.3M (Nodal)
    $32.8M (Total)
  Revision on 7/13
    Acceleration of projects to 2007 ($5.3M)
      Projects to be accelerated still
        being determined
  Revised 2008 project budget $27.5M (Revised Total)

## Slide 4: PMO Update
Recent Project Implementations
  August
    No market-facing project implementations to report
CBA Review Board
  Next meeting – 10/4/2007, 1pm-2pm
    Objective: Review/revise “Guidelines for Project Prioritization”

## Slide 5: PMO Update
NPRR Status
  Baselines 1 and 2 approved by Board of Directors on 7/17
  Next Baseline (known as “Post-Baseline 2”)
    15 NOGRRs - All approved by ROS on 9/13
      12 with No Impact
        NOGRRs 3, 4, 6, 7, 8a, 8b, 8c, 8d, 8e, 8f, 8g, 8h
      3 with Impacts that will be absorbed in current budget and schedule or recommended for grey-box language
        NOGRRs 1, 2, 5
    Other Items in this Baseline
      NPRR 77
The Nodal projects are now well into Delivery mode
It is important that we address only essential changes
Changes put both schedule and budget at risk