|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for September 2007 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | ERCOT is currently tracking 195 active generation interconnection requests totaling over 83,000 MW. This includes over 35,000 MW of Wind Generation. |  |  |  |  |  |  |  |
| 2. | Regional Planning is currently reviewing proposed transmission improvements with a total cost of $24.8 M. |  |  |  |  |  |  |  |
| 3. | 2007 Jan-Aug CSC Utilization Report presented to WMS |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1.	New Generation Beginning Commercial Operations	1

1.2.	Active Generation Interconnection Requests	1

1.3.	Potential Future Generation Interconnections	2

2.	Regional Planning Group Project Reviews	3

3.	Congestion Management	4

4.	Other Notable Activities	4

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” data folder posted in the “Operations and System Planning” data area on the ERCOT website.

## New Generation Beginning Commercial Operations

- Post Oak Wind Farm in Shackelford County, 200 MW

## Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Currently tracking 182 active generation interconnection or change requests As of September 30, 2007 |  |  |  |  |  |
|  |  | North | South | West | Total |
| Security Screening Study |  | 8 | 4 | 14 | 26 |
| SSS Completed |  | 8 | 9 | 16 | 33 |
| Full Interconnect Study |  | 21 | 25 | 57 | 103 |
| FIS Completed |  | 0 | 2 | 2 | 4 |
| Interconnect Agreement Completed |  | 6 | 4 | 19 | 29 |
| Capacity for Grid, MW |  | 22,594 | 28,622 | 32,580 | 83,796 |
| Wind Capacity, MW |  | 2,068 | 3,608 | 29,835 | 35,511 |

| Fuel | Public (MW) | Non-public (MW) | Total (MW) |
| --- | --- | --- | --- |
| Natural gas | 3,185 | 22,340 | 25,525 |
| Nuclear | 5,986 | 6,400 | 12,386 |
| Coal | 4,761 | 5,188 | 9,949 |
| Wind | 8,916 | 26,595 | 35,511 |
| Other | 0 | 425 | 425 |
| Totals | 22,848 | 60,948 | 83,796 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter)

| FUTURE GENERATION INTERCONNECTIONS (PUBLIC PROJECTS) As of September 30, 2007 |
| --- |
| INR # | Site Name | Status | County | Region | Fuel | In Service Date | MW into Grid | Change from Last Report |
| 07INR0003 | Whirlwind 1 | IA | Floyd | West | Wind | Oct-07 | 60 |  |
| 06INR0021 | Barton Chapel | IA | Jack | North | Wind | Oct-07 | 120 |  |
| 07INR0045 | Airtricity Champion | IA | Scurry | West | Wind | Dec-07 | 126 | Signed IA |
| 07INR0028 | Goat Wind 1 | IA | Sterling | West | Wind | Dec-07 | 150 |  |
| 04INR0017 | Ocotillo Wind Farm 1 | IA | Howard | West | Wind | Dec-07 | 59 |  |
| 04INR0020 | Project Snyder | IA | Scurry | West | Wind | Dec-07 | 63 |  |
| 07INR0010 | Stanton Wind 1 | IA | Martin | West | Wind | Dec-07 | 101 |  |
| 03INR0034 | Silver Star 1 | IA | Erath | North | Wind | Dec-07 | 60 |  |
| 07INR0045 | Roscoe 1 | IA | Scurry | West | Wind | Mar-08 | 209 |  |
| 07INR0030 | Louis (Buffalo Gap 3) | IA | Nolan | West | Wind | Apr-08 | 138 |  |
| 06INR0035 | Colorado Bend 2 | IA | Wharton | South | Gas | May-08 | 275 |  |
| 06INR0036 | Quail Run 2 | IA | Ector | West | Gas | May-08 | 275 |  |
| 07INR0022 | Airtricity Panther Creek | IA | Howard | West | Wind | Jun-08 | 150 |  |
| 03INR0030 | Wild Horse 2 | IA | Cottle | West | Wind | Aug-08 | 39 |  |
| 07INR0045 | Airtricity Inadale | PL | Scurry | West | Wind | Oct-08 | 197 |  |
| 07INR0025 | Airtricity Lamesa | IA | Dawson | West | Wind | Oct-08 | 183 |  |
| 07INR0045 | Airtricity Pyron | PL | Scurry | West | Wind | Oct-08 | 249 |  |
| 07INR0037 | Bull Creek Wind Plant | IA | Borden | West | Wind | Oct-08 | 180 |  |
| 04INR0011 | Mesquite Wind 3 | IA | Shackelford | West | Wind | Nov-08 | 136 | Changed date |
| 04INR0011 | Mesquite Wind 4 | IA | Shackelford | West | Wind | Nov-08 | 100 | Changed date |
| 03INR0030 | Wild Horse 1 | IA | Cottle | West | Wind | Nov-08 | 60 |  |
| 08INR0059 | Gray Wind Project | PL | Borden | West | Wind | Dec-08 | 141 | Public letter |
| 05INR0015 | Gulf Wind 1 | IA | Kenedy | South | Wind | Dec-08 | 187 | Signed IA, change date and capacity |
| 07INR0011 | Turkey Track Energy Center | PL | Nolan | West | Wind | Dec-08 | 300 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Wind | Dec-08 | 120 | Signed IA |
| 08INR0018 | Gunsight Energy Center | PL | Howard | West | Wind | Dec-08 | 200 |  |
| 04INR0011 | Hackberry Wind Farm | IA | Shackelford | West | Wind | Dec-08 | 165 | Signed IA |
| 06INR0022 | Penascal Wind Farm 1 | IA | Kenedy | South | Wind | Dec-08 | 202 | Signed IA |
| 08INR0025 | Pistol Hill Energy Center | Pl | Ector | West | Wind | Dec-08 | 300 |  |
| 07INR0029 | South Trent Wind Farm | IA | Taylor | West | Wind | Dec-08 | 101 |  |
| 08INR0047 | Buffalo Gap 4 | PL | Nolan | West | Wind | Mar-09 | 378 | Public letter |
| 09INR0006 | Greenville | PL | Hunt | North | Gas | May-09 | 1750 |  |
| 08INR0040 | Wind Tex Energy Lenorah Wind Farm | PL | Martin | West | Wind | May-09 | 350 |  |
| 09INR0028 | V H Braunig 6 | PL | Bexar | South | Gas | May-09 | 185 |  |
| 09INR0060 | Wind Tex Energy Stephens Wind Farm | PL | Borden | West | Wind | May-09 | 141 |  |
| 09INR0025 | Sterling Energy Center | PL | Sterling | West | Wind | Jun-09 | 300 |  |
| 09INR0036 | McAdoo Energy Center | PL | Dickens | West | Wind | Jun-09 | 500 |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Coal | Jul-09 | 581 |  |
| 05INR0015 | Gulf Wind 2 | PL | Kenedy | South | Wind | Sep-09 | 400 |  |
| 09INR0015 | B&B Panhandle Wind | PL | Carson | West | Wind | Sep-09 | 1001 |  |
| 09INR0015 | Comanche Peak 1 & 2 Upgrade | PL | Somervell | North | Nuclear | Oct-09 | 86 |  |
| 09INR0006 | Oak Grove 1 | IA | Robertson | North | Coal | Nov-09 | 855 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Wind | Dec-09 | 200 |  |
| 7INR0004 | Pampa Energy Center | PL | Gray | West | Coal | Dec-09 | 165 |  |
| 09INR0037 | Camp Springs Energy Center III | PL | Scurry | West | Wind | Mar-10 | 350 |  |
| 09INR0006 | Oak Grove 2 | IA | Robertson | North | Coal | May-10 | 855 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Coal | Jun-10 | 750 |  |
| 05INR0015 | Gulf Wind 3 | PL | Kenedy | South | Wind | Sep-10 | 400 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Coal | Sep-10 | 925 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Wind | Dec-10 | 400 |  |
| 11INR0007 | Mountain Creek | PL | Dallas | North | Gas | Apr-11 | 700 |  |
| 11INR0001 | Twin Oaks 3 | PL | Robertson | North | Coal | Jun-11 | 630 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Wind | Jul-12 | 400 |  |
| 15INR0002 | Comanche Peak 3 & 4 | PL | Somervell | North | Nuclear | Jan-15 | 3200 |  |
| 15INR0008 | South Texas Project 3 & 4 | PL | Matagorda | South | Nuclear | Jan-15 | 2700 |  |
|  |  |  |  |  |  | Total | 22,848 |  |

# Regional Planning Group Project Reviews

- LCRA submitted a project to add a third 345/138 kV auto at Lytton Springs and upgrade related 138 kV lines.  This $20.4 M project in Caldwell and Hays counties has completed RPG review and an RPG Acceptance letter was issued to LCRA on September 17, 2007.

- Luminant has submitted two interrelated, yet independent projects for review.  The first project is an acceleration of the planned upgrade of the Tyler Northeast to Tyler East 138 kV line, currently planned to be complete in May 2012, to May 2009 with an estimated total project cost of $4 M.  The second related project is the addition of the Tyler Grande (Tyler Southeast) 345/138 kV autotransformer and an increase in the planned capacity of Tyler Grande (Southeast) to Tyler South from 326 MVA to 400 MVA.  The second project is planned to be complete in May 2009 with a cost of approximately $10 M and will require ERCOT Board approval due to the new 345/138 kV Tyler Grande switching station and associated autotransformer.

- Oncor submitted a project to rebuild the Big Spring – Chalk – McDonald Road 69 kV line.  This project will alleviate overloads due to new wind projects on the Morgan Creek to McDonald Road 138 kV circuit by adding a new 138 kV from Big Spring into McDonald Road on double circuit 138/69 kV structures that will replace the existing 69 kV single circuit structures.  The cost of the project is $10.8 M and due for completion in December 2008.

# Congestion Management

- 2007 January – August CSC Utilization Report:  For the details of the table below (intervals, flows / limits, costs and quantities) see Item 7 in Key Documents of the September WMS at the following link: http://www.ercot.com/calendar/2007/09/20070919-WMS.html

| ($Million) | E_N | N_H | S_H | S_N | N_W | W_N | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2007 total | -- | 23.3 | 4.7 | -0.3 | 2.4 | 1.2 | 31.3 |
| 2006: Q1-2+ | 7.4 | 5.8 | 13.1 | 1.2 | 3.0 | 0.1 | 30.6 |
| 2006 total | 7.4 | 8.4 | 31.4 | 1.5 | 3.0 | 0.2 | 52.0 |

Settlement quality data available through August 2007

# Other Notable Activities

- The Wind Impact/Ancillary Services study is continuing.  GE is working on Phase I of the study, which is a statistical analysis of the increased variability in net load (load minus wind generation) resulting from increased levels of wind generation on the ERCOT system.  GE is evaluating 4 scenarios of wind capacity on the system:  5,000 MW, 2 scenarios of 10,000 MW, and 15,000 MW.

- CREZ Study (SB20)

  - System Planning has started analyzing potential transmission solutions as part of the CREZ Transmission Optimization Study.  The Interim Order requesting this analysis was issued by the PUCT on October 2, 2007.

- 2007 Five Year Plan

  - Nearing the completion of the reliability phase for years 2010, 2011, and 2012.

  - Economic project identification phase is nearing completion for year 2012.

- The Generation Interconnection Request Procedure is being clarified as it relates to responsibilities associated with Power System Stabilizers.

- Prepared and submitted NERC Winter Assessment