## Slide 1: Texas Nodal Program Update
Jerry Sullivan, Executive Director

## Slide 2: Agenda
Item | Who | Purpose
Nodal Program Status | Jerry Sullivan | For Information
Nodal Schedule Update | Jerry Sullivan | For Information
ERCOT Readiness | Jerry Sullivan | For Information
Texas NODAL Market Readiness | Jerry Sullivan | For Information

## Slide 3: Overall Program Status Remains Amber
Cost
Schedule
Scope / Quality
Legend
Summary
Green
Additional costs (Integration, Release Management, MMS, BL 1 & 2, and Internal Allocation) exceeding existing contingency
Forecast is about $10 million over $263 million budget. Budget Reviews are being conducted to reduce costs.
Amber
Amber
Currently fully aligned with protocols.
Red
Amber
Green
Estimate at Complete = <$263m
Estimate at Complete = < $263m + 10%
Estimate at Complete = >$263m + 10%
Go-live = 12/1/08
Go-live = <30 days+
Go-live = >30 days+
Program is aligned with current protocols
Program is aligned to previous protocol version
Program is not aligned to protocols
Current EDS 1-3 milestones being achieved and are on track. On track to achieve near-term milestones.
EDS 4 milestones are still at risk due to MMS schedule.
Amber
Current product quality is not sufficient for Nodal launch
Most Nodal products currently achieve quality standards
All Nodal products currently achieve quality standards
Significant design issues still open with MMS solution.
100% Success Rate in EDS3 R5 “SCED Testing”
QA plans for EMS, MMS, OS in for review
Scope/
Quality
Schedule
Cost
Nodal
Delivery

## Slide 4: Tactical deliverables and actions
# | Topic | Solution/Action
1 | MMS | Working with vendor to improve confidence in MMS schedule deliveries; EDS 4 still at risk. All design issues for the 11/30/07 release have been addressed with vendor; approximately 50 open design issues still being negotiated. Commercial implications still pending for remaining MMS deliverables; 10/31/07 planned completion. Third iteration of mutual detailed plan to be delivered this week for review and validation by ERCOT. Working with other Nodal teams to ensure EDS 4 can start on schedule (early involvement from integration and testing)
2 | EDS 1 Start: 6/4/07 End: Revised to 10/15/07 for 99% Revised to 11/15/07 for 100% | Confidence in achieving the milestone is High: 95% complete with P2P, with 4% error rate. All QSEs will be completed and tested by 10/1/07, except for Austin Energy (currently upgrading their EMS). Expect to regression test quality code correction with MPs in early October. Local ICCP Fail-over scheduled for this week and next.
3 | EDS 2 State Estimator and Telemetry Start: 9/4 End: 12/31/07 | EDS 2 R 3, SE tuning activities started on 9/7 as planned. TAP estimation to be reconfigured / software corrected by end of EDS 2 Release 3. Help required in State Estimator Tuning; drafting a SOW for AREVA resource to help. 50% of QSEs ICCP feeds to Nodal are not active; working with QSEs one-on-one to resolve issues by 10/1/07.
4 | EDS 3 EMS interfacing with SCED Start: 8/24/07 End: 7/15/08 | Confidence in achieving the milestone (11/1) is Medium (EMS to MMS). Cross functional project team working to complete build and conduct end to end testing – progress being made via concentrated team. Delivery of SCED reports, confidence is medium for 11/1/07 – MIS team working with EMS, MMS and EIP to ensure delivery of reports. Working toward early environment shakeout to improve confidence. Developed consolidated list of data elements, assigning responsible parties for delivery (Network Model, Registration, EMS, MMS); will probably require ongoing effort to finalize data. Investigating functionality to support ICCP handbook – ERCOT to QSEs (Hub and Zone LMPs).
5 | EDS2 R4 NMMS NOMCR Start: 11/1/07 End: 3/31/08 | Confidence in achieving the milestone is Medium, with known challenges (data reconciliation and validation, AREVA load capabilities, MP availability). Phase 1c delivery at end of September 2007 being pushed to Mid-October; Defining testing approach to leverage system functionality in the order it’s delivered. EDS Hardware for NMMS purchased, ready 10/1/07.
Scope/
Quality
Schedule
Cost5
Nodal
Delivery

## Slide 5: Readiness Reporting Concepts
ERCOT will report several readiness metrics
  Mid-September kick-off with ERCOT officers.
  Now analyzing ERCOT readiness self-reporting survey results.
  Along with the regular Nodal Delivery Status, ERCOT will report on Market and ERCOT readiness to TPTF, TAC, and the BoD on a monthly basis.
Market Participants will:
  Have a view of upcoming metrics well in advance of reporting.
  Receive advance notice of any “RED” metrics from the NODAL team in advance of reporting to BoD.
  Receive help from the NODAL team to achieve “GREEN” readiness status.

## Slide 6: The Readiness Map Shows Metrics Overlaid Across the Nodal Delivery Chart
POCs: Chris Wilkinson, 512 248 4214 Primary
Tim Pare, 512 248 6367 Alternate

## Slide 7
Readiness Metrics: Key Events and Milestones
Iteration 1
TPTF Approval
Iteration 1
TAC Approval
Iteration 1
PROD Release
Iteration 2
TPTF Review
Iteration 2
TPTF Approval
Iteration 2
TAC Approval
Iteration 2
PROD Release
Iteration 3
TPTF Review
Iteration 3
TPTF Approval
Iteration 3
TAC Approval


Completed
Within 30 days of planned milestone date
On schedule
More than 30 days from planned milestone
√
Milestone Complete






As of 9/28/2007
Market Readiness capability progressing against plan. Actively monitoring 13 metrics with another 7 on-line by end of year
Key Events |  |  |  |  | 
Release | Metrics | TPTF Review | TPTF Approval | TAC Approval | Available in Scorecard
Iteration 1 | MP1 | 7/23/2007 | 7/23/2007 | 8/2/2007 | 8/27/2007
Iteration 2 | MP2, MP3, MP5, MP11, MP13, E1, E6, E8, E9, N1 | 8/13/2007 | 8/27 – 8/29/2007 | 9/6/2007 | End September 2007
Iteration 3 | MP6, E3, E5, EMO9, N2, N3, MO4, MO5, MP12 | 9/10 – 9/11/2007 | 9/24 – 9/26/2007 | 10/5/2007 | TBD ~End November 2007
Milestones

## Slide 8: Market Readiness Update – Scorecard
Scorecard.ercot.com
Accountable Executive login available from ERCOT Client Service
Additional metrics available this week
Available drill-downs to Market Participant-specific data

## Slide 9
Market Readiness – 3 Month Planning Horizon
Delivery and Readiness metrics rolling into Readiness Scorecard.
Market Participant Engagement results available now on NODAL.ERCOT.com
 | NODAL Delivery | ERCOT Readiness | Market Participant Readiness
Currently Measuring | Telemetry Alarm Processing Telemetry / ICCP System Failover | ERCOT Training (EDS 1 & 2) Develop NODAL Operating Guides ERCOT Staffed for NODAL operations Procedure Development | Market Participant Engagement Connectivity to EDS Environment QSEs with Resources Upload SCED to EDS ICCP Point to Point Telemetry Test QSE and TSP Telemetry / ICCP System Availability Registration Activities
October | SCED Execution | ERCOT Training (EDS 3) | EDS2 Market Trials Participation Market Participant Engagement (2nd survey)
December | SCED Quality Validate Security Analysis Results State Estimator Performance and Accuracy |  | EDS3-Related Market Participant Training

## Slide 10
Market Readiness – 3 Month Planning Horizon
EDS1-related metrics for Telemetry and ICCP measuring GREEN
Input | ERCOT personnel NODAL Delivery Teams TPTF
Measured By | EDS Project Managers and Market Readiness Team using “Red / Amber / Green” rules as defined in metric
Scorecard Availability | Telemetry and ICCP metrics available in October
NODAL Delivery | 
Currently Measuring | Telemetry Alarm Processing Telemetry / ICCP System Failover
October | SCED Execution
December | SCED Quality Validate Security Analysis Results State Estimator Performance and Accuracy

## Slide 11
Market Readiness – 3 Month Planning Horizon
New ERCOT Engagement metric parallels Market Participant Engagement metric
ERCOT Readiness | 
Currently Measuring | ERCOT Training (EDS 1 & 2) Develop NODAL Operating Guides ERCOT Staffed for NODAL operations Procedure Development
October | ERCOT Training (EDS 3)
December | 
Input | TPTF ERCOT Readiness Team (ERT)
Measured By | ERT and Market Readiness Team using “Red / Amber / Green” rules as defined in metric
Scorecard Availability | Current ERCOT Readiness metrics available in October

## Slide 12
Market Readiness – 3 Month Planning Horizon
Five of six Market Participant metrics GREEN. YELLOW Engagement metric measured again in October
Market Participant Readiness | 
Currently Measuring | Market Participant Engagement Connectivity to EDS Environment QSEs with Resources Upload SCED to EDS ICCP Point to Point Telemetry Test QSE and TSP Telemetry / ICCP System Availability Registration Activities
October | EDS2 Market Trials Participation Market Participant Engagement (2nd Survey)
December | EDS3-Related Market Participant Training
Input | TPTF ERCOTClient Services NODAL Delivery Teams
Measured By | ERCOT Client Services and Market Readiness Team using “Red / Amber / Green” rules as defined in metric
Scorecard Availability | Market Participant engagement currently reported in Scorecard Others will follow in October