## Slide 1: RO Projects Financial Overview Retail Market Subcommittee October 10, 2007 Justin Rasberry Market Operations Division Projects Organization

## Slide 2: 2007 RO PPL
Unplanned 2006
Carry-over Projects
(Green Shaded Area)
Projects ABOVE the
current Capability Line
(Orange Shaded Area)
Projects BELOW the
current Capability Line
(Yellow Shaded Area)

## Slide 3: Unplanned 2006 Carry-Over Projects
PR-60006_01 Moved back into execution to ensure successful delivery.
  This projects remaining forecast will be funded via MORO portfolio variance

## Slide 4: Projects ABOVE the Capability Line
No Status Change on these projects
Notes: 50061_01 Moved to ON Hold: Freed up approx. $120k, however not recommended for release by CART

## Slide 5: Projects BELOW the Capability Line
No status change on these projects
Notes: ERCOT will continue to evaluate the projects under the line to determine if we can move anything up. Currently the items just below the line are funded with the 2008 PPL

## Slide 6: Financial Overview as of 8/31/2007
DPO fully expects that we may see the variance rise as we continue throughout 2007 and get better accuracy with projects gating from Initiation to Planning and from Planning to Execution
RO PPL Budget Activity | Amount | Notes/comments
Approved RO Capability Line Budget Funding | $4.88M | Current approved RO funding allocation Designates where the capability line falls Updated $5.17 budget to $4.88 to reflect accurate funding
Current Forecast Spend of projects above the Capability Line | $3.11M | Based on current expectations and run rates for active and not started projects above the capability line Budget range of $3M – $4M
Budget Variance | ~$1.77M | Budget Variance is difference between RO Capability Line Budget Funding and Current Forecast Spend of projects above the Capability Line $273k resulting from projects running under budget $2.05M due to amounts forecasted into 2008 for current projects -$287k resulting from project budget corrections -$270k resulting from taking PR-60006_01 back to execution

## Slide 7: Budget Variance Allocation
Below is the updated view of under spend categories. These categories will be monitored throughout the year to assess potential reallocations.
RO Released
Approx. $1.1M
MO/RO Budget Variance
2007; $ thousand
$1617
$650
$207
RO Total = $1270
No Concerns
Should be monitored
Should not Release
RO Total = $371
RO Total = $122
CART, COPS, and RMS have all reviewed the MO-RO portfolio and acknowledged the release of $1.3M from the overall portfolio budget variance of approx. $2.5M.
Note: Previously $2.9 however newly approved projects reduced to $2.5

## Slide 8: Questions / Contact
Justin Rasberry
Manager, MO DPO
Market Operations Divisional Projects Organization
ERCOT
(512) 248-3991
jrasberry@ercot.com