EDS 3

SCED Market Participant Handbook

v2.0

Thursday, September 27, 2007

Revision History

| Document Revisions |  |  |  |
| --- | --- | --- | --- |
| Date | Version | Description | Author(s) |
| 5/23 | 0.1 | Draft document created for EDS 3 SCED Planning Workshop w/ Market Participants. This version is a working draft for planning discussion with Participants. | IRT |
| 6/1 | 0.02 | Restructured TOC & added consistent sub areas for each phase for improved flow. Updates to many sections for clarity based on internal review and EDS 3 SCED Planning Workshop. Added more detail from IRT continued planning. | IRT |
| 6/7 | 0.03 | Detailed Phase 1 of SCED Testing for WebEx and feedback from MPs by Wednesday, June 13th latest. | IRT |
| 6/12 | 0.04 | Detailed Phase 1 of SCED Testing for WebEx on Thursday, June 14th. | IRT |
| 6/15 | 0.90 | Provided clarity on Phase 1 sections based on comments from ERCOT SMEs and MP feedback. Submission for TPTF approval | IRT |
| 6/22 | .091 | Updated document w/ TPTF review comments from NRG | IRT |
| 6/26 | 1.0 | Updated per TPTF Approval of Section 1, 2, 3 on June 27th 2007, the document was updated through end of Phase 1 with Approved / Rejected changes and clarifications based on TPTF process. | IRT |
| 6/27 | 1.01 | Continued work on updating Phase 2. Included scenarios documentation and details started in internal working sessions. | EDS Team |
| 7/09 | 1.02 | Updated Phase 2 to include draft SCED Scenarios descriptions based on workshop feedback. Updated some details on Phase 1 and Phase 2. Scenario details added to appendix. | EDS Team |
| 8/30 | 1.03 | Updated Phase 2 based on TPTF presentation (8/28) and new plan for synchronizing RARF, Curves, and ICCP data required for Integrated EMS/MMS EDS environment. Update Phase 3 with more details. Removed Appendix C – Testing Scenarios | EDS Team |
| 9/20 | 1.04 | Revised to include comments received from TPTF | EDS Team |
| 9/27 | 2.0 | All revisions accepted based on TPTF Approval | EDS Team |

Approval History

| Document Sections Approved by TPTF |  |  |
| --- | --- | --- |
| Date | Section(s) | Description |
| 6/26 | 1, 2, 3 | Received TPTF approval for sections 1, 2, 3 of the SCED MP Handbook v0.91. All tracked changes in these sections were approved and TPTF comments included for version 1.0. (other than this approval history table added in version 1.02). Going forward any changes to sections 1,2,3 will have changes tracked for TPTF review in future updates of the document. |
| 9/27 | 1,2,3,4 | Accepted all revisions in version 1.04 after ‘Motion to approve EDS 3 SCED MP Handbook v1.04 with updates as submitted by EDS on September 25, 2007’ carried |

Table of Contents

1	Introduction	5

1.1	Market Participant Handbook	6

1.2	Document Structure	7

2	Release Overview	8

2.1	Early Deliveries	8

2.2	Nodal Sandbox	9

2.3	Supporting Documents	9

3	SCED R5.1 - Input Data Submittal and Validation	10

3.1	Phase Overview	10

3.2	EDS Testing Activities	13

3.3	Market Participant Involvement	16

4	SCED R5.2 – Nodal Registration Data Updates	18

4.1	Release Overview	18

4.2	EDS Activities	24

4.3	Market Participant Involvement	24

5	SCED R5.3 - Integrated SCED Execution (RT ICCP)	25

5.1	Phase Overview	25

5.2	EDS Activities	29

5.3	Market Participant Involvement	29

6	SCED R5.4 - Six Month LMP Posting	31

6.1	Phase Overview	31

6.2	EDS Activities	32

6.3	Market Participant Involvement	33

7	EDS Communications	35

7.1	EDS Planning Workshops	35

7.2	Online Readiness Center	35

7.3	EDS Kickoff Session	35

7.4	EDS Weekly Conference Calls	35

7.5	Weekly Status Bulletin	36

7.6	Issue Tracking Process	36

7.7	Entry / Exit Criteria	36

8	Appendix A	37

NOTE: Removed Sample XML from document to avoid confusion. Please see Readiness Center on the Nodal Website.	37

9	Appendix B	37

9.1	Issue Submission Lifecycle	37

9.2	Draft Issue Submission Form	38

- Introduction

The ERCOT Nodal Transition Plan, approved by the Technical Advisory Committee (TAC), organizes transition activities into four tracks, which required participation from both ERCOT and market participants. The Texas Nodal Program defined four Early Delivery Systems (EDS) sequences to meet the requirements of the Systems Testing and Nodal Market Implementation track of the Transition Plan. These sequences were further refined based on the Nodal project delivery schedules to group Nodal functionality and features into nine incremental software releases that will be used to meet the requirements outlined in the Nodal Transition Plan.

The EDS sequences and releases are outlined below:

EDS 1

- Release 1  –  Alarm Processing

- Release 2  –  Point-to-Point Checkout

EDS 2

- Release 3  –  Trial Operation of State Estimator & Network Security Analysis

- Release 4  –  Trial Operation of NMMS (Network Model Validation)

EDS 3

- Release 5  –  Trial Operation of SCED, 6 month LMP posting	  (SCED MP Handbook)

  - R5.1 – Input Data Submittal and Validation

  - R5.2 – Nodal Registration Data Updates

  - R5.3 – Integrated SCED Execution (RT ICCP)

  - R5.4 – Six Month LMP Posting

- Release 6  –  Trial Operation of LFC, ACE

- Release 7  –  Trial Operation of CRR, sample Settlement Statements

EDS 4

- Release 8  –  Trial Operation of RT Settlements (No Extracts)

- Release 9  –  Trial Operation of DAM, RUC, SASM, Full Settlements, EDW Extracts

- TXMACS 1.0  –  Full Nodal Functionality & 168 hour testing

The Nodal program has adopted an incremental approach for releasing functionality into the EDS environment to maximize the overall benefit of EDS, by providing system functionality to the Market Participants to begin testing as early as possible. The objective of these early deliveries is to provide MPs with sufficient tools to enable development of their systems.  The EDS environment will be updated incrementally as soon as a set of Nodal functionality has been tested internally by ERCOT.  Once the integrated set of system functionality has completed the internal ERCOT quality control testing, the EDS environment will be updated for formal milestone testing activities. This incremental approach is diagramed below:

## Market Participant Handbook

The Market Participant Handbook has been created to provide a detailed testing guide for participation in the Early Delivery System (EDS) activities. The Handbooks are one of the guiding documents to help Market Participants understand how to prepare, participate and when to engage in EDS. This Handbook will cover the details for Release 5 – Trial Operation of SCED, 6 month LMP Posting.

The testing areas described in this document will be guided by the Nodal Transition Plan and the Nodal delivery schedule; however, the detailed testing activities and schedule will be completed by working collaboratively with ERCOT subject matter experts and Market Participant representatives.

The Early Delivery Systems are intended to:

- Provide Market Participants with the tools to complete development and testing of updated Nodal systems in as realistic environment as possible.

- Validate Nodal functionality and timelines including Day-Ahead, Adjustment Period and Real-Time activities for ERCOT, Transmission Service Providers (TSPs) and Market Participants (MPs).

- Build stakeholder confidence that Nodal design and systems adhere to Nodal Protocols and Nodal Transition Plan requirements.

- Generate Locational Marginal Prices (LMPs) for distribution to ERCOT Market Participants for at least six months prior to the Nodal Markets going live.

- Confirm through a series of structured and unstructured testing that

"stable and accurate operation of the SCADA, Network Security Analysis, Transmission Constraint Management, SCED, LFC, DAM, RUC, and real time settlement system can be declared"

## Document Structure

It is critical that all participants have a common understanding of EDS activities, start dates, and participation expectations. This document will cover the following topics to ensure that both ERCOT and Market Participants are ready for each EDS phase.

Release Overview – This section outlines the specific phases, objectives, and supporting documents for the EDS Release 5 – Trail Operation of SCED, 6 month LMP Posting.

For Each Phase

- EDS Phase Overview

  - EDS Environment

  - Testing Schedule

  - Functionality Available (Available Interfaces, Validation, Functionality, Data)

- EDS Testing Activities

  - Testing Structure (Required vs. Optional Involvement, Structured vs. Unstructured Testing, …)

  - Test Scenarios and Scripts

  - Test Data

- Market Participant Involvement

  - Target Roles

  - Preparation Activities (Data, Digital Certificates, Workshop involvement, New Data, Training)

  - Ongoing involvement (What activities, how often, expectations)

  - System Readiness ( MP EDS, Tools, Capabilities )

# Release Overview

For EDS 3, SCED will be the first business functionality to be released to the EDS environment. The release procedure will follow the ERCOT release mechanism described earlier in this document. The initial system delivery will provide QSEs the opportunity to submit, modify, cancel, and retrieve input data and receive validation results required for SCED execution. During the release, the EDS environment will be incrementally upgraded to provide the functionality for SCED execution, distribution of Base Points and LMPs, utilization of Real-Time ICCP data, and SCED reporting.

## Early Deliveries

The Trial Operations of SCED will be executed in several phases, incrementally adding interfaces and functionality until a fully integrated and internally tested product is released to the EDS environment The Early Delivery System approach will allow ERCOT and Market Participants to begin Market testing as early as practical.

The following objectives have been defined:

R5.1 - Input Data Submittal and Validation

- Provide a SCED environment for Market Participant EDS Activities

- Verify QSEs ability to use  Web Service interfaces to submit, modify, cancel, and retrieve three part offers, COP, and output schedules

- Use stub Resource Registration data

- Verify QSEs understanding of SCED input validation rules

- Use  both the User Interface and Web Services interfaces for SCED inputs

R5.2 -  Nodal Registration Data Updates

- Review Resource Asset Registration data and upload into EDS for Generation Resources

- Provide feedback to Market Participants on RARF issues, naming standards, Nodal changes for upload into test systems.

- Establish initial test data for specific Network Model components

- Provide EDS base data back to Market Participants for upload into systems for EDS testing

- Setup predefined Offer Curves for testing

- Ensure QSEs can submit submission items for all Resources on a daily basis

- Correct any registration and curve data to finalize a baseline set of input data

- Begin SCED execution with a full set of MP input data

R5.3 - Integrated SCED Execution (RT ICCP)

- Use RT Telemetry data

- Use SCED Market Participant Offer Methodology (align with RT operations)

- Verify SCED inputs from real-time operations

- Verify QSE ability to receive correct Resource Base Points and LMPs via ICCP

- Review SCED produced Base Points, LMPs and SPPs for reasonability (including the LMPs for Hubs and Load Zones)

- For QSEs under test, allow Offers through API or UI (according to methodology - TBD)

- Execute SCED and distribute test output to the QSEs participating in EDS

- Review SCED output data

R5.4 - Six Month LMP Posting

- LMP reasonability attainment verified

- Publish LMPs and other data available as required in the Nodal Protocols

- Use SCED Market Participant Offer Methodology (align with Zonal operations)

- Begin six months of SCED execution and LMP posting period as required by the Nodal Transition Plan

REMOVED OUT OF DATE TABLE

## Nodal Sandbox

The Nodal Sandbox is a Pre-Early Delivery Systems (EDS) Environment for development and testing of interfaces between Market Participants and ERCOT. This environment provides the tools for QSEs to interface with the Web Services architecture prior to delivery of the core EDS systems. This environment is not intended for application functionality, stress, stability, or full production verification.  All of the services on the Sandbox will use the same XML structures and functions that will be deployed to the EDS but have loop back functionality to provide correct XML responses but do not interact with back-end ERCOT applications. Target delivery timelines are outlined in each phase below.

ERCOT highly recommends Market Participants use the Nodal Sandbox, prior to EDS testing, to validate connectivity, understanding of specific web services, and technical architecture.

## Supporting Documents

The following documentation should be reviewed for a better understanding of the overall EDS 3 Approach, Market System Requirements and Validation, and Web Services Architecture.

| Reference: Nodal Website | Description | Version |
| --- | --- | --- |
| EDS 3 Approach | EDS 3 Approach document | 1.0 |
| MMS SCED Requirements | Market Management Systems (MMS) Requirement Specification For SCED and Real-Time MMS Processes | 1.0.0 |
| MMS DA Requirements | Market Management Systems (MMS) Requirement Specification for Day-Ahead Market (DAM) and Supplemental Ancillary Service Market (SASM) | 1.0.0 |
| MMS Overall Requirements | MMS Requirements Specification for Overall MMS System and Other Processes | 1.0 |
| Market Participant Submission Items | Market Management Systems (MMS) Explanation of Market Submission Items | 0.1 |
| Machine to Machine Interfaces | Intro/Background External Interfaces Specification | 1.02 |

# SCED R5.1 - Input Data Submittal and Validation

## Phase Overview

EDS Environment

* Note: Only the colored components will be tested during this phase.

During the Input Data Submittal and Validation release, the EDS environment will be upgraded to include a stand alone SCED environment and the External Web Service infrastructure to support data submittal into the SCED system for validation. Market Participants planning on utilizing the External Web Services for communicating with Nodal Systems and who have progressed past the capabilities of the Nodal Sandbox will be able to request access to the EDS environment and signup for support workshops to test interconnectivity with SCED. QSEs who would like to test the MP User Interface will be able to sign up for testing workshops.  The diagram above highlights the components that will be tested during this phase.

The applications deployed for this phase of testing will be installed on Testing hardware rather than Production hardware. These systems are not intended to perform to production standards at this point during the EDS testing; therefore the number of QSEs with access to these environments will be managed by the testing calendar.

The EDS systems will be available and supported according to the Service Level Agreements for EDS 3 approved by TPTF. Any impact on testing schedules will be reflected in the EDS testing calendar and communicated to Market Participants.

Note:  The MMS team is currently working with Vendor to implement changes to COP Validation rules to provide a warning message as opposed to rejection.  These changes are not implemented in the current release.

EDS Testing Schedule

The Input Data Submission and Validation release is targeted to take place during August and September 2007. During this two month period the EDS environment will be available for QSEs who have moved past the loop back capabilities of the Nodal Sandbox and want to begin testing backend validation capabilities. The EDS team will provide a schedule of testing support calls (2 hours each) that will kick off an open testing window (7 calendar days) where QSEs will have access to the EDS environment. QSEs will be able to sign up for the support on a first come first serve basis.

The diagram below shows a typical EDS testing week:

- Monday Conference Call - Used to communicate with all EDS participants on

  - EDS activities planned for the week

  - Updates to online support documents & tools

  - Resolved issues or environment updates

- Mid Week Support Calls - The EDS support team will have support calls slots for each day Tuesday, Wednesday, and Thursday that Individual QSEs will have the opportunity to signup for support from ERCOT Subject Matter Experts to walk through EDS testing activities or work on individual QSE integration issues. A detailed calendar of EDS workshops will be available on the Nodal Website.

- Friday Conference Call - Used to communicate with all EDS participants on

  - EDS activities accomplished during the week

  - Updates to online support documents and tools

  - Identified software or environment updates

During the support calls QSEs will use Market Participant Input Data Interfaces (User Interface, Web Services) to upload and retrieve the following submission items required for SCED execution.

- Three-Part Offers (Energy Curve component; including FIP & FOP)

- Current Operating Plan (COP)

- Output Schedule

- Incremental and Decremental Offer Curves (DSR)

EDS Functionality

This section outlines the system interfaces, web services, and requirements functionality that will be tested for this phase:

MMS SCED User Interface

The following MMS User Interface screens will be available for Market Participant testing:

- COP Display

- Three-Part Energy Offer Display

- Output Schedule Display

- Incremental, Decremental Offer Curve Display

Note: Web Service data inputs can be viewed via the SCED User Interface.

External Web Services

During this testing phase, the priority 1 External Web Services outlined below will be incrementally deployed into the EDS environment as the back-end integration and internal testing is complete.  All of the priority 1 Web Services will be available as stubs in the Nodal Sandbox environment prior to EDS.

Priority 1 - External Web Services Availability (SCED)

| Submission Type | Imp Group | Sandbox Target | EDS 3 Target |
| --- | --- | --- | --- |
| Offers |  |  |  |
| Three-Part Supply Offer (Energy) | 1 | Jul 07 | Aug 07* |
| Inc/Dec Energy Offer | 1 | Jul 07 | Aug 07 |
| Schedules |  |  |  |
| Output Schedule (incl. DSR) | 1 | July 07 | Aug 07 |
| Other Market Interfaces |  |  |  |
| COP | 1 | July 07 | Aug 07 |
| Other Web Service Components |  |  |  |
| Offer and Bid Set Acceptance | 1 | July 07 | Aug 07* |
| Offer and Bid Set Error | 1 | July 07 | Aug 07 |
| Get MRID | 1 | July 07 | Aug 07 |
| System Status | 1 | July 07 | Aug 07 |

Note: Some of the required fields in the Web Services interface specifications may not apply to the early SCED testing, however, stub data will need to be used to ensure that the Web Services can be successfully submitted. Supporting details are located at: http://nodal.ercot.com/readiness/eds3/documents/index.html in EDS 3 - Phase 1 Test Package zip file

Market Management System Functionality (SCED)

The initial EDS environment will provide Market Participants the capability to submit input data prior to the Operating Day and during the Adjustment Period. The tables below describe the capabilities and requirement coverage of the initial MMS system to support input data validation. The requirements documentation and specific details can be found on the Nodal Website.

Pre-DAM Activities

| Req | Req Specification Name | Description |
| --- | --- | --- |
| PD2 | QSE Submittal of COP, Bids, Offers, and Trades | Partial - Only for COP, Output Schedules, Three-part offers and Inc-Dec Offers |
| PD3 | General Validation Process of QSE Input | Partial - No Credit Limit validation; no Phase 2 validation |

Validation of DAM Submissions and Other Trades

| Req | Req Specification Name | Description |
| --- | --- | --- |
| VA10 | Validation of Three-Part Supply Offer - Start-Up and Minimum-Energy Offer and Energy Offer Curve | Partial - Energy Curves Only |
| VA13 | Notice of Validation Rules | Partial |
| VA14 | Validation of COP |  |

Adjustment Period QSE Input Data Validation

| Req | Req Specification Name | Description |
| --- | --- | --- |
| FR1 | Adjustment Period QSE Data Submission | Partial - COP; Energy Offer Curves; Output Schedule (non DSR); Inc/Dec Offers (DSR) |
| FR2 | DSR Output Schedule Submission | Full - |
| FR78 | Energy Offer Curve Submission and Modification | Partial - |
| FR79 | Energy Offer Curve Withdrawal | Partial |
| FR4 | Energy Offer Curve Validation | Full |
| FR4-1 | Percentage of FIP and Percentage of FOP | Full |
| FR5 | Mitigated Offer Cap and Floor Calculation Process | Partial |
| FR6 | Energy Offer Curve and Output Schedule for RMR Resource | Partial |
| FR7 | Output Schedule Validation | Partial |
| FR8 | Output Schedule Validation at Submission | Full |
| FR10 | Output Schedule Notification Two Hour Ahead | Full |
| FR10-1 | Output Schedule Validation at the End of Adjustment Period | Full |
| FR12 | Additional Incremental/Decremental Energy Offer Validation | Full |

## EDS Testing Activities

The early testing of SCED input data validation will provide the opportunity to test a subset of the system functionality and validation components. Specific Market Participant submission testing activities will be defined during the EDS planning workshops and included in this Handbook.

Testing Structure

The Input Data Submittal and Validation Phase has been defined as “Highly Recommended” activities for Market Participants prior to the formal start of EDS 3. However, those participants that are not able to perform these activities prior to October will still be required to perform them as entry criteria into the next phase.

This phase will be a Structured Test where Market Participants will be limited in the types of activities and inputs that can be performed. The Structured Testing will be conducted by providing support workshops where EDS team members will be available over a conference bridge to support MP while they complete the SCED submission activities. Participants will also have access to the EDS systems during a defined testing period to independently complete any of the defined testing activities.

Participating QSEs will be required to perform the following test scenarios at least once, before proceeding to conduct unstructured testing based on QSE’s own offer strategy.

Test Scenarios and Scripts

During this EDS phase, the test scenarios will be defined based on the Market System submission types and validation rules described in the MMS requirements specifications and Market Participant submission items support document posted on the Nodal website.

Below is the list of QSE submission activities (based on the requirements currently implemented in the MMS software):

MMS User Interface / External Web Services

Current Operating Plan - COP Display / COP

- Verify each QSE can Submit, Update and Query a COP using COP UI and External Web Services

- Receive valid Transaction Identifier / mRID for both Valid and Invalid transactions

- Reject COP with corresponding error message(s) if at least one of the following conditions is not met:

  - Resource name must be a valid registered Resource name

  - Resource Status must be a valid status code (Currently there are no validations for specific load or generation statuses. The system only validates for an acceptable Status)

  - HSL must be less than or equal to High Reasonability Limit

  - LSL must be greater than or equal to Low Reasonability Limit

  - HEL must be greater than or equal to HSL

  - LEL must be less than or equal to LSL

  - HSL must be greater than or equal to the sum of (Reg Up Resource Responsibility + Responsive Reserve Resource Responsibility + Non-Spin Resource Responsibility +LSL)  * Note: Need to validate calculation and if Reg- Down Resource Responsibility is required for this validation.

  - COP is submitted for an invalid time period (e.g. in the past)

- Issue corresponding warning(s) if at least one of the following conditions is not met:

  - A Resource with a Resource Status of ONTEST must have a corresponding valid Output Schedule

  - For combined-cycle Resources, the COP data items must be submitted for each registered configuration

Three-Part Energy Offer Display / Three Part Supply Offer

- Submit, Update, Query, Cancel

- Cancel w/ valid Output Schedule

- Submit w/ specific Expiration Date/Time

- Validate overwriting behavior of Energy Offer Curve

- Reject if FIP% and FOP% incorrect (Resource type dependent)

- Receive valid Transaction Identifier / mRID

- Rejection due to invalid Energy Offer Curve (must be monotonically non-decreasing and all prices within applicable caps/floors, last MW point must be >= 1 MW, no more than 10 price/quantity pairs, )

- Review all results

Output Schedule Display / Output Schedule

- Submit, Update, Query (DSR/Non-DSR)

- Rejection due to valid Energy Offer Curve

- Receive valid Transaction Identifier / mRID

- Rejection due to no COP (This feature may change as indicated earlier in the document)

- Rejection when MW level is not between LSL & HSL of COP (This feature may change as indicated earlier in the document)

- Rejection due to violation of SCED Up/Down ramp rates calculated based on COP data.

- Market window

- Review results

Incremental, Decremental Offer Curve Display  /  Inc/Dec Energy Offer

- Submit, Update, Query, Cancel (DSR)

- Receive Transaction identifier / mRID

- Rejection if first pq quantity is not 0 MW

- Must be monotonically increasing for Inc and monotonically decreasing for DEC

- Market window

- Review results

QSE Notifications / Notices and Alerts (Avail in Phase 2)

- Notification for SCED related items only

Other Web Service Components

Acceptance / Error Notification

- Receive Offer and Bid Set Acceptance

- Receive Offer and Bid Set Error

To support the MMS User Interface testing, ERCOT will provide Market Participants with documented test scripts that will provide step-by-step instructions for performing the required submission activities. These test scripts will show all steps by role that need to be performed by both ERCOT and MPs

Test Data

For the structured testing, ERCOT shall provide Market Participants with sample data and templates for each of the following inputs. These samples are being provided to enable QSEs to create their own test data. The sample data to support specific submission items will be distributed prior to this release. Generic examples of the current specifications can be found in Appendix A,

- COP

- Three Part Offer

- Output Schedule

- Inc / Dec Curve

New Nodal Resource Data - To support the testing activities the EDS team will provide QSEs with new Nodal test data currently in the MMS system for the Generation Resources that will be tested. MPs will have the opportunity to provide updates prior to EDS testing.

Listed below are some of the new data fields required for SCED Validation:

| New Nodal Resource Parameters | Comments |
| --- | --- |
| Normal Ramp Rate Curve |  |
| Emergency Ramp Rate Curve |  |
| High Reasonability Limit | Not available, but have other limits that can approximate |
| Low Reasonability Limit | Not available, but have other limits that can approximate |
| QSEs qualified by ERCOT to have DSR |  |
| CC Plant and configuration mapping |  |
| TBD (more to be identified) |  |

Additional data fields required from MPs will be identified prior to requesting from QSEs. Other required data such as FIP, FOP and Network Model will be simulated or stubbed into SCED.

## Market Participant Involvement

Target Roles

The activities and functionality being tested in EDS 3 are relevant to the following groups:

QSEs with Resources:  SCED Input Data Submissions

ERCOT:  offer receipt, external interfaces and integration, data processing and
 		validations

Preparation Activities

The EDS SCED Input Data Submission and Validation interfaces will be available for all Market Participants to begin validation and testing of internal systems to ensure Go-Live readiness in December 2008.  Participation during this phase of is highly recommended for all QSEs.

There is a limited set of activities that should be completed at least once to ensure: connectivity, ability to submit inputs, and ability to receive outputs. These include

- Signing up for EDS testing activities.  ERCOT will post the SCED testing sign-up sheet on the Nodal Readiness center 2 weeks prior to the start of the release.  A communication will be sent to the Market Participants once the sign up calendar has been posted.

- Obtaining digital certificates

- Connecting to the Nodal Sandbox to test the External Web Services

- Schedule time to familiarize with SCED UI

The EDS test team realizes that the project schedules for each of the Market Participants will vary.  To ensure that everyone is aware of the latest updates on the EDS we recommend attending conference calls at least once a week and checking the Readiness Center for EDS 3 documentation updates during the entire period.

There is no specific training required for Market Participants prior to start of this release.  ERCOT shall conduct the necessary training and demos with QSEs individually during this release.  In addition, ERCOT will be circulating a SCED User Interface Manual to ensure that Market Participants familiarize themselves with the SCED system. MPs should check the Readiness Center for the latest updates.

EDS Involvement

During Release 5.1, participating QSEs are required to successfully perform all activities listed under “3.2  EDS Testing Activities” as applicable. Those participants that are not able to perform these activities prior to October will still be required to perform them as entry criteria into the next release.  ERCOT will work with the QSEs to ensure that they are sufficiently trained and will address appropriate issues to ensure proper testing. This release will be conducted one QSE at a time, where ERCOT will run the QSE through a few scenarios before handing off the test scenarios and test data to the QSEs for testing.

ERCOT plans to conduct structured testing during the initial period, wherein QSEs will be given the scenarios and the data necessary for testing SCED validation. Once this is complete MPs will have the opportunity to perform unstructured testing in the EDS environment and upload necessary offers or any other input data as necessary.

System Readiness

Market Participants planning on using Web Services in production should have an Early Delivery System or tools to support data creation in the correct XML format and the ability to submit and receive data through the Web Services architecture. These systems should be first tested with the Nodal Sandbox to test security, connectivity and XML message formats.

Market Participants planning to test the SCED User Interface will be provided a User Interface guide to support testing. Participants should review the guide and outline their data inputs prior to a scheduled workshop. Access to the EDS environment will only require an Internet Connected computer, Web Browser, and a specific Digital Certificate.

# SCED R5.2 – Nodal Registration Data Updates

## Release Overview

This releases focuses on ensuring ERCOT’s system can process SCED inputs from all QSEs with Resources for all Generation Resources in ERCOT. It will be used to validate that registration data used by ERCOT and QSEs with Resources are consistent.  The tests will validate that all now Nodal ICCP data required for SCED is being provided by QSEs with Resources, and lastly will enable ERCOT to execute SCED.

Activities

During this release the EDS team will be working with Market Participants to:

- Validate and upload Resource Asset Registration data into EDS systems for Generation Resources

- Finalize and test a set of predefined Offer Curves for all QSE Generation Resources

- Ensure QSEs are sending new Nodal ICCP data required for SCED execution

Validate and Upload Resource Asset Registration Data

To support Nodal Readiness ERCOT has revised the Generation Asset Registration Form (GARF) to include additional data required for Nodal operations. The new form, named the Resource Asset Registration Form (RARF), was reviewed by TPTF and released to Market Participants requesting as subset of date to support EDS 3 testing be returned by September 4th for Generation Resources.

During the month of September and early October ERCOT will review and validate the data received in the RARFs, work with Market Participants to resolve discrepancies, and create an initial set of test data for EDS 3 testing. As part of this process ERCOT will be correcting data where required, standardizing Combined Cycle naming conventions, and loading both internal and EDS test systems with the new data. Once the initial set of data has been complete the EDS team will work with QSEs to ensure input data is aligned with the SCED system. [Will QSEs be required to resubmit the RARFs if ERCOT desires a “correction”?] Where deviations are required, ERCOT will update the RARF and the QSE shall resubmit the RARF to assure the RARFs are current with EDS testing parameters.

The new Nodal Registration Data requested included general Generation Resource site, contact, and unit information including specific parameters for EDS 3 (outlined below):

High / Low Reasonability Limit for each Unit

High / Low Reasonability Ramp Rate Limit for each Unit

Normal Ramp Rate Curve (upward / downward) for each Unit

Emergency Ramp Rate Curve (upward / downward) for each Unit

Combined Cycle Train Configurations

Combined Cycle Train Transitions between Configurations

High / Low Reasonability Limit for each CC Configuration

High / Low Reasonability Ramp Rate Limit for each CC Configuration

Normal Ramp Rate Curve (upward / downward) for each CC Config

Emergency Ramp Rate (upward / downward) for each CC Config

Wind Unit Reasonability Limits / Ramp Rates

Wind Unit Latitude / Longitude (center of farm)

Wind Unit # turbines by Equipment

Wind Unit Ramp Rate / Emergency Ramp Rate Curves

Other Wind Unit info

Finalize and test a set of predefined Offer Curves for all QSE Resources

To support Nodal testing the EDS team requested at TPTF and received approval for Market Participants to provide specific data coefficients or offer curve pairs. This data will be used by ERCOT and Market Participants to create a predefined set of Offer Curves for testing SCED.

During August and September the EDS team has been reviewing and working with Market Participants to validate the coefficients and curves submitted. The EDS team with the internal testing team will convert these curves into XML files for upload into the system for both internal and EDS environment readiness testing. Any issues that are found will be communicated back to Market Participants to ensure ERCOT and Market Participant predefined curves are the same. The curves will provide the baseline set of input data for SCED testing.

In the first few weeks of October Market Participants should be updating their EDS test system with the data necessary to generate and submit COP and TPO submissions for their entire portfolio on a daily basis, starting the third week of October using the offer curve data as described above.

Ensure QSEs are sending new Nodal ICCP data required for SCED execution

The section outlines preparation and verification activities for the new Nodal data points required for SCED R5.3 testing in November.

*  EDS 2 Required Data

The EDS 1 Release 2 Point to Point (PtP) testing covers all real-time data points needed to support State Estimator (SE) EDS 2 requirements. Currently QSEs are populating these points for EDS1 with reasonable values and are crucial for EDS 2.  For reference a list of the data points is provided below.

Minimum generation points (data) needed for EDS 2 (covered by EDS 1 PtP testing)

Net Mw, Net Mvar, Breaker status and AVR status of typical generating unit (TU).

Net Mw, Net Mvar, Breaker status and AVR status of each unit of combined cycle (CC) train.

Net Mw, Net Mvar, Breaker status and AVR status of master (physical) split generator Resource/unit (SGR).

Is the AVR status in the ICCP Handbook or Protocols?

*  EDS 3 Required Data

There are specific new data points for Generation Resources (QSE data) that were manually simulated (0 values) in EDS 1 Release 2 PtP testing, however to prepare for EDS 3, QSEs need to have the capability to provide real time values showing actual generation operations  to support SCED execution in early November. ERCOT plans to validate that each QSE is providing real values (data) from their Nodal system/environment for these points during October.

There are two sets of new data points that are required for SCED testing:

- ERCOT can perform basic SCED without LFC points with the availability of the reasonable values for the following additional ICCP points (unit specific)

Minimum generation points (data) needed for SCED testing:

High Sustained Limit (HSL) of each Generation Resource Low Sustained Limit (LSL) of each Generation Resource Resource Status of each Generation Resource Mw for each Combined Cycle (CC) mode HSL for each CC mode LSL for each CC mode Resource Status for each CC mode Combined cycle mode for each CC mode Mw for each individual Split Generation Resources (SGRs) HSL for each individual SGR LSL for each individual SGR Resource Status of individual SGR

* Points needed for basic SCED testing; current estimate is 2,000 points

(350 Typical Units x 3 data points + 150 Combined Cycle x 6 data points + 6 Split Generation Resources x 5 data points)

- For more advanced SCED testing prior to the six month LMP Posting and Load Frequency Control testing  the Resource Limit Calculator (RLC) and AS Capacity Monitor will require the remaining points listed in the ICCP Change Request Form Example 2.0 (current estimate is 2,000 additional points adding points outlined in the ICCP form example tabs). Note: Normal and emergency ramp rates are not needed to be populated because SCED will use the values coming from RARF for those points rather from ICCP.

* Testing Schedule

ERCOT will test the extended 4,000 points (about 170 points per QSE) at one time for each QSE during October leading up to SCED R5.3 testing. This will give ERCOT the highest confidence in the MPs being ready to provide real-time data for the market trials and SCED testing to begin in November 2007 and the 6 months of LMP posting starting January 2008.

*  Testing Process

ERCOT will schedule with each QSE to test in October for these additional points checking for Real-Time values for each Generation Resource.  The EDS 1 checklists with existing PtP results can be generated as Excel spreadsheets and an additional column can be added to verify these points for real time values. As the tests are completed, the results will be reported in one list to the EDS 3 project team.

EDS Environment

*

After SCED R5.1 is complete the temporary EDS environment will be shut down and rebuilt to production specifications. This configuration will support the performance necessary for running SCED with the full set of QSE  Generation Resources and offer curves. In addition, the EDS environment will be loaded with the new Resource Asset Registration data collected and validated from the RARFs. The testing during this EDS release will provide ERCOT data to benchmark performance. While the systems are intended to perform to production standards, with all QSEs submitting input for their entire portfolio the EDS team requests that activities that would put unnecessary load on the system be controlled. For example the number of  Generation Resources submitted at one time, all QSEs submitting at the end of the test adjustment period, use of any performance simulation tools. These types of testing will be possible in R5.3 once the initial environment performance measurement and some tuning has been completed.

The EDS systems will be available and supported from 8am to 5pm on designated “EDS Testing Days” based on the defined EDS calendar. During off hours and non-testing days the system may be unavailable for system updates, ERCOT testing, or other testing activities. Any changes in testing schedules will be reflected in the EDS testing calendar and communicated to Market Participants.

EDS Schedule

The SCED R5.2 EDS activities are targeted to take place during October to prepare for R5.3 in November.

The diagram below outlines the EDS preparation and testing activities:

EDS Functionality

Market Management System (MMS) – SCED

Offer Creation and Validation

| Req | Req Specification Name | Description |
| --- | --- | --- |
| FR14 | Energy Offer Curve Cancellation and Output Schedule Submission |  |
| FR15 | Energy Offer Curve Submission and Output Schedule Cancellation |  |
| FR16 | Notification to QSE for Data Submission Validation |  |
| FR17 | Insufficient Data for On-Line Non-DSR QF and On-Line non-DSR IRR |  |
| FR18 | Insufficient Data for On-line DSR |  |
| FR19 | Insufficient Data for Other Non-DSR On-line at the End of Adjustment Period |  |
| FR20 | Insufficient Data for Other Non-DSR Off-line at the End of Adjustment Period |  |
| FR21 | Proxy Offer Curve Creation: Output Schedule |  |
| FR22 | Proxy Offer Curve Creation: Output Schedule and Incremental/Decremental Offer |  |
| FR23 | Proxy Offer Curve Creation: Non-Wind/Wind Resource without Full Offer Range |  |
| FR24 | Proxy Offer Curve Creation: Wind Resource, without Offer |  |
| FR25-1 | Proxy Offer Curve Creation: Defining Constants |  |
| FR74 | Output Schedule when Non-Spin Deployment |  |

SCED Execution

| Req | Req Specification Name | Description |
| --- | --- | --- |
| FR36 | SCED Objective and Constraints |  |
| FR51 | SCED Execution |  |
| FR51-1 | SCED Triggered by Other System |  |
| FR51-2 | Multiple SCED Triggering Signals |  |
| FR33 | Input from EMS / Resource Limit Calculator |  |
| FR33-1 | System Total Generation Requirement |  |
| FR27 | Input from SE |  |
| FR27-1 | Delayed SE Data |  |
| FR28 | Telemetry Input from EMS/Gen Sub-system |  |
| FR28-4 | Input Flags from EMS |  |
| FR29 | Network Constraints from EMS |  |
| FR29-1 | Competitive Constraints from CCT |  |
| FR31 | Use of Mitigated Offer Cap Curve |  |
| FR35 | SCED Output Data |  |
| FR35-1 | Resource Parameter Violation |  |
| FR35-3 | SCED Output Flags |  |
| FR35-4 | Generation Sub-system Publish Control |  |
| FR37 | SCED Step 1 |  |
| FR38 | Data Processing between SCED Step 1 and 2 |  |
| FR39 | SCED Step 2 |  |
| FR41 | LMP when EECP |  |
| FR42 | SCED Data Archiving |  |
| FR44 | Combined-Cycle Resource |  |
| FR45 | Resource with Output Schedule Dispatch Option |  |
| FR45-1 | Resource with ONTEST Status |  |
| FR46 | Use of Maximum Shadow Price |  |
| FR47 | SCED Penalty Factors |  |
| FR47-1 | LMP Calc under System Constraint Violation |  |
| FR47-2 | Tie Breaking Rules for SCED Dispatch |  |
| FR48 | Operator Manual Override HDL and LDL |  |
| FR53 | Unresolved Constraint Alarm |  |
| FR55 | Resource Movement Limitation Alarm |  |
| FR55-1 | Suggestion Plan for Unresolved Constraint |  |
| FR59 | Base Point Summary for Operator |  |
| FR60 | On-line/Off-line Status in SCED |  |

## EDS Activities

EDS Testing Structure

During the last two weeks in October Market Participants will be required to submit a Current Operations Plan (COP) and the set of predefined Offer Curves for all Generation Resources in their portfolio. These submissions will be performed for the next operating day and up to seven days in advance. The EDS team will monitor the daily submissions and work with QSEs to resolve any issues.

Testing Scenarios and Scripts

This Release is intended to prepare ERCOT and Market Participants for Integrated SCED testing using Real-Time ICCP inputs and EMS RLC/TCM calculations. It build upon R5.1 to ensure that ERCOT and Market Participant systems are aligned with the same underlying data for all Generation Resources and a predefined set of Offer Curves can be consistently submitted. In addition, the new ICCP data points required for SCED execution must be verified. The EDS team will provide ongoing reporting on the progress.

Test Data

QSEs will be required to create input data based on a defined methodology as described by the Nodal Transition Plan. An initial methodology for creating a baseline set of data has been documented and approved by TPTF. The same curves will be submitted daily during this testing.

EDS Testing Data - To support the testing activities the MMS system will be populated with appropriate QSE Generation Resource data from the RARF process and current production data where appropriate. Based on the validation and alignment effort during the early part of October a final set of EDS testing data will be established. The EDS team will work individually with MPs to communicate any deviations to the RARF or current data to ensure alignment. Where deviations are required, ERCOT will update the RARF and the QSE shall resubmit the RARF to assure the RARFs are current with EDS testing parameters.

## Market Participant Involvement

Target Roles

The activities and functionality being tested in EDS 3 are relevant to the following Market Participant groups:

QSEs with Resources:  SCED Input Data Submissions

ERCOT:  offer receipt, external interfaces and integration, data processing and

Preparation Activities

This Release of SCED testing has been identified as "Required" for all Market Participants, identified above, as a critical milestone to ensure Go-Live readiness in December 2008. Lack of participation during this phase will not only put the Market Participant behind schedule for readiness, but also could result in lower quality output for other participants.

There are a number of activities that should be completed prior to the start of Release 5.2. These include

- Completion of Phase 1 Data Input and Validation activities

- Reviewing the SCED MP Handbook and participating in the EDS planning workshops

- Attending the EDS 3 R5.2 Kickoff Meeting

- Updating systems with Offer Curve and new Generation Resource data aligned with EDS

- Completing the required ICCP feeds

The EDS test team realizes that the project schedules for each QSE will vary. To ensure that everyone is aware of the latest updates on the EDS we recommend attending EDS planning sessions and checking the Readiness Center for EDS 3 documentation updates during the entire period.

EDS Involvement

All Market Participants identified above are required to perform the SCED testing activities outlined in this section and provide the required submission on a regular basis. An official EDS 3 testing calendar will be available on the Readiness Center that will define "All Market Participant" testing days, "Limited Participation" testing days (optional), scheduled system outage windows, and other non-required testing days (Holidays, …). ERCOT will continue to work with the Market Participants to ensure that they are sufficiently trained and will address appropriate issues to ensure proper testing.

System Readiness

Market Participants planning on using Web Services in production should have an Early Delivery System in place to support daily EDS activities. This includes data creation in the correct XML format and the ability to submit and receive those Web Services identified in this phase.

# SCED R5.3 - Integrated SCED Execution (RT ICCP)

## Phase Overview

EDS Environment

During this phase, the EDS environment will be upgraded by integrating the Nodal EMS with SCED.  This will ensure that SCED is receiving real-time ICCP feed from the grid, thereby improving the quality of input data into SCED.  In addition, new web services will be introduced to ensure that Dynamic Ratings, Shift Factors and Binding constraints can be received by the Nodal EMS solution

One of the important features planned for this phase is the release of SCED reporting through MIS.  QSEs will be able to view SCED outputs such as LMPs, Hub and Load Zone Prices through the Nodal MIS and Nodal EDW.  In addition, the Nodal Identity Management solution would be introduced during this phase to ensure stable security architecture.  The main objective of this phase is to ensure that “Reasonable LMPs” are produced and QSEs gain confidence on the SCED reports being generated.  The diagram below highlights the components that will be tested during this phase.

* Note: Only the colored components will be tested during this phase.

EDS Testing Schedule

The Integrated SCED Execution (RT ICCP) phase is targeted to take place during November and December 2007. The EDS environment and SCED outputs will be available for QSEs who have participated in prior phases of SCED and in the Nodal Sandbox.  Periodic participation from all QSEs will be required to ensure quality of input data.  The EDS team will publish a detailed calendar on the Nodal Readiness Center before the start of this phase.

The diagram below shows a sample EDS calendar:

EDS Functionality

This phase of SCED testing will enable MPs to perform all RT operations and to view the outputs generated by SCED as mandated by the Nodal Transition Plan.  Following are some of the upgrades to the functionality available in the EDS environment

External Web Services

During this testing phase, the following External Web Services outlined below will be incrementally deployed into the EDS environment as the back-end integration and internal testing is complete.

| Submission Type | Imp Group | Sandbox Target | EDS 3 Target |
| --- | --- | --- | --- |
| Outputs |  |  |  |
| Real-Time System Load | 2 | Aug 07 | Nov 07 |
| Market LMPs, (HUBs, and SPPs (November) | 2 | Aug 07 | Nov 07 |
| Resource Availability | 3 | Sep 07 | Dec 07 |
| Notifications |  |  |  |
| Notices and Alerts | 3 | Sep 07 | Nov 07 |

External Web Services Availability (SCED)

| Submission Type | Imp Group | Sandbox Target | EDS 3 Target |
| --- | --- | --- | --- |
| Outputs |  |  |  |
| Load Distribution Factors | 4 | Oct 07 | Dec 07 |

External Web Services Availability (SCED)

| Submission Type | Imp Group | Sandbox Target | EDS 3 Target |
| --- | --- | --- | --- |
| Outputs |  |  |  |
| Binding Constraints | 5 | Nov 07 | Jan 08 |
| Active Contingencies in SCED | 5 | Nov 07 | Jan 08 |
| Competitive Constraints | 5 | Nov 07 | Jan 08 |
| Shift Factors | 5 | Nov 07 | Jan 08 |
| Dynamic Ratings | 6 | Dec 07 | Jan 08 |

Market Management System (MMS) – SCED

During this phase, QSEs will be able to download Hub and Load Zone Prices from SCED.  SCED reporting will be upgraded to allow display of reports on the Nodal MIS.  The tables below describe the capabilities and requirement coverage of the initial MMS system to support input data validation. The requirements documentation and specific details can be found on the Nodal Website.

|  | Req | Req Specification Name | Description |
| --- | --- | --- | --- |
| 1 | FR 63 | Settlement Point Price Calculation: General |  |
| 2 | FR 64 | Settlement Point Price Calculation: Resource Node |  |
| 3 | FR 65 | SPP Calculation: Load Zone |  |
| 4 | FR 66 | SPP Calculation: Time-weighted Trading Hub |  |
| 5 | FR 67 | SPP Calculation: Hub Average 345kV Trading Hub |  |
| 6 | FR 68 | SPP Calculation: Bus Average 345kV Trading Hub |  |

EMS

SCED will be integrated with the Nodal EMS solution to ensure live ICCP feed from the grid.  The features that will be added into this phase include all EDS 1 & 2 EMS components such as State Estimator, Network Security Analysis in addition to Resource Limit Calculator and Transmission Constraint Manager.

MIS

SCED reporting will be available through the MIS interface during this phase of SCED Testing.  This will include LMP graphs, Settlement Point Prices such as Hub and Load Zone Prices and any other information as mandated in the Nodal Transition Plan

EDW

## EDS Activities

During this phase of SCED testing, QSEs will be able to perform all operations on SCED.  In addition, QSEs will be able to test the new Nodal Security architecture

Testing Structure

SCED Integrated System

- Use SCED Market Participant Offer Methodology

- EMS Real Time ICCP Data Inputs (Required for SCED)

- Execution of SCED using Real-Time ICCP data

- Distribution of SCED outputs through ICCP

- SCED External API Outputs

- SCED MIS Reporting

Test Scenarios and Scripts

For this phase ERCOT will publish test scenarios to test the reasonableness of the LMPs and allow download of LMPs from the MIS secure area.  In addition, test cases would be published to verify the calculation of the Settlement Point Price (SPP) at each settlement point from the LMP calculated in the SCED process. The calculation types are:

Resource Node

Load Zone

North Hub

Houston Hub

West Hub

South Hub

ERCOT 345kV  Hub

ERCOT 345kV Bus Hub

Test Data

SCED MP Input Data –For the third phase of SCED testing, the offer curves will be created by Market Participants based on the defined formula and methodology as outlined in the Nodal Transition Plan. The EDS team will be working with the TPTF and IMM to finalize the methodology.

## Market Participant Involvement

Target Roles

The activities and functionality being during this phase of EDS 3 are relevant to the following groups:

QSEs with Resources:

ERCOT:

Preparation Activities

All QSEs are required to participate in this phase of SCED testing.  QSEs are urged to download the LMPs, their Base Points and Settlement Point prices regularly and provide feedback to ERCOT on the quality of LMPs.  This will help ERCOT in demonstrating the “Reasonableness of LMPs” Need to involve the TSPs here too some way.  Not just QSEs?

In addition, QSEs are required to have participated in previous phases of SCED testing and should have established connectivity to External Web Services through the Nodal Sandbox.

EDS Involvement

ERCOT plans to conduct structured testing during this phase, wherein QSEs will be given the scenarios and the data or data definition requirements necessary for SCED input. Over time the scenarios will become more complex and Market Participants will have the ability to submit any reasonable inputs based on the defined operating scenario.

System Readiness

The quality of LMPs is highly dependent on the quality of input data provided by the QSEs.  All QSEs should have successfully tested their interfaces in the Nodal Sandbox and should have participated in the previous phases of SCED. QSEs must monitor and continuously participate in ERCOT nodal systems testing providing Nodal telemetry, COP updates, offers, output schedules, etc. as needed to support simulated market activity

Market Participants that will use the User Interface will be provided Scripts to support testing. Participants should review the Scripts and outline their data inputs prior to a scheduled workshop.

# SCED R5.4 - Six Month LMP Posting

## Phase Overview

EDS Environment

By this phase ERCOT plans to attain a stable and quality SCED that is producing reasonable LMPs.  Once the quality of the LMPs is ascertained, ERCOT shall begin posting of the LMPs on the Nodal MIS for a minimum of 6 months as required by the Nodal Transition Plan.   All applications related to SCED should have gone through the Nodal Quality Process and any defects or issues reported by the MPs would have been addressed by this time.

The EDS environment will be upgraded to run all applications on Production class hardware.  In addition, support will be available for SCED to ensure MP questions and concerns can be addressed within well defined SLAs.  The diagram below highlights the components that will be tested during this phase.

* Note: Only the colored components will be tested during this phase

EDS Testing Schedule

This six month posting of LMPs is targeted to begin in January 2008 and continue through the first half of the year.   The EDS environment and SCED outputs will be available for QSEs who have participated in prior phases of SCED and in the Nodal Sandbox.  Periodic participation from all QSEs will be required to ensure quality of input data.  In addition LMPs will be published to relevant MPs (e.g. LSEs) who need to view the outputs.  The EDS team will publish a detailed calendar on the Nodal Readiness Center before the start of this phase.

The diagram below shows a typical EDS testing week:

EDS Functionality

All SCED functionality will be available during this phase.  This includes MMS SCED, External Web Services for both SCED input and outputs, Nodal EMS solution integrated with SCED for Resource Limit Calculations, ICCP, RT NSA and State Estimator, MIS and the Nodal EDW.

## EDS Activities

During this phase ERCOT will begin publishing of LMPs for a minimum of six months as mandated by the Nodal Transition Plan.  QSEs will be able to perform all operations on SCED and will also receive support from ERCOT for SCED execution.

Testing Structure

The proposed testing structure during this phase, consists of two stages

- Use SCED Market Participant Offer Methodology (initial period TBD)

- Allow Market Participants to submit any Offers and Output Schedules (transition date TBD)

Further details will be elaborated by working with Market Participants and ERCOT business to include testing scenarios such as structured testing vs. unstructured testing etc.

Test Scenarios and Scripts

ERCOT is currently developing End to End test scenarios for SCED execution.  These test scenarios will be communicated to the Market Participants over the next few months.

Test Data

This phase of SCED testing will run on Market Participant inputs with minimal or no data stubs.  Key inputs required from the Market Participants include

- Registration Data (Best estimate as of December 2007)

- Energy Offer Curve

- Incremental and Decremental Offer Curve

- Output Schedules

Other Inputs

- SCADA Data

- Resource Limit Calculations

- State Estimator

Further details on data input will be elaborated after discussions with Market Participants

## Market Participant Involvement

Target Roles

The activities and functionality being tested in EDS 3 are relevant to the following groups:

QSEs with Resources:

ERCOT:

All QSEs are urged to participate in this phase, as this will help in increasing the quality of input data to SCED.  We recommend Market Participants to attend conference calls at least once a week and to check the Readiness Center periodically for documentation updates, updates on EDS activities and overall progress.

Preparation Activities

All QSEs are required to participate in this phase of SCED testing.  QSEs are urged to download the LMPs, Base Points and Settlement Point prices regularly and provide feedback to ERCOT on the quality of LMPs.

The Nodal Identity Management solution will be rolled out for this phase and Market Participants are required to test their Security infrastructure (such as Digital Certificates) and other access rights prior to start of this phase.  In addition, QSEs are required to have participated in previous phases of SCED testing and should have established connectivity to External Web Services through the Nodal Sandbox.

Ongoing Involvement

The EDS 3 team will work with the Market Participants to figure out the schedule of events, the type of functions to be performed and the frequency of activities during this phase of SCED testing.  We strongly recommend attending conference calls and WebEx planning sessions to detail out the same.

System Readiness

The quality of LMPs is highly dependent on the quality of input data provided by the QSEs.  All QSEs should have successfully tested their interfaces in the Nodal Sandbox and should have participated in the previous phases of SCED.  All QSEs must continuously participate in this phase.

All SCED related training should have been completed by the Market Participants prior to participation in this phase.

List training courses that are mandatory for SCED

# EDS Communications

To ensure that Market Participants are kept abreast of the developments before and during the EDS’, ERCOT has designed the following communication channels

## EDS Planning Workshops

To ensure that both ERCOT and the Market Participants maximize the benefits of the EDS, starting May 2007 the EDS team will be scheduling monthly planning workshops and ongoing conference calls to complete the details required for EDS execution. The workshops will focus on: test preparations; testing scenarios; the detailed test procedures and schedule of the test sequences; test sequence planning at the QSE and Resource level; and a substantive list of specific entry and exit criteria for each EDS Release; and the final exit criteria that signifies the completion of all Transition Plan activities that support a declaration of readiness. The EDS planning workshops will provide input for the test plans and test scenarios to support the day-to-day testing activities.

## Online Readiness Center

Online readiness support for the ERCOT and market participant transition to the nodal market as well as supporting EDS documentation can be found in the Nodal Transition Readiness Center on the ERCOT Nodal Website: http://nodal.ercot.com/readiness/index.html

## EDS Kickoff Session

Need to refine

Channel: Meeting (Austin),

WebExAudience: NTPM, EDSC

Timing: 3 wks. before EDS start

Materials: Agenda, EDS Handbook

Notes: Cover the following:

• Pre-EDS preparation activities that should be nearing completion

• Review enrollment process for preliminary testing

• Review how MPs will be able to access systems

• Q&AAfter meeting, post meeting notes, Q&A, presentation on web

## EDS Weekly Conference Calls

Need to refine

Channel: Conference Call

Audience: Participating MPs

Timing: TBD

Materials: TBD

## Weekly Status Bulletin

Need to refine:

Channel: Market Notice, web

Audience: EDSC, NTPM

Timing: End of test week

Materials: Weekly status bulletin

Notes: Covers weekly status during formal testing. Interim bulletins may be sent, as needed.

## Issue Tracking Process

Prior to the delivery of market systems and associated business functionality to the EDS environment each application will be run through a series of testing phases to identify and resolve as many of the defects as possible. Some of the testing phases include Pre-FAT that would be done at the vendor site, Factory Acceptance Testing (FAT) that would be executed at ERCOT and finally Integration Testing (ITest) aimed at integrate testing all Nodal applications. Defects identified during these phases would be logged and tracked internally for resolution.  Given the accelerated release of many of the systems into the EDS environment and the gradual increase in quality of systems, it is anticipated that there will be defects discovered by the Market Participants.  These defects should be reported to ERCOT using a Market Participant Issue Reporting Form (sample in appendix).   All items will be investigated by ERCOT testing personnel and logged into the internal defect tracking system.  Defect statuses will be discussed at the end of the week wrap-up call as well as posted on the Nodal Readiness Center website which will be updated weekly (process overview in appendix- TBD)

## Entry / Exit Criteria

To begin and end each of the EDS 3 Releases, a defined set of entrance and exit criteria must be defined to ensure readiness. Specific criteria will need to be defined for both ERCOT and the Market Participants to help ensure that the test phase will be productive. During the market trials planning phase, the team will be working with Market Participants to finalize a set of measurable criteria. Need to tie to Readiness Metrics

- Appendix A

Following are some XML examples to define the structure. These are not in alignment with any test scenarios but only representative of different SCED inputs pulled from the "TN_EIP_External_Interface Specification_1_01" document available on the Texas Nodal Website.  It is recommended that Market Participants participate in the API subgroup to better understand these Specifications.

- NOTE: Removed Sample XML from document to avoid confusion. Please see Readiness Center on the Nodal Website.

- Appendix B

## Issue Submission Lifecycle

## Draft Issue Submission Form

http://nodal.ercot.com/docs/pd/eds/eds3/toc/ResourceOfferCurveForSCEDTesting.zip