## TPTF
Number | Description | Comments | Document that initiated item | Date added | STATUS (closed, open) | Notes
1 | TPTF will discuss the rules for uplifting 1) fixed quantity block offers that are cleared below their offer price and 2) fixed quantity block bids that are cleared above their bid price. | Issue # 26, 110 | DAM & SASM Requirements | 2007-01-25 | CLOSED | Based on TPTF approval of the MMS DAM Business Requirements and Conceptual Design Documents, Mssrs Siddiqi and Spangler felt that further considerations related to this matter were better conducted in the context of the PRS NPRR process rather than under the TPTF charter.
4 | NPRR for section 6.4.8.2(2) |  | DAM & SASM Requirements | 2007-01-25 | CLOSED | ERCOT MMS Team will draft an NPRR to update table (eliminate 2nd para for X+30 min) for SASM to be in line with the self-provide provisisions and update AS offers described elsewhere in the Nodal protocols text (6.4.8.2.1 (paragraph 1(c) )). Work with Ronnie (GP&L),Shams & Bob Spangler.
6 | TPTF will discuss the following Settlement Issue: 1) How to calculate of clawback cost for Resources with Output Schedule. | Issue #10 | SCED & RT Requirements | 2007-01-25 | CLOSED | This issue is closed based on TPTF approval of the MMS DAM BusinessRequirements and Conceptual Design Documents as revised during TPTF review.
7 | How is cumulative deployment of Regulation minimized? | Issue #4 | SCED & RT Requirements | 2007-01-25 | CLOSED | Part of the GTBD discussion. General issue resolved 2/5/07 with decision to implement vendor option 4; will be added to EMS requirements. --Confirmed added to EMS requirements discussed at 2/28/07 meeting
8 | Review Generation Subsystem's Resource Limit Calculator |  | SCED & RT Requirements | 2007-01-25 | CLOSED | Resource Limit Calculator is a process that runs under the Generation Subsystem. To be reviewed with EMS requirements document. EMS Requirements approved Mar 1
9 | TPTF will discuss the impact of not distributing Pseudo Resource Dispatch to Resources providing Responsive Reserve |  | SCED & RT Requirements | 2007-01-25 | CLOSED | Pending draft NPRR that will remove the Psuedo Resource. TPTF approved draft NPRR removing the Pseudo Resource on March 7
10 | When viewing MMS approved documents on nodal.ercot.com, some of the filenames of the documents are the same |  | None | 2007-02-07 | CLOSED | Per Patricia Meyer, the filenames has different paths and that is how they are differentiated: http://nodal.ercot.com/docs/pd/mms/pd/osop/Texas%20Nodal%20Market%20Management%20Systems%20%28MMS%29%20Requirement%20Spec.doc http://nodal.ercot.com/docs/pd/mms/pd/scedrt/Texas%20Nodal%20Market%20Management%20Systems%20%28MMS%29%20Requirement%20Spec.doc http://nodal.ercot.com/docs/pd/mms/pd/cct/Texas%20Nodal%20Market%20Management%20Systems%20%28MMS%29%20Requirement%20Spec.doc
17 | Determine status of companion NPRR to PRR 697, Posting Requirements |  |  | 2007-02-22 | CLOSED | This NPRR is currently being drafted by ERCOT Legal and will be reviewed at the March 22-23 TPTF Became NPRR057
2 | ERCOT will report back to TPTF after analysing the option of changing requirements related to the confirmation of trades to allow both buyer and seller to submit the same trade and ERCOT backend processes will do the "matching" | Issue #11, 49 | DAM & SASM Requirements | 2007-01-25 | CLOSED | Confirmation logic will be changed to support both MPs submitting the same trade and ERCOT background process will manage confirmation. ERCOT to prepare NPRR to clarify confirmation of trades. Discussed on 2/12/07
3 | TPTF needs more time in reviewing the clarification note: "Explanation of Market Submission items.doc" The title in the document is " Explanation of Transaction IDs. Trade IDs, Logic for handling Overlapping ..." 1/8/2007: ERCOT will rework and resubmit for TPTF review this document to capture decisions made on 1/08/2007 TPTF meeting. | Issue # 135,5 | DAM & SASM Requirements | 2007-01-25 | OPEN | MMS Team working on finalizing this document. As of 07/09/07, MMS Team is updating with vendor and will release the document next week.
5 | Training of scenarios regarding relation of DAM committments into RUC (DAM awards not reflected in COP) |  | RUC Requirements | 2007-01-25 | OPEN | ERCOT to address and return to TPTF
11 | More clarity required for "simple outage" | Possibly discuss March 6 or 7? | Outage Scheduler Requirements | 2007-02-12 | CLOSED | See TAC approved definition for simple outage
12 | Conference call needed to discuss confirmation of trades | Sai will send notice to the group | Outage Scheduler Requirements | 2007-02-12 | CLOSED | Closed based on discussion above regarding market submission items documents
13 | Informal review needed of SCR746 to determine if a NPRR is required | SCR746, Dynamic Rating Data to TSP using Inter-Control Center Communications Protocol (ICCP) Link. Projected increase for exported SCADA values | SCADA EMS Requirements | 2007-01-23 | OPEN | Trip will consult with Richard Howard and the ICCP group in order to find out if they are interested in producing an NPRR to reverse decision in SCR746 07/09/2007: Richard Howard - will capture requirement in nodal without any additional SCRs or NPRRs Check with Bill Blevins whether this requirement is in the ICCP Handbook and what is the speed
14 | All the aforementioned data inputs (specification data, operational data and unit availability) are provided by ERCOT to the wind power production forecasting service for utilization along with their additional meteorological information. The wind-power production forecasting service will strive to produce the most accurate hourly forecast of total ERCOT wind-power production (minimum dispersion of the probability distribution for each hour), The forecast will consist of two components, a probabilistic hourly forecast of the Total ERCOT wind-power production for each of the next 48 hours and distribution factors for each individual WGR for each of the next 48 hours. The cumulative probability distribution table shall consist of at least 20 points from 5% confidence to 95% confidence that the total ERCOT wind-power production will exceed. It shall not be assumed to be a normal distribution. The distribution factors for each WGR shall be that WGRs proportion of the total ERCOT wind power production for that hour. ERCOT shall use the total ERCOT probabilistic forecast and the WGR distribution factors (which shall total to one) to calculate the STWPF and the WGRPP for each WGR. ... | Moved from the IDA Punchlist. This recommendation goes beyond what protocols require and it is not supported further by any specific functional or supplemental requirements. The requirements as written have performance criteria sufficient to require the wind power forecasting service to provide accurate forecast while allowing for flexibility by the service in producing the forecast. It is ERCOT staff opinion that as written the requirements align with the Wind Coalitions comments regarding the forecasting services performance and flexibility requirements. Update requirements to get probability distribution table for forecast generated for each WGR for each hour. TPTF will revisit the proposal from W. Reid. | Wind Power Forecasting | 2007-02-22 | OPEN | As of 07/09/2007, there is an approved Wind Power Forecasting Requirements
15 | DC Ties and Controllable Load Resources providing AS | Joel Firestone agreed to conference with Brett, Richard and Shams to discuss issues |  | 2007-02-23 | OPEN | Carrie will check with Firestone to see if this is an open issue; Shams says there may be a conflict between ERCOT Protocols allowing DC Ties to provide AS and NERC not allowing.
16 | Discuss beta testing for EDS 1 when testing complete |  | EDS-1 detailed plan overview | 2007-02-22 | CLOSED | Closed based on EDS 1 workshop presentations
18 | Review changes to MMS Requirements with regard to the TAC/ROS-approved Non-Spin deployment procedure | Deployment message and how it is communicated; same issue with RRS on Load | EMS Requirements (Generation Subsystem) | 2007-02-28 | OPEN
19 | TSA shall complete all calculations within 25 min for ERCOT system with 100 contingencies. Q: How frequently are the TSA constraints active. A: The TSA constraints become active very rarely. EMS took action item on this topic and will investigate whether or not a NPRR is needed and share the results with TPTF |  | EMS Requirements (NSSA) | 2007-03-01 | OPEN | EMS Team should follow up with TPTF on status. Will send Al Hirsch a note and cc John Adams.
20 | MMS Requirements to be revisted to verify incorporated on GS-FR23 from the EMS Generation Subsystem Requirements |  | EMS Requirements (Gen Subsystem) | 2007-03-01 | OPEN | GS-FR23 - Related to adjustment of HASLs after deployment of Non Spin (v0.9) Refer to EMS Generation Subsystem Requirement GS-FR25 Confirm with Baseline 2 MMS requirements
21 | Funding/Accounting during market trials |  | Metrics review | 2007-03-06 | OPEN | 07/09/2007: Cheryl Yager will talk with TPTF regarding credit transition to nodal at the July 23-25 TPTF meeting Request Daryl Cote to follow up on this issue after LFC test procedures are finalized
22 | Issue of xml version of Statesments and Invoices by API should be tracked by ERCOT for potential implementation post go-live |  | COMS Reqs | 2007-05-24 | OPEN
23 | Discuss HSL and URL issues at a future TPTF meeting |  | IDA Whitepaper IDA013 | 2007-06-21 | OPEN | Diran to follow up with TPTF
24 | Include validation rules for the start-state and end-state as an active part of an EDS Handbook. | Should this be documented by the MMS Team? | EDS SCED MP Handbook | 2007-06-27 | OPEN | As of 07/09/2007, has not been updated
25 | ERCOT investigate the possibility of adjusting the format of the trade submissions to improve updates without necessary cancellations when net buyer becomes net seller. |  |  | 2007-07-09 | OPEN
26 | Need to confirm that buyer and seller can be the same entity with a switch indicating whether it’s a net buy or sell. Need to understand how confirms work for this also. |  |  | 2007-07-09 | OPEN | Stacy will contact Al Hirsch for confirmation
27 | ERCOT to return to TPTF with proposal for validating DSR output schedules including PCRR with refund validation. |  |  | 2007-07-09 | OPEN | See Resmi and Kenneth Ragsdale
28 | Scott Privette to confirm determinants included in settlements extracts |  |  | 2007-07-09 | OPEN
29 | Need update from EDS Team on plan for publishing validation rules for various phases of EDS 3 |  |  | 2007-07-09 | OPEN
30 | Issue of substation names in retail market business; should they be consistent with the ERCOT network model and if so, what is the plan to get that done including the timeline |  |  | 2007-07-09 | OPEN | Trip will touch base with Raj Chudgar
31 | ERCOT Legal to confirm NDA process in email to TPTF exploder | Chad Seely |  | 2007-07-09 | OPEN
32 | Ask ERCOT for a decision on the possibility of converting zonal RTUs to a zonal ICCP and using that in nodal |  |  | 2007-07-09 | OPEN
33 | Update the CMM CSD to indicate that the definition of CRR includes PCRRs and MCFRIs. |  | CMM CSD | 2007-07-11 | OPEN
34 | ERCOT to discuss how Quality Center is being used in testing and traceability |  | Discussion of INT testing | 2007-07-11 | OPEN
35 | ERCOT to elaborate method for assigning appropriate Hub prices when DAM is executed but specific DAM SPP is not available |  | CMM CSD | 2007-07-11 | OPEN
36 | Elaborate the manual processes for CMM and document them in the CMM Operating Procedures (See the CMM Punch Tab in this workbook) |  | CMM Requirements/ CMM CSD | 2007-07-11 | OPEN
37 | ERCOT to discuss who is leading Nodal Program in identifying Electrical Buses for Settlements | Settlements/ NMMS |  | 2007-07-11 | OPEN
38 | Discuss whether Offer validations in DAM should be based upon HRL/LRL rather than HSL/LSL | To be added as a discussion item to a future TPTF agenda |  | 2007-10-19 | OPEN | This Punch List item arose during the discussion of the MMS DAM and SASM Requirements at the Oct.8-9 TPTF Meeting. Discussion recommendation from Shams Siddiqi.
39 | Discuss options for linking AS Offers to Energy Offers in the DAM co-optimization following MMS discussions with vendor | S. Moorty and MMS team to follow up. |  | 2007-10-19 | OPEN | This Punch List item arose during the discussion of the MMS CCT Requirements at the Oct.8-9 TPTF Meeting.
40 | Develop a business process for DAM execution (i.e., provisions for equipment failure, invalid submission items, aborted executions, etc.) | S. Moorty and MMS team to follow up. |  | 2007-10-19 | OPEN | This Punch List item arose during the discussion of the MMS DAM and SASM Requirements at the Oct.8-9 TPTF Meeting.

## CMM Punch Tab
This worksheet contains all of the modified spreadsheet items from the TPTF discussion of the updated CMM Requirements and CSD on July 9, 2007. These items were identified as follow-up items associated with the approving vote for the CMM Requirements v1.2 and the CMM CSD v1.2 as documented in the 070907 TPTF Meeting Minutes.
CMM Punch Tab: COMS Credit Monitoring and Management Conceptual System Design
Issuing Entity | Section | Description | Accepted /Rejected /Response | Reviewer | Comment
Reliant | n/a | Note that all assumptions for credit for CRRs hold for PCRRs as well. Under Protocols 7.1(2) PCRRs and MCFRIs are a subset of CRRs. Please confirm that the use of CRR in this document and other credit document includes the treatment of PCRRs and MCFRIs. A global statement to this effect should be made here and the systems should recognize and import/calculate with the PCRR/MCFRI data as well. | accepted, multiple occurrence | ERCOT | CMM gets the CRR owned by the CRR owner from the CRR system. If the CRR ownership should include PCRR as well as MCFRI, they will be defined so in the integration interfaces.
Reliant | 1.6, page 9 | they are time weighted averages | response | ERCOT | yes. Will be covered in the detailed design, including block or rolling.
Reliant | 2.19.5.1, page 47 | what will ERCOT credit do with the messages? Will action be taken? | response, will further address in operating procedures | ERCOT | These messages are informatioal to provide early warning so that ERCOT could analyze credit risks to the whole market or specific Counter-Parties. Please refer to Protocols 16.11.4.1 (3). Version 1.0 of the requirements was presented to CWG and approved by them. If there are any specific concerns, please specify them to be addressed.
CMM Punch Tab: COMS Credit Monitoring and Management Requirements Specification
Issuing Entity | Section | Description | Accepted /Rejected /Response | Reviewer | Comment
Reliant | 2.3.7 | [Reliant: if this state impacts a Market Participant’s ability to transact in ERCOT markets, the Participant should be notified AND consideration should be provided for how to accommodate their participation in the interim until ERCOT gets its systems working.] | response, will further address in operating procedures | ERCOT | This is part of a mostly manual business process to notify the impacted MP and obtain necessary info in a timely manner. Please refer to Alternative Scenario 2.
Reliant | 2.3.8 | [Reliant: what does this mean? Adjusted to account for specific conditions? If so, such conditions should be described.] | response, will further address in operating procedures | ERCOT | The unsecured credit limits are reviewed and modified if needed as per ERCOT creditworthiness standards.
Reliant | 2.4.14 | [Reliant: same comment as above. What is the equation for calculating this?] | response, will further address in operating procedures | ERCOT | This will be addressed in detailed design.
Reliant | 2.4.15 | [Reliant: what does this mean? Adjustment up or down on what basis? Details require documentation.] | response, will further address in operating procedures | ERCOT | Adjustments are intended for correcting errors or to entered based on manual calculation if needed.
Reliant | 2.4.15 | [Reliant: What would determine the need? Is this a work around for system failure or does it mean ‘adjustment as analyst sees fit?’ This not allowed for under the Protocols 16.11.4.3.] | pending operatiing procedures | ERCOT | Adjustments are intended for correcting errors or to entered based on manual calculation, if needed. Please refer to Protocols section 16.11.4.1.(3)
Reliant | 2.4.16 | [Reliant: what does this mean? Adjustment up or down on what basis? Details require documentation.] The Credit Anlayst may adjust the RTL component as needed to reflect business conditions | response, will further address in operating procedures | ERCOT | Adjustments are intended for correcting errors or to entered based on manual calculation if needed.
Reliant | 2.4.17 | [Reliant: what does this mean? Adjustment up or down on what basis? Details require documentation.] | response, will further address in operating procedures | ERCOT | Adjustments are intended for correcting errors or to entered based on manual calculation if needed.
Reliant | 2.4.18 | [Reliant: what does this mean? Adjustment up or down on what basis? Details require documentation.] | response, will further address in operating procedures | ERCOT | Adjustments are intended for correcting errors or to entered based on manual calculation if needed.
Reliant | 2.4.23 | [Reliant: what does this mean? Adjustment up or down on what basis? Details require documentation.] | response, will further address in operating procedures | ERCOT | Adjustments are intended for correcting errors or to entered based on manual calculation if needed.
Reliant | 2.4.23 | [Reliant: what is envisioned here? Say that there is a price that exceeds a defined parameter. What would be done that isn’t captured in the credit processes already? Would you run calculations earlier? Look at certain counterparties? Where will these business processes be defined? Recommend that they be discussed with CWG.] | response, will further address in operating procedures | ERCOT | These messages are informational to provide early warning so that ERCOT could analyze credit risks to the whole market or specific Counter-Parties. Please refer to Protocols 16.11.4.1 (3). Version 1.0 of the requirments was presented to CWG and approved by them. If there are any specific concerns, please specify them to be addressed.
Reliant | 2.4.4 | [Reliant: what does this mean? Adjustment up or down on what basis?] | response, will further address in operating procedures | ERCOT | Adjustments are intended for correcting errors or to entered based on manual calculation if needed.
Reliant | 2.4.5 | [is interface anticipated in either or both of these systems?] | response, will further address in operating procedures | ERCOT | Programmatic interfaces with both of these systems will be deployed.
Reliant | 2.4.5 | [Reliant: Would be useful to discuss how the ‘appropriate’ Hub prices will be determined.] | Response, Nodal needs to clarify this further | ERCOT | This will be addressed in detailed design.
Reliant | 2.4.6 | [Reliant: Would be useful to discuss how the ‘appropriate’ Hub prices will be determined.] | Response, Nodal needs to clarify this further | ERCOT | This will be addressed in detailed design.