## Slide 1: Role of Account Management at ERCOT
Market Engagement and Readiness (MER)
Training Update
TPTF Meeting
October 22nd, 2007
Market Education
Notes: <number>

## Slide 2: Agenda
    Training Development
      Completed courses
      In development
      Upcoming Courses
    Training Delivery
      New Releases
      Progress Report
      Scheduled Training
    Proposed new additions
    Training readiness reports
Market Training
ERCOT Nodal Market Transition

## Slide 3: Training Development – Completed Courses
Course | Length | Initiated | Training Sub-Group Review | Beta Course | Class Room Training |  | Web-Based Training | 
 |  |  |  |  | Due Date | Status | Due Date | Status
ERCOT Nodal 101: The Basics | 1 - Day |  |  |  | Done |  | Feb – 07 | 
Economics of LMP | 1 - Day |  |  |  | Done |  | N/A | N/A
Transition To Nodal Markets | Web-Based |  |  | N/A | N/A | N/A | May – 07 | 
Load Serving Entity 201 | 2 - Days |  |  |  | Done |  | Sept – 07 | 
Notes: <number>

## Slide 4: Training Development – In Development
Course | Length | Initiated | Training Sub-Group Review | Beta Course | Class Room Training |  | Web-Based Training | 
 |  |  |  |  | Due Date | Status | Due Date | Status
Basic Training Program | 5 - Days |  |  |  | Oct – 07 |  | Feb – 08 | 50%
NOIE QSE Operations | 1 - Day |  |  | Nov – 07 | Dec – 07 | 60% | Jan – 07 | 20%
Network Model Management | 2 - Days |  |  | Oct – 07 | Nov – 07 | 70% | Dec – 07 | 30%
Congestion Revenue Rights | 2 - Days |  |  | Nov – 07 | Nov – 07 | 70% | Jan – 07 | 30%
Market Settlement 301 | 2 - days |  |  | Nov – 07 | Dec – 07 | 70% | N/A | N/A
Generation 101 | 1 - Day |  |  | Nov – 07 | Nov – 07 | 70% | Feb – 08 | 30%
Generation 201 | 1 - Day |  | Dec – 07 | Feb – 08 | Mar – 08 | 20% | Apr – 08 | 0%
Generation 301 | 1 - Day |  | Jan – 08 | Feb – 08 | Mar – 08 | 10% | Apr – 08 | 0%
Market Information System | 2 - Days |  | Jan - 08 | N / A | N/A | 10% | Apr – 08 | 10%
Notes: <number>

## Slide 5: Training Development – Upcoming Courses
Course | Length | Delivery Date
Transmission 101 | 2 ½ – Days | Mar - 08
ERCOT 101 for Wind Generation | 1 - Day | Mar - 08
Course | Length | Delivery Date
Extended Training - System Dynamics | 1 - Day | Once a month within the first 12 months of full Texas Nodal Market Operations
Scenario-Based Training for QSEs with Generation Resources | 1 - Day | Once a Quarter 2009 only
Scenario-Based Training for Load Serving Entities | 1 - Day | Once a Quarter 2009 only
Scenario-Based Training for TSPs and DSPs | 1 - Day | Once a Quarter 2009 only
Deliver in 2008
Deliver after go-live

## Slide 6: Training Delivery – New Releases
  Basic Training Program
    NERC continuing education hours
    First course – October 22nd-26th
    Delivery schedule
      Once a month (Austin, Dallas, Houston)
      Looking for host in the Northeast
      Spring seminar
        Course will be delivered as the 25th annual ERCOT Operations Training Seminar
        6 weeks (March 24th – May 2nd)
        ~700 attendees expected
    5 day course
      Day 1 – (Course Introduction, Fundamentals of the Nodal Market, Day-Ahead Market)
      Day 2 – (Day-Ahead Market , Transmission Security Analysis & RUC )
      Day 3 – (Transmission Security Analysis & RUC, Adjustment Period)
      Day 4 – (Adjustment Period , Operating Period)
      Day 5 – (Operating Period, Abnormal Emergency Operations)

## Slide 7: Training Delivery – Progress Report
Course | Delivery Options | No. of Instructor Led sessions | Passed / Attempted |  | 
 |  |  | MP | ERCOT | Total
ERCOT Nodal 101: The Basics | Instructor Led Web Based Test Only | 47 | 1318/1810 | 485/669 | 1804/2479
Economics of LMP | Instructor Led | 16 | 509 | 176 | 685*
Transitions to Nodal Markets | Web Based | N/A | 113/215 | 76/116 | 189/331**
LSE 201 | Instructor Led Web Based | 3 | 147/252 | 7/22 | 154/274
* ILT only - No exam
** WBT – No exam – Completed reviewing 75% or more of the slides

## Slide 8: Training Delivery – Scheduled Training
ERCOT Nodal 101: The Basics | 
Date | Location
Nov 5, 2007 | CenterPoint Energy (Houston)
The Economics of LMP | 
Oct 29, 2007 | Stream Energy (Dallas)
Load Serving Entity 201 | 
Nov 14th – 15th , 2007 | Suez Energy (Houston)
Dec 3rd – 4th , 2007 | TBD (Austin)
Basic Training Program | 
October 22-26, 2007 | University of Texas (MCC Auditorium) (Austin)
Nov 12th – 16th , 2007 | Center Point Tower (Houston)
Dec 10th – 14th , 2007 | Luminant Energy (Dallas)
Jan 7th – 11th - , 2007 | TBD (Austin)
Feb 18th – 22nd , 2008 | NRG Energy (Houston)
March 24th – May 2nd , 2008 (6 consecutive sessions) | ERCOT Met Center (Austin)
Notes: <number>

## Slide 9: Training Curriculum – Proposed additions
    User Interface Training
      Scope
        CRR, Outage Scheduler, MMS
      Design / Delivery
        Web-based training
        Menu driven and task based
        Job aid after go-live
      Status
        CRR – To be developed by 12/31/07
        Outage Schedule and MMS – Awaiting design work
        Need to be added to training curriculum
Notes: <number>

## Slide 10: Training Curriculum – Proposed additions
Notes: <number>

## Slide 11: Training Readiness Reports
    Training Readiness Reports
      Now available
      ERCOT will provide reports to Accountable Executives
      Accountable Executives will report on readiness
      Contents
        List of courses and attendees
        Completion status
      Frequency
        Initial reports coming soon
        Quarterly updates or on demand
Notes: <number>

## Slide 12: Questions
Questions ??
Market Training
ERCOT Nodal Market Transition
Notes: <number>