## AEP
ID | Submitting Company | Page | Comment | Response Type | Response
1 | AEP | 26 | One of the important features planned for this phase is the release of SCED reporting through MIS. QSEs will be able to view SCED outputs such as LMPs, Hub and Load Zone Prices through the Nodal MIS. - EDW was deleted but is still in the picture. | clarification | EDW will be included in the solution to provide the reports. The deletion 'and Nodal EDW' was rejected.
4 | Luminant | 26 | In addition, the Nodal Identity Management solution is scheduled for release for EDS test purposes during this phase and will be exercised during the test sequences to ensure stable security architecture. The main objective of this phase is to ensure that “Reasonable LMPs”, in the context of the test energy offer curves, | Accepted
5 | Luminant | 26 | Successful conclusion of the EDS 3 R5.1 and Market Readiness Criteria is contingent on the participation of all QSEs with Resources to ensure quality of input data. | Accepted with changes | Successful conclusion of the EDS 3 R5.3 and Market Readiness Criteria is contingent on the participation of all QSEs with Resources to ensure quality of input data.
6 | Luminant | 26 | 'test', 'to provide test data', reflect test' | Accepted with changes | Replaced 'actual' with 'dynamic field test'
11 | LCRA | 26 | EDS Testing pg. 26: The dates should read November 1, 2007 - January 15, 2008 | Accepted
12 | LCRA | 27 | EDS Testing Schedule pg. 27: Since there is no LFC testing during 5.3 it seems like this group of bullets could be removed. | clarification | R6.1 testing is expected to early in 2008 so there might be a small overlap
13 | LCRA | 27 | Initially the selected data.... {please add the date range, it's there for the other sections} | Accepted | sentence updated to, "Initially the selected data to be provided between November 1, 2007 and December 2, 2007 is as follows:"
14 | LCRA | 30 | ICCP pg. 30 When can QSE's with Resources expect to start receiving information? November 1? | clarification | During P2P testing it was confirmed that QSEs could scan the LMPs and Base Points. Once the EMS - MMS interface is inplace these values will get updated when SCED runs. The interface is expected to be in place by Nov 1.
2 | AEP | 31 | R5.3 exit Criteria R5.3 - right before this section the following was deleted - Market Participants that will use the User Interface will be provided Scripts to support testing. Participants should review the Scripts and outline their data inputs prior to a scheduled workshop. Why? | clarification | The purpose of R5.3 testing is for MPs to submit SCED inputs following the market timeline and adjust said inputs when real-time condition warrant the change. Beyond the activites and clarification of specific data to input as outlines in section 5 SCED R5.3 - Integrated SCED Execution (RT ICCP), 5.1 Phase Overview, EDS Testing Schedule, there will be no scripting.
7 | Luminant | 32 | Lack of participation during this phase may put the Market Participant behind schedule for readiness, and also could result in lower quality output for other participants. | Accepted
8 | Luminant | 32 | There are a number of activities that test participants should complete prior to the start of Release 5.3. These include | Accepted
16 | LCRA | 32 | Preparation Activities pg. 32 The correction of ERCOT's 5.2 performance problem needs to be corrected if we are to achieve the stated objectives of 5.3. | clarified | • The existing performance issues pertaining to COP and TPO submissions are corrected
9 | Luminant | 34 | This six month posting of LMPs will begin on January 15, 2008 and continue as a minimum through mid-June 2008 as later instructed by TPTF. R5.4 will run concurrently with LFC testing (R6.1 through 6.3). The testing schedule, required inputs, and requirements for R6.1 through R6.3 supersede the test schedule and plans outline herein {Note: What does this mean? Please provide further clarification of what test schedules and plans that are subject to being superseded.}. | clarification | LFC and SCED testing will run concurrently in 2008. The testing objectives and schedule for R5.4 (Jan 15, 2007 to June 15, 2007) have not been defined yet but the testing needs of LFC trump any conflicting plans for SCED testing. R5.4 will be refined and presented to TPTF for comment and approval later in 2007. Rejected the updates to version 2.0 to get the section back to the previously approved text.
17 | LCRA | 35 | System Readiness pg. 35 Were the training courses going to be identified? | Open | The EDS team will update this section when we present R5.4 to TPTF
3 | AEP | 38 | Should the following appendix be removed? 1 Appendix A Following are some XML examples to define the structure. These are not in alignment with any test scenarios but only representative of different SCED inputs pulled from the "TN_EIP_External_Interface Specification_1_01" document available on the Texas Nodal Website. It is recommended that Market Participants participate in the API subgroup to better understand these Specifications. | Accepted | Appendix A was removed
10 | LCRA |  | Section 5.1 Will SCED Reports really be generated during Phase 3? | clarification | yes
15 | LCRA |  | Section 5.2 The Identity Management documents referenced a December implementation date. What part will be available in November? | clarification | R5.3 spans from Nov1 to January 15 and the EDS team expects the identity management system to be in the EDS environment sometime during this period. I do not expect it to be used in November