## Slide 1: Texas Nodal Program Update
Jerry Sullivan, Executive Director

## Slide 2: Agenda
Item | Who | Purpose
Nodal Program Status | Jerry Sullivan | For Information
Executive Vendor (Partner) Forum w/ Market Participants | Jerry Sullivan | For Information
ERCOT Engagement | Jerry Sullivan | For Information
ERCOT and Market Readiness Scorecards | Jerry Sullivan | For Information
Measurement Planning Horizon | Jerry Sullivan | For Information
Nodal Schedule Update | Jerry Sullivan | For Information

## Slide 3: Overall program status remains amber
Cost
Schedule
Scope / Quality
Legend
Summary
Green
Effort being made to keep costs to $263 Million. Latest forecast as of Oct 5 is between $273 and $280 with continuing effort being made on efficiencies and finding savings without jeopardizing quality issues
Amber
Amber
Currently fully aligned with protocols
Red
Amber
Green
Estimate at Complete = <$263m
Estimate at Complete = < $263m + 10%
Estimate at Complete = >$263m + 10%
Go-live = 12/1/08
Go-live = <30 days+
Go-live = >30 days+
Program is aligned with current protocols
Program is aligned to previous protocol version
Program is not aligned to protocols
Concerns over key upstream deliverable slippage
Looking to optimize sequence of releases into Early Delivery Systems
Pursuing retention measures to mitigate disruption resulting from staff attrition
Scope/
Quality
Schedule
Cost
Nodal
Delivery
Amber
Current product quality is not sufficient for Nodal launch
Most Nodal products currently achieve quality standards
All Nodal products currently achieve quality standards
Resolved IDA and Integration Test PM losses

## Slide 4: ERCOT Executive Vendor Forum held 10/18/07
Workshop 1 dealt with resourcing and employee retention items:
  Improve Quality of Life and Work environment
    – identified top items to address for managing current attrition trends
    set the stage for a priority planning and working session between ERCOT Executives and the Nodal Program Director (conducted on October 22 and 24)
  Identified ways to shorten length of the “On-boarding process”
  Emphasized effective deployment & re-deployment strategies for nodal staffing plans
  Detailed the need for a review of the contractor “rate card”
Workshop 2 dealt with improving the confidence of the Nodal Program Schedule
  ‘Co-location’ possibilities for reducing communication issues and cycle times
    - Major vendors to co-locate at Taylor to help with problem resolution
    Continued use of ERCOT staff at vendor sites.
  Identified several opportunities to improve best practices for code delivery:
    -Separate new development from ‘bug’ fixes
    -Identify causes for large number of work-arounds and revise processes to solve
    -Optimize releases with workload
Integration and Testing
  Developed an optimized way forward to ensure testing and releases will meet the schedule and ensure quality.
  Work with MPs as experts for testing and SoSA prioritization
Executive
Management
Emphasis
Conducting
a series of Scheduling
Workshops
Revitalizing
Testing
Team`
ERCOT conducted its second annual Executive Vendor Conference on October 18. Guests were executives from various market participants, ERCOT, and vendor partners working on the Nodal Program. There were three workshops:

## Slide 5: ERCOT Engagement Status
Results will be exposed via the Readiness Scorecard, transparent to all
First round of self reporting completed by ERCOT leadership
Analogous to existing reporting by Market Participant “Accountable Executives”
“Initiation” gaps relate to completion of business impact assessment
All areas have committed to being ready for the trials using Early Delivery Systems

## Slide 6: ERCOT Readiness Update
Overall ERCOT Readiness on track
Non-market-critical departments in CFO and Information Technology organizations have not yet completed training
These departments’ training status is pulling ERCOT’s overall score yellow
ERT team is working with the yellow departments to catch up on training
Drill-down to department-level metrics available on the Readiness Scorecard this week

## Slide 7: Market Readiness Update – Scorecard
http://Scorecard.ercot.com
Accountable Executive login available from ERCOT Client Service
We are measuring Market Participants across a wide range of metrics, spread over the appropriate timeframe on the Nodal Delivery Schedule.
The tool allows drill-downs to visualize ` Market Participant-specific data
The second round of MP self reporting will be reported in mid-November

## Slide 8
Market Readiness – 3 Month Planning Horizon
Delivery and Readiness metrics rolling into Readiness Scorecard.
Market Participant Engagement results available now on NODAL.ERCOT.com
 | NODAL Delivery | ERCOT Readiness | Market Participant Readiness
Currently Measuring | Telemetry Alarm Processing Telemetry / ICCP System Failover | ERCOT Training (EDS 1 & 2) Develop NODAL Operating Guides ERCOT Staffed for NODAL operations Procedure Development | Market Participant Engagement Connectivity to EDS Environment QSEs with Resources Upload SCED to EDS ICCP Point to Point Telemetry Test QSE and TSP Telemetry / ICCP System Availability Registration Activities
October | SCED Execution | ERCOT Training (EDS 3) | EDS2 Market Trials Participation Market Participant Engagement (2nd survey)
December | SCED Quality Validate Security Analysis Results State Estimator Performance and Accuracy |  | EDS3-Related Market Participant Training

## Slide 9: EDS Schedule Update
# | Topic | Solution/Action
1 | EDS 1 Start: 6/4/07 End: Revised to Oct 30th for 99% Revised to Nov 15 for 100% | Confidence in achieving the milestone is High: 95% complete with P2P, with 4% error rate
2 | EDS 2 State Estimator and Telemetry Start: 9/4 End: 12/31/07 | EDS 2 R 3, SE tuning activities started on 9/7 as planned TAP estimation to be reconfigured / software corrected by end of EDS 2 Release 3 ICCP clean up of 20-25% of Nodal generation is yet to occur
3 | EDS 3 Nodal Registration Data Update Start: 10/15/07 End: 10/31/08 | Started EDS 3 Release 5.2 as planned on 10/15 EDS environment (MMS and EIP) upgrades to production hardware Updated Registration data in MMS based on RARF submissions
3 | EDS 3 EMS interfacing with SCED Start: 11/1/08 End: 1/15/08 | Milestone achieved 7 days in advance Integrated SCED currently generating test LMPs in the EDS environment. Delivery of SCED reports, confidence is High – MIS team working with EMS, MMS and EIP to ensure delivery of reports Published sample reports to the Market Participants for format verification
4 | EDS2 R4 NMMS NOMCR Start: 11/1/07 End: 3/31/08 | Confidence in achieving the milestone is low, with known challenges (initial data load from AREVA, Hardware, Software variances) ERCOT Network Model yet to be loaded into NMMS without significant errors Phase 1c delivery at end of Sept 2007 being pushed to end of Oct; Defining testing approach to leverage system functionality in the order it’s delivered Lack of hardware to start EDS phase
Major `Achievement