## Slide 1: TCR to CRR Transition Plan
Proposed method for TCR Auction Revenue refunds
Contingency plans
For TAC
Nov 1st, 2007

## Slide 2: Outline
Objectives
Plan for transition – Part 1
  Proposed Annual TCR Auction Revenue refund methodology
Plan for transition – Part 2
  Contingency plans
Next steps
WMS and TPTF approved option 1

## Slide 3: Objectives
The TCR to CRR Transition Plan is intended to describe the plan(s) for transitioning from the TCR to CRR market.
This plan will fulfill Market Readiness Criteria:
  CRR2 – Develop TCR to CRR Transition Plan
  (see appendix for details)
Development of this plan involves Nodal CRR, CMM and COMS (Settlements) projects and Zonal TCR/Settlements department.
ERCOT seeks TPTF approval of this plan (part 1). *ERCOT received WMS approval for part 1 on Sep 19th 2007.

## Slide 4: Plan to transition from TCR to CRR market - Part 1 (1/3)
The plan is to run an annual TCR Auction in Dec 07 for all of 2008 and run monthly TCR Auctions in 2008 up to December (i.e. no monthly TCR auction for Dec).
After go-live on 12/1/08, annual TCR/PCR owners will be refunded for the month of Dec 08.
Assumptions:
Nodal go-live date is 12/1/08
CRR, NMMS, COMS (S&B) successfully pass EDS testing
Should CMM-CRR interface not be completed as expected, manual process for 1st auction
Refund to TCR/PCR owners for the month of Dec will be as proposed on next slide…
2008
Feb | Start CRR EDS Testing
Oct | CRR Allocation
Nov | CRR Auction
12/1/08:
Nodal Go-Live
Dec | Refund TCR amount for month of Dec
2007
Dec | TCR Annual Auction for 2008

## Slide 5: How we plan to refund annual TCRs – Part 1 (2/3)
Every month from Jan to Nov 08, ERCOT will, as usual, divide the 2008 annual auction TCR/PCR revenues into monthly revenues in the same proportion as ERCOT’s monthly energy forecast (see graph below) and distribute them to QSEs based on their Load Ratio Share (LRS).
In Dec 08 (when TCRs/PCRs are no longer in effect), ERCOT proposes to refund remaining 2008 TCR/PCR annual auction revenue to TCR/PCR owners based on TCR/PCR purchase allocation % (see formula below).
JAN
FEB
MAR
APR
JUN
JUL
AUG
SEP
OCT
NOV
MAY
DEC
Total $ TCR purchases by TCR Account Holder in 2008 annual auction
Total $ TCR/PCR purchases by ALL TCR Account Holders in 2008 annual auction
TCR purchase allocation %
=
Refund to TCR/PCR Owner * = * *
Total revenue for 2008 TCR/PCR annual auction
Dec load forecast
Total load forecast
TCR purchase
allocation %
where
*Note: For PCRs, purchase allocation % is based on $ amount paid, not equivalent TCR clearing price
WMS and TPTF approved this option

## Slide 6: An alternative (option 2) – Part 1 (3/3)
Every month from Jan to Nov 08, ERCOT will, as usual, divide the 2008 annual auction TCR/PCR revenues into monthly revenues in the same proportion as ERCOT’s monthly energy forecast (see graph below) and distribute them to QSEs based on their Load Ratio Share (LRS).
In Dec 08 (when TCRs/PCRs are no longer in effect), ERCOT will calculate TCR/PCR revenue for Dec and refund that amount to TCR/PCR owners.
Because “Refund to TCR/PCR Owner * (option 2)” > remaining 2008 TCR/PCR annual auction revenue, ERCOT will first need to collect back some revenue previously allocated to QSEs based on LRS before being able to refund TCR/PCR owners.
*Note: For PCRs, purchase allocation % is based on $ amount paid, not equivalent TCR clearing price
Refund to TCR/PCR Owner * (option 2) = TCR/PCR revenue = Clearing price* MW * # hours in Dec
JAN
FEB
MAR
APR
JUN
JUL
AUG
SEP
OCT
NOV
MAY
DEC
for Dec

## Slide 7: Questions on proposed refund method?
Next: contingency plans…

## Slide 8: Contingency plans - Part 2 (1/3)
The following two slides describe contingency plans in preparation for circumstances that may cause the Nodal market go-live date to be later than 12/1/08
These contingency plans were developed with the following assumptions:
  Nodal go-live date is later than 12/1/08
  New go-live date is determined at least 5 months in advance of the new Nodal go-live date
  New go-live date is on the first day of the month

## Slide 9: Plan to transition from TCR to CRR market – Part 2 (2/3)
Should the Nodal go-live date be postponed till after Jan 1st 2009, the contingency plan is to run an annual TCR Auction in Dec 07 for all of 2008, and run an annual TCR Auction in Dec 08 for all of 2009 (while running monthly TCR auctions as usual until go live).
Annual TCR/PCR owners will be refunded for the remaining months in 2009 after new Nodal go-live date.
Assumptions:
Nodal go-live date is after 1/1/09
CRR, NMMS, COMS (S&B) successfully pass EDS testing
Should CMM-CRR interface not be completed as expected, manual process for 1st auction
Able to run an annual TCR auction in Dec 2008
For any remaining months after Nodal go-live, TCR/PCR owners will be refunded as proposed in Plan A
2007
2008
Dec | TCR Annual Auction for 2008
Feb | CRR EDS Testing
X | Refund TCR amount for remaining months
Dec | TCR Annual Auction for 2009
2009
X-2m | CRR Allocation
X-1m | CRR Auction
Date X:
Nodal Go-Live

## Slide 10: Plan to transition from TCR to CRR market – Part 2 (3/3)
Should the Nodal go-live date be postponed till after Jan 1st 2009, an alternative contingency plan is to run the 2008 TCR annual auction in Dec 07, but starting Dec 09, run only monthly TCR Auctions until the new Nodal go-live date.
TCR/PCR owners will not need to be refunded.
PCRs will be allocated monthly.
Jan | TCR Monthly Auction only
Feb | TCR Monthly Auction only
…till X
X-2m | CRR Allocation
X-1m | CRR Auction
2007
2008
Dec | TCR Annual Auction for 2008
Feb | CRR EDS Testing
Dec | TCR Monthly Auction only
2009
Date X:
Nodal Go-Live
Assumptions:
Nodal go-live date is after 1/1/09
CRR, NMMS, COMS (S&B) successfully pass EDS testing
Should CMM-CRR interface not be completed as expected, manual process for 1st auction
Able to allocate PCRs monthly
Able to run monthly auctions without holding an annual auction (will need Zonal PRR)

## Slide 11: Questions on proposed contingency plans?
Proposed next steps:
  Vote of approval on TCR to CRR transition plan (part 1)
  Nov 1st 2007: Present to TAC
  Nov 14th 2007: Post 2008 TCR Annual Auction notice
    *Notice will include refund methodology as agreed in this plan

## Slide 12: Appendix
Market Readiness Criteria
Metric CRR2 - Develop TCR to CRR Transition Plan
Reported By: ERCOT |  |  | EDS: Not Defined
Target Completion: Go Live Activities less 270 days |  |  | 
Metric Description: ERCOT will provide detailed TCR to CRR plan describing each step of the transition. |  |  | 
Background: The intent of this metric is to verify the existence and publication of the TCR to CRR transition Plan. |  |  | 
Criteria: The Readiness Team will review, from a public source, the TCR to CRR transition plan including rebate, timing and other CRR details of interest. Readiness will be achieved when the Readiness Team will be provided with documentation that verifies that the TCR to CRR transition plan has been created. TCR to CRR Transition Plan exists |  |  | 
Reporting Data Sources: TCR to CRR Transition Plan / ERCOT CRR PM |  |  | 
References | TP: N/A | TNP: |