## Working Schedule
Number | Phase | Original Name | Current Centerfold short Name | Description / Functionality | Baseline Start (Published in March) | Baseline End (Published in March) | Centerfold v10/12/2007 Start | Centerfold v10/12/2007 End | Comments | NOTES | Confidence factor to Finish on time | Ripple Effect
EDS 1
1 | FAT | N/A | EMS 1 | • Base EMS Platform (Replication, Failover etc.,) • Base EMS Data Models • Base Alarm function • Base SCADA functions • Base State Estimator • Base Network Security Analysis (RT/ST) • Base Power Flow | N/A | N/A | N/A | 2007-02-01 | > Deployed on schedule |  | Deployed
2 | FAT |  | EMS 2A | • OAG 2.4 Base to address dual redundant ICCP from TSP and QSE | N/A | 2007-05-14 | 2007-04-30 | 2007-05-11 | > Deployed on schedule |  | Deployed
3 | EDS 1 | N/A | Point to Point Beta | • To test the testing process planned for point-to-point verification of telemetry by ERCOT operators and TSP/QSE operators. • To verify real-time values and status for selected TSP and QSE stations. • To verify that the TSP and QSE substation topology diagrams match the ERCOT one line substation diagrams. • To streamline the point to point testing process and reduce the time to complete by working closely with the operators who perform the test. • To record and analyze systematic issues and to communicate back to TSPs, QSEs and ERCOT operations. • To prepare for the point-to-point testing activity. | N/A | N/A | N/A | N/A | > Started on time and finished on time > Completed milestone > Baseline dates defined in EDS 1 handbook |  | Completed
4 | EDS 1 Release 1 | Alarm Processing | Point to Point Alarm Processing | • To identify the desired alarm process configuration working with ERCOT operators • To design an approach to categorize, organize and prioritize alarms • To gain approval of the alarm configuration design by ERCOT Operations Management • Configure the approved design using the Nodal EMS (COTS) System • Verify the configuration with selected TSPs and QSEs, by having Operators randomly test selected breakers and switches and enter values that exceed selected limits to test message organization/categorization • Implement Alarm Configuration on the Nodal EMS System | 2007-04-01 | 2007-06-30 | 2007-06-01 | 2007-09-30 | > Ongoing effort as new functionality / data is released in EMS system > Testing defects and TSP/QSE functionality > On-going effort due to testing with MPs and ERCOT anytime an EMS release is deployed. |  | Low | > All EMS releases and 168 hr test will be at risk if not completed
5 | EDS 1 Release 2 | Point-to-Point Checkout | Point-to-Point Telemetry | • Verify ICCP performance for each TSP and QSE during failover configurations • Verify ICCP and EMS failover performance at ERCOT • Verify ERCOT’s substation topology diagrams match TSP’s one line diagrams • Perform point-to-point testing by station for all TSPs and QSEs o Verify status by toggling each breaker and switch and verifying change in status and in quality code o Perform analog verification by cross-checking displayed values at ERCOT and at TSPs/QSEs for each telemetered analog point o Verify correct operation of telemetered quality codes by manually replacing selected analog points • Identify issues and request TSPs and QSEs to submit change request to correct errors • Place the SCADA database under a full change control process • Resolve all outstanding PtP testing issues down to an error rate of 3% or less for each MP. | 2007-06-01 | 2007-09-30 | 2007-06-01 | 2007-09-30 | > Austin Energy will test in November, others are scheduled. > 63, 339 points out of 65, 934 points have been tested > 4 MPs still outstanding > Projection end date dependency on MPs |  | Low | > State estimator and telemetry criteria/reporting EDS2 R3 is directly tied to the completion of this release
EDS 2
6 | FAT |  | EMS 2B | • State Estimator o State Estimator Performance Standards • SCADA o Telemetry Performance Standards o RT Weather Zone calculations o Dynamic Ratings for single model o FOD – Actual Outage Detection • NSA o SPS/RAP o Constraint Management (RT Tracking and Archival) | N/A | 2007-07-05 | 2007-08-27 | 2007-09-06 | > All slack in schedule consumed by project. >Vendor functionality delivery lined up to meet EDS schedule (early drop) > Completed later than scheduled |  | Deployed | > Caused integration between EMS and MMS to be delayed > Tested late, and not corrected all defects > Impacting execution of SE tuning > Impacts exit criteria for EDS 2
7 | FAT |  | NMMS 1 | • Full CIM model • Base capability to add changes • Testing initial load from EMS • Testing NMMS to EMS functionality | N/A | 2007-06-25 | 2007-06-05 | 2007-06-25 | > Deployed with defects |  | Deployed
8 | FAT |  | NMMS 2 | • PTC UI • PTC Schema • Interfaces for NOMCR, PMCR • Full Case Builder | N/A | 2007-09-01 | 2007-07-31 | 2007-09-01 | > Deployed with defects |  | Deployed
9 | FAT |  | EDW 1 | • SE Reporting | N/A | 2007-07-15 | 2007-09-30 | 2008-01-25 | > Potential to have EDW environment in late November > Currently re-planning so dates are TBD. Revised plan will not be ready before 12/3/2007 > Still need to connect to EMS for Replication and report generation |  | Low | > Impacts ERCOT's ability to generate SE peformance reports and Telemetry availability reports
10 | FAT | N/A | NMMS 2A | • Fully functional NMMS ready for EDS 2 Release 4 | N/A | N/A | 2007-10-01 | 2007-11-01 | > Release was missing from March Baseline >Still at vendor location undergoing Pre-FAT -- planning to be out with no Sev 1 defects by 11/15 > Major HW issue (lacking clustering switches) > AREVA data load not completed |  | Low | > Directly impacts the start of EDS 2 Release 4 (11/1/2007) > Need stable model to be sent to MMS and EMS vendors for developing the CIM importers > Potential impact to Single entry model Go Live milestone (3/31/2008)
11 | FAT |  | EIP 1 | • EIP auditing mechanism for CIM importers | 2007-09-01 | 2007-10-01 | 2008-02-06 | 2008-03-11 | > Development of monitoring applications could be delayed further as resources are being assigned to help develop Real-Time reports > TIBCO monitoring of data transfer. Requires both EMS CIM importer and NMMS to be operational > Work to start as soon as valid data model in NMMS > Importers developed by EMS, MMS, and CRR vendors and EIP to develop orchestration layer only |  | Low | > Will effect EDS4 R9 testing if not complete.
12 | EDS 2 Release 3 | SE Verification | State EstimatorVerification. | Telemetry Verification • Telemetry Performance • Develop ERCOT Operations procedures to detect and correct telemetry issues State Estimator Verification • SE Tuning • Network Topology Builder • SE Performance • Develop ERCOT Operations procedures to detect and resolve SE performance issues • Bus Load Forecast Topology Consistency Analyzer • Verify incorrect status indicators • Verify alarm notification whenever there is a topology inconsistency Forced Outage Detection • Verify alarm notification on change in status of breakers and switches • Verify alarm notification when Resources, transmission lines and transformers, and Load disconnected from the Network Operations Model changes Network Security Analysis • Verify Dynamic Ratings • Overload Alarms Processor • Contingency List • Special Protection Schemes and Remedial Action Plans • Load Rollover • Transmission Constraint Management • Develop Nodal NSA operating procedures • Develop operating procedures for determining validity of constraints using Transmission Constraint Management for input into SCED • Benchmark results against Zonal real-time operations | 2007-08-15 | 2007-11-30 | 2007-09-07 | 2007-12-31 | > On going activity, but we are not reporting on results due to lack of EDW solution > Collecting data and tracking convergence rate. Can't create reports to MPs, but can query internally | > ERCOT and AREVA staff to start working on SE solution next week until convergence is within tolerance | High | > State Estimator convergence is crucial for stability of LMPs.
13 | EDS 2 Release 3 | N/A | MIS Available |  | N/A | N/A | 2007-11-01 |  | > MIS launched in EDS environment on Nov 01. > EDW reports not currently developed |  | Deployed
14 | EDS 2 Release 3 | N/A | MPs Receive performance reporting | SE and Telemetry Availability reports published to Market Participants | N/A | N/A | Nov 16, 1007 | 2007-12-31 | > Dates at risk due to FAT deployment of EDW solution not solid > Milestone detailed in EDS 2 Handbook > Report availability called out as "MIS Available" in centerfold |  | Low | > Inability to post reports impacts ERCOT's ability to exit EDS 2 Release 3 > In ability to get to 168hr test
15 | EDS 2 Release 4 | NOMCR Checkout and Network Model verification | Network Model Verification | Network Model Management System • Verify that the Network Model Management System (NMMS) database has been successfully loaded with: o Network Operations Model database o ICCP modeling point database • Verify that the NMMS database has been placed under change control • Verify NMMS integration with Nodal EMS o Compare pre and post NMMS Telemetry and State Estimator performance o Verify Nodal one-line displays against the Zonal one-line displays Network Operations Model Change Request • Verify Network Operations Model change request process (NOMCR) o Verify submission of NOMCR changes o Verify NOM has been correctly updated o Verify that ERCOT uses an automated process to manage the CIM compliant NOMCRs upload to the ERCOT Network Operations Model o Verify that non-CIM compliant, as utilized by ERCOT, package submittals are rejected o Verify NOMCRs are applied to the NOM in the correct sequence with no adverse affect on downstream applications o Verify specific NOMCR package updates to the NOM o Verify ERCOT procedure to notify NOMCR submitter when updates have been processed and implemented o Verify that the completed NOMCR is posted in CIM format to MIS o Verify the ERCOT procedure to notify NOMCR submitter when there are deficiencies. o Verify updates to clarify NOMCR have been posted to the ERCOT MIS within 3 Business Days of the submission o Verify the ERCOT procedure to approve or reject the NOMCR within 15 Business Days of the submission o Verify the ability for TSPs to submit NOMCRs up to one year prior to the implementation of changes Single Entry Model • Verify that ERCOT has processes in place to use a “single entry point” to maintain both Nodal and Zonal network model databases when MPs submit changes via the NOMCR process • Verify results of a NOMCR submitted change to both Nodal and Zonal systems using the NOMCR process Network Model Export • TSPs and QSEs may review the exported Network Operations Model o Verify that ERCOT shall make available the full transmission model that is used to manage the reliability of the transmission system. o Verify the export is in CIM format and Web-based XML communications | 2007-09-15 | 2008-01-31 | 2007-11-01 | 2008-03-31 | > Will not start Market trials without EDS HW (Production Grade) > Can start Data Sync activities with TSPs once have AREVA data export (still targetting Nov 1) > Will not start Market trials with any Sev 1 defects (with no patch plans) > Training material for TSPs nearly complete > Training class for all MPs in Beta test mode > Shown in March Timeline as "NOMCR Checkout", "Network Model Verification", "NMMS/EMS Integration" |  | Low | > Can not start Model integration testing until Release starts. > Can not complete EDS 4 testing without model
EDS 3
16 | FAT |  | REG 1 | • Registration for MPs • Registration of CRR Account holders • Ability for MPs to submit forms on-line | N/A | 2007-06-01 | 2007-04-01 | 2007-06-23 | > Completed on schedule and deployed to production with texas Set 3.0 due to code constraints |  | Deployed
17 | FAT |  | MMS 1 | • SCED • All MMS components used by SCED to compute LMPs • COP • Energy Offer Curves • Inc / Dec offer Curves • Output Schedules | N/A | 2007-06-19 | 2007-05-25 | 2007-06-19 | > Deployed on schedule at accelerated pace |  | Deployed
18 | FAT |  | EIP 2 | • SCED Input Interfaces - TPO, COP, Output Schedules and Inc/Dec Offer curves | N/A | 2007-07-31 | Sept 15 2007 | 2007-10-15 | > Deployed later than scheduled > Delayed due to MMS1 build deployed late to integration environments > Will update the centerfold with a closed triangle on finish going forward |  | Deployed | > No impact to overall schedule
19 | FAT |  | S&B 1 | • CMM base product • Template for Statements and Invoices | N/A | 2007-09-03 | 2007-06-01 | 2007-09-03 | > Completed on schedule, with defects > Met with COPs in August to finalize statements |  | Deployed | > Statements published to COPs
20 | FAT |  | EMS 2C | • NSA o Calculation of Shift Factors o MVA to MW conversion for constraints o Constraint Direction • Generation Sub-system o Resource Limit Calculator o SCED Interfaces | N/A | 2007-09-06 | 2007-08-27 | 2007-09-06 | > Deployed with defects |  | Deployed | > Needed for beginning Release 5.3 - Integrated SCED execution
21 | FAT |  | MIS 1 | • Search • Link to EDW (MIR) • Link to public data (ERCOT.com) • Click thru screens • Links to applications as available | N/A | 2007-09-30 | 2007-09-01 | 2007-09-30 | > Completed on time with defects > Future MIS releases being planned to incorporate EDW and Real Time Reports postings. Revised plan will not be available before 12/3/2007 |  | Deployed | > MIS 1 delivery enables posting of LMPs on to the website
22 | FAT |  | EIP 3 | • EMS to MMS for LMP testing • Market Queries | N/A | 2007-09-30 | 2007-10-01 | 2007-10-26 | > EMS - MMS interface deployed > Market Queries and FIP / FOP integration with MMS delayed, currently forecast to be released in January 2008 > Release will be broken up in next centerfold since EMS-MMS interface has been deployed |  | Medium | > Delivery of Market Queries web services impacts MPs ability to receive LMPs, Settlement Point Prices etc through web services
23 | FAT |  | EDW 2 | • LMP Reports | N/A | 2007-09-30 | 2007-10-05 | 2007-11-15 | > Currently re-planning. Revised plan will not be ready before 12/3/2007 > Milestone not achieved, will correct start with an open triangle going forward |  | Low | > Must be complete by 168hr test
24 | FAT | EMS 3 | EMS 3A | Final Build of • State Estimator • RT NSA • TCM | N/A | 2007-11-05 | 2007-11-05 | 2007-11-16 | > Final build of State Estimator being delivered to meet EDS 2 requirements |  | High | > EMS release is needed for complete EDS 2 Release 3 - SE tuning and verification
25 | FAT | EMS 3 | EMS 3B | • Initial build of LFC • Real Time Reporting | N/A | 2007-11-05 | 2007-11-30 | 2007-12-07 | > Partial delivery in December, some scope shifted to EMS 3C > Looking to increase scope of build to include all parts needed for LFC testing in EDS |  | Low | > EMS 3B delivery is needed for starting EDS 3 Release 6.1
26 | FAT | EMS 3 | EMS 3C | • Final Build of LFC • Inputs to HA, DA RUC • Build for DAM • Build for ASM and CIM importer | N/A | 2007-11-05 | 2008-02-08 | 2008-02-15 | > Complete delivery of LFC to align with EDS requirements > Looking to accelerate LFC to EDS 3B for MP testing |  | Low | > Can not complete LFC testing without this build
27 | FAT |  | EDW 3 | • LFC Reports | N/A | 2007-11-05 | 2007-10-25 | 2007-12-15 | > Currently re-planning. Revised plan will not be ready before 12/3/2007 > Dates are TBD until replanning is complete |  | Low | > Can not finish 168hr test without release
28 | FAT |  | EIP 4 | • MMS to EMS Interfaces for LFC | N/A | 2007-12-07 | 2007-11-17 | 2007-12-17 | > Developed and deployed as part of EMS - MMS interface testing for SCED |  | Deployed
29 | FAT | N/A | CRR 0 |  | N/A | N/A | 2007-12-01 | 2008-02-02 | > EDS milestone erroneously added to FAT line. Corresponds to EDS 3 Release 7.1 |  | N/A
30 | FAT |  | CRR 1 | • Ability to upload Input data or enter them manually via CRR UI • All CRR components necessary to run CRR Markets • CRR Database Subsystem • CRR Calculation Engine • CRR Data Interface Subsystem • CRR Market Operator and Market Participant UI • Ability to run CRR Allocations, Auctions, Bilateral Trades and export results | N/A | 2007-12-01 | 2007-09-26 | Feb 15 2008 | > FAT testing extended to include performance and stress testing > Will correct with a closed triangle going forward on start date > Date will be corrected to 1/21/2007 in future centerfold release |  | High | > Needed for EDS 3 Release 7, conducting CRR testing with Market Participants
31 | FAT |  | EIP 5 | • Registration to CRR • CMM to CRR • CRR to CMM • Registration to CMM | N/A | 2007-01-01 | 2007-12-31 | 2008-01-29 | > Currently forecast to be complete by 3/15/2008 > Manual workaround capable for EDS testing until integration is complete |  | Low | > Must complete for automated end to end before CRR Go Live
32 | FAT |  | EDW 4 | • CRR Reports | N/A | 2007-12-01 | 2007-10-30 | 2007-01-25 | > Currently re-planning. Revised plan will not be ready before 12/3/2007 > Dates are TBD until replanning is complete |  | Low | EDW does not create any reports for CRR. EDW just needs to replicate the CRR System.
33 | EDS 3 Release 5.1 | Upload Offers | SCED connectivity and validation rules checkout | • Provide a SCED environment for Market Participant EDS Activities • Verify QSEs ability to submit 3 Part Offers , COP, and Output Schedules • Verify QSEs understanding of SCED input validation rules • Utilize both the User Interface and Web Services interfaces for SCED inputs | N/A | 2007-10-01 | 2007-08-24 | 2007-10-04 | > Completed on Schedule > Shown in March Timeline as "Upload Offers" |  | Completed
34 | EDS 3 Release 5.2 | Registration | Nodal Registration Data Update | • Review Resource Asset Registration data and upload into EDS • Provide feedback to Market Participants on RARF issues, naming standards, Nodal changes for upload into test systems. • Establish initial test data for specific Network Model components • Provide EDS base data back to Market Participants for upload into systems for EDS testing • Setup predefined Offer Curves for testing • Ensure QSEs can submit submission items for all resources on a daily basis • Correct any registration and curve data to finalize a baseline set of input data • Begin SCED execution with a full set of MP input data | N/A | N/A | 2007-10-17 | 2007-10-31 | > Ongoing activity, completed round 1 of RARF on schedule, in the process for round 2, and round 3 early next year (all manual process) > Data required for MMS, NMMS, and connectivity of systems > Shown in March Timeline as "Registration" > Going forward ERCOT will split this release into the individual RARF timelines > Sufficent number of MPs have completed, ~5% outstanding as of 11/1/2007 |  | Medium | > Must be completed to complete model deployment (NMMS Go Live) > Must be complete before EDS 4 testing is complete
35 | EDS 3 Release 5.3 | SCED testing | Integrated SCED Execution Real Time ICCP | • Use RT Telemetry data • Use SCED Market Participant Offer Methodology (align with RT operations) • Verify SCED inputs from real-time operations • Verify QSE ability to receive correct Resource Base Points and LMPs via ICCP • Review SCED produced Base Points, LMPs and SPPs for reasonability (including the LMPs for Hubs and Load Zones) • For QSEs under test, allow Offers through API or UI (according to methodology - TBD) • Execute SCED and distribute test output to the QSEs participating in EDS • Review SCED output data | N/A | N/A | 2007-11-01 | 2008-01-11 | > Major milestone to start publishing LMPs. > Note initial LMP deployment is without NMMS integration (not planned until next year) > Future centerfold release will align the date back to Jan 15, th 2008 |  | Medium | > Can not start 6 month LMP posting without this release completing
36 | EDS 3 Release 5.4 | 6 month LMP Posting | 6 Month LMP Posting | • LMP reasonability attainment verified • Publish LMPs and other data available as required in the Nodal Protocols • Begin six months of SCED execution and LMP posting | N/A | 2008-07-15 | 2008-01-14 | 2008-06-15 | > Need to add one month to fit with the transition plan requirement 6 Month LMP posting |  | Medium | > Can not move to 168hr test without completing LMP reasonability
37 | EDS 3 Release 6.1 | LFC Comms and Testing | ACE calculation and preconditions | • QSE has completed AS Attestation documentation • Compare continuously for 7 days Nodal ACE results with Zonal ACE results for accuracy • Validate completion of all communication system testing • Verify calculations of HASL, LASL, SURAMP, SDRAMP, HDL, LDL • Verify ability to calculate and issue Emergency Base Points to QSEs | 2008-01-01 | 2008-03-31 | 2008-01-07 | 2008-03-31 | > Shown in March Timeline as "LFC Comms and Testing" |  | Medium | > Can not start Relesae 6.2 without completing this release
38 | EDS 3 Release 6.2 | LFC Testing | LFC testing - individual QSE | • Verify for each QSE and Resource attesting to provide Reg Up and Reg Down in Nodal, the ability to provide individual response and Regulation Control on Nodal Systems. | 2008-04-01 | 2008-06-30 | 2008-04-01 | 2008-05-25 | > Shown in March Timeline as "LFC Testing" > Confidence Factor based on EMS delivery |  | Low | > Can not start Relase 6.3 without exiting this release
39 | EDS 3 Release 6.3 | N/A | LFC testing ERCOT system | Verify for all QSE and Resource can maintain and control total system frequency on Nodal System. • 2 Hr Test • 8 Hr Test • 48 Hr Test | N/A | 2008-06-30 | 2008-06-02 | 2008-06-30 | > New milestone detailed in LFC handbook |  | Low | > Can not finish EDS 4
40 | EDS 3 Release 7.0 | N/A | Registration, Allocation pre-work, Training | • Registration of MPs as CRR Account Holders • Assign MP CRR Digital Certificate rights • NOIE contract receipt and entitlement creation in the system • NOIE load zone identification | N/A | N/A | 2007-12-01 | 2008-02-02 | > Paperwork, no system demands. Data configuration > Split into multiple phases of testing as detailed in the CRR handbook |  | High | > Required for EDS 3 Release 7.1 start
41 | EDS 3 Release 7.1 | CRR data validation | UI connectivity, data upload/download | • Validate MP CRR Digital Certificate rights • Validate AH system connection – uploads and downloads | 2008-01-02 | 2008-07-15 | 2008-02-02 | 2008-02-18 | > Split into multiple phases of testing as detailed in the CRR handbook |  | High | > All future EDS 3 R7 releases dependent on completion of this release
42 | EDS 3 Release 7.2 | N/A | Mock monthly allocation and auction (ERCOT-provided data) | • Conduct mock CRR monthly auction – ERCOT directed bids • Conduct mock CRR monthly allocation – AH created nominations • Verify market result download • Verify bilateral trade functionality | 2008-01-02 | 2008-07-15 | 2008-02-18 | 2008-03-14 | > Split into multiple phases of testing as detailed in the CRR handbook |  | High | > All future EDS 3 R7 releases dependent on completion of this release
43 | EDS 3 Release 7.3 | Trial operations of CRR | Mock monthly auction (MP-created data) | • Conduct mock CRR monthly auction – AH determined bids • Conduct secondary trading – AH directed • Verify Credit constraint in optimization | 2008-04-15 | 2008-07-15 | 2008-03-14 | 2008-04-20 | > Split into multiple phases of testing as detailed in the CRR handbook |  | Medium | > All future EDS 3 R7 releases dependent on completion of this release
44 | EDS 3 Release 7.4 | N/A | Mock multi-month allocation and auction (MP-created data) | • Conduct mock CRR annual auction – AH determined bids • Conduct mock CRR annual allocation – AH created nominations | 2008-04-15 | 2008-07-15 | 2008-04-20 | 2008-05-19 | > Split into multiple phases of testing as detailed in the CRR handbook |  | Medium | > All future EDS 3 R7 releases dependent on completion of this release
45 | EDS 3 Release 7.5 |  | Integration testing | • Optional phase to be confirmed. | N/A | N/A | TBD | 2008-07-10 | > Placeholder for integration testing of CRR > Split into multiple phases of testing as detailed in the CRR handbook |  | Medium | > All future EDS 3 R7 releases dependent on completion of this release
EDS 4
46 | FAT |  | S&B 2 | • Settlements & Billing, Statements & Invoices - Core Calculations • CMM Core Calculations | N/A | 2007-12-15 | 2007-11-01 | 2007-12-15 | > Settlements and Billing core calculations will be covered in this release. All error handling and bug fixes will be released as part of S&B 3 |  | High | > Must have for settlements and billing as well as CMM > can not perform EDS 4 R8 without all pieces
47 | FAT |  | MMS 2 | • External Interfaces • Background Process; Data Templates and Validation Rules; MOI; and MPI • DAM; DEF; HRUC; DRUC; POD; SCED Additional; and SFT • NPRR 012, 016, 033, 064, 069 • WPIDA 009 • Partial CR 010, 057 • Partial NPRR 005, 006, 035, 065, 079, • Partial WPIDA 003, 007, 015, 021, 041 • Additional Settlements Interface Tables (DAM/RUC/SCED output populated) | 2007-09-25 | 2007-10-31 | 2007-12-03 | 2008-01-11 | > Target date was Jan 11, but due to integration concerns this could be delayed till 2/15/2008 > MMS 2 from March Timeline, has been split into MMS 2, 3,4,5 |  | Medium | > Enables us to begin EDS 4 to validate MP submission items
48 | FAT |  | OS | • Nodal Outage Scheduler Full functionality | N/A | 2007-12-14 | 2008-01-21 | 2008-02-01 | > Could not make the Nov drop and instead delivered a prototype (on time) and XSD, delivered on 10/5/2007 |  | Low | > Can not complete EDS 4 R9 testing without OS > Can not complete NMMS R3 and NMMs Go Live without functionality
49 | FAT |  | NMMS 3 | • PTC Updates • Time based MP editing model • Case builder to create time based model • Outages • Contingency Editor • Fully defined Model management system • Baseline 2 • SPS/RAPs • Combined cycle • Jointly Owned Units | N/A | 2008-01-01 | 2007-12-01 | 2008-01-15 | > Impacted by delays to NMMS 2A delivery |  | Medium | > Single Entry Model Go-Live milestone is dependent on achievement of this milestone
50 | FAT |  | EIP 6 | • MMS and Settlements Interfaces | N/A | 2008-03-01 | 2007-11-01 | 2008-03-04 | > Scope moved over to CSI. > CSI being re-planned into 4 iterations with deliveries from January to May 2008. |  | Low | > Can not test static shadow settlements wihout this system and can not test MMS to COMS connections without this system
51 | FAT |  | EDW 5 | • Shadow Settlements Extracts | N/A | 2007-12-15 | 2008-01-05 | 2008-05-15 | > Currently re-planning. Revised plan will not be ready before 12/3/2007 > Dates are TBD until replanning is complete |  | Low | > Needed for shadow settlement verification
52 | FAT |  | EMS 4 | • CIM Importer Final Build of • MTLF • LTLF • RPP • Forecast Weather Data for LF • Study NSA • Support RT Stability Analysis • TCM • Dynamic Ratings • Forced Outage Detection | N/A | 2008-02-22 | 2008-01-28 | 2008-02-15 |  |  | Medium | > Needed for running the RUC market > Required for testing the CIM import from NMMS into EMS
53 | FAT |  | EDW 6 | • DAM Reports | N/A | 2008-02-22 | 2008-04-28 | 2008-06-30 | > Currently re-planning. Revised plan will not be ready before 12/3/2007 > Dates are TBD until replanning is complete |  | Low | > Required for EDS4 R9
54 | FAT |  | EIP 7 | • EMS - MMS Interfaces for DAM • NMMS to CRR • Registration to Outage Scheduler • Registration to NMMS | N/A | 2008-03-07 | 2008-02-28 | 2008-03-20 | > Currently re-planning and potential to be delayed till 4/27/2008 |  | Low | > Can not autopopulate downstream applications listed without integration > Have manual workarounds in place
55 | FAT |  | EMS 5 | • Outage Evaluation o Multi-hour STNET o Outage Sensitivity Calculations • Voltage Support | N/A | 2008-04-11 | 2008-03-05 | 2008-04-11 | > Currently forecast to be delivered by 3/31/2008 |  | Medium | > Required before starting 168hr test
56 | FAT | Dis | S&B 4 | • Disputes and Disputes Processes | N/A | 2008-05-31 | 2008-03-01 | 2008-05-31 | > Was shown as "DIS" in March Timeline |  | High | > Not needed until 168 hr test
57 | FAT |  | MMS 3 | • Includes functionality from MMS 2 release plus: • CIM importer (no dual model support) • SASM | N/A | N/A | 2008-01-24 | 2008-02-14 | > See comment under MMS 2 > New release for MMS due to functionality split |  | Low | > This is required for testing the import of the CIM model from NMMS into MMS
58 | FAT |  | S&B 3 | • Financial Transfer • Interfaces with settlements and finance • Testing of banking statements • Registration (Siebel) Clean-up fields for downstream applications to work • Settlements and Billing - Baseline 1 and Baseline 2 • Settlements and Billing - Bugfixes | N/A | N/A | 2008-01-01 | 2008-03-01 | > New milestone added for FT deployment, and S&B cleanup due to 4.7 release |  | Medium | > Required for EDS4 Release 9 testing and 168 hr test
59 | FAT |  | MMS 4 | • DC Tie, RMR Offers, VDI • NSLR, CCT, WRUC • NPRR 002, 008, 009, 014, 024, 057, 061, 062, 071 • CR 067 • WPIDA 013 • Remaining CR 010, 057 • Remaining NPRR 005, 006, 035, 047, 065, 070, • Remaining WPIDA 003, 007, 015, 021, 041 | N/A | N/A | 2008-04-07 | 2008-05-28 | > Final MMS delivery of core functionality > Baseline 1 and Baseline 2 functionality added as modified |  | Low | > Need to re-test Settlements after NPRR 35 has been implemented by ABB as part of MMS 4
60 | EDS 4 Release 8.1: | [5 empty] | TBD | TBD | > Will be finalized based with EDS4 R8 approach document |  | N/A
61 | EDS 4 Release 8.2: | [5 empty] | TBD | TBD | > Will be finalized based with EDS4 R8 approach document |  | N/A
62 | EDS 4 Release 8.3 | [5 empty] | TBD | TBD | > Will be finalized based with EDS4 R8 approach document |  | N/A
63 | EDS 4 Release 8.4 | [5 empty] | TBD | TBD | > Will be finalized based with EDS4 R8 approach document |  | N/A
64 | EDS 4 Release 9.1 | [5 empty] | TBD | TBD | > Will be finalized with EDS4 R9 approach document |  | N/A
65 | EDS 4 Release 9.2 | [5 empty] | TBD | TBD | > Will be finalized with EDS4 R9 approach document |  | N/A
66 | EDS 4 Release 9.3 | [5 empty] | TBD | TBD | > Will be finalized with EDS4 R9 approach document |  | N/A
67 | EDS 4 Release 9.4 | [5 empty] | TBD | TBD | > Will be finalized with EDS4 R9 approach document |  | N/A
68 | EDS 4 Release 9.5 | [5 empty] | TBD | TBD | > Will be finalized with EDS4 R9 approach document |  | N/A
Note on K2: rchudgar: For notes to pass to group, but will not be published