## Plan
Metric | Milestone Target Completion | Owner | Metric Measurement Start Date | Iteration | TPTF Review | TPTF Approval | TAC Approval | Release in Dashboard (NLT)
MP1 – MP Engagement | 6-month LMP posting – Start less 45 days, TBD, TBD | MP self report | 2007-06-01 | 1 | 2007-07-23 | 2007-07-23 | 2007-08-02 | 2007-09-05
N1 – ERCOT Telemetry Alarm Processing | EDS 1 – Release 1 Complete plus 14 days | EDS 1 PM | 2007-07-15 | 2 | 2007-08-13 | 2007-08-27 | 2007-09-06 | 2007-10-08
E1 - ERCOT Staff Completes Training | Start of EDS 2 | ERCOT Readiness PM | 2007-08-06 | 2 | 2007-08-13 | 2007-08-27 | 2007-09-06 | 2007-10-08
E8 – ERCOT Staffed for Texas Nodal Operations | EDS 4 – Full Nodal Functionality 24*7 Operations Major Milestone less 60 days | ERCOT Readiness PM | 2007-09-01 | 2 | 2007-08-13 | 2007-08-27 | 2007-09-06 | 2007-10-08
E9 – Develop TN Procedures | Go-Live less 60 days | ERCOT Readiness PM | 2007-09-01 | 2 | 2007-08-13 | 2007-08-27 | 2007-09-06 | 2007-10-08
MP2 – QSE with Resources Connectivity to EDS Environment | LMP Data Validation Milestone less 30 days | EDS 3 PM | 2007-09-01 | 2 | 2007-08-13 | 2007-08-27 | 2007-09-06 | 2007-10-08
MP11 – MP Registration Activities | EDS 3 – Registration EDS Trial Preparation Milestone plus 14 days | ERCOT Manager of Wholesale Client Services | 2007-09-17 | 2 | 2007-08-13 | 2007-08-27 | 2007-09-06 | 2007-10-08
E1 - ERCOT Staff Completes Training | Start of EDS 3 | ERCOT Readiness PM | 2007-10-01 | 2 | 2007-08-13 | 2007-08-27 | 2007-09-06 | 2007-10-08
MP14 – MP EDS-2 Trials Participation | EDS 2 – Start of Release 4 plus 14 days | EDS 2 PM | 2007-10-01 | 2 | 2007-08-13 | 2007-08-27 | 2007-09-06 | 2007-10-08
MP3 – QSE with Resources Upload of SCED Offers to EDS | LMP Data Validation Milestone | EDS 3 PM | 2007-10-01 | 2 | 2007-08-13 | 2007-08-27 | 2007-09-06 | 2007-10-08
MO5 – Generate LMPs for 6 months | Test 1- 6 Month LMP Posting minus 90 days | EDS 3 PM | 2007-10-15 | 3 | 2007-09-10 | 2007-09-24 | 2007-10-05 | 2007-10-15
MP1 – MP Engagement | 6-month LMP posting – Start less 45 days June 1, TBD, TBD | MP self report | 2007-10-15 | 3 | 2007-09-10 | 2007-09-24 | 2007-10-05 | 2007-10-15
MP5 – ICCP Point to Point Telemetry Test | EDS 1 - Release 2 Complete plus 14 days | EDS 2 PM | 2007-10-15 | 2 | 2007-08-13 | 2007-08-27 | 2007-09-06 | 2007-09-30
N2 – ERCOT Telemetry/ICCP System Failover | EDS 1 – Release 2 Complete plus 14 days | EDS 1 PM | 2007-10-15 | 3 | 2007-09-10 | 2007-09-24 | 2007-10-05 | 2007-10-15
E6 – Develop Nodal Operating Guides | Go Live Less 360 days | ERCOT Readiness PM | 2007-12-01 | 2 | 2007-08-13 | 2007-08-27 | 2007-09-06 | 2007-09-30
E3 – Validate Telemetry/SE-EDW/MIS Access & Data Accuracy | EDS 2 – Release 3 complete | EDS 2 PM | 2007-12-03 | 3.1 | 2007-09-10 | 2007-09-24 | 2007-10-05 | 2007-12-01
EMO9 – Validate Zonal and Nodal Common Constraints | EDS 2 Release 3 complete | EDS 2 PM | 2007-12-03 | 3.1 | 2007-09-10 | 2007-09-24 | 2007-10-05 | 2007-12-01
N3 – Validate SE performance and Accuracy | EDS 2 – Release 3 complete | EDS 2 PM | 2007-12-03 | 3.1 | 2007-09-10 | 2007-09-24 | 2007-10-05 | 2007-12-01
MP12 – MP Completes EDS-3 Related Training | First – EDS 3 – 6 Month LMP Posting Major Milestone less 30 days Second – Market Open less 30 days | MP Self Reported | 2007-12-17 | 3.1 | 2007-09-10 | 2007-09-24 | 2007-10-05 | 2007-12-01
MP6 – QSE and TSP Telemetry/ICCP System Availability | EDS 2 – Release 3 plus 14 days | EDS 1 & 2 PM | 2007-12-17 | 3.1 | 2007-09-10 | 2007-09-24 | 2007-10-05 | 2007-12-01
E1 - ERCOT Staff Completes Training | Start of EDS 4 | ERCOT Readiness PM | 2008-01-01 | 3.1 | 2007-09-10 | 2007-09-24 | 2007-10-05 | 2007-12-01
MP1 – MP Engagement | 6-month LMP posting – Start less 45 days June 1, TBD, TBD | MP self report | 2008-01-01 | 3.1 | 2007-09-10 | 2007-09-24 | 2007-10-05 | 2007-12-01
MO4 – Verify Base Point Generation | 6 Month LMP Posting plus 14 days | EDS 3 PM | 2008-01-28 | 3.1 | 2007-09-10 | 2007-09-24 | 2007-10-05 | 2007-12-01
CRR1 – Develop CRR Test Plan | 180 days prior to the first monthly CRR auction | EDS 3 PM | 2008-03-03 | 4 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
CRR2 – Develop TCR to CRR Transition Plan | Go Live Activities less 270 days | CRR PM | 2008-03-03 | 4 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
CRR3 – Trial operation of Monthly CRR Auction | EDS-3 – Release 7 complete milestone | EDS 3 PM | 2008-07-20 | 5 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
CRR4 – Implement TCR to CRR Transition Plan | Go Live Activities less 120 days | CRR PM | 2008-08-01 | 6 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
CRR5 – Trial Operation of Annual CRR Auction during Trials | EDS-3 – Release 7 Completion | EDS 3 PM | 2008-07-21 | 5 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
MP16 – MP EDS-4 Trials Participation | EDS 4 Release 9 – DAM, RUC, SASM less 14 days | EDS 4 PM | 2008-03-28 | 4 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-02-01
E12 MIS Compliance Test | EDS-4 Full Nodal Functionality Major Milestone plus 30 | MIS PM | 2008-08-04 | 6 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
E13 – Standard Form Agreements Executed | Go Live Activities less 120 days | Manager of Wholesale Client Services | 2008-09-02 | 6 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
E10 – Validate EDW Commercial Systems Access & Accuracy | EDW 6 FAT Milestone plus 90 days | EDS 4 PM | 2008-03-01 | 5 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-06-01
E11 – Validate EDW Compliance Data Access | EDW 6 FAT Milestone plus 90 days | EDS 4 PM | 2008-03-01 | 5 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-06-01
E7 – Validate EDW WEMM Access & Accuracy | EDW 6 FAT Milestone plus 90 days | EDS 4 PM | 2008-03-01 | 5 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-06-01
E5 – Nodal SAS 70 Preparedness | Go Live Activities less 45 days | ERCOT Readiness PM | 2008-10-15 | 3 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
EMO1 – Network Security Analysis & Transmission Constraint Management | EDS 2 – Release 3 complete plus 60 days | EDS 2 PM | 2008-02-02 | 4 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
EMO2 – Verify Voltage Support Functionality | EDS-4 Full Nodal Functionality Milestone | EDS 4 PM | 2008-01-01 | 5 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
CO9 – Verify Financial Transfer and Processing | EDS-4 Full Nodal Functionality Major Milestone | EDS 4 PM | 2008-03-01 | 5 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-06-01
EMO5 – Verify ACE performance | EDS-3 LFC Major Milestone Start + 30 days | EDS 3 PM | 2008-02-04 | 4 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
MO3 Verify Supplemental Ancillary Services market (SASM) | Full Nodal Functionality 24*7 Operations | EDS 4 PM | 2008-03-01 | 5 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-06-01
EMO6 – QSE Response to Dispatch | EDS-3 Major Milestone LFC Testing + 60 days | EDS 3 PM | 2008-06-02 | 5 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
MP9 – QSE, DAM MIS and Web Service Transactions | EDS-4 Release 9 – 24*7 Operations plus 7 days | EDS 4 PM | 2008-03-01 | 5 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-06-01
CO5 Verify RTM Settlement Statements | EDS-4 Release 8 complete plus 14 days | EDS 4 PM | 2008-03-01 | 5 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-06-01
CO6 – Verify RTM Settlement Invoices | EDS-4 Release 8 complete plus 14 days | EDS 4 PM | 2008-03-01 | 5 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-06-01
EMO7 – Verify Load Forecast Accuracy | EDS-4 Release 9 Start + 120 days | EDS 4 PM | 2008-01-01 | 4 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
MP10 – Mapping of Resources to Resource Nodes and Resources to Revenue Quality Meters is Complete | Start Go Live Activities less 120 days | ERCOT Manager of Wholesale Client Services | 2008-03-02 | 4 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
MP13 – MP Completes EDS-4 Related training | First – EDS 4 – Full Nodal Functionality 24*7 Operations less 20 days Second – Market Open less 30 Days | MP Self Reported | 2008-06-05 | 5 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
CO3 – Verify DAM Settlement Statements | EDS-4 Full Nodal Functionality Major Milestone plus 30 days | EDS 4 PM | 2008-03-01 | 6 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-08-01
CO7 – Verify DAM Invoices | EDS-4 Full Nodal Functionality Major Milestone plus 30 days | EDS 4 PM | 2008-08-04 | 6 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-08-01
MP15 – MP EDS-3 Trials Participation | EDS 3 trials Start plus 14 days | EDS 3 PM | 2008-04-29 | 4 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
E14 – Verify QSE Performance Monitoring Test Plan | EDS 4 – 168 Hour Test Major Milestone less 30 days | ERCOT Readiness PM | 2008-08-04 | 6 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-08-01
E15 – Verify TSP Performance Monitoring Test Plan | EDS 4 – 168 Hour Test Major Milestone less 30 days | ERCOT Readiness PM | 2008-08-04 | 6 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-08-01
E2 – Verify ERCOT Performance Monitoring Test Plan | EDS 4 - 168 Hour Test major Milestone less 30 days | ERCOT Readiness PM | 2008-08-04 | 6 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-08-01
E4 – Price Protection Mechanisms | Go Live Activities less 90 days | ERCOT Readiness PM | 2008-08-04 | 6 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-08-01
EMO8 – Conduct EECP Test | EDS 4 – 168 Hour Test Major Milestone less 30 days | EDS 2 PM | 2008-08-04 | 6 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-08-01
MP17.1 – MP Qualification Activities | EDS 4 168 Hour Testing Major Milestone less 90 days, less 30 days, less 14 days | ERCOT Manager of Wholesale Client Services | 2008-06-02 | 5 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
C010 – Verify Credit Calculations | EDS-4 168-Hour Test Major Milestone less 14 days | EDS 4 PM | 2008-08-18 | 6 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-08-01
MP17.2 – MP Qualification Activities | EDS 4 168 Hour Testing Major Milestone less 90 days, less 30 days, less 14 days | ERCOT Manager of Wholesale Client Services | 2008-08-04 | 6 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
CO8 – Verify CRR Auction Invoices | EDS-3 End of Trial Operations of CRR Major Milestone plus 30 days | EDS 4 PM | 2008-08-20 | 6 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-08-01
CO4 – Zonal/Nodal Coordinated Settlement Operations | EDS 4 168 Hour Test Major Milestone | EDS 4 PM | 2008-09-01 | 6 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-08-01
MO1 – Operate DA market for 7 Days | Full Nodal Functionality 24*7 Operations plus 60 days | EDS 4 PM | 2008-09-01 | 6 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-08-01
MO2 Operate 7 Day Market with RUC | Full Nodal Functionality 24*7 Operations plus 60 days | EDS 4 PM | 2008-09-01 | 6 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-08-01
MO6 - Verify DAM Ancillary Services | Full Nodal Functionality 24*7 Operations plus 60 days | EDS 4 PM | 2008-09-01 | 6 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-08-01
R2 – Develop Texas Nodal Market Launch Plan | Go Live Activities less 90 days | ERCOT Readiness PM | 2008-09-01 | 6 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-08-01
MP17.3 – MP Qualification Activities | EDS 4 168 Hour Testing Major Milestone less 90 days, less 30 days, less 14 days | ERCOT Manager of Wholesale Client Services | 2008-08-18 | 6 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
C1 – Contingency Plan for Weekly, Daily and Hourly RUC Failure | Go Live Activities less 60 days | EDS 4 PM | 2008-10-01 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
C2 – Contingency Plan for DAM/LMP Failure | Go Live Activities less 60 days | EDS 4 PM | 2008-10-01 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
C3 – Contingency Plan for ICCP Data Failure | Go Live Activities less 60 days | EDS 2 PM | 2008-10-01 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
C4 – Contingency Plan for SCED Failure | Go Live Activities less 60 days | EDS 3 PM | 2008-10-01 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
C5 – Contingency Plans for Key Settlement and Financial Transfer Processes | Go Live Activities less 60 days | EDS 4 PM | 2008-10-01 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
C6 – Develop Plan for SE Failure | Go Live Activities less 60 days | EDS 2 PM | 2008-10-01 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
C7 – Contingency Plan for a Backup Facility | Go Live Activities less 60 days | EDS 4 PM | 2008-10-01 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
C8- Contingency Plan for Portal/API Failure | Go Live Activities less 60 days | EDS 4 PM | 2008-10-01 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
R1 – Nodal Readiness declaration | Go Live less 60 days | ERCOT NODAL Program Executive Director | 2008-10-01 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
C10 – Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS | Go Live Activities less 60 days | EDS 4 PM | 2008-10-06 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
C9 – Contingency Plan for Site Unavailability | Go Live Activities less 60 days | EDS 4 PM | 2008-10-06 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
MP8 – QSE, AP & RTM MIS and Web Service Transactions | EDS-4 Release 9 – 24*7 Operations plus 7 days | EDS 3 & 4 PM | 2008-07-08 | 5 | 2007-11-09 | 2007-11-09 | 2007-11-29 | TBD
CO1 – Settle market for 7 Days and provide appropriate extracts | EDS-4 Release 9 Complete | EDS 4 PM | 2008-11-03 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
CO2 Verify Dispute Process of 168 Hour Test | EDS-4 Release 9 Complete | EDS 4 PM | 2008-11-03 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
EMO3 – Verify Outage Evaluation System Functionality | EDS-4 Release 9 Complete | EDS 4 PM | 2008-11-03 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
EMO4 – Run 7 Day Stability Test | Go live Less 30 days | EDS 4 PM | 2008-11-03 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01
IMM1 | EDS 4 – Release 9 Complete, Go Live Activities less 14 days | ERCOR PMO PM | 2008-11-03 | 7 | First TPTF Meeting in January | Second TPTF Meeting in January | February 2008 TAC Meeting | 2008-10-01

## Legend
Legend:
Date | Forecasted on Target
Date | Forecasted Behind Schedule (Forcast - Target <= 30 Days)
Date | Forecasted Behind Schedule (Forcast - Target > 30 Days)
Date | Milestone Complete
Date | Future Metric