Texas Nodal:

EDS CRR Testing

Market Participant Handbook

This is a living document, drafted for discussion with relevant parties. Based on workshops, ongoing planning meetings, and Nodal Project deliveries details of this document will be further refined.

v1.04

Nov 26, 2007

Revision History

| Document Revisions |  |  |  |
| --- | --- | --- | --- |
| Date | Version | Description | Author(s) |
| 2007/07/25 | 0.01 | Draft document created for EDS 3 CRR Planning Workshop w/ EDS 3 team. This version is a working draft for planning discussion. | D. Kurdy |
| 2007/07/31 | 0.02 | Updated with Phase 5 overview based on discussion with K. Sumanam; clarification edits from T. Madden; general clarification edits | D. Kurdy |
| 2007/08/01 | 0.03 | Updated with comments from the CRR Home Team and general clarification edits | D. Kurdy |
| 2007/08/14 | 0.04 | Minor consistency/clarification edits | R. Cheng |
| 2007/09/25 | 1.0 | Updated with TPTF comments from 9/25 meeting, and to reflect approval from TPTF. | R. Cheng |
| 2007/11/26 | 1.04 | - Changed phase naming convention - Changed R7.4 from multi-month auction to full annual auction (as per market readiness criteria update) - Updated details on R7.5, test data, credit, invoices, etc. | R. Cheng |

Table of Contents

1	Introduction	5

1.1	Market Participant Handbook	6

1.2	Document Structure	7

2	Overview of EDS 3 Release 7 (CRR)	8

2.1	EDS3 R7 Sub-Release Objectives	8

2.2	High-level Schedule	9

2.3	Supporting Documents	9

3	CRR – R7.0: Registration, Allocation & Training Pre-work	10

3.1	Overview	10

3.2	Market Participant Involvement	11

4	CRR – R7.1: UI Connectivity	12

4.1	Overview	12

4.2	EDS Testing Activities	14

4.3	Market Participant Involvement	16

4.4	R7.1 Exit Criteria	16

5	CRR – R7.2: Mock Monthly Allocation/Auction (Structured)	17

5.1	Overview	17

5.2	EDS Testing Activities	19

5.3	Market Participant Involvement	21

5.4	R7.2 Exit Criteria	21

6	CRR – R7.3: Mock Monthly Allocation/Auction (Unstructured)	22

6.1	Overview	22

6.2	EDS Testing Activities	24

6.3	Market Participant Involvement	26

6.4	R7.3 Exit Criteria	26

7	CRR – R7.4: Mock Annual Allocation/Auction (Unstructured)	27

7.1	Overview	27

7.2	EDS Testing Activities	29

7.3	Market Participant Involvement	31

7.4	R7.4 Exit Criteria	31

8	CRR – R7.5: Mock Monthly Auction (Unstructured)	32

8.1	Overview	32

8.2	EDS Testing Activities	34

8.3	Market Participant Involvement	36

8.4	R7.5 Exit Criteria	36

9	Appendix: EDS Defects/Issues Resolution Process	37

9.1	Issue Tracking Process	37

9.2	Issue Submission Lifecycle	37

9.3	Draft Issue Submission Form	38

- Introduction

*NOTE: THIS SECTION IS CONSISTENT ACROSS ALL EDS HANDBOOKS – IF YOU ARE FAMILIAR WITH OTHER EDS HANDBOOKS, SKIP TO RELEASE 7 (CRR) OVERVIEW.

The ERCOT Nodal Transition Plan, approved by the Technical Advisory Committee (TAC), organizes transition activities into four tracks, which required participation from both ERCOT and market participants. The Texas Nodal Program defined four Early Delivery Systems (EDS) sequences to meet the requirements of the Systems Testing and Nodal Market Implementation track of the Transition Plan. These sequences were further refined based on the Nodal project delivery schedules to group Nodal functionality and features into nine incremental software releases that will be used to meet the requirements outlined in the Nodal Transition Plan.

The EDS sequences and releases are outlined below:

EDS 1

- Release 1  –  Alarm Processing

- Release 2  –  Point-to-Point Checkout

EDS 2

- Release 3  –  Trial Operation of State Estimator & Network Security Analysis

- Release 4  –  Trial Operation of NMMS (Network Model Validation)

EDS 3

- Release 5  –  Trial Operation of SCED, 6 month LMP posting

- Release 6  –  Trial Operation of LFC, ACE

- Release 7  –  Trial Operation of CRR (This document - CRR MP Handbook)

EDS 4

- Release 8  –  Trial Operation of RT Settlements (No Extracts)

- Release 9  –  Trial Operation of DAM, RUC, SASM, Full Settlements, EDW Extracts

- TXMACS 1.0  –  Full Nodal Functionality & 168 hour testing

The Nodal program has adopted an incremental approach for releasing functionality into the EDS environment to maximize the overall benefit of EDS, by providing system functionality to the Market Participants to begin testing as early as possible. The objective of these early deliveries is to provide MPs with sufficient tools to enable development of their systems.  The EDS environment will be updated incrementally as soon as a set of Nodal functionality has been tested internally by ERCOT.  Once the integrated set of system functionality has completed the internal ERCOT quality control testing, the EDS environment will be updated for formal milestone testing activities. This incremental approach is diagramed below:

## Market Participant Handbook

The Market Participant Handbook has been created to provide a detailed testing guide for participation in the Early Delivery System (EDS) activities. The Handbooks are one of the guiding documents to help Market Participants understand how to prepare, participate and when to engage in EDS. This Handbook will cover the details for Release 7 – Trial Operation of CRR.

The testing areas described in this document will be guided by the Nodal Transition Plan and the Nodal delivery schedule; however, the detailed testing activities and schedule will be completed by working collaboratively with ERCOT subject matter experts and Market Participant representatives.

The Early Delivery Systems are intended to:

- Provide Market Participants with the tools to complete development and testing of updated Nodal systems in as realistic environment as possible.

- Validate Nodal functionality and timelines including Day-Ahead, Adjustment Period and Real-Time activities for ERCOT, Transmission Service Providers (TSPs) and Market Participants (MPs).

- Build stakeholder confidence that Nodal design and systems adhere to Nodal Protocols and Nodal Transition Plan requirements.

- Generate Locational Marginal Prices (LMPs) for distribution to ERCOT Market Participants for at least six months prior to the Nodal Markets going live.

- Confirm through a series of structured and unstructured testing that

"stable and accurate operation of the SCADA, Network Security Analysis, Transmission Constraint Management, SCED, LFC, DAM, RUC, and real time settlement system can be declared"

## Document Structure

It is critical that all participants have a common understanding of EDS activities, start dates, and participation expectations. This document will cover the following topics to ensure that both ERCOT and Market Participants are ready for each EDS phase.

Release Overview – This section outlines the specific phases, objectives, and supporting documents for the EDS Release 7 – Trial Operation of CRR.

<For Each Sub-release>

- Overview

  - EDS Environment

  - Testing Schedule

  - Functionality Available (Available Interfaces, Validation, Functionality, Data)

- EDS Testing Activities

  - Testing Structure (Required vs. Optional Involvement, Structured vs. Unstructured Testing, etc.)

  - Test Scenarios

  - Test Data

- Market Participant Involvement

  - Target Roles (Show relevant roles w/ Participation Expectations)

  - Preparation Activities (Data, Digital Certificates, Workshop involvement, New Data, Training)

  - System Readiness (MP EDS, Tools, Capabilities)

# Overview of EDS 3 Release 7 (CRR)

EDS 3 Release 7 (EDS3 R7) provides Market Participants with the opportunity to participate in the trial operation of CRR market activities including allocations, auctions and bilateral trades. EDS3 R7 progresses from UI connectivity tests and fully structured mock allocation/auction tests, to unstructured allocation/auction tests. By the end of this release, the CRR system is fully integrated with other Nodal systems; including credit assignment and invoice functionality.

Note 1: CRR-related activities in EDS 4 (DAM, Settlements) are aligned with latter EDS3 R7 sub-releases, wherever possible.

Note 2: Because participation in CRR markets is voluntary, exit criteria for this EDS release are different in nature to those EDS releases that test grid reliability functionality.

Note 3: Automated Programming Interfaces for CRR are not part of the current Nodal scope.

## EDS3 R7 Sub-Release Objectives

The Trial Operations of CRR is executed in several incremental sub-releases, until all CRR market functionality is tested. Each sub-release and its objectives are as follows:

CRR – R7.0:  Registration, Allocation and Training Pre-work

- Market Participants wishing to participate in EDS3 R7 indicate their intention to do so

- Market Participants register as CRR AHs and have appropriate test digital certificates

- Market Participants complete CRR Training

- NOIEs and McCamey WGRs submit Allocation Eligibility Form to ERCOT

- NOIEs wishing to establish own NOIE Load Zones submit relevant form

- ERCOT verifies receipt of contracts/forms and inputs this information into the system

CRR – R7.1: UI connectivity - 2/4/08

- CRR AHs are able to connect to the CRR system using a digital certificate

- CRR AHs are able to upload and download information to/from CRR system

CRR – R7.2: Mock Monthly Allocation/Auction (Structured) - 2/18/08

- ERCOT conducts mock monthly allocation (NOIEs submit ERCOT-provided nominations)

- ERCOT conducts mock monthly auction (CRR AHs submit ERCOT-provided bids and offers)

- CRR AHs bilaterally trade CRRs as orchestrated by ERCOT

CRR – R7.3: Mock Monthly Allocation/Auction (Unstructured) - 3/10/08

- ERCOT conducts mock monthly allocation (NOIEs submit self-created nominations)

- ERCOT conducts mock monthly auction (CRR AHs submit self-created bids; NOIE offers)

- CP assign credit limit to CRR market; CRR AH submits self-imposed credit limit

- CRR AHs bilaterally trade CRRs

CRR – R7.4: Mock Annual Allocation/Auction (Unstructured) - 3/31/08

- ERCOT conducts mock 24-month allocation (NOIEs submit self-created nominations)

- ERCOT conducts mock 24-month auction (CRR AHs submit self-created bids; NOIE offers)

- CP assign credit limit to CRR market; CRR AH submits self-imposed credit limit

- CRR AHs bilaterally trade CRRs

CRR – R7.5: Mock Monthly Auction (Unstructured) - TBD 5/5/08?

- ERCOT conducts mock monthly auction (CRR AHs submit self-created bids and offers)

- CP assign credit limit to CRR market; CRR AH submits self-imposed credit limit

- CRR AHs bilaterally trade CRRs

## High-level Schedule

## Supporting Documents

Documents below include guiding material and relevant forms for EDS 3 Release 7.

| Name and Description | Location |
| --- | --- |
| EDS 3 Approach The overall EDS 3 Approach document | http://nodal.ercot.com/readiness/eds3/documents/index.html (under General EDS 3 docs) |
| CRR Requirements The Congestion Revenue Rights (CRR) Requirement Specification | http://nodal.ercot.com/docs/pd/crr/index.html#req |
| CRR Conceptual System Design The CRR system design overview document | http://nodal.ercot.com/docs/pd/crr/index.html#des |
| Standard Form Market Participant Agreement | http://nodal.ercot.com/protocols/2007/08/22B/Nodal_22B-080107.doc |
| CRR Account Holder Application This form includes credit qualifications but excludes digital certification. | http://www.ercot.com/services/rq/crr/index.html |
| Allocation Eligibility Form Both PCRR and MCFRI eligibility information will be submitted to ERCOT through this form. | http://nodal.ercot.com/readiness/eds3/documents/index.html (under EDS 3 Release 7) |
| NOIE Load Zone Establishment Form This form requests information on Load Zone details. *Note: for EDS, submission of this form is not binding (testing purposes only). See Oct 2nd 07 Market Notice. | http://nodal.ercot.com/readiness/eds3/documents/index.html (under EDS 3 Release 7) |
| CRR Market Submission and Retrieval Items This describes the data entities relevant to the CRR market – includes formats (CSV, XML, etc.) and attributes. | TBD (still in draft) – currently available on TPTF review website |
| Nodal Market Notices Includes reminders, more detailed explanations, etc. | http://nodal.ercot.com/readiness/notices/index.html |
| CRR Market Participant User Manual Includes details on how to navigate around the CRR system. | TBD (still in draft) |
| CRR Training Course Materials Course material for Congestion Revenue Rights training. | http://nodal.ercot.com/training/courses/nc07.html#materials |

# CRR – R7.0: Registration, Allocation & Training Pre-work

## Overview

CRR – R7.0 covers all preparatory activities for the start of EDS 3 Release 7. This includes informing ERCOT of an intention to participate in EDS 3 Release 7, registering as a CRR Account Holder and attending relevant training courses.

For eligible NOIEs or WGRs wishing to test the allocation process or declaration of NOIE Load Zone during this EDS, this sub-release also covers the submission of (in addition to the above) the Allocation Eligibility Form and NOIE Load Zone Establishment form.

EDS Testing Schedule

The CRR Pre-EDS 3 Release 7 Testing Schedule will consist of several dates by which activities must be met:

- December 1, 2007

  - Market Participants wishing to participate in the EDS3-R7 activities must email eds3@ercot.com to inform ERCOT of their intention to do so

    - Email must include Primary Contact Name, Email and Telephone Number, as well as DUNS number of participating CRR AH.

  - NOIEs wishing to test requesting/receiving PCRRs during EDS must submit Allocation Eligibility Form, along with proof of eligibility

    - Proof of eligibility includes copy of long-term contract or, if own resource, the following: Board of Directors Resolutions, Construction Contracts, Certificates of Completion of Construction, Property Tax Statements, Insurance Policies Listing the Generation Resource or Audited Financial Statements.

  - NOIEs wishing to be considered as NOIE Load Zones per NP 3.4.3 during EDS 3 R7 must submit the NOIE Load Zone Establishment form

    - This notification will not be considered binding for Nodal go-live, however the indication will allow ERCOT to appropriately form the network model for EDS activities.

  - Wind Generation Resources (WGRs) within the boundaries McCamey Area wishing to receive MCFRIs during EDS must submit the Allocation Eligibility Form

  - NOIEs and WGRs who submit the Allocation Eligibility Form must also submit the CRR AH application.

- January 15, 2008

  - Market Participants wishing to participate in EDS3-R7 submit the CRR AH application.

  - Market Participants wishing to participate must have registered for and completed ERCOT CRR Training.

    - Note: only one representative from each participant organization is required to attend CRR Training. If not able to attend CRR courses as scheduled, please contact eds3@ercot.com.

## Market Participant Involvement

Target Roles

The relevant roles and responsibilities in R7.0 are as follows:

CRR AHs: submission of relevant paperwork; participation in CRR training

ERCOT: preparation of forms; validation of submitted paperwork; delivery of CRR training; preparation of test digital certificates

# CRR – R7.1: UI Connectivity

## Overview

This intention of CRR – R7.1 is to ensure that CRR AHs are able to connect to the CRR System, and to allow CRR AHs to familiarize themselves with the CRR Market User Interface functionality. Note: no allocations or auctions will be executed in this phase.

EDS Environment

* Note: Only the colored components will be tested during this phase.

For R7.1, the EDS environment will be upgraded to include the CRR System. The applications deployed for this sub-release will be in a testing configuration rather than a production one – they are not intended to perform to production standards at this point.

The EDS systems will be available according to the ERCOT EDS Service Level Agreement. Any changes in testing schedules will be reflected in the EDS testing calendar and communicated to Market Participants.

EDS Testing Schedule

R7.1 is currently scheduled for two weeks. It may run shorter than scheduled if all exit criteria is met before the end of two weeks.

- Monday Conference Call - Used to communicate with all EDS participants on

  - EDS activities planned for the week

  - Updates to online support documents & tools

  - Resolved issues or environment updates

- Workshops - ERCOT will guide CRR AHs through the testing activities through either WebEx, Conference Call or in-person workshops. During this time, CRR AHs will have the opportunity to ask questions and receive direct support from ERCOT Subject Matter Experts (SMEs).

- Friday Conference Call - Used to communicate with all EDS participants on

  - EDS activities accomplished during the week

  - Updates to online support documents and tools

  - Identified software or environment updates

EDS Functionality

This section outlines the system interfaces and requirements functionality that will be tested for this phase:

CRR System Functionality

* Note: Only the colored components will be tested during this phase.

| Req | Req Specification Name | Description |
| --- | --- | --- |
| FR9 | General CRR Account Holder capabilities | Partial (excludes messaging activity in this sub-release ) |
| FR22 | CRR System Access | Partial |

## EDS Testing Activities

Testing Structure

R7.1 is a fully structured test. ERCOT will provide CRR AHs with test scripts on how to log-in, download pre-auction data, upload provided bid/offer portfolios and download post-auction results. All activities are scheduled within the workshop hours. One-on-one phone support can also be scheduled in addition to workshops, if desired.

Test Scenarios

Market Information System (MIS) portal; CRR system landing page

- Log-in to MIS; view portal

- Launch CRR application through MIS; verify correct CRR AH user profile

Downloads (pre-market)

- Select active market; download pre-auction information (see Test Data below)

Allocation Manager

- Submit nominations (see Test Data below)

Auction Portfolio Manager

- Upload Bid/Offer Portfolio (see Test Data below); save

- Create New Bid/Offer Portfolio; edit a bid/offer in the portfolio; save

- Assign Bid/Offer Portfolio to active market

Downloads (post-market)

- Select market; download post-auction information (see Test Data below)

Bilateral Market

- Initiate targeted/non-targeted sell trade; accept sell trade

- Initiate non-targeted buy trades

Test Data

1. Market Submission items – refer to the CRR Market Submission/Retrieval document for details:

| Name | Data created by |
| --- | --- |
| PCRR Nominations | CRR Business team (file is provided to eligible CRR AH) |
| CRR Bid/Offer (incl. Portfolio) | CRR Business team (file is provided to CRR AH) |
| CRR Bilateral Trade Posting | CRR Business team (directs CRR AH) |

2. Market Retrieval items – refer to the CRR Market Submission/Retrieval document for details:

| Name | Data output from |
| --- | --- |
| CRR Network Model – PSSE | CRR system |
| Sources and Sinks | CRR system (CRR Business team uploads into CRR system using settlement point names from NMMS) |
| CRR Auction Results – Private | CRR system (for R7.1, the market was already pre-run by CRR Business team) |

3. Inputs from other Nodal systems into the CRR system:

| Name | Data source |
| --- | --- |
| CRR AH Information | Stubbed by CRR Business team for R7.1 |
| CRR Network Model | Stubbed by CRR Business team for R7.1 (uses PSSE output from NMMS, augments and uploads into CRR system) |
| Counter Party Credit Limit | Stubbed by CRR Business team for R7.1 |

## Market Participant Involvement

Target Roles

The relevant roles and responsibilities in R7.1 are as follows:

CRR AHs: log-in to CRR application; submission (upload) of bid/offer portfolio (provided by ERCOT); download of pre/post-auction information; initiation/acceptance of trades

ERCOT: upload of necessary system parameters, network information, credit limits and AH information to set-up and run auction (before phase starts – so participants can immediately begin downloading information), as well as orchestrate trades

Preparation Activities

To participate in any phase of EDS3-R7 Market Participants must have completed all necessary activities relevant to their role as outlined in the previous section EDS 3 R7.0.

System Readiness

Participants will require an internet connected computer, a web browser that supports java applets and an EDS 3 R7 test digital certificate.

## R7.1 Exit Criteria

All participants each successfully complete all of the following:

- Logged-in and accessed the CRR application

- Downloaded one of the pre-auction market information

- Uploaded a bid/offer portfolio (in either XML or CSV)

- Edited a bid/offer within a portfolio (confirms web browser supports java applets)

- Downloaded auction market results

- Created a sell/buy bilateral trade posting

- Accepted a sell bilateral trade posting

Note: Meeting the R7.1 exit criteria above is equivalent to completing the CRR AH Qualification Checklist, which entitles the CRR AH to a Nodal production digital certificate.

# CRR – R7.2: Mock Monthly Allocation/Auction (Structured)

## Overview

R7.2 is a fully structured test intended to demonstrate the allocation, auction and bilateral trade functionality of the system. NOIEs will be guided on how and what to submit to the allocation and CRR AHs will be provided with bid/offers that they will submit to the auction. ERCOT will engage CRR AHs to explain the auction/allocation results and describe the impacts of variation in the input data (largely bids/offers).

Note: If the CRR AH’s Counter Party is participating in EDS3 Release 7 as well, the Counter Party can test submitting a credit limit (provided by ERCOT) for this auction. If not, ERCOT will include credit limits to constrain awards in the auction.

The reason for using ERCOT-designed bids/offers is to ensure the input data will show multiple dimensions of the CRR System optimization.

EDS Environment

* Note: Only the colored components will be tested during this phase.

For R7.2, the EDS environment may include a release of the CMM application. The applications deployed for sub-release will be in a Testing configuration rather than a Production one – they are not intended to perform to production standards at this point.

The EDS systems will be available according to the ERCOT EDS Service Level Agreement. Any changes in testing schedules will be reflected in the EDS testing calendar and communicated to Market Participants.

EDS Testing Schedule

R7.2 is currently scheduled for three weeks. The first week involves just eligible NOIEs and WGRs for the mock allocation market. The second and third weeks involve all EDS3 R7 participants for the mock auction market and bilateral trades.

Note: A day is set aside to bring up to speed (if necessary) any participants who did not participate in R7.1.

See R7.1 testing schedule for more details on the conference calls/workshops.

EDS Functionality

This section outlines the system interfaces and requirements functionality that will be tested for this phase:

CRR System Functionality

* Note: All CRR components will be tested during this phase.

| Req | Req Specification Name | Description |
| --- | --- | --- |
|  | All | Partial (excluding annual auction requirements) |

## EDS Testing Activities

Testing Structure

R7.2 is a fully structured test. ERCOT will provide CRR AHs with test scripts on how to submit nominations, bids/offers, download pre-market and post-market information and conduct bilateral trades. All activities are scheduled within the workshop hours. One-on-one phone support can also be scheduled in addition to workshops, if desired.

Test Scenarios

All previously defined scenarios

Credit Assignment Manager

- Assign credit limit to market

Test Data

1. Market Submission items – refer to the CRR Market Submission/Retrieval document for details:

| Name | Data created by |
| --- | --- |
| CRR Market Credit Limit | CRR Business team (data provided to CP, if CP is participating) |
| PCRR Nominations | CRR Business team (file is provided to eligible CRR AH) |
| CRR Bid/Offer (incl. Portfolio) | CRR Business team (file is provided to CRR AH) |
| CRR Bilateral Trade Posting | CRR Business team (directs CRR AH) |

2. Market Retrieval items – refer to the CRR Market Submission/Retrieval document for details:

| Name | Data output from |
| --- | --- |
| CRR Network Model – PSSE | CRR system (CRR Business team retrieves from NMMS system, augments and uploads into CRR system) |
| McCamey Area Flowgate Limits/MCFRI Directional Network Elements | CRR system |
| One Line Diagram | Market Information Repository (MIR) – TBD |
| Outages | Market Information Repository (MIR) |
| Contingencies | CRR system |
| Non-Thermal Constraints | CRR system |
| Monitored Lines and Transformers | CRR system |
| Dynamic Ratings Inputs | Market Information Repository (MIR) |
| Sources and Sinks | CRR system |
| Allocation Results | CRR system |
| Allocation Binding Constraints | CRR system |
| Auction Results – Private | CRR system |
| Auction Results – Public | CRR system |
| Auction Flowgate Shadow Prices | CRR system |
| Auction Source/Sink Shadow Prices | CRR system |
| Auction Binding Constraints | CRR system |
| Auction Bids and Offers | CRR system |
| CRR Ownership of Record | Market Information Repository (MIR) – TBD |

3. Inputs from other Nodal systems into the CRR system:

| Name | Data source |
| --- | --- |
| CRR AH Information | Registration (integrated) |
| CRR Network Model | Stubbed by CRR Business team for R7.2 (uses PSSE output from NMMS, augments and uploads into CRR system) |
| Counter Party Available Credit Limit | Stubbed by CRR Business team for R7.2 |
| Auction Payment Confirmation | Stubbed by CRR Business team for R7.2 |
| Bilateral Trade Credit Acceptance/Rejection | Stubbed by CRR Business team for R7.2 |

## Market Participant Involvement

Target Roles

The relevant roles and responsibilities in R7.2 are as follows:

CRR AHs: nomination/bid/offer submission, download of pre/post-market information, initiation/completion of bilateral trades

Counter Party: assignment of credit limit to market

ERCOT: upload of necessary system parameters, network information, credit limits and AH information to set-up and run auction; direction of bilateral trades

Preparation Activities

To participate in any phase of EDS3-R7 Market Participants must have completed all necessary activities relevant to their role as outlined in the previous section EDS 3 R7.0.

System Readiness

Participants will require an internet connected computer, a web browser that supports java applets and an EDS 3 R7 test digital certificate.

## R7.2 Exit Criteria

All participants each successfully complete all of the following:

- Uploaded the bid/offer portfolios provided by ERCOT (in either XML or CSV)

- Downloaded auction results

- Initiated and/or accepted (as orchestrated by ERCOT) bilateral trades

- If eligible NOIE – uploaded nomination information provided by ERCOT

- If eligible NOIE – downloaded allocation results

- If CP – entered credit limit assigned to market provided by ERCOT

# CRR – R7.3: Mock Monthly Allocation/Auction (Unstructured)

## Overview

The intention of R7.3 is to allow CRR AHs to better understand the intricacies of the allocation/auction by creating their own nominations and/or bid/offer portfolios. Participants have the opportunity to test their nomination options or exercise their bidding strategies, and test bilaterally trading their allocated/awarded CRRs on their own. ERCOT SMEs will be available to support participants during these submission periods. Note, however, that ERCOT cannot provide any advice to any participant on options/strategies. Also note that because these inputs are created by CRR AHs themselves, ERCOT may not have sufficient time to evaluate the impact of each individual bid/offer and therefore may not be able to explain the results in detail.

R7.3 also enables CRR AHs to self-impose credit limits and see the effect of this binding constraint in the auction results.

This sub-release will fulfill Market Readiness Criteria CRR3 – Operation of Monthly Auction and Allocation.

EDS Environment

* Note: Only the colored components will be tested during this phase.

For R7.3, the EDS environment may include, in addition to R7.2, a release of the CMM and/or S&B applications.  The applications deployed for this sub-release will be in a Testing configuration rather than a Production one. These systems are not intended to perform to production standards at this point.

The EDS systems will be available according to the ERCOT EDS Service Level Agreement. Any changes in testing schedules will be reflected in the EDS testing calendar and communicated to Market Participants.

EDS Testing Schedule

R7.3 is scheduled for three weeks. The schedule is similar to that of R7.2 – workshop hours are scheduled so CRR AHs have an opportunity direct any questions/complications to SMEs or discuss pre-auction information (awareness of network data/inputs other than bids/offers going into the auction calculations).

Note: A day is set aside to bring up to speed (if necessary) any participants who did not participate in R7.1 or R7.2.

See R7.1 testing schedule for more details on the conference calls/workshops.

EDS Functionality

No added functionality is tested in this sub-release (see R7.2 EDS functionality), except for the ability to enter a self-imposed credit limit.

| Req | Req Specification Name | Description |
| --- | --- | --- |
|  | (All requirements in R7.2) |  |
| FR25 | CRR Auction Process | FR25.12 only - FULL |
| FR52 | Creating and Validating Bids and Offers | FR52.34 only - FULL |

## EDS Testing Activities

Testing Structure

R7.3 is an unstructured (but guided) test. Participants may be advised to limit themselves to a number of bids (or option bids). CRR AHs can use the test scripts from R7.2 as guidelines on how to submit nominations, bids/offers, download pre-market and post-market information and conduct bilateral trades. All activities are scheduled within the workshop hours. One-on-one phone support can also be scheduled in addition to workshops, if desired.

Test Scenarios

Scenarios for R7.3 are similar to R7.2 (with different data). Only addition below:

Credit Assignment Manager

- Enter self-imposed credit limit

Test Data

1. Market Submission items – refer to the CRR Market Submission/Retrieval document for details:

| Name | Data created by |
| --- | --- |
| CRR Market Credit Limit | CP |
| PCRR Nominations | CRR AH |
| CRR Bid/Offer (incl. Portfolio) | CRR AH |
| CRR Bilateral Trade Posting | CRR AH |
| Self-Imposed Credit Limit | CRR AH |

2. Market Retrieval items – refer to the CRR Market Submission/Retrieval document for details:

| Name | Data output from |
| --- | --- |
| CRR Network Model – PSSE | CRR system (CRR Business team retrieves from NMMS system, augments and uploads into CRR system) |
| McCamey Area Flowgate Limits/MCFRI Directional Network Elements | CRR system |
| One Line Diagram | Market Information Repository (MIR) – TBD |
| Outages | Market Information Repository (MIR) |
| Contingencies | CRR system |
| Non-Thermal Constraints | CRR system |
| Monitored Lines and Transformers | CRR system |
| Dynamic Ratings Inputs | Market Information Repository (MIR) |
| Sources and Sinks | CRR system |
| Allocation Results | CRR system |
| Allocation Binding Constraints | CRR system |
| Auction Results – Private | CRR system |
| Auction Results – Public | CRR system |
| Auction Flowgate Shadow Prices | CRR system |
| Auction Source/Sink Shadow Prices | CRR system |
| Auction Binding Constraints | CRR system |
| Auction Bids and Offers | CRR system |
| CRR Ownership of Record | Market Information Repository (MIR) – TBD |

3. Inputs from other Nodal systems into the CRR system:

| Name | Data source |
| --- | --- |
| CRR AH Information | Registration (integrated) |
| CRR Network Model | Stubbed by CRR Business team for R7.3 (uses PSSE output from NMMS, augments and uploads into CRR system) |
| Counter Party Credit Limit | CMM (integrated) |
| Auction Payment Confirmation | S&B (integrated) |
| Bilateral Trade Credit Acceptance/Rejection | CMM (integrated) |

## Market Participant Involvement

Target Roles

No added roles being tested in R7.3 - see R7.2 Market Participant involvement. Only addition is the ability for a CRR AH to enter a self-imposed credit limit.

Preparation Activities

To participate in any phase of EDS3-R7 Market Participants must have completed all necessary activities relevant to their role as outlined in the previous section EDS 3 R7.0.

System Readiness

Participants will require an internet connected computer, a web browser that supports java applets and an EDS 3 R7 test digital certificate.

## R7.3 Exit Criteria

This sub-release is complete when:

- The allocation successfully optimizes all submitted nominations

- The auction successfully optimizes all submitted bids/offers within required time

- The auction results are successfully downloaded by CRR AHs who wish to view them

Note: Completion of this sub-release will meet Market Readiness Criteria CRR3 – Operation of Monthly CRR Auction and Allocation.

# CRR – R7.4: Mock Annual Allocation/Auction (Unstructured)

## Overview

The intention of CRR – R7.4 is to allow CRR AHs to create their own nominations and/or bids for a full 24-month allocation and auction. Because of the multi-month time period involved, this allocation and auction is an increased level of complexity in comparison to previous sub-releases, and provides an opportunity for participants to practice bidding strategies over different months. As in R7.4, participants have the opportunity to test their nomination options or exercise their bidding strategies. ERCOT SMEs will be available to support participants during these submission periods, but cannot provide any advice to any participant on options/strategies. Similar to R7.4, ERCOT may not have sufficient time to evaluate the impact of each individual bid and therefore may not be able to explain the results in detail.

This sub-release will fulfill Market Readiness Criteria CRR5 – Operation of Annual Auction and Allocation.

Note: This test is for bids only (with the exception of PCRR offers). Results from this annual auction will serve as inputs to R7.5 (i.e. network capacity is reduced based on CRRs awarded in the annual, for that month, and CRR Owners who were awarded/traded CRRs can offer their owned CRRs in the R7.5 monthly auction).

EDS Environment

* Note: Only the colored components will be tested during this phase.

For R7.4, the EDS environment may include, in addition to R7.3, a release of the NMMS application.  At this point in the testing phase the CRR System will move largely to a production configuration – note though, that some application releases will have yet to include full go-live functionality.

The EDS systems will be available according to the ERCOT EDS Service Level Agreement. Any changes in testing schedules will be reflected in the EDS testing calendar and communicated to Market Participants.

EDS Testing Schedule

R7.4 is scheduled for four weeks. This schedule is slightly different from that of R7.2 and R7.3; differences listed below:

- An additional week was added to allow additional Q&A sessions regarding annual auctions and/or to bring any new participants up to speed

- Pre-auction information is available earlier (same week as allocation market week) to allow additional days for CRR AHs to prepare 24-month bid portfolios

- A day was set aside for ERCOT to review the auction results internally before posting them to CRR AHs

- The bilateral trade period is extended to one week – note, these trades are inputs to R7.5

See R7.1 testing schedule for more details on the conference calls/workshops.

EDS Functionality

CRR System Functionality

No added functionality is tested in this sub-release (see R7.3 EDS functionality).

| Req | Req Specification Name | Description |
| --- | --- | --- |
|  | All | Full (including annual auction parts) |

## EDS Testing Activities

Testing Structure

R7.4 is an unstructured (but guided) test. Participants may be advised to limit themselves to a number of bids (or option bids). Similar to R7.3, CRR AHs can use the test scripts from R7.2 as guidelines on how to submit nominations, bids, download pre-market and post-market information and conduct bilateral trades. All activities are scheduled within the workshop hours. One-on-one phone support can also be scheduled in addition to workshops, if desired.

Test Scenarios

Scenarios for R7.4 are similar to R7.3.

Test Data

1. Market Submission items – refer to the CRR Market Submission/Retrieval document for details:

| Name | Data created by |
| --- | --- |
| CRR Market Credit Limit | CP |
| PCRR Nominations | CRR AH |
| CRR Bid/Offer (incl. Portfolio) | CRR AH |
| CRR Bilateral Trade Posting | CRR AH |
| Self-Imposed Credit Limit | CRR AH |

2. Market Retrieval items – refer to the CRR Market Submission/Retrieval document for details:

| Name | Data output from |
| --- | --- |
| CRR Network Model – PSSE | CRR system (CRR Business team retrieves from NMMS system, augments and uploads into CRR system) |
| McCamey Area Flowgate Limits/MCFRI Directional Network Elements | CRR system |
| One Line Diagram | Market Information Repository (MIR) – TBD |
| Outages | Market Information Repository (MIR) |
| Contingencies | CRR system |
| Non-Thermal Constraints | CRR system |
| Monitored Lines and Transformers | CRR system |
| Dynamic Ratings Inputs | Market Information Repository (MIR) |
| Sources and Sinks | CRR system |
| Allocation Results | CRR system |
| Allocation Binding Constraints | CRR system |
| Auction Results – Private | CRR system |
| Auction Results – Public | CRR system |
| Auction Flowgate Shadow Prices | CRR system |
| Auction Source/Sink Shadow Prices | CRR system |
| Auction Binding Constraints | CRR system |
| Auction Bids and Offers | CRR system |
| CRR Ownership of Record | Market Information Repository (MIR) – TBD |

3. Inputs from other Nodal systems into the CRR system:

| Name | Data source |
| --- | --- |
| CRR AH Information | Registration (integrated) |
| CRR Network Model | NMMS (integrated) |
| Counter Party Credit Limit | CMM (integrated) |
| Auction Payment Confirmation | S&B (integrated) |
| Bilateral Trade Credit Acceptance/Rejection | CMM (integrated) |

## Market Participant Involvement

Target Roles

No added roles are being tested in R7.4 - see R7.3 Market Participant involvement.

Preparation Activities

To participate in any phase of EDS3-R7 Market Participants must have completed all necessary activities relevant to their role as outlined in the previous section EDS 3 R7.0.

System Readiness

Participants will require an internet connected computer, a web browser that supports java applets and an EDS 3 R7 test digital certificate.

## R7.4 Exit Criteria

This sub-release is complete when:

- The allocation successfully optimizes all submitted nominations

- The auction successfully optimizes all submitted bids within required time

- The auction results are successfully downloaded by CRR AHs who wish to view them

Note: Completion of this sub-release will meet Market Readiness Criteria CRR5 – Operation of Annual CRR Auction and Allocation.

# CRR – R7.5: Mock Monthly Auction (Unstructured)

## Overview

This intention of CRR – R7.5 is to give CRR AHs the opportunity to offer CRRs awarded in the annual auction into the monthly auction (thus, exercising the logical progression that will take place in production). This sub-release will also, similar to R7.3 and 7.4, give CRR AHs yet another opportunity to create their own bids/offers and practice bidding strategies. Note: a true-up allocation will be run before the monthly auction (again, exercising the process that will take place in production) and these allocated CRRs can be offered in to the monthly auction as well.

Another purpose of R7.5 is also to validate (if not already) the integration of CRR with its upstream Nodal systems (NMMS, S&B and CMM), and provide some data coherency between R7.4, R.7.5 and the relevant EDS 4 activities – namely, Day Ahead Market (DAM) and Settlements & Billing (S&B) activities. With that, EDS3 R7 participants who are also participating in EDS4 activities can see how their CRRs owned in R7.4 and 7.5 are settled in the DAM.

Caveat: Because of the dependencies involved in fully integrating CRR with other systems mentioned above, the schedule for this sub-release is preliminary – TBD when more EDS 4 details are known.

EDS Environment

* Note: Only the colored components will be tested during this phase.

For R7.5, the EDS environment should include all upstream systems.  At this point in the testing phase the CRR System will move largely to a production configuration – note though, that some application releases will have yet to include full go-live functionality.

The EDS systems will be available according to the ERCOT EDS Service Level Agreement. Any changes in testing schedules will be reflected in the EDS testing calendar and communicated to Market Participants.

EDS Testing Schedule

R7.5 is preliminarily scheduled for three weeks. The schedule is similar to that of R7.3.

Caveat: as mentioned in Section 8.1 Overview – dates are TBD.

See R7.1 testing schedule for more details on the conference calls/workshops.

EDS Functionality

CRR System Functionality

In addition to all functionality in R7.4, all CRR-related integration functionality will be tested.

## EDS Testing Activities

Testing Structure

R7.5 is an unstructured (but guided) test. Participants may be advised to limit themselves to a number of bids (or option bids). Similar to R7.3, CRR AHs can use the test scripts from R7.2 as guidelines on how to submit bids/offer, download pre-market and post-market information and conduct bilateral trades. All activities are scheduled within the workshop hours. One-on-one phone support can also be scheduled in addition to workshops, if desired.

Test Scenarios

Scenarios for R7.5 are similar to R7.3 (with different data). Only exception is that no nominations are submitted.

Test Data

1. Market Submission items – refer to the CRR Market Submission/Retrieval document for details:

| Name | Data created by |
| --- | --- |
| CRR Market Credit Limit | CP |
| PCRR Nominations | CRR AH |
| CRR Bid/Offer (incl. Portfolio) | CRR AH |
| CRR Bilateral Trade Posting | CRR AH |
| Self-Imposed Credit Limit | CRR AH |

2. Market Retrieval items – refer to the CRR Market Submission/Retrieval document for details:

| Name | Data output from |
| --- | --- |
| Previously Allocated/Awarded CRRs | CRR system (from R7.4) |
| CRR Network Model – PSSE | CRR system (CRR Business team retrieves from NMMS system, augments and uploads into CRR system) |
| McCamey Area Flowgate Limits/MCFRI Directional Network Elements | CRR system |
| One Line Diagram | Market Information Repository (MIR) – TBD |
| Outages | Market Information Repository (MIR) |
| Contingencies | CRR system |
| Non-Thermal Constraints | CRR system |
| Monitored Lines and Transformers | CRR system |
| Dynamic Ratings Inputs | Market Information Repository (MIR) |
| Sources and Sinks | CRR system |
| Allocation Results | CRR system |
| Allocation Binding Constraints | CRR system |
| Auction Results – Private | CRR system |
| Auction Results – Public | CRR system |
| Auction Flowgate Shadow Prices | CRR system |
| Auction Source/Sink Shadow Prices | CRR system |
| Auction Binding Constraints | CRR system |
| Auction Bids and Offers | CRR system |
| CRR Ownership of Record | Market Information Repository (MIR) – TBD |

3. Inputs from other Nodal systems into the CRR system:

| Name | Data source |
| --- | --- |
| CRR AH Information | Registration (integrated) |
| CRR Network Model | NMMS (integrated) |
| Counter Party Credit Limit | CMM (integrated) |
| Auction Payment Confirmation | S&B (integrated) |
| Bilateral Trade Credit Acceptance/Rejection | CMM (integrated) |

## Market Participant Involvement

Target Roles

No added roles are being tested in R7.5 - see R7.3 Market Participant involvement.

Preparation Activities

To participate in any phase of EDS3-R7 Market Participants must have completed all necessary activities relevant to their role as outlined in the previous section EDS 3 R7.0.

System Readiness

Participants will require an internet connected computer, a web browser that supports java applets and an EDS 3 R7 test digital certificate.

## R7.5 Exit Criteria

This sub-release is complete when:

- The auction successfully optimizes all submitted bids/offers within required time

- The auction results are successfully downloaded by CRR AHs who wish to view them

- Information is successfully received from upstream Nodal systems

# Appendix: EDS Defects/Issues Resolution Process

## Issue Tracking Process

Prior to the delivery of market systems and associated business functionality to the EDS environment each application will be run through a series of testing phases to identify and resolve as many of the defects as possible. Some of the testing phases include Pre-FAT that would be done at the vendor site, Factory Acceptance Testing (FAT) that would be executed at ERCOT and finally Integration Testing (ITest) aimed at integrate testing all Nodal applications. Defects identified during these phases would be logged and tracked internally for resolution.  Given the accelerated release of many of the systems into the EDS environment and the gradual increase in quality of systems, it is anticipated that there will be defects discovered by the Market Participants.  These defects should be reported to ERCOT using a  Market Participant Issue Reporting Form (sample in appendix).   All items will be investigated by ERCOT testing personnel and logged into the internal defect tracking system.  Defect statuses will be discussed at the end of the week wrap-up call as well as posted on the Nodal Readiness Center website which will be updated weekly (process overview in appendix- TBD)

## Issue Submission Lifecycle

## Draft Issue Submission Form