## Revision History
Date | Version | Description
2007-01-01 | 0.1 | Initial version for the 11.05 TPTF meeting
2007-11-15 | 0.2 | Update for November publication
2007-11-26 | 0.3 | Updates from TPTF 11/26/2007 meeting
2007-11-30 | 0.4 | Added EDS 4 milestones

## Legends
Instructions
The center fold and this Excel document should be used in combination, and most of the time will be released at the same time.
The purpose of the Excel document is to add additional details, as well as comments related to each milestone activity.
Legends
Key changes since last TPTF presentation
BOLD and Green | Activity complete or Software deployed in the EDS environment
Blue | Activity in progress
Deployed | The project functionality (e.g. MMS 2) is available in the EDS environment
Completed | The EDS activity is complete
Confidence Factor | Assessment made by Delivery Assurance team based on Vendor delivery and project status. Factor will change as plans solidify/change
Low | Multiple threats to success in various areas - schedule, quality, development, resources etc
Medium | Known threats with established mitigation plans
High | Few threats to meeting milestone
Questions | deliveryAssurance@ercot.com
Raj Chudgar: o: 512-248-6580, c: 832-722-6388

## Working Schedule
Number | Project / System | Phase | Original Name | Current Centerfold short Name | Description / Functionality | Baseline Start (Published in March) | Baseline End (Published in March) | Centerfold v10/12/2007 Start | Centerfold v10/12/2007 End | Current Centerfold v11/30/2007 Start | Current Centerfold v11/30/2007 End | Comments | Confidence factor to Finish on time | Dependencies | Ripple Effect
EDS 1
1 | EMS | FAT | N/A | EMS 1 | • Base EMS Platform (Replication, Failover etc.,) • Base EMS Data Models • Base Alarm function • Base SCADA functions • Base State Estimator • Base Network Security Analysis (RT/ST) • Base Power Flow | N/A | N/A | N/A | 2007-02-01 | N/A | 2007-02-01 | > Deployed on schedule | Deployed
2 | EMS | FAT |  | EMS 2A | • OAG 2.4 Base to address dual redundant ICCP from TSP and QSE | N/A | 2007-05-14 | 2007-04-30 | 2007-05-11 | 2007-04-30 | 2007-05-11 | > Deployed on schedule | Deployed | EMS1
3 |  | EDS 1 | N/A | Point to Point Beta | • To test the testing process planned for point-to-point verification of telemetry by ERCOT operators and TSP/QSE operators. • To verify real-time values and status for selected TSP and QSE stations. • To verify that the TSP and QSE substation topology diagrams match the ERCOT one line substation diagrams. • To streamline the point to point testing process and reduce the time to complete by working closely with the operators who perform the test. • To record and analyze systematic issues and to communicate back to TSPs, QSEs and ERCOT operations. • To prepare for the point-to-point testing activity. | N/A | N/A | N/A | N/A | N/A | N/A | > Started on time and finished on time > Completed milestone > Baseline dates defined in EDS 1 handbook | Completed | EMS2A
4 |  | EDS 1 Release 1 | Alarm Processing | Point to Point Alarm Processing | • To identify the desired alarm process configuration working with ERCOT operators • To design an approach to categorize, organize and prioritize alarms • To gain approval of the alarm configuration design by ERCOT Operations Management • Configure the approved design using the Nodal EMS (COTS) System • Verify the configuration with selected TSPs and QSEs, by having Operators randomly test selected breakers and switches and enter values that exceed selected limits to test message organization/categorization • Implement Alarm Configuration on the Nodal EMS System | 2007-04-01 | 2007-06-30 | 2007-06-01 | Sept. 30, 2007 | 2007-06-01 | 2008-05-01 | > Ongoing effort as new functionality / data is released in EMS system > Testing defects and TSP/QSE functionality > On-going effort due to testing with MPs and ERCOT anytime an EMS release is deployed. > Last EMS release scheduled for April 2008 > List of Alarms that have been completed will be provided by EDS group as requested. List will be updated as ERCOT continues to update functionality | Low | ALL EMS RELEASES | > All EMS releases and 168 hr test will be at risk if not completed
5 |  | EDS 1 Release 2 | Point-to-Point Checkout | Point-to-Point Telemetry | • Verify ICCP performance for each TSP and QSE during failover configurations • Verify ICCP and EMS failover performance at ERCOT • Verify ERCOT’s substation topology diagrams match TSP’s one line diagrams • Perform point-to-point testing by station for all TSPs and QSEs o Verify status by toggling each breaker and switch and verifying change in status and in quality code o Perform analog verification by cross-checking displayed values at ERCOT and at TSPs/QSEs for each telemetered analog point o Verify correct operation of telemetered quality codes by manually replacing selected analog points • Identify issues and request TSPs and QSEs to submit change request to correct errors • Place the SCADA database under a full change control process • Resolve all outstanding PtP testing issues down to an error rate of 3% or less for each MP. | 2007-06-01 | 2007-09-30 | 2007-06-01 | 2007-09-30 | 2007-06-01 | 2007-12-12 | > 2 MPs still outstanding, but have been scheduled > Projection end date to be Dec 12, 2007 | Low | EMS2A | > State estimator and telemetry criteria/reporting EDS2 R3 is directly tied to the completion of this release
EDS 2
6 | EMS | FAT |  | EMS 2B | • State Estimator o State Estimator Performance Standards • SCADA o Telemetry Performance Standards o RT Weather Zone calculations o Dynamic Ratings for single model o FOD – Actual Outage Detection • NSA o SPS/RAP o Constraint Management (RT Tracking and Archival) | N/A | 2007-07-05 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | > All slack in schedule consumed by project. >Vendor functionality delivery lined up to meet EDS schedule (early drop) > Deployed late with defects | Deployed | EMS 2A | > Caused integration between EMS and MMS to be delayed > Tested late, and not corrected all defects > Impacting execution of SE tuning > Impacts exit criteria for EDS 2
7 | NMMS | FAT |  | NMMS 1 | • Full CIM model • Base capability to add changes • Testing initial load from EMS • Testing NMMS to EMS functionality | N/A | 2007-06-25 | 2007-06-05 | 2007-06-25 | 2007-06-05 | 2007-06-25 | > Deployed with defects | Deployed
8 | NMMS | FAT |  | NMMS 2 | • PTC UI • PTC Schema • Interfaces for NOMCR, PMCR • Full Case Builder | N/A | 2007-09-01 | 2007-07-31 | 2007-09-01 | 2007-07-31 | 2007-09-01 | > Deployed with defects | Deployed | NMMS 1
9 | EDW | FAT |  | EDW 1 | • SE Reporting | N/A | 2007-07-15 | N/A | N/A | TBD | TBD | > Potential to have EDW environment in late November > Currently re-planning so dates are TBD. Revised plan will not be ready before 12/3/2007 > Still need to connect to EMS for Replication and report generation | Low |  | > Impacts ERCOT's ability to generate SE peformance reports and Telemetry availability reports
10 | NMMS | FAT | N/A | NMMS 2A | • Fully functional NMMS ready for EDS 2 Release 4 | N/A | N/A | 2007-10-01 | 2007-11-01 | 2007-11-05 | 2008-01-01 | > Release was missing from March Baseline >Software at ERCOT -- planning to to obtain patch to address Sev 1 defects by 12/15 > Major HW issue (lacking clustering switches) -- schedule to be ready by 11/30/2007 > AREVA data load fixed (can load the file) > Plan to start with connectivity testing only, until Sev 1 defect patch at ERCOT and tested by middle of Dec | Low | NMMS 2 | > Directly impacts the start of EDS 2 Release 4 (11/1/2007) > Need stable model to be sent to MMS and EMS vendors for developing the CIM importers > Potential impact to Single entry model Go Live milestone (3/31/2008)
11 | EIP | FAT |  | EIP 1 | • EIP auditing mechanism for CIM importers | 2007-09-01 | 2007-10-01 | 2008-02-06 | 2008-03-11 | 2008-02-06 | 2008-03-11 | > Development of monitoring applications could be delayed further as resources are being assigned to help develop Real-Time reports > TIBCO monitoring of data transfer. Requires both EMS CIM importer and NMMS to be operational > Work to start as soon as valid data model in NMMS > Importers developed by EMS, MMS, and CRR vendors and EIP to develop orchestration layer only | Low |  | > Will effect EDS4 R9 testing if not complete.
12 |  | EDS 2 Release 3 | SE Verification | State Estimator Verification | Telemetry Verification • Telemetry Performance • Develop ERCOT Operations procedures to detect and correct telemetry issues State Estimator Verification • SE Tuning • Network Topology Builder • SE Performance • Develop ERCOT Operations procedures to detect and resolve SE performance issues • Bus Load Forecast Topology Consistency Analyzer • Verify incorrect status indicators • Verify alarm notification whenever there is a topology inconsistency Forced Outage Detection • Verify alarm notification on change in status of breakers and switches • Verify alarm notification when Resources, transmission lines and transformers, and Load disconnected from the Network Operations Model changes Network Security Analysis • Verify Dynamic Ratings • Overload Alarms Processor • Contingency List • Special Protection Schemes and Remedial Action Plans • Load Rollover • Transmission Constraint Management • Develop Nodal NSA operating procedures • Develop operating procedures for determining validity of constraints using Transmission Constraint Management for input into SCED • Benchmark results against Zonal real-time operations | 2007-08-15 | 2007-11-30 | 2007-09-07 | 2007-12-31 | 2007-09-07 | 2007-12-31 | > On going activity, but we are not reporting on results due to lack of EDW solution > Collecting data and tracking convergence rate. Can't create reports to MPs, but can query internally | High | EMS 2B | > State Estimator convergence is crucial for stability of LMPs.
13 |  | EDS 2 Release 3 | N/A | MIS Available |  | N/A | N/A | 2007-11-01 |  | 2007-11-01 |  | > MIS launched in EDS environment on Nov 01. > EDW reports not currently developed | Deployed
14 |  | EDS 2 Release 3 | N/A | MPs Receive performance reporting | SE and Telemetry Availability reports published to Market Participants | N/A | N/A | 2007-12-31 |  | 2007-12-31 |  | > Dates at risk due to FAT deployment of EDW solution not solid > Milestone detailed in EDS 2 Handbook > Report availability called out as "MIS Available" in centerfold | Low |  | > Inability to post reports impacts ERCOT's ability to exit EDS 2 Release 3 > In ability to get to 168hr test
15 |  | EDS 2 Release 4 | NOMCR Checkout and Network Model verification | Network Model Verification | Network Model Management System • Verify that the Network Model Management System (NMMS) database has been successfully loaded with: o Network Operations Model database o ICCP modeling point database • Verify that the NMMS database has been placed under change control • Verify NMMS integration with Nodal EMS o Compare pre and post NMMS Telemetry and State Estimator performance o Verify Nodal one-line displays against the Zonal one-line displays Network Operations Model Change Request • Verify Network Operations Model change request process (NOMCR) o Verify submission of NOMCR changes o Verify NOM has been correctly updated o Verify that ERCOT uses an automated process to manage the CIM compliant NOMCRs upload to the ERCOT Network Operations Model o Verify that non-CIM compliant, as utilized by ERCOT, package submittals are rejected o Verify NOMCRs are applied to the NOM in the correct sequence with no adverse affect on downstream applications o Verify specific NOMCR package updates to the NOM o Verify ERCOT procedure to notify NOMCR submitter when updates have been processed and implemented o Verify that the completed NOMCR is posted in CIM format to MIS o Verify the ERCOT procedure to notify NOMCR submitter when there are deficiencies. o Verify updates to clarify NOMCR have been posted to the ERCOT MIS within 3 Business Days of the submission o Verify the ERCOT procedure to approve or reject the NOMCR within 15 Business Days of the submission o Verify the ability for TSPs to submit NOMCRs up to one year prior to the implementation of changes Single Entry Model • Verify that ERCOT has processes in place to use a “single entry point” to maintain both Nodal and Zonal network model databases when MPs submit changes via the NOMCR process • Verify results of a NOMCR submitted change to both Nodal and Zonal systems using the NOMCR process Network Model Export • TSPs and QSEs may review the exported Network Operations Model o Verify that ERCOT shall make available the full transmission model that is used to manage the reliability of the transmission system. o Verify the export is in CIM format and Web-based XML communications | 2007-09-15 | 2008-01-31 | 2007-10-31 | 2008-03-31 | 2008-01-15 | 2008-03-31 | > Will not start Market trials without EDS HW (Production Grade) > Can start Data Sync activities with TSPs once have AREVA data export > Will not start Market trials functionality testing with any Sev 1 defects (with no patch plans) > Training material for TSPs complete > Training class for all MPs in Beta test mode > Shown in March Timeline as "NOMCR Checkout", "Network Model Verification", "NMMS/EMS Integration" | Low | NMMS 2A, EIP 1 | > Can not start Model integration testing until Release starts. > Can not complete EDS 4 testing without model
EDS 3
16 | COMS | FAT |  | REG 1 | • Registration for MPs • Registration of CRR Account holders • Ability for MPs to submit forms on-line | N/A | 2007-06-01 | 2007-04-01 | 2007-06-23 | 2007-04-01 | 2007-06-23 | > Completed on schedule and deployed to production with texas Set 3.0 due to code constraints | Deployed
17 | MMS | FAT |  | MMS 1 | • SCED • All MMS components used by SCED to compute LMPs • COP • Energy Offer Curves • Inc / Dec offer Curves • Output Schedules | N/A | 2007-06-19 | 2007-05-25 | 2007-06-19 | 2007-05-25 | 2007-06-19 | > Deployed on schedule at accelerated pace | Deployed
18 | EIP | FAT |  | EIP 2 | • SCED Input Interfaces - TPO, COP, Output Schedules and Inc/Dec Offer curves | N/A | 2007-07-31 | Sept 15 2007 | 2007-10-15 | Sept 15 2007 | 2007-10-15 | > Deployed later than scheduled > Delayed due to MMS1 build deployed late to integration environments > Will update the centerfold with a closed triangle on finish going forward | Deployed |  | > No impact to overall schedule
19 | COMS | FAT |  | S&B 1 | • CMM base product • Template for Statements and Invoices | N/A | 2007-09-03 | 2007-06-01 | 2007-09-03 | 2007-06-01 | 2007-09-03 | > Completed on schedule, with defects > Met with COPs in August to finalize statements | Deployed |  | > Statements published to COPs
20 | EMS | FAT |  | EMS 2C | • NSA o Calculation of Shift Factors o MVA to MW conversion for constraints o Constraint Direction • Generation Sub-system o Resource Limit Calculator o SCED Interfaces | N/A | 2007-09-06 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | > Deployed with defects | Deployed | EMS 2B | > Needed for beginning Release 5.3 - Integrated SCED execution
21 | MIS | FAT |  | MIS 1 | • Search • Link to EDW (MIR) • Link to public data (ERCOT.com) • Click thru screens • Links to applications as available | N/A | 2007-09-30 | 2007-09-01 | 2007-09-30 | 2007-09-01 | 2007-09-30 | > Completed on time with defects > Future MIS releases being planned to incorporate EDW and Real Time Reports postings. Revised plan will not be available before 12/3/2007 | Deployed |  | > MIS 1 delivery enables posting of LMPs on to the website
22 | EIP | FAT |  | EIP 3 | • EMS to MMS for LMP testing • Market Queries | N/A | 2007-09-30 | 2007-10-01 | 2007-10-26 | 2007-10-01 | 2007-10-26 | > EMS - MMS interface deployed > Market Queries and FIP / FOP integration with MMS delayed, currently forecast to be released in January 2008 | Medium |  | > Delivery of Market Queries web services impacts MPs ability to receive LMPs, Settlement Point Prices etc through web services
23 | EDW | FAT |  | EDW 2 | • LMP Reports | N/A | 2007-09-30 | N/A | N/A | TBD | TBD | > Currently re-planning. Revised plan will not be ready before 12/3/2007 > Milestone not achieved, will correct start with an open triangle going forward | Low |  | > Must be complete by 168hr test
24 | EMS | FAT | EMS 3 | EMS 3A | Final Build of • State Estimator • RT NSA • TCM | N/A | 2007-11-05 | 2007-11-05 | 2007-11-16 | 2007-11-05 | 2007-11-30 | > Final build of State Estimator being delivered to meet EDS 2 requirements > Deployed with defects > In deployment process to EDS | Completed | EMS 2C | > EMS release is needed for complete EDS 2 Release 3 - SE tuning and verification
25 | EMS | FAT | EMS 3 | EMS 3B | • Initial build of LFC • Real Time Reporting | N/A | 2007-11-05 | 2007-11-30 | 2007-12-07 | 2007-11-30 | 2007-12-07 | > Very low confidence in delivery by 12/07. Currently working through critical defects identified in Pre-FAT > Will have a direct impact on start of EDS 3 Release 6.1 > Partial delivery in December, some scope shifted to EMS 3C | Low | EMS 3A | > EMS 3B delivery is needed for starting EDS 3 Release 6.1
26 | EMS | FAT | EMS 3 | EMS 3C | • Final Build of LFC • Inputs to HA, DA RUC • Build for DAM • Build for ASM and CIM importer | N/A | 2007-11-05 | 2008-02-08 | 2008-02-15 | 2008-02-08 | 2008-02-15 | > Complete delivery of LFC to align with EDS requirements > Looking to accelerate LFC to EDS 3B for MP testing | Low | EMS 3B | > Can not complete LFC testing without this build
27 | EDW | FAT |  | EDW 3 | • LFC Reports | N/A | 2007-11-05 | N/A | N/A | TBD | TBD | > Currently re-planning. Revised plan will not be ready before 12/3/2007 > Dates are TBD until replanning is complete | Low |  | > Can not finish 168hr test without release
28 | EIP | FAT |  | EIP 4 | • MMS to EMS Interfaces for LFC | N/A | 2007-12-07 | 2007-11-17 | 2007-12-17 | 2007-10-01 | 2007-10-26 | > Developed as part of EMS - MMS interface testing for SCED | Deployed
29 | CRR | FAT |  | CRR 1 | • Ability to upload Input data or enter them manually via CRR UI • All CRR components necessary to run CRR Markets • CRR Database Subsystem • CRR Calculation Engine • CRR Data Interface Subsystem • CRR Market Operator and Market Participant UI • Ability to run CRR Allocations, Auctions, Bilateral Trades and export results | N/A | 2007-12-01 | 2007-09-26 | 2008-01-21 | 2007-09-26 | 2008-01-21 | > FAT testing extended to include performance and stress testing > Will correct with a closed triangle going forward on start date | High |  | > Needed for EDS 3 Release 7, conducting CRR testing with Market Participants
30 | EIP | FAT |  | EIP 5 | • Registration to CRR • CMM to CRR • CRR to CMM • Registration to CMM | N/A | 2007-01-01 | 2007-12-31 | 2008-01-29 | 2007-12-31 | 2008-01-29 | > Currently forecast to be complete by 3/15/2008 > Manual workaround capable for EDS testing until integration is complete | Low |  | > Must complete for automated end to end before CRR Go Live
31 | EDW | FAT |  | EDW 4 | • CRR Reports | N/A | 2007-12-01 | N/A | N/A | TBD | TBD | > Currently re-planning. Revised plan will not be ready before 12/3/2007 > Dates are TBD until replanning is complete | Low |  | EDW does not create any reports for CRR. EDW just needs to replicate the CRR System.
32 | INF | FAT | N/A | MPIM | • Market Participant Identity Management |  |  | N/A | N/A | 2007-11-15 | 2007-12-07 |  | Medium
33 |  | EDS 3 Release 5.1 | Upload Offers | SCED connectivity and validation rules checkout | • Provide a SCED environment for Market Participant EDS Activities • Verify QSEs ability to submit 3 Part Offers , COP, and Output Schedules • Verify QSEs understanding of SCED input validation rules • Utilize both the User Interface and Web Services interfaces for SCED inputs | N/A | 2007-10-01 | 2007-08-24 | 2007-10-04 | 2007-08-24 | 2007-10-04 | > Completed on Schedule > Shown in March Timeline as "Upload Offers" | Completed | MMS 1, MIS 1, EIP 4, EIP 3
34 |  | EDS 3 Release 5.2 | Registration | Nodal Registration Data | • Review Resource Asset Registration data and upload into EDS • Provide feedback to Market Participants on RARF issues, naming standards, Nodal changes for upload into test systems. • Establish initial test data for specific Network Model components • Provide EDS base data back to Market Participants for upload into systems for EDS testing • Setup predefined Offer Curves for testing • Ensure QSEs can submit submission items for all resources on a daily basis • Correct any registration and curve data to finalize a baseline set of input data • Begin SCED execution with a full set of MP input data | N/A | N/A | 2007-10-17 | 2007-10-31 | 2007-10-17 | 2007-10-31 | > Sufficent number of MPs have completed, ~5% outstanding as of 11/1/2007 > Data required for MMS, NMMS, and connectivity of systems > Shown in March Timeline as "Registration" | Completed | REG 1 | > Must be completed to complete model deployment (NMMS Go Live) > Must be complete before EDS 4 testing is complete
35 |  | EDS 3 Release 5.3 | SCED testing | Integrated SCED Execution Real Time ICCP | • Use RT Telemetry data • Use SCED Market Participant Offer Methodology (align with RT operations) • Verify SCED inputs from real-time operations • Verify QSE ability to receive correct Resource Base Points and LMPs via ICCP • Review SCED produced Base Points, LMPs and SPPs for reasonability (including the LMPs for Hubs and Load Zones) • For QSEs under test, allow Offers through API or UI (according to methodology - TBD) • Execute SCED and distribute test output to the QSEs participating in EDS • Review SCED output data | N/A | N/A | 2007-11-01 | 2008-01-11 | 2007-11-01 | 2008-01-11 | > Major milestone to start publishing LMPs. > Note initial LMP deployment is without NMMS integration (not planned until next year) > Future centerfold release will align the date back to Jan 15, th 2008 | Medium | MMS 1, MIS 1, EIP 4, EIP 3, EDS 3 Release 5.1 | > Can not start 6 month LMP posting without this release completing
36 |  | EDS 3 Release 5.4 | 6 month LMP Posting | 6 Month LMP Posting | • LMP reasonability attainment verified • Publish LMPs and other data available as required in the Nodal Protocols • Begin six months of SCED execution and LMP posting | N/A | 2008-07-15 | 2008-01-14 | 2008-07-15 | 2008-01-14 | 2008-07-15 |  | Medium | EDW 3 Release 5.3 | > Can not move to 168hr test without completing LMP reasonability
37 |  | EDS 3 Release 6.1 | LFC Comms and Testing | ACE calculation and preconditions | • QSE has completed AS Attestation documentation • Compare continuously for 7 days Nodal ACE results with Zonal ACE results for accuracy • Validate completion of all communication system testing • Verify calculations of HASL, LASL, SURAMP, SDRAMP, HDL, LDL • Verify ability to calculate and issue Emergency Base Points to QSEs | 2008-01-01 | 2008-03-31 | 2008-01-07 | 2008-03-31 | 2008-01-07 | 2008-02-28 | > Shown in March Timeline as "LFC Comms and Testing" | Low | EMS 3A | > Can not start Relesae 6.2 without completing this release
37.5 |  | EDS Release 6.2A | LFC Testing | n/a | • Shakeout period for early adopters to start LFC shakeout before formal testing is started. This will be staggered for QSEs as the Phase 6.2 starts. | n/a | n/a | n/a | n/a | 2008-02-25 | 2008-03-01 | > Not shown in centerfold > Early adopters will start shake out testing with ERCOT before testing begins (similar to Point to Point checkout concept) |  | EMS 3B, EDS Release 6.1
38 |  | EDS 3 Release 6.2 | LFC Testing | LFC testing - individual QSE | • Verify for each QSE and Resource attesting to provide Reg Up and Reg Down in Nodal, the ability to provide individual response and Regulation Control on Nodal Systems. | 2008-04-01 | 2008-06-30 | 2008-04-01 | 2008-05-25 | 2008-03-01 | 2008-05-25 | > Shown in March Timeline as "LFC Testing" > Confidence Factor based on EMS delivery > All QSEs should be be able to test LFC by April 11th 2007 | Low | EMS 3B, EDS 3 Release 6.1 | > Can not start Relase 6.3 without exiting this release
39 |  | EDS 3 Release 6.3 | N/A | LFC testing ERCOT system | Verify for all QSE and Resource can maintain and control total system frequency on Nodal System. • 2 Hr Test • 8 Hr Test • 48 Hr Test | N/A | 2008-06-30 | 2008-06-02 | 2008-06-30 | 2008-06-01 | 2008-06-30 | > New milestone detailed in LFC handbook | Low | EMS 3C, EDS 3 Release 6.2 | > Can not finish EDS 4
40 |  | EDS 3 Release 7.0 | N/A | Registration, Allocation pre-work, Training | • Registration of MPs as CRR Account Holders • Assign MP CRR Digital Certificate rights • NOIE contract receipt and entitlement creation in the system • NOIE load zone identification | N/A | N/A | 2007-12-01 | 2008-02-02 | 2007-12-01 | 2008-02-02 | > Paperwork, no system demands. Data configuration > Split into multiple phases of testing as detailed in the CRR handbook | High |  | > Required for EDS 3 Release 7.1 start
41 |  | EDS 3 Release 7.1 | CRR data validation | UI connectivity, data upload/download | • Validate MP CRR Digital Certificate rights • Validate AH system connection – uploads and downloads | 2008-01-02 | 2008-07-15 | 2008-02-02 | 2008-02-18 | 2008-02-02 | 2008-02-18 | > Split into multiple phases of testing as detailed in the CRR handbook | High | CRR1 | > All future EDS 3 R7 releases dependent on completion of this release
42 |  | EDS 3 Release 7.2 | N/A | Mock monthly allocation and auction (ERCOT-provided data) | • Conduct mock CRR monthly auction – ERCOT directed bids • Conduct mock CRR monthly allocation – AH created nominations • Verify market result download • Verify bilateral trade functionality | 2008-01-02 | 2008-07-15 | 2008-02-18 | 2008-03-14 | 2008-02-18 | 2008-03-14 | > Split into multiple phases of testing as detailed in the CRR handbook | High | CRR1, EDS 3, Release 7.1 | > All future EDS 3 R7 releases dependent on completion of this release
43 |  | EDS 3 Release 7.3 | Trial operations of CRR | Mock monthly auction (MP-created data) | • Conduct mock CRR monthly auction – AH determined bids • Conduct secondary trading – AH directed • Verify Credit constraint in optimization | 2008-04-15 | 2008-07-15 | 2008-03-14 | 2008-04-20 | 2008-03-14 | 2008-04-20 | > Split into multiple phases of testing as detailed in the CRR handbook | Medium | CRR1, EDS 3, Release 7.2 | > All future EDS 3 R7 releases dependent on completion of this release
44 |  | EDS 3 Release 7.4 | N/A | Mock multi-month allocation and auction (MP-created data) | • Conduct mock CRR multi-month auction – AH determined bids • Conduct mock CRR multi-month allocation – AH created nominations | 2008-04-15 | 2008-07-15 | 2008-04-20 | 2008-05-19 | 2008-04-20 | 2008-05-19 | > Split into multiple phases of testing as detailed in the CRR handbook | Medium | CRR1, EDS 3, Release 7.2 | > All future EDS 3 R7 releases dependent on completion of this release
45 |  | EDS 3 Release 7.5 |  | Integration testing | • Optional phase to be confirmed. | N/A | N/A | TBD | 2008-07-10 | TBD | 2008-07-10 | > Placeholder for integration testing of CRR > Split into multiple phases of testing as detailed in the CRR handbook | Medium |  | > All future EDS 3 R7 releases dependent on completion of this release
EDS 4
46 | COMS | FAT |  | S&B 2 | • Settlements & Billing, Statements & Invoices - Core Calculations • CMM Core Calculations | N/A | 2007-12-15 | 2007-11-01 | 2007-12-15 | 2007-11-01 | 2007-12-15 | > Settlements and Billing core calculations will be covered in this release. All error handling and bug fixes will be released as part of S&B 3 | High |  | > Must have for settlements and billing as well as CMM > can not perform EDS 4 R8 without all pieces
47 | MMS | FAT |  | MMS 2 | • External Interfaces • Background Process; Data Templates and Validation Rules; MOI; and MPI • DAM; DEF; HRUC; DRUC; POD; SCED Additional; and SFT • NPRR 012, 016, 033, 064, 069 • WPIDA 009 • Partial CR 010, 057 • Partial NPRR 005, 006, 035, 065, 079, • Partial WPIDA 003, 007, 015, 021, 041 • Additional Settlements Interface Tables (DAM/RUC/SCED output populated) | 2007-09-25 | 2007-10-31 | 2007-12-03 | 2008-01-11 | 2007-12-03 | 2008-01-11 | > Currently working to finish MMS submission items integration by Jan 15 for EDS 9.1 release > MMS 2 from March Timeline, has been split into MMS 2, 3,4,5 | Medium |  | > Enables us to begin EDS 4 to validate MP submission items
48 | MMS | FAT |  | OS | • Nodal Outage Scheduler Full functionality | N/A | 2007-12-14 | 2008-01-21 | 2008-02-01 | 2008-01-21 | 2008-02-01 | > Could not make the Nov drop and instead delivered a prototype (on time) and XSD, delivered on 10/5/2007 | Low |  | > Can not complete EDS 4 R9 testing without OS > Can not complete NMMS R3 and NMMs Go Live without functionality
49 | NMMS | FAT |  | NMMS 3 | • PTC Updates • Time based MP editing model • Case builder to create time based model • Outages • Contingency Editor • Fully defined Model management system • Baseline 2 • SPS/RAPs • Combined cycle • Jointly Owned Units | N/A | 2008-01-01 | 2007-12-01 | 2008-01-15 | 2008-01-15 | 2008-03-15 | > Impacted by delays to NMMS 2A delivery | Low | NMMS 2A, EIP 1 | > Single Entry Model Go-Live milestone is dependent on achievement of this milestone
50 | EIP | FAT |  | EIP 6 | • MMS and Settlements Interfaces | N/A | 2008-03-01 | 2007-11-01 | 2008-03-04 | 2007-11-01 | 2008-03-04 | > Scope moved over to CSI. > CSI being re-planned into 4 iterations with deliveries from January to May 2008. | Low |  | > Can not test static shadow settlements wihout this system and can not test MMS to COMS connections without this system
51 | EDW | FAT |  | EDW 5 | • Shadow Settlements Extracts | N/A | 2007-12-15 | N/A | N/A | TBD | TBD | > Currently re-planning. Revised plan will not be ready before 12/3/2007 > Dates are TBD until replanning is complete | Low |  | > Needed for shadow settlement verification
52 | EMS | FAT |  | EMS 4 | • CIM Importer Final Build of • MTLF • LTLF • RPP • Forecast Weather Data for LF • Study NSA • Support RT Stability Analysis • TCM • Dynamic Ratings • Forced Outage Detection | N/A | 2008-02-22 | 2008-01-28 | 2008-02-15 | 2008-01-28 | 2008-02-15 | > On target to complete testing by Feb 15, 2008 | Medium | EMS 3C | > Needed for running the RUC market > Required for testing the CIM import from NMMS into EMS
53 | EDW | FAT |  | EDW 6 | • DAM Reports | N/A | 2008-02-22 | N/A | N/A | TBD | TBD | > Currently re-planning. Revised plan will not be ready before 12/3/2007 > Dates are TBD until replanning is complete | Low |  | > Required for EDS4 R9
54 | EIP | FAT |  | EIP 7 | • EMS - MMS Interfaces for DAM • NMMS to CRR • Registration to Outage Scheduler • Registration to NMMS | N/A | 2008-03-07 | 2008-02-28 | 2008-03-20 | 2008-02-28 | 2008-03-20 | > Currently re-planning and potential to be delayed till 4/27/2008 | Low |  | > Can not autopopulate downstream applications listed without integration > Have manual workarounds in place
55 | EMS | FAT |  | EMS 5 | • Outage Evaluation o Multi-hour STNET o Outage Sensitivity Calculations • Voltage Support | N/A | 2008-04-11 | 2008-03-05 | 2008-03-31 | 2008-03-05 | 2008-03-31 | > Currently forecast to be delivered by 3/31/2008 | Medium | EMS 4 | > Required before starting 168hr test
56 | MMS | FAT |  | MMS 3 | • Includes functionality from MMS 2 release plus: • CIM importer (no dual model support) • SASM • Settlements and Billing snapshots | N/A | N/A | 2008-01-24 | 2008-02-14 | 2008-02-15 | 2008-03-31 | > Program has communicated the vendor to deliver on these dates. Currently working through issues to ensure delivery > New release for MMS due to functionality split > high confidence on SASM delivery on time, but CIM importer has many depenencies on it so low confidence | Low |  | > This is required for testing the import of the CIM xml from NMMS into MMS
57 | COMS | FAT |  | S&B 3 | • Financial Transfer • Interfaces with settlements and finance • Testing of banking statements • Registration (Siebel) Clean-up fields for downstream applications to work • Settlements and Billing - Baseline 1 and Baseline 2 • Settlements and Billing - Bugfixes | N/A | N/A | 2008-01-01 | 2008-03-01 | 2008-01-01 | 2008-03-01 | > New milestone added for FT deployment, and S&B cleanup due to 4.7 release | Medium |  | > Required for EDS4 Release 9 testing and 168 hr test
58 | COMS | FAT | Dis | S&B 4 | • Disputes and Disputes Processes | N/A | 2008-05-31 | 2008-03-01 | 2008-05-31 | 2008-03-01 | 2008-05-31 | > Was shown as "DIS" in March Timeline | High |  | > Not needed until 168 hr test
59 | MMS | FAT |  | MMS 4 | • All functionality needed for 168 hour test including Baseline 1 & 2 | N/A | N/A | 2008-04-07 | 2008-05-28 | 2008-04-22 | 2008-07-01 | > Program has communicated the vendor to deliver on these dates. Currently working through issues to confirm delivery | Low |  | > Need to re-test Settlements after NPRR 35 has been implemented by ABB as part of MMS 4
60 |  | EDS 4 Release 8.1: |  | CMM and CRR Invoices | > Post CP Credit limit on MIS > Post mock CRR auction invoices > Post CRR auction invoices based on actual CRR testing results | TBD | TBD | TBD | TBD | 2008-03-01 | 2008-08-31 | > May 1 is the target start for Mock settlements and July 1 is the target start date for integrated settlements with extracts | Medium
61 |  | EDS 4 Release 8.2: |  | DAM Settlements and Invoices | > Post mock DAM Settlement Statements and Invoices > Post mock CRR balancing account invoices, CARD Invoices, Late Fee Invoices > Post DAM Settlement Statements and Invoices based on EDS DAM testing results > Validate DAM Re-settlement Statements and Invoices | TBD | TBD | TBD | TBD | 2008-05-01 | 2008-08-31 | > May 1 is the target start for Mock settlements and July 1 is the target start date for integrated settlements with extracts | Medium
62 |  | EDS 4 Release 8.3 |  | RTM Settlements and Invoices | > Post mock RT Settlement Statements and Invoices > Post RT Settlement Statements and Invoices based on EDS RTM testing results > Post settlement extracts | TBD | TBD | TBD | TBD | 2008-05-01 | 2008-08-31 | > May 1 is the target start for Mock settlements and July 1 is the target start date for integrated settlements with extracts | Medium
63 |  | EDS 4 Release 8.4 |  | Verifiable Costs | > Verifiable costs | TBD | TBD | TBD | TBD | 2008-03-01 | 2008-08-31 | > Will need to work with MPs on "real" verifiable cost versus EDS verifiable cost information > changes will be packaged with Retail release to production | Medium
64 |  | EDS 4 Release 8.5 |  | Disputes | > Disputes | TBD | TBD | TBD | TBD | 2008-06-01 | 2008-08-31 | > Changes are packaged with retail release to production | Medium
65 |  | EDS 4 Release 9.1 |  | DAM / RUC Submission testing | > MP submission of > Three Part Supply Offers (to include Start-Up and Min Energy costs) > DAM Energy Only Offers > A/S Offers > CRR Offers > DAM Energy Bid > PTP Obligation Bid > Capacity trade > Energy Trade > AS Trade > AS Self-Arrangement > DC-Tie Schedules | TBD | TBD | TBD | TBD | 2008-01-15 | 2008-03-31 |  | Medium
66 |  | EDS 4 Release 9.2 |  | Outage Scheduler submission testing | > Outage Scheduler submission testing | TBD | TBD | TBD | TBD | 2008-03-18 | 2008-08-15 |  | Medium
67 |  | EDS 4 Release 9.3 |  | Initial DAM / RUC Execution | > Execution of DAM > Execution of RUC > Posting of DAM and RUC results (QSE A/S Obligations, Load Profiles, Hourly Load Forecast (MTLF), Distribution Loss Factors, Wind Generation Renewable , Production Potential, Post Available Credit Limits (ACL), Post System Wide Offer Caps) > Dynamic Ratings | TBD | TBD | TBD | TBD | 2008-04-01 | 2008-05-15 |  | Low
68 |  | EDS 4 Release 9.4 |  | DAM, RUC and Adj Period Execution | > ERCOT perform pre-DAM evaluation and posting > QSE submission of DAM/RUC bids/offers > ERCOT execution of DAM and posting of results > QSE submission of updates to COP and Trades > ERCOT execution of DRUC and posting of results > ERCOT Adjustment Period Activities, Hour Ahead Sequence > QSE submissions continue for Adjustment Period > ERCOT executes HRUC > ERCOT executes SASM > ERCOT Operating Hour Activities, including SCED | TBD | TBD | TBD | TBD | 2008-05-01 | 2008-06-30 |  | Low
69 |  | EDS 4 Release 9.5 |  | Execute full Nodal Integrated System | > Fully integrated Nodal system | TBD | TBD | TBD | TBD | 2008-07-01 | 2008-08-31 |  | Low
MP Activities
70 |  | MP Activities |  | RARF 2 |  | N/A |  | N/A |  | 2007-11-09 |  |  | N/A
71 |  | MP Activities |  | RARF 3 |  | N/A |  | N/A |  | 2007-12-31 |  |  | N/A
72 |  | MP Activities |  | RARF Complete |  | N/A |  | N/A |  | 2008-04-01 |  |  | N/A
73 |  | MP Activities |  | Begin 6 Month LMP Posting |  | N/A |  | N/A |  | 2008-01-15
74 |  | MP Activities |  | DAM Readiness | > Ability to input the following transactions into MMS system > Three Part Supply Offers (to include Start-Up and Min Energy costs) > DAM Energy Only Offers > Ancillary Service Offers > CRR Offers > DAM Energy Bid > PTP Obligation Bid > Capacity trade > Energy Trade > Ancillary Service Trade > Ancillary Service Self-Arrangement > DC-Tie Schedules | N/A |  | N/A |  | 2008-01-15
75 |  | MP Activities |  | Begin LFC 6.2 testing | > Start MP level LFC testing. All MPs should be ready to test LFC with ERCOT | N/A |  | N/A |  | 2008-03-01
76 |  | MP Activities |  | LFC Readiness | > Prepare to demonstrate the ability of Resources to respond correctly to the UDBP’s as calculated by LFC > Ability to receive Responsive reserve deployment signal, update Responsive Reserve Ancillary Service Schedule(s) and provide updated schedules to ERCOT | N/A |  | N/A |  | 2008-04-11
77 |  | MP Activities |  | Begin LFC 6.3 testing | > Start of full market testing of LFC | N/A |  | N/A |  | 2008-06-01
78 |  | MP Activities |  | CRR Readiness | > Register as a CRR Account Holder and complete the ERCOT CRR Training | N/A |  | N/A |  | 2008-01-15
79 |  | MP Activities |  | Begin CRR Testing | > Start full CRR auction testing | N/A |  | N/A |  | 2008-02-02
80 |  | MP Activities |  | PCRR Allocation | > PCRR allocation before 1st CRR Monthly auction | N/A |  | N/A |  | 2008-10-01
Go-Live Activities
81 |  | Go-Live Activities |  | MP Interface Spec. |  | 2007-03-31 |  | 2007-03-31 |  | 2007-03-31 |  |  | N/A
82 |  | Go-Live Activities |  | Single-Entry Model |  | 2008-03-31 |  | 2008-03-31 |  | 2008-03-31 |  |  | N/A
83 |  | Go-Live Activities |  | 1st CRR Monthly Auction |  | N/A | N/A | 2008-11-03 |  | 2008-11-03 |  |  | N/A
84 |  | Go-Live Activities |  | 168-Hour test |  | 2008-08-31 |  | 2008-08-31 |  | 2008-08-31 |  |  | N/A
85 |  | Go-Live Activities |  | RTM Go-Live |  | 2008-12-01 |  | 2008-12-01 |  | 2008-12-01 |  |  | N/A
86 |  | Go-Live Activities |  | DAM Go-Live |  | 2008-12-08 |  | 2008-12-08 |  | 2008-12-08 |  |  | N/A