## Slide 1: COMS Nodal Commercial Systems Project Update
COPs Meeting
December 2007
Raj Chudgar & Bill Barnes

## Slide 2: Agenda
Item | Purpose | Presenter
Deliverables Update | For Information | Bill Barnes
Delivery Schedule Update | For Information | Justin Rasberry
Questions | For Information | Bill and Justin

## Slide 3: COMS Requirements Update
Activities around baseline 2 synchronization are continuing, all 23 requirements have been updated and submitted for TPTF approval
All associated documentation (use cases, CSDs, test cases, etc) will be updated as Baselines approved
COPs personnel should stay abreast with COMS requirement changes.

## Slide 4: COMS CSD Update
All COMS Conceptual System Design (CSDs) will be rolled into the v3.0(thru baseline 2) and submitted to TPTF following approval of the requirements

## Slide 5: Nodal Statements and Invoices – Presentation Format
Finalize Late Fee Invoice presentation format
  Detailed Option Preferred at Nov COPs
  Do not show days where late fee is $0
Review Invoice presentation format
  Dec COPs - Uplift Invoice

## Slide 6: Development Update
Detailed Design on task
  Final Draft 1 complete
  Will continue to update with “As-Built” information throughout development cycle
Lodestar version 4.7 continues to stabilize
  Corrected majority of major issues which impacted design and build strategies
  Monitoring remaining issues and enhancements to ensure we stay on schedule
  Remains a risk to overall S&B coding delivery schedule
    Risk probability reduced as major issues corrected
Lodestar metadata changes remain ongoing
Unit testing in progress
  Initial testing at the Modular level and will “build up” to batch
Build 1 complete: FAT in progress

## Slide 7: Development Update
Most build packages consists of multiple modules
  Modules aligned into business functional components (i.e. DAM Energy, DAM AS, CRR, etc.)
Target FAT completion by late 4th quarter 2007
Target SAT completion by late 1st quarter 2008
Currently, Lodestar S&B slated for EDS 3 & 4
  Statements and Invoice format for EDS 3
  Shadow Settlements EDS 4 (requires Extracts)
Settlements Go Live with 1st CRR auction

## Slide 8: Questions ??
Justin Rasberry
Manager, MO DPO
Market Operations Divisional Projects Organization
ERCOT
(512) 248-3991
jrasberry@ercot.com
Bill Barnes
Manager, Settlements and Billing
ERCOT
(512) 248-6850
bbarnes@ercot.com