## Slide 1: Texas Nodal Program Update
Jerry Sullivan, Executive Director

## Slide 2: Agenda
Item | Who | Purpose
Nodal Program Status | Jerry Sullivan | For Information
Delivery Assurance Group | Jerry Sullivan | For Information
Schedule and Cost Discussion | Jerry Sullivan | For Information
Sponsorship and Metrics | Jerry Sullivan | For Information
Budget Discussion | Jerry Sullivan | For Information

## Slide 3: Overall program status remains amber
Cost
Schedule
Scope / Quality
Legend
Summary
Green
Latest forecast (Oct 31) approximately $285.3M with continuing focus on finding efficiencies and savings without compromising quality.
Amber
Amber
Currently fully aligned with protocols
Red
Amber
Green
Estimate at Complete = <$263m
Estimate at Complete = < $263m + 10%
Estimate at Complete = >$263m + 10%
Go-live = 12/1/08
Go-live = <30 days+
Go-live = >30 days+
Program is aligned with current protocols
Program is aligned to previous protocol version
Program is not aligned to protocols
New Release Management tool
Improves controls and traceability for releases across the program
Automates manual processes
Amber
Current product quality is not sufficient for Nodal launch
Most Nodal products currently achieve quality standards
All Nodal products currently achieve quality standards
Now being managed by Delivery Assurance Group
Nodal
Delivery
Quality
Schedule
Cost

## Slide 4: Delivery Assurance Group approved timeline
We have concurrence / understanding of our detailed schedule with TPTF which we now discuss on a regular basis
December 1 is achievable
EDS 3 and 4 is a major focus
We still have issues with EDW and Real-Time Reporting

## Slide 5: Schedule and Cost
Schedule issues
  Currently we are still striving to make the Dec 1st Go Live date.
  While we have some scheduling uncertainty, we are working to develop fully resourced plans to make our Go Live date.
Cost issues
  We are reviewing every project for possible staffing and vendor savings.
  We are negotiating with major vendors for schedule and cost certainty.
  We are reviewing costs to ensure a quality delivery with no ‘boxed out’ protocols (i.e. to deliver full functionality).

## Slide 6
ERCOT Executive sponsorship of the Nodal Program is aligned to the project level

## Slide 7: ERCOT Engagement and Readiness Status
Results have been exposed via the Readiness Scorecard, transparent to all
Metric measurements become more rigorous as iterations progress
Second round of self reporting for ERCOT leadership will be live November 27. Will drill down to manager level
Focus will be on specific mobilization and engagement
Any negative responses will create a RED status
ERCOT leadership will have view into all metrics, internal and external by mid-December
ERCOT Readiness Transition team will continue working with groups not achieving green statuses

## Slide 8: Market Readiness Update – Scorecard
Austin Energy GREEN for ICCP Testing. Two MPs still outstanding for ICCP Testing and will report RED in next measurement.
Last iteration of survey results are RED for QSEs without resources based on non-engagement.
The second iteration of Self-Reporting live November 16th and is open through December 3rd
Rules and questions in this round are more specific, including LSE-specific metrics
Achieving GREEN self-reporting status in the second round will require more activity than last metric measurement (ie: activity and not just a response)
http://Scorecard.ercot.com
Clear path to Green status for all segments in the next few weeks via completed ICCP testing and updated Survey results
.
.
.
.

## Slide 9: Budget Update - Cost Element Summary

## Slide 10: Budget Update – Project Summary

## Slide 11: Release Management Update HP Openview PPM implementation
Value Proposition:
  Formalized SDLC will allow us to manage release volume for across Nodal Projects
Benefits:
  Creates repeatable processes for ERCOT to carry forward
  Establishes ‘immediate’ and future release management process control for internal teams
  Helps identify redundancies and delays with visibility into release management process and decision points
  Clarifies distinction between enhancements, bug fixes, and integration issues (ie: transparency via version control)
  Automates Migration Control Document submission
  Provides inbuilt scripting of ‘undo’ function for release management and application support teams
Limitations:
  Additional cost
  Cycles required for rollout, training, and multiple queues is additional strain on resources
Next Steps:
  Release Management team to work with project managers to prioritize rollouts
  Richard Howard and Christian Brennan teams to begin immediate screen capture of MCR related work

## Slide 12: Questions
<number>
<footer>
Questions ??
ERCOT Nodal Market Transition
Notes: <number>
<footer>
<header>
<date/time>
<number>