|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for November 2007 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | ERCOT is currently tracking 204 active generation interconnection requests totaling over 87,000 MW. This includes over 39,000 MW of Wind Generation. |  |  |  |  |  |  |  |
| 2. | Regional Planning is currently reviewing proposed transmission improvements with an estimated total cost of $105.6 M. |  |  |  |  |  |  |  |
| 3. | Report of Congestion Events presented to WMS November 14, 2007 |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1.	New Generation Beginning Commercial Operations	1

1.2.	Active Generation Interconnection Requests	1

1.3.	Potential Future Generation Interconnections	2

2.	Regional Planning Group Project Reviews	4

3.	Congestion Management	5

4.	Other Notable Activities	5

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” data folder posted in the “Operations and System Planning” data area on the ERCOT website.

## New Generation Beginning Commercial Operations

No new generators went into commercial operation in November 2007.

## Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Currently tracking 204 active generation interconnection or change requests As of November 30, 2007 |  |  |  |  |  |
|  |  | North | South | West | Total |
| Security Screening Study |  | 8 | 4 | 24 | 36 |
| SSS Completed |  | 6 | 3 | 9 | 18 |
| Full Interconnect Study |  | 20 | 28 | 62 | 110 |
| FIS Completed |  | 0 | 2 | 2 | 4 |
| Interconnect Agreement Completed |  | 8 | 4 | 24 | 36 |
| Capacity for Grid, MW |  | 26,619 | 24,794 | 36,255 | 87,668 |
| Wind Capacity, MW |  | 2,083 | 4,043 | 33,510 | 39,636 |

| Fuel | Public (MW) | Non-public (MW) | Total (MW) |
| --- | --- | --- | --- |
| Natural gas | 3,730 | 23,942 | 27,672 |
| Nuclear | 5,986 | 6,400 | 12,386 |
| Coal | 4,841 | 2,708 | 7,549 |
| Wind | 9,531 | 30,106 | 39,636 |
| Other | 0 | 425 | 425 |
| Totals | 24,088 | 63,581 | 87,668 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter)

| FUTURE GENERATION INTERCONNECTIONS (PUBLIC PROJECTS) As of November 30, 2007 |
| --- |
| INR # | Site Name | Status | County | Region | Fuel | In Service Date | MW into Grid | Change from Last Report |
| 06INR0021 | Barton Chapel | IA | Jack | North | Wind | Oct-07 | 120 |  |
| 07INR0003 | Whirlwind | IA | Floyd | West | Wind | Oct-07 | 60 |  |
| 07INR0034 | Wolf Ridge | IA | Cooke | North | Wind | Oct-07 | 201 | Signed IA |
| 07INR0049 | J T Deely Upgrade | PL | Bexar | South | Coal | Nov-07 | 80 | Public Letter |
| 03INR0034 | Silver Star Project - Clipper | IA | Erath | North | Wind | Dec-07 | 60 |  |
| 04INR0017 | Ocotillo Wind Farm 1 | IA | Howard | West | Wind | Dec-07 | 59 |  |
| 04INR0020 | Project Snyder | IA | Scurry | West | wind | Dec-07 | 63 |  |
| 07INR0010 | Stanton Wind Energy | IA | Martin | West | Wind | Dec-07 | 101 |  |
| 07INR0028 | Goat Wind | IA | Sterling | West | Wind | Dec-07 | 150 |  |
| 07INR0045 | Airtricity Champion | IA | Scurry | West | Wind | Dec-07 | 126 |  |
| 07INR0045 | Roscoe 1 | IA | Scurry | West | Wind | Mar-08 | 209 |  |
| 07INR0030 | Louis (Buffalo Gap 3) | IA | Nolan | West | Wind | Apr-08 | 138 |  |
| 06INR0035 | Colorado Bend Energy Center 2 | IA | Wharton | South | Gas | May-08 | 275 |  |
| 06INR0036 | Quail Run Energy Center 2 | IA | Ector | West | Gas | May-08 | 275 |  |
| 07INR0022 | Airtricity Panther Creek | IA | Howard | West | Wind | Jun-08 | 150 |  |
| 04INR0011 | Cottonwood Wind | IA | Shackelford | West | Wind | Aug-08 | 100 |  |
| 04INR0011 | Mesquite Wind Phase 4 | IA | Shackelford | West | Wind | Aug-08 | 136 |  |
| 03INR0030 | Wild Horse 2 | IA | Cottle | West | Wind | Aug-08 | 39 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Wind | Sep-08 | 194 |  |
| 07INR0025 | Airtricity Lamesa Wind Plant | IA | Dawson | West | Wind | Oct-08 | 183 |  |
| 07INR0037 | Bull Creek Wind Plant | IA | Borden | West | Wind | Oct-08 | 180 |  |
| 07INR0045 | Airtricity Inadale | IA | Scurry | West | Wind | Nov-08 | 212 |  |
| 07INR0045 | Airtricity Pyron | IA | Scurry | West | Wind | Nov-08 | 303 |  |
| 05INR0015 | Gulf Wind 1 | IA | Kenedy | South | Wind | Dec-08 | 187 |  |
| 04INR0011 | Hackberry Wind Farm | IA | Shackelford | West | Wind | Dec-08 | 165 |  |
| 06INR0022 | Penascal Wind Farm 1 | IA | Kenedy | South | Wind | Dec-08 | 202 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Wind | Dec-08 | 120 |  |
| 07INR0005 | Notrees-1 | IA | Ector | West | Wind | Dec-08 | 151 |  |
| 07INR0011 | Turkey Track Energy Center | PL | Nolan | West | Wind | Dec-08 | 300 |  |
| 07INR0029 | South Trent Wind Farm | IA | Taylor | West | Wind | Dec-08 | 101 |  |
| 08INR0018 | Gunsight Energy Center | IA | Howard | West | Wind | Dec-08 | 200 | Signed IA |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Wind | Dec-08 | 300 |  |
| 08INR0059 | Gray Wind Project | PL | Borden | West | Wind | Dec-08 | 141 |  |
| 08INR0046 | Bosque Expansion | IA | Bosque | North | Gas | Mar-09 | 255 |  |
| 08INR0047 | Buffalo Gap 4 | PL | Nolan | West | Wind | Mar-09 | 378 |  |
| 06INR0006 | Cobisa-Greenville | PL | Hunt | North | gas | May-09 | 1750 |  |
| 08INR0040 | Lenorah Project | PL | Martin | West | Wind | May-09 | 350 |  |
| 09INR0028 | V H Braunig 6 | PL | Bexar | South | Gas | May-09 | 185 |  |
| 09INR0060 | Wind Tex Energy Stephens Wind Farm | PL | Borden | West | Wind | May-09 | 141 |  |
| 09INR0026 | Sterling Energy Center | PL | Sterling | West | Wind | Jun-09 | 300 |  |
| 09INR0027 | Winchester Peaking Plant | PL | Fayette | South | gas | Jun-09 | 200 | Public Letter |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Wind | Jun-09 | 500 |  |
| 09INR0045 | Sand Hill Peakers | PL | Travis | South | Gas | Jun-09 | 90 | Public Letter |
| 08INR0003 | Sandow 5 | IA | Milam | North | Coal | Jul-09 | 581 |  |
| 05INR0015 | Gulf Wind 2 | PL | Kenedy | South | Wind | Sep-09 | 400 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Wind | Sep-09 | 1001 |  |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Nuclear | Oct-09 | 86 |  |
| 03INR0030 | Wild Horse Wind Farm 1 | IA | Cottle | West | Wind | Nov-09 | 60 | Changed date |
| 09INR0006 | Oak Grove SES 1 | IA | Robertson | North | Coal | Nov-09 | 855 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | Coal | Dec-09 | 165 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Wind | Dec-09 | 200 |  |
| 09INR0037 | Camp Springs Energy Center III | PL | Scurry | West | Wind | Mar-10 | 350 |  |
| 09INR0006 | Oak Grove SES 2 | PL | Robertson | North | Coal | May-10 | 855 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | coal | Jun-10 | 750 |  |
| 05INR0015 | Gulf Wind 3 | PL | Kenedy | South | Wind | Sep-10 | 400 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | coal | Sep-10 | 925 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Wind | Dec-10 | 400 |  |
| 11INR0007 | Mountain Creek | PL | Dallas | North | Gas | Apr-11 | 700 | Changed date |
| 11INR0001 | Twin Oaks 3 | PL | Robertson | North | coal | Jun-11 | 630 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Wind | Jul-12 | 400 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Nuclear | Jan-15 | 3200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Nuclear | Jan-15 | 2700 |  |
|  |  |  |  |  |  | Total | 24,088 |  |

# Regional Planning Group Project Reviews

- Luminant has submitted two interrelated, yet independent projects for review.  The first project is an acceleration of the planned upgrade of the Tyler Northeast to Tyler East 138 kV line, currently planned to be complete in May 2012, to May 2009 with an estimated total project cost of $4 M.  The second related project is the addition of the Tyler Grande (Tyler Southeast) 345/138 kV autotransformer and an increase in the planned capacity of Tyler Grande (Southeast) to Tyler South from 326 MVA to 400 MVA.  The second project is planned to be complete in May 2009 with a cost of approximately $10 M and will require ERCOT Board approval due to the new 345/138 kV Tyler Grande switching station and associated autotransformer. This project is in ERCOT Independent Review.

- Oncor submitted a project to rebuild the Big Spring – Chalk – McDonald Road 69 kV line.  This project will alleviate overloads due to new wind projects on the Morgan Creek to McDonald Road 138 kV circuit by adding a new 138 kV from Big Spring into McDonald Road on double circuit 138/69 kV structures that will replace the existing 69 kV single circuit structures.  The cost of the project is $10.8 M and due for completion in December 2008.  This project is now in ERCOT Independent Review, which ends January 3rd.

- Oncor submitted a project to relieve congestion that will occur when two new Wind units are connected to the transmission system in the Lamesa area.  This project will upgrade both ends, but not the middle of the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, and build a new 138 kV Ackerly Vealmoor station.  All transmission rebuilds will utilize double circuit construction with one circuit in place, except the Lamesa to Ackerly Vealmoor 138/69 kv double circuit.  The cost of these upgrades is $40.3 M.  This project has additional work to be done for a third wind unit that will add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The additional cost of these upgrades is $40.5 M.  This project is now in ERCOT Independent Review, which ends December 28th.

# Congestion Management

- The following is a summary of the Congestion Report presented to WMS on November 14, 2007.

|  | Duration in 2007 | Planned Outages | Financial Impact |
| --- | --- | --- | --- |
| Northeast | 10/25 – 10/26 11/2 – 11/4 | Martin Lake to Tri Corner | $1.5M in local congestion costs |
|  | 10/29 – 11/1 | Martin Lake to Elkton | $1.3M in local congestion costs |
| South -> Houston (reported in last month’s report) | 10/1 – 10/3 | STP to Hillje | $7.2M in zonal congestion charges $14.9M paid to TCR holders $7.7M uplifted to BENA |
| North | 11/1-11/12 | Gibbons Creek to Twin Oak Switch | $9.5M in directly assigned zonal congestion charges $14.2M paid to TCR holders $4.6M uplifted to BENA |
|  |  |  | $328k OOMC costs |

The above dollar amounts are estimated and therefore are NOT Settlement quality.

# Other Notable Activities

- The Wind Impact/Ancillary Services study is near completion.  GE is evaluating 4 scenarios of wind capacity on the system:  5,000 MW, 2 scenarios of 10,000 MW, and 15,000 MW.  Phase I of the study (a statistical analysis of increased variability with increasing amounts of wind) was completed in October.  GE is currently finalizing Phase II of the study, an analysis of the ramping capabilities of units in the existing ERCOT generation fleet and determination of required ancillary services.  Draft Phase II results are expected within the next two weeks.

- CREZ Study (SB20)

  - System Planning is analyzing transmission solutions as part of the CREZ Transmission Optimization Study.  The next RPG-CREZ Task Force meeting will be held on December 14, 2007

- 2007 Five Year Plan

  - Economic phase is nearing completion

  - Starting the write-up of the Five Year Plan documentation

- The TPIT With Cost was sent to TO’s and the TPIT No Cost report has been posted and sent to RPG members and TOs.

- The 2007 Constraints and Needs Report will be published mid-December.