## Slide 1: NMMS schedule and delivery capability
John Moseley
Network Modeling Group

## Slide 2: NMMS High Level Timeline
2007
2008
2009
April ’07:
Phase 1a Build Complete
June ’07:
Phase 1b Complete
Jan ’08:
Interface with EMS Complete
Oct ’07:
Input Nodal Data with TSP
Aug ’07:
Phase 1c Complete
Feb ’08:
NMMS Model checkout
Nov ’07:
TSP Training on NMMS starts
Dec ’07:
Phase 2 Complete
Mar ’08:
Start TSP transition to NOMCR from SR
Jun ’08:
Shut down SR, all TSP transitioned to NOMCR
Aug ’08:
All Planning data in NMMS
Dec ’08:
Nodal Go Live

## Slide 3: NMMS Schedule
 | Phase 1A Deliverables | Apr-07
 | · IMM 1.0 | 
 | · Thick Client | 
 | · Topology Processor | 
 | · IMM 1.0/MOD integration to produce bus/branch model | 
 | Phase 1B Deliverables | Jun-07
 | · Project Tracker & Coordinator (PTC) UI | 
 | · PTC schema | 
 | · PTC Interfaces for NOMCR, PMCR, and SAMR | 
 | · TNA Network Applications | 
 | · Pre-release of Case Builder | 

## Slide 4: NMMS Schedule
Phase 1C Deliverables | Sep-07
· PTC updates | 
· Time based Market Participant editing | 
· Case Builder to create time based models | 
· Contingency Editor | 
ERCOT will deploy Phase 1c to Early Delivery System (EDS) 2 for TSP testing and model verification.
TSPs will be asked to verify data in NMMS model including new fields (e.g. ownership, Electrical Bus). TSP size will determine effort
ERCOT will provide hands on training to TSP to convert over to NMMS from Service Requests (SR)

## Slide 5: NMMS Timeline with TSPs
Final NMMS Modal checkout will be in early 2008 in order to start converting all TSP from SR to NOMCR
ERCOT will continue to input changes into current Zonal modeling system until or past Nodal Go Live (~Dec 2008) as required.
No double submissions of data will be required by MPs
Risk:
Thus far, ERCOT is on schedule, to avoid significant issues due to rapid delivery and parallel design input with less time for corrections, ERCOT is requesting that TSPs bring up any concerns to ERCOT early and often.

## Slide 6: NMMS Information
First, if you have not already, sign up on the NMFG email list.
  http://lists.ercot.com
Second, the website:
  http://nodal.ercot.com/docs/pd/nmms/
Finally, my email
  jmoseley@ercot.com
Questions?