## Open TX SET Action Items
Date Opened | Action Item | Resolution | Status | Date Last Updated
2007-01-07 | TX SET Issue 650_02 YNQ Segment (Issue 2006-I046) - (Suzette Sondag) This is considered a guide clean-up on a non-emergency basis. This is combining the 2-YNQ segments into one YNQ segment. Approved as written and will need to be submitted into change control; Suzette Sondag will prepare draft and submit. | Approved as written and needs to be written as a change control. Suzette Sondag will write the change control. 02/22/07 -- Change Control still needs to written or combined into one change control already created by Susan Munson 2007-705 03/28/07 Leave pending until time can be allotted for discussion till open item until change control is updated or introduced 05/23/07 - still open item until change control is updated or introduced 07/12/2007 - Suzette will write change control | Pending | 2007-07-12
2007-01-07 | TX SET Issue 810_02 BIG 05 Replacement Cross Reference - (Issue 2006-I047) (Suzette Sondag) – Changes were discussed and made to the proposed language. TX SET agreed that a change control was needed to be clear on the process and to prevent development issues with validation. Change control will be written by Suzette Sondag. | Approved as written and needs to be written as a change control. Suzette Sondag will write the change control. 02/22/07 -- Change Control still needs to written or combined into one change control already created by Susan Munson 03/28/07 - Same status as last month 04/25/07 - still open item until change control is updated or introduced till open item until change control is updated or introduced 05/23/07 - still open item until change control is updated or introduced 07/12/2007 - Suzette will write change control | Pending | 2007-07-12
2007-01-07 | TX SET Issue 814_03 and 814_14 Clean-up of Customer Name Information in gray boxes - (2006-I048) (Rob Bevill) Approved by TX SET – clean-up to the guides because of the process was changed via the Rulemaking. | Approved as written Rob Bevill will write a change control to correct the guides with the appropriate process that was approved and scheduled for implementation with 3.0 for Customer Billing Information 02/22/07 -- Change Control still needs to written or combined into one change control already created by Susan Munson 2007-705 03/28/07 - Same status as last month 04/25/07 - still open item until change control is updated or introduced 05/23/07 - still open item until change control is updated or introduced 07/12/2007 -Rob will write change control | Pending | 2007-07-12
2007-03-07 | Susan Munson/Catherine Meiners to remove Drop to AREP references from the version of the Solution to Stacking Guide located on the Texas Standard Electronic Transaction Guides page of ERCOT.com. | 04/25/2007 - Redlined and posted to the Website under 4/25/07 TX SET meeting. Waiting for MPs to review for approval at the May TX SET Meeting 05/23/2007- Document written, but not reviewed/approved by TX SET with redlined changes 07/12/2007 - Susan and Catherine have made updates to Solution to Stacking Guide but changes have not been reviewed by TX SET. Change will be placed on the August agenda for review and approval by TX SET. | Pending | 2007-07-12
2007-04-07 | TX SET issue needed to revise grayboxes on 650_04 for use of BGN06 on reconnect for denial of access. In addition, this issue will contain changes for Disconnect for Non-pay BGN matching discussed at previous meeting. | Cary Reed to write TX SET issue for future implementation (after Texas SET 3.0) 05/23/2007 - Issue document will be written by Cary Reed | Pending | 2007-07-12
2007-05-07 | Clarifying language is needed in the 814_28 PT Implementation Guide | 05/23/2007 - Catherine Meiners to write the TX SET issue 07/12/2007 - Catherine wrote redline changes that were review my TX SET, however Cary Reed suggested making some changing to existing language for more clarification. Cary will redline document with those corrections and submit to TX SET for review/approval | Pending | 2007-07-12
2007-05-07 | For Issue 059, a change control is needed for clarification so that the 814_14 will look just like the 05. | 05/23/2007 - Kyle Patrick to write change control 07/12/2007 - Kyle should have change control available for next meeting in August | Pending | 2007-07-12
2007-05-07 | Review Issues/Change controls for future implementation. Also, there is a need to show better visibility between issues and related change controls. | 5/23/2007 - Susan Munson to add change control number to issues log to tie them together. TX SET leadership and ERCOT to review Issues/Change Control lists to see what change controls need to be written for future implementation 07/12/2007 - Rob, Susan, and Kathy will schedule a meeting prior to August TX SET/MCT meeting to clear-up/organize issues/change control documents on ERCOT.com TX SET website | Pending | 2007-07-12
2007-05-07 | MOU/EC 810 Transactional Issues | 5/23/2007 - Eloise Flores to write TX SET Issue for potential MOU/EC Transactional Changes 07/12/2007- Issue 2007-I060 was approved by TX SET and now change control needs to be written to add new SAC04 codes to 810_03 transaction | Pending | 2007-07-12
2007-07-07 | Include TTPT V3.0 Lessons Learned with TX SET Lessons Learned | 7/12/2007 - Kyle Patrick to bring TTPT V3.0 Lessons Learned to MCT/TX SET Lessons Learned session in August | Pending | 2007-07-12
2007-07-07 | Investigate use of tick marks in data (emailed question from Suzette Sondag). Should this cause a transaction reject? | 7/12/2007 - Kim Wall to research 4010 extended character sets and report back to TX SET | Pending | 2007-07-12
2007-07-07 | Review all reject codes and their uses on transactions (ex. NFI Reject Code on 814_25) | 7/12/2007 - Cary Reed to write issue and change control to disallow TDSPs from using NFI on 814_25. TX SET to review uses of all reject codes on all transactions. | Pending | 2007-07-12
2007-07-07 | TDSPs need to see 814_21 rejects from the CR since they need to know the reason for reject. Currently, these do not get forwarded to the TDSP. | 7/12/2007 - Dave Lowder to compile preliminary list of rejects that need to go back to the TDSP. TDSPs to meet and discuss this. | Pending | 2007-07-12
2007-07-07 | Clean up Retail Market Guide to revise processes that will be changed or deleted after Texas SET 3.0 goes into production (transferred from MCT Action Items list) | Consider the governance process timeline and add to MCT agenda accordingly - 11/6 - add to December MCT meeting to begin work; 12/11 - clean up RMG after TX SET 3.0 Implementation; 7/13 - transferred to TX SET action items to review the RMG for potential changes needed | Pending | 2007-07-13
2007-10-07 | ERCOT - Issue 071 - will research whether the MarkeTrak cancel issues logged in error are limited to a few CRs or if it is across the board. |  | New | 2007-10-25
2007-10-07 | ERCOT - Issue 073 - will do further research to determine how many instances occurred under this same scenario, also to determine what it would take to make the appropriate changes. |  | New | 2007-10-25
2007-10-07 | ERCOT - Issue 074 - will investigate the volume of orders affected by this scenario. |  | New | 2007-10-25
2007-10-07 | ERCOT - Texas SET Procedures –will update Issues Form and include where to send issue. |  | New | 2007-10-25

## Closed Action Items
Date Opened | Action Item | Resolution | Status | Date Last Updated
2006-02-28 | TX SET Leadership (Kathy Scott ) will take updated TX SET Procedures Document to RMS for approval. | Approved at RMS on 4/12/06 and will be discussed at TAC in May for their approval | Closed | 2006-04-26
2006-02-28 | SIR 10528 – Backdating Transactions – ERCOT will implement validation to reject any transaction received that backdated prior to 01/01/1999. | This action item has been resolved with the implementation of SIR 10528 by ERCOT on April 22, 2006 | Closed | 2006-04-26
2006-02-28 | Multiple DTM~140s on the 867_04 transaction received from TDSP. Bill Reily will bring an example of when TXU ED has provided multiple meter information in the 867_04 to enable TX SET to fully discuss the appropriate transactional process. | Discussion on 4/25/06 at TX SET identified that issue has been resolved | Closed | 2006-04-26
2006-03-06 | TX Leadership to develop language to specify that the Change Control Form is for use by TX SET after the approval of an Issue | Leadership had discussed with Jennifer Fredrick to update the Change Control Form on the web for TX SET Use only, however that information had not been posted at the time of this meeting - Susan Munson will work with Jennifer to get this updated. | Closed | 2006-06-07
2006-03-06 | Market Participants and ERCOT to go back to their shops and determine what they need to implement changes in their systems. Provide feedback at the April 5th meeting. | Market Participants provided the necessary feedback at the April 5, 2006 meeting concerning Mass Transition changes and implementation schedule | Closed | 2006-04-26
2006-03-06 | Each Market Participant has been asked to evaluate cost estimates of what it would cost to implement Mass Transistion Long Term Transactional Solution. Provide feedback at the April 5th meeting. | Market Participants provided the necessary feedback at the April 5, 2006 meeting concerning Mass Transition changes and implementation schedule | Closed | 2006-04-26
2006-05-06 | Ts Cs - POLR Rule Reference 4.3.4 - Is a new reject code necessary to reject off cycle fee. CRs will evaluate need for new reject code prior to TX SET meeting. | Assigned to Rob Bevill; No reject code needed; handle through dispute process | Closed | 2006-06-07
2006-05-06 | Ts Cs - POLR Rule Reference 4.4.3 - Do we need a reject code when a re-bill comes in greater than 150 days? Note: 5 day reject rule applies. | Assigned to Rob Bevill; No reject code needed; handle through dispute process | Closed | 2006-06-07
2006-02-28 | TX SET membership was assigned to review and propose revision changes to TX SET Implementation Guides to support Mass Transition Project and high level design at March Meeting. | Discussed at March TX SET Meeting - 04/26/06 - This is a work in progress. 6/7/06 - Still pending until change controls and documents are agreed upon. 06/27/06 - Defer closing this item until POLR rule is approved to ensure all changes have been identified and incorporated into Implementation Guides 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-02-28 | TX SET Leadership (Kathy Scott) will develop an RMGRR to incorporate MCT Roles and Responsibilities Document into the Retail Market Guide. | Glen Wingerd and Sonja Mingo do not think this should be a part of the Retail Market Guide. Recommend adding MCT Roles and Responsibilities document to RMS Agenda for discussion with a vote if needed. 07/28/06- Decision by RMS Leadership that this should not be a RMGRR Change only post the Roles and Responsibilites to the Website under MCT reporting to RMS | Closed | 2006-07-28
2006-02-28 | Revise the 867_04 Implementation Guide to remove invalid example. TX SET discussed example 2 of 5 found on page 19 of this Implementation Guide. | Need and issue created to remove the incorrect or correct the examples on this transaction - Johnny Robertson will draft issue 06/27/06 - Change control still needs to be done to correct example 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-02-28 | Revise grey boxes in transactions to clarify that only 5 or 9 digit zip codes are allowed all others would be rejected by ERCOT. | Catherine Meiners drafted issue. Change control must be written 06/27/06 - Catherine Meiners will write change control for implemented change 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-05-06 | Ts Cs - POLR Rule Reference 4.3.7 - will look at the Implementation Guide for potential transaction flow and grey box changes for the 814_PC process. | Assigned to Johnny Robertson. (Gray box change only.) 6/7/06 - This will be part of the change control for Ts Cs 06/27/06 - The 814_PC Implementation Guide has been redline waiting change control conference call on 7/28 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-05-06 | Ts Cs - POLR Rule Reference 4.4.5 - Review the 820 Implementation guide for conformity with the rule. | Assigned to Kathy Scott, Cary Reed, Bill Reily (regarding clarity between 820/810 pairs). 6/7/06 - Cleaned up verbiage in Implementation Guide; this will be part of the change control for Ts Cs 06/27/06 - The 814_PC Implementation Guide has been redline waiting change control conference call on 7/28 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-05-06 | Ts Cs - POLR Rule Reference 4.8.3 - Modify 810_02 existing “05” replacement code to allow for a new provision. | Will look at 867 monthly and final and 810 for "05" replacement code. Assigned to Diana Rehfeldt, Johnny Robertson 06/27/06 Still a work in progress- need redlined changes completed in implementation guide 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-06-06 | Estimated Meter Reads | Diana Rehfeldt, Bill Reily, and Johnny Robertson will create a strawman 867 redline for this. TDSPs need to figure out the codes. 06/27/06 Still a work in progress- need redlined changes completed in implementation guide 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-06-06 | New Codes in the 650s for Denial of Access | Cary Reed, Rob Bevill, Kyle Patrick, and Suzette Sondag to work on these codes. Reason codes for estimated reads will be assigned to Bill Reily, Kathy Scott, and Alan Burke. 06/27/06 - Need to include redlined changes with Change control document to be scheduled for 7/28/06 Change Control Conference Call 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-07-06 | Post Implementation Guides and SEF files to ERCOT.com for Texas SET 3.0 | Susan Munson to send out redlined Guides to volunteer reviewers - 8/8/2006. Reviewers to return corrected redlined Guides by 8/18/2006. TX SET to review complete set of Guides on 8/22 - 8/24/2006. Susan Munson to post Draft Version 3.0 Implementation Guides to ERCOT.com on 9/1/2006. SEF Files to be posted and distributed by 9/15/2006. | Closed | 2006-08-30
2006-08-06 | TDSPs to provide priority codes for inclusion in Version 3.0 Market Requirements document |  | Closed | 2006-09-12
2006-08-06 | ERCOT will investigate communications protocol options for CSV Customer Billing Information file (i.e. Secure FTP vs. FTP with PGP). (RMGRR042) | ERCOT filed comments to RMGRR042 with their recommendations on 10/4/06. To be discussed at 10/5 TDTWG and considered at RMS on 10/11/06. | Closed | 2006-10-26
2006-08-06 | 814_20 Mass Volumes will be addressed by the PRR672 task force | This has been sent back to Texas SET for discussion. Still collaborating. 10/26/2006 - 2- SIRs will be implemented by ERCOT to address short term recommendation | Closed | 2006-10-26
2006-10-06 | Rob Bevill to take Appendices F3, F4 of the Retail Market Guide for ESI ID spreadsheets for Mass Transition and modify based on Market needs. TDSPs to review Appendix F2. | To be discussed at 10/25-26 meetings and RMGRR filed. | Closed | 2006-10-26
2006-10-06 | Susan Munson to work with Cary Reed to write up the 650_01 priority reconnect issue and send out to TX SET listserve - communicate to CRs to review process |  | Closed | 2006-10-26
2006-10-06 | ERCOT to find security response to this question: If ERCOT does adopt Secure FTP for the process of sending Customer Billing Information to CRs during mass transition event, before the CR opens the file, where does the file physically exist? | Relates to the question of liability in the event of 'hacking' | Closed | 2006-10-26
2006-10-06 | CRs to find out if they can handle receiving maximum of 100K 814_20s per day. Can their systems handle? | To be discussed at 10/25-26 meetings and RMGRR filed. 10/26/2006 CRs felt that their system design would be able to manage a large volume received at one time. | Closed | 2006-10-26
2006-10-06 | Swimlane Sub-team to meet and determine new strategy for creating and maintaining swimlanes | Team to meet on 10/12/06 chaired by Kyle Patrick 10/26/06 - Sub-team will present to TX SET their changes at the November meeting | Closed | 2007-01-25
2006-10-06 | Protocol Revision Request is necessary for re-try queue for the 814_20 Maintenance Transction when the maintenance request is rejected for A76 - ESI ID Invalid | 11/07/06 - ERCOT will review and provide comments back to TX SET at the 12/06 meeting 01/25/2007 Changes implemented with PRR 707 currently up for vote at February RMS | Closed | 2007-01-25
2007-01-07 | Review updated Swimlanes for Final Approval Discussed removal of gray boxes – agreed to delete gray boxes. Kyle Patrick will update swimlanes and remove gray boxes, then will distribute to group. Susan Munson will post the new swimlanes to ERCOT.com in PDF format instead of Visio. | Susan Munson will post the new swimlanes to ERCOT.com in PDF format instead of Visio. 02/22/2007-- These documents have been added to ERCOT.com under TX SET in the PDF.format | Closed | 2007-02-22
2007-01-07 | Johnny Robertson discussed new issue concerning 650_01 - PER IC – PER 02; will write up issue and provide next month regarding segment call ahead number Should be added to MCT issues log and February agenda. Confirm current system setup | Johnny Robertson will write-up issue for further TX SET discussion 02/22/07 -- Per Johnny Robertson this issue is closed no additional documentation is needed | Closed | 2007-02-22
2007-01-07 | Catherine Meiners stated PER03 in the PER IC segment in 814_03 is required. What should be populated in the PER03 for a mass transition? Or should the PER segment not be sent if the ‘TS’ code is present? – Catherine will write up an Issue as urgent. TDSP’s would like to have a little bit of time to follow up on their processes and send back a response to Susan Munson regarding the preferred solution. Answers due back asap. Emergency change control call can be held if necessary. Issue 2006-I052 Written by ERCOT for Emergency Conference Call | Susan Munson will send out issue to Texas SET listserv to solicit feedback from TDSPs on the proposed solutions. ERCOT to draft Change Control for emergency Change Control call. 02/22/07 -- The change control 2007-704 has been approved as emergency change control for implementation into version 3.0 | Closed | 2007-02-22
2007-01-07 | Cary Reed dicussed potential issue with 867_03. Currently, AEP will not allow a bi-directional meter to run backward – NET Zero--- plans would be to bill on the positive usage for billing by the TDSP and let the CR buy-back on the negative value from the meter. 867_03 does not support negative values in usage. At this time hold off assigning a sub-team to discuss and recommend possible changes to the 867_03 until after discussion is held with Metering Group. TX SET Leadership will consult Competitive Metering/Metering Working Groups to determine what type of metering equipment should be utilized for this type of application. 867 needs to be reviewed by group. | This issue could potentially become an urgent release before next update. Assign a subteam for recommendations to 867_03. Susan Munson will follow up regarding what QSEs are doing. Action item of getting with both metering groups – Rob & Kathy Scott 02/22/2007 - Per AEP (Cary Reed) she has a way of handling the reading and information received from customer was not completely correct. TX SET leadership will take the issue to RMS for discussion and guidance since this is bigger than just transactions and system processing. 03/28/2007 - This can be closed for now due to the fact that it is being transferred over to COMET WG for discussion and potential recommendations | Closed | 2007-03-28
2007-01-07 | A request was made to link to the MIMO Stacking documentation from the current Texas SET guides page of ERCOT.com and not just under the Version 2.0 archives. Susan Munson will get this posted for now, with an updated description of the document stating that this was implemented in Texas SET Version 2.0; however, this logic still guides retail transaction processing today. | Susan Munson will get this posted for now, with an updated description of the document 02/22/07 -- Minor removal from document references to 2.0 change controls and version 2.0 in table of contents 03/28/2007 - Corrections have been completed | Closed | 2007-03-28
2007-01-07 | Brainstorming Session on Drop to AREP - Process following implementation of Rule (Customer Protection) changes, how to implement prior to version 3.0, if necessary. Unclear when this will be taken up by the Commission. When PUCT decides to do away with Drop to AREP, what will be the impact to ERCOT and to the market? PUCT draft timeline shows recommendation to adopt at open meeting February 8. It is possible this could be approved in March with an implementation date in May. REPs must stop using Drop to AREPs as of the effective date of the Rule. New reject code on 814_11s; | ERCOT will follow up to see what can be done by a SIR or as a part of Texas SET 3.0. Catherine will follow up as to what kind of change it is for ERCOT to start rejecting 814_10s, impact if prior to 3.0 and also after; various options. Could possibly take a look at who is sending in transactions and determine if it is a few CRs that are submitting or if it is a lot of CRs. Possibly, ERCOT can just cancel the 814_10s and contact the REPs to stop sending them. Discussed updates if needed for guides. Put action items on agenda for February & March 03/28/2007 TX SET is in the process of making changes to Protocols Chpter 15 and 19 to remove Drop to AREP processes, along with RMGRR changes to Timing Matrix to synch-up with new Protocols PRR 672, 707, and 693. Catherine Meiners and Katherine Thurman will also review the MIMO documentation for Drop to AREP language/processes for updates to be brought forward to TX SET in April | Closed | 2007-04-25
2007-03-07 | For TX SET Issue 051, Susan Munson to write change control. |  | Closed | 2007-04-25
2007-03-07 | For TX SET Issue 055, TX SET requests ERCOT and CRs determine internally if there are system issues with meter readings or number of dials that register 6 positions (5.1) or this could be considered 7 positions if CNP includes the 6 or 7 position that includes the decimal point. | Some CRs reported at March meeting; all CRs and ERCOT requested to respond at April 25 meeting. | Closed | 2007-04-25
2007-01-07 | Catherine Meiners discussed issue currently in production, e-mail address can be used as contact type on move-outs, but not on move-ins or switches (versus phone number) – | Catherine Meiners will write up issue to allow email as a valid contact type in the PER~IC on all initiating transactions 02/22/07 -- This issue was discussed and we need feedback from Nueces (Frank Wilson) concerning correct resolution to issue. 03/28/2007 - Nueces and NECRD did not think this EM email communications was needed in the 814_24, therefore a change control will be written by Catherine Meiners (ERCOT) to remove the EM requirement from the 814_24 transaction | Closed | 2007-05-23
2007-03-07 | For TX SET Issue 036, Jennifer Garcia to chair sub-team to investigate this issue further. Jennifer Garcia will gather stats; Catherine Meiners to gather MarkeTrak/FasTrak stats. Rob Bevill said we should find out why this is an issue for some MPs and not others. | 04/25/07 - Jennifer will bring back examples to TX SET along with proposal for SCR | Closed | 2007-05-23
2007-03-07 | For TX SET Issue 040, Catherine Meiners will research the option of ERCOT logging MarkeTrak issues to CRs when we get 814_28 PT on a MVI – it will be a manual effort for ERCOT, but since volumes are low, this should not be a problem. | 4/25/07 - Johnny will get some examples to Catherine Meiners and if no examples by next meeting - Johnny will close/withdraw this issue | Closed | 2007-05-23
2006-10-06 | MPs to take Texas SET transaction checklist back to their shops; review necessity for negative response transactions | Kathy Scott to send out; To be discussed at 10/25-26 meetings and RMGRR filed. 10/26/2006 - May require additional discussion at a later time - Need to evaluate the benefit of changing the current process. 1/25/07 -- Transactions may need to be looked at for value -- Expectations of the receiver of such transactions --- Can this be part of the 814_10 discussion, 814_21 rejects, 814_07, 814_29, 824 EV 05/23/2007 - Still open for future discussion of transactional changes | Closed | 2007-07-12
2006-10-06 | PUCT has issued a proposal for publication - Project 33025 which among other things proposes to eliminate "Drop to AREP" Process - once the project is approved and adopted by the PUCT TX SET will need to review to determine what needs to be done with the 814_10 Drop to AREP transaction | 11/07/06 TX SET will monitor rulemaking process 01/25/2007 --- Catherine Meiners will discuss internally with ERCOT for options on the 814_10 either reject transactions or other and bring back to the February and/or March TX SET Meeting 02/22/07 - Discussed what actions still need to be completed to remove 814_10 from automated process, including documentation and PRR changes. MMWG will look at reporting change. TTPT will look at Test Script Changes 04/25/07 - Pending until PRR and RMGRR is submitted to RMS | Closed | 2007-07-12
2007-05-07 | Discussion is requested how TDSPs match the REF~4P and REF~IX segments on the 814_05 transaction. | 05/23/2007 - Esther Melcer to forward questions to Kathy Scott and TDSPs will review how it is done at their shops 07/12/2007 - TDSPs provide Esther Melcer with answers to questions via email-no follow-up needed | Closed | 2007-07-12

## Parking Lot Items
Date Opened | Parking Lot Item | Resolution | Status | Date Last Updated
2006-02-28 | Update RMGRR to make sure there is a way to drop the Customer Information to the TDSP as well as the CR for updates. | Due to issues and POLR rulemaking has not been settled this may not be an issue for TX SET. Can re-open if needed at a later date when all issues have been resolved. | Closed | 2006-04-26
2006-02-28 | (Chuck Moore) Look at RMGRR Long Term language to see if ERCOT will still send a list of pending transactions to the Gaining CRs. This request is for when the current CR is defaulting the new gaining CR receives a spreadsheet that notifies them of pending transactions to see if the gaining CR has an opportunity to gain (Switch) the Retail Customer earlier preventing them from going to POLR. | ERCOT will investigate if this functionality or process can be added to the Mass Transition requirements document. TX SET Leadership will also add this item to the agenda for May 22/23 meetings to discuss what needs to be added and to document the requirement needs for ERCOT. | Closed | 2006-08-24
2006-02-28 | Possibly look at ERCOT dropping a 814_03 for ESI IDs with pending MVIs that are on day 1, 2, or 3. Might need to look at a priority code and/or code to let the TDSP know that this is a MVI and the lights are not on so that they know it will not be processed as a Switch. | Per TX SET discussion the cost of building this logic would be more than the benefit because of the volume that would apply for this situation. | Closed | 2006-04-26
2006-02-28 | (Kyle Patrick) Need a way for CRs to submit a Switch on customers that are with them as the POLR but have requested Non-POLR service. | This issue may be resolved through the adopted POLR Rule and the selection criteria for POLRs that are within the Rule. | Closed | 2006-04-26
2006-02-28 | Work to consolidate implementation materials for Retail Releases. Work to make sure that information provided concerning releases is consistent across all documentation involved in the project and/or release. | TX SET in conjuction with MCT will work to creating this as our goal | Pending | 2006-04-26