## eds 4 approach comments
Item | Author | Page | Section | Comment | Response Type | Response | TPTF Discussion
1 | Reliant | 6 | 5.4.16 (EECP) (p6) | Although not specifically described in the Transition Plan, it seems that the testing of the DA Network Security sequence and the Hour Ahead Security Sequence must take place in EDS 4 to be complete enough to be ready for 168 hour test. The protocols require that these network security sequences be run prior to DA RUC and HA RUC with the result being reviewed by operators. It is desirable that the same software run in real time as input to SCED, also be used to screen the system for security violations in the DA and HA so that SCED and the ERCOT operators detect issues early prior to them affecting the dispatch of generation. | Accepted | See language added in section "C -Release 9.3 item 2".
2 | Reliant | 7 | Release 8.4 – Verifiable Costs | Test correct application to SCED price mitigation as required by protocols | Accepted | See language added in section C -Release 8.4 and section C Release 9.3.
3 | Reliant | 8 | Release 9.2 OS | a. TSP submittals for Transmission Lines, etc. b. QSE submittals for Generation Resources and Load Resources a. Comparison with reporting requirements from Section 3.2.3 System Adequacy Reports | Accepted
4 | Reliant | 8 | 9.3 Initial DAM/RUC Execution | 1. ERCOT executes DAM and communicates results a. Without Outages from OS b. With Outages from OS c. With network model built by NMMS | Accepted
5 | Reliant | 8 | Release 9.3 – Initial DAM/RUC Execution | 2. ERCOT executes RUC and communicates results a. Without and with Outages from OS b. DA Transmission Sequence | Accepted
6 | Reliant | 8 | Release 9.3 – Initial DAM/RUC Execution | Project schedule shows network Model Go live on April 1, 2008. Is this part of the testing of EDS 4 to verify that this is ready? To go-live with a nodal function requires 30 days notice to the market. To give the notice, TPTF, TAC and the BOD must approve. So, to go-live on April 1, TPTF needs to approve in BOD must approve in February. Right? Does schedule and testing support this timeline? | Response | ERCOT will follow the procedures described in PRR 727 and is addressed in Zonal Protocols 21.12.2 (a) Single Entry Model.
7 | Reliant | 9 | Release 9.5 – Pre-Test for 168-hour Test | 2. Full integration of all required software including that from AREVA and ABB | Accepted
8 | Reliant | 13 | II. Release 8.1 Credit Monitoring and CRR Auction Invoices | Release 8.1-1 is focused on verifying that ERCOT can produce and post each Counterparty ACL’s to the MIS Certified Area. The purpose of this phase of the release is to post the ACL’s so that ERCOT and the Market Participants confirm that the daily ACL’s can be posted and retrieved appropriately and that the file format is as expected. When will QSE’s offers and bids be subject to the ACL? | Response | In the beginning of Release 9.3 high ACL's will be stubbed into to MMS.
9 | Reliant | 15 | Exit Criteria for EDS 4 Release 8.1 | ERCOT should be able to accurately calculate ACL, post ACL’s, approve CRR Bilateral Trades and forward Residual Credit Limits to MMS. Does this also mean that MMS must be able to use the ACL? | Response | Yes. See language added in Section 10 Release 9.4.
10 | Reliant | 24 | EDS 4 Release 9.1 - Upload DAM/RUC Input Data (p 24) | During this timeframe, ERCOT and QSEs with Generation Resources will continue to support all EDS3/SCED submission items. For other QSEs , this will phase will address much of the initial set-up and testing including everything from digital certificates to connecting to the API and User Interface. | Accepted
11 | Reliant | 25 | EDS 4 Release 9.1 | Latest RARF data configured in MMS (will this be compatible with EDS 3 testing of LFC all Resources having the same data in all systems?) | Response | Yes The latest RARF data will be synchronized across MMS/EMS systems for LFC DAM and RUC testing.
12 | Reliant | 26 | EDS 4 Release 9.1 | MP Enrty Criteria: RARF Round 3 submitted (for all Resources) | Accepted
13 | Reliant | 26 | EDS 4 Release 9.1 | ERCOT Exit Criteria: DAM Execution meets minimum performance criteria on full network model? | Rejected
14 | Reliant | 27 | Release 9.2 | For TSPs and QSEs connecting to the Outage Scheduler application through MIS will need to have a digital certificate and test connectivity to the website. TSPs and QSEs desiring to interact with the Outage Scheduler via machine-to-machine interfaces should have developed their software and validated connection to the Nodal Sandbox. (not sure we have advertised to all TSPs this requirement) | Response | This has been communicated to Chris Wilkerson to consider that this metric be added to the Readiness Metric Inventory.
15 | Reliant | 28 | Release 9.2 | All TSPs and QSEs with Resources successfully entering outages into both Zonal and Nodal systems. | Accepted
16 | Reliant | 29 | Release 9.3 | ERCOT exit criteria: Post DAM results as outlined in Protocols section 4.5.3 Communicating DAM Results including LMP price couture maps | Accepted
17 | Reliant | 30 | Release 9.4 | ERCOT execution of pre-RUC activities of DA Network Security Analysis (AREVA Software?) | Accepted | Included reference to 5.5.1 Security Sequence.
18 | Reliant | 30 | Release 9.4 | ERCOT Adjustment Period Activities, Hour Ahead Sequence execution | Accepted
19 | Reliant | 32 | Release 9.4 | ERCOT exit criteria: Execute full operational market timeline for 7 consecutive days with all functions required in the nodal protocols Full integration into the day to day activities of the ERCOT Operations of all nodal functions. All work processes needed to support Nodal operations and systems maintenance in place | Response | ERCOT will execute full market timeline for seven days, but all functions in Protocols will not be available until 9.5. Items moved to 9.5. Added bullet describing full integration of ERCOT Operations day to day activities.
20 | Reliant | 34 | Exit Criteria Release 9.5 | All ERCOT operations and maintenance processes in place and ready for final testing | Accepted
21 | Reliant | 35 | XII Staffing (p 35) | Not clear how the EDS 4 team will hand off responsibility for the 168 hour testing to the ERCOT Operations and Maintenance groups who will be actually running the dispatch, market, security analysis, etc. | Accepted | See updated language to capture ERCOT support of EDS 4 and 168 hour test.
22 | Tenaska | 4 | EDS 4 – OVERVIEW | (Need to include target start and stop dates or include link to timeline.) EDS 4 Release 8, COMS, target start March 1, 2008, target stop October 31, 2008 EDS 4 Release 9, DAM, target start January 1, 2008, target stop October 31, 2008 See Early Delivery system Sequence Timeline for target start and stop dates for EDS 4 Release 8 and EDS 4 Release 9, http://nodal.ercot.com/about/po/sch/kd/timeline_1114.pdf. | Accepted | Timelines have been inserted into the document.
23 | Tenaska | various |  | Various Grammatical Corrections | Accept
24 | ERCOT |  |  | Add "self schedules" to Releas 9.1 DAM/RUC submission testing. | Accept