PMO

Active Readiness Metric Inventory

v2.2

December 5, 2007

Table of Contents

Revision History	4

Introduction	7

EDS Timeline Cross Reference for all Metrics (Approved and Future)	9

Market Participant Metrics	16

MP1 - MP Engagement	16

MP2 – QSE with Resources Connectivity to EDS Environment	17

MP3 – QSE with Resources Upload of SCED Offers to EDS	17

MP5 – ICCP Point to Point Telemetry Test	19

MP6 - QSE and TSP Telemetry/ICCP System Availability	20

MP8 - QSE Ability to Submit Transactions Via MIS	20

MP9 – QSE Ability to Submit Web Service Transactions	21

MP10 - Mapping of Resources to Resource Nodes and Resources to EPS Meters is Complete	22

MP11 - MP Registration Activities	22

MP11 - MP Registration Activities – Revised by TPTF on 12/3/07	23

MP12 - MP Completes EDS-3 Related Training	26

MP13 - MP Completes EDS-4 Related Training	27

MP14 - MP EDS-2 Trials Participation	28

MP15 - MP EDS-3 Participation	29

MP17 - MP Qualification Activities	29

Commercial Operations MetricsCongestion Revenue Rights Metrics	31

Congestion Revenue Rights Metrics	32

CRR2 - Develop TCR to CRR Transition Plan	32

CRR3 –Operation of Monthly CRR Auction and Allocation	33

CRR4 - Implement TCR to CRR Transition Plan	34

CRR5 - Operation of Annual CRR Auction and Allocation	35

ERCOT Internal Metrics	36

E0 - ERCOT Engagement	36

E1 - ERCOT Staff Completes Training	36

E3 - Validate Telemetry/SE EDW/ Data Accuracy	38

E5 - Nodal SAS 70	38

E6 - Develop Nodal Operating Guides	39

E8 - ERCOT Staffed for Texas Nodal Operations	40

E9 - Develop TN Procedures	41

E12 - MIS Compliance Test	41

Energy Management Operations Metrics	42

EMO1 - Network Security Analysis & Transmission Constraint Management	42

EMO2 - Verify Voltage Support Functionality	43

EMO5 - Verify ACE Performance	43

EMO6 - QSE Response to Dispatch	44

EMO7 - Verify Load Forecast Accuracy	45

EMO9 - Validate Zonal and Nodal Security Analysis Results	45

EMO10 - Network Operations Model and SE Performance	46

EMO11 – Operating Personnel and Facilities Readiness	46

Network Model Management Metrics	48

N1 - ERCOT Telemetry Alarm Processing	48

N2 - ERCOT Telemetry/ICCP System Failover	48

N3 - Validate SE Performance and Accuracy	49

Market Operations Metrics	50

MO4 - Verify SCED Execution Quality	50

MO5 - Generate LMPs for 6 months	50

Contingency Metrics	52

IMM Metrics	53

Overall Readiness Metrics	54

# Revision History

| Date | Author | Version Number | Description of Revision |
| --- | --- | --- | --- |
| 8/27/2007 | Chris Wilkinson | 0.91 | Initial Version The intent of this document is to inventory all Texas NODAL Market Readiness Metrics that the NODAL PMO is actively measuring. These metrics have been reviewed and approved by TPTF and TAC. This version picks up where 17a_Metric_Inventory_metric_descriptions_V24.doc left off, which was the last consolidated view of metrics presented to TPTF. Going forward, al TPTF future metrics will be housed in the Future Metric Inventory document. This document is different than 17a_Metric_Inventory_metric_descriptions_V24.doc in that it covers the following active metrics only: - MP1 - MP2 - MP3 - MP5 - MP11 - MP14 - E1 - E6 - E8 - E9 - N1 |
| 8/29/2007 | Chris Wilkinson | 1.0 | Incremented document to V1.0 to reflect TPTF approval of - MP1 - MP2 - MP3 - MP5 - MP11 - MP14 - E1 - E6 - E8 - E9 - N1 |
| 8/31/2007 | Chris Wilkinson | 1.1 | Updated for iteration 3. Moved the following metrics from the Future Inventory to the Active Metric Inventory V1.1. These will be reviewed by TPTF on 9/10/07. - MO5 - N2 - E5 - E3 - EMO9 - N3 - MP6 - MP12 - MO4 |
| 9/5/2007 | Chris Wilkinson | 1.2 | Updated Iteration 3 metrics with feedback from ERT and EDS teams MP6 – Server failover and com link failover measured beginning in October 2007. Remaining three criteria will be measured in January 2008. E3 – Removed MIS Access from Title. Noted RAG Rules – Amber end of October, Red end of November. E5 – Moved back to Future Metric Inventory EMO9 – Removed “Associated Shift Factors” from second metric and noted that the metric will be measured monthly. Zonal does not include shift factors in the constraints. N2 – Corrected spelling on “minutes” in criteria N3 – Added clarification to three metrics that the sample elements were predetermined. Also cleaned up sentence structure to clarify monthly periodicity. MO5 – Noted 50 percent targets between September 2007 and April 2008 to allow for EDS system down-time. |
| 9/18/07 | Chris Wilkinson | 1.3 | Noted that MP12 and E3 were approved by TPTF on 9/11/07 by accepting redlines on those two metrics. Updated MP6 to reflect criteria from most current Texas NODAL Market Telemetry Standard. Edited EMO9 to limit scope to Security Analysis Results Edited N3 to reflect language from Texas NODAL Market State Estimator Standard. Did not change criteria. Added E0 ERCOT Engagement to track ERCOT survey results. Changed criteria of MO5 to reflect 100 percent LMP posting after April 2008. Updated file name to reflect ERCOT.com naming conventions |
| 10/01/07 | Chris Wilkinson | 1.4 | Accepted red-line changes based on TPTF approvals on 9/26/07 for: - MP6 - E3 - EMO9 - N2 - N3 - MO5 - E0 MO4 remains redlined for future consideration. This metric was pended to allow for general conversation around “reasonable LMP” in October. |
| 11/9/07 | Chris Wilkinson | 1.5 | Updates to MO4 to reflect 11/5/07 discussion of LMP reasonability Updated MP11 to Reflect November RARF deadlines. |
| 11/12/07 | Chris Wilkinson | 2.0 | Updated document to include the following metrics. These metrics were approved in November 9, 2009 TPTF session: - E5 - E12 - EMO1 - EMO2 - EMO5 - EMO6 - EMO7 - EMO10 - EMO11 - CRR2 - CRR3 - CRR4 - CRR5 - MO4 |
| 11/28/07 | Chris Wilkinson | 2.1 | TAC approved these metrics on November 28, 2007: - EMO1 - EMO2 - EMO5 - EMO6 - EMO7 - EMO10 - EMO11 - CRR2 - CRR3 - CRR4 - CRR5 - MO4 The following metrics are awaiting TAC approval: - E5 - E12 - MP8 - MP9 - MP10 - MP13 - MP15 - MP17 |
| 12/05/07 | Chris Wilkinson | 2.2 | Added MP11 for TAC approval. MP11 was approved by TPTF on 12/3/07. |

# Introduction

The Readiness Metric Inventory is a detailed report of all readiness metrics.  The following table outlines the information provided per metric. The intent of this document is to inventory all Texas NODAL Market Readiness Metrics that the NODAL PMO is actively measuring.  These metrics have been reviewed by TPTF and TAC and will be governed by a change control process going forward once approved.

Metric Number – Metric Name

| Reported By: Indicates if the metric is discoverable by ERCOT, Market Participants, WEMM or any combination thereof. |  |  | EDS: Indicates the related Early Delivery System, if applicable. |
| --- | --- | --- | --- |
| Target Completion: Indicates the time period that the metric result will be published. |  |  |  |
| Category: Indicates how the data will roll up functionally in the Readiness Dashboard tool. |  |  |  |
| Metric Description: Provides a description of the metric. |  |  |  |
| Background: Indicates the intent of the metric. |  |  |  |
| Criteria: Outlines the criteria used to determine if the metric has been successfully completed. Provides a concrete measurement standard to evaluate the metric against |  |  |  |
| Reporting Data Sources: Indicates the source of the data to be used when evaluating the measurement standard and or the individual or team responsible for reporting status. |  |  |  |
| References | TP: Cross reference to the Transition Plan | TNP: Cross reference to the Texas Nodal Protocols |  |

The Metric Map is a time based graphical representation of the Metrics.

Sample Metric Map

# EDS Timeline Cross Reference for all Metrics (Approved and Future)

| Metric | Milestone Target Completion | Owner | Date |
| --- | --- | --- | --- |
| MP7 – MP Use of MIS - REMOVED | Deleted |  | Deleted |
| MP1 – MP Engagement | 6-month LMP posting – Start less 45 days, TBD, TBD | MP self report | June 1, 2007 |
| MP1 – MP Engagement | 6-month LMP posting – Start less 45 days June 1, TBD, TBD | MP self report | TBD |
| MP1 – MP Engagement | 6-month LMP posting – Start less 45 days June 1, TBD, TBD | MP self report | TBD |
| N1 – ERCOT Telemetry Alarm Processing | EDS 1 – Release 1 Complete plus 14 days | EDS 1 PM | July 15, 2007 |
| E1 - ERCOT Staff Completes Training | Start of EDS 2 | ERCOT Readiness PM | August 6, 2007 |
| MP11 – MP Registration Activities | EDS 3 – Registration EDS Trial Preparation Milestone plus 14 days | ERCOT Manager of Wholesale Client Services | September 17, 2007 |
| MP14 – MP EDS-2 Trials Participation | EDS 2 – Start of Release 4 plus 14 days | EDS 2 PM | October 1, 2007 |
| MO5 – Generate LMPs for 6 months | Test 1- 6 Month LMP Posting minus 90 days | EDS 3 PM | October 15, 2007 |
| MP5 – ICCP Point to Point Telemetry Test | EDS 1 - Release 2 Complete plus 14 days | EDS 2 PM | October 15, 2007 |
| N2 – ERCOT Telemetry/ICCP System Failover | EDS 1 – Release 2 Complete plus 14 days | EDS 1 PM | October 15, 2007 |
| MP4 – QSE Test Digital Certificates Obtained - Removed | 6-month LMP posting major milestone less60 days |  | November 15, 2007 |
| MP2 – QSE with Resources Connectivity to EDS Environment | LMP Data Validation Milestone less 30 days | EDS 3 PM | September 1, 2007 |
| MP3 – QSE with Resources Upload of SCED Offers to EDS | LMP Data Validation Milestone | EDS 3 PM | October 1, 2007 |
| E1 - ERCOT Staff Completes Training | Start of EDS 3 | ERCOT Readiness PM | October 1, 2007 |
| MO5 – Generate LMPs for 6 months | Test 2 – 6 Month LMP Posting minus 90 days | EDS 3 PM | October 15, 2007 |
| E6 – Develop Nodal Operating Guides | Go Live Less 360 days | ERCOT Readiness PM | December 1, 2007 |
| E3 – Validate Telemetry/SE-EDW/MIS Access & Data Accuracy | EDS 2 – Release 3 complete | EDS 2 PM | December 3, 2007 |
| EMO9 – Validate Zonal and Nodal Common Constraints | EDS 2 Release 3 complete | EDS 2 PM | December 3, 2007 |
| N3 – Validate SE performance and Accuracy | EDS 2 – Release 3 complete | EDS 2 PM | December 3, 2007 |
| MP6 – QSE and TSP Telemetry/ICCP System Availability | EDS 2 – Release 3 plus 14 days | EDS 1 & 2 PM | December 17, 2007 |
| MP12 – MP Completes EDS-3 Related Training | First – EDS 3 – 6 Month LMP Posting Major Milestone less 30 days Second – Market Open less 30 days | MP Self Reported | December 17, 2007 |
| E1 - ERCOT Staff Completes Training | Start of EDS 4 | ERCOT Readiness PM | January 1, 2008 |
| MO5 – Generate LMPs for 6 months | First – 6 Month LMP Posting plus 14 days | EDS 3 PM | January 28, 2008 |
| MO4 – Verify Base Point Generation | 6 Month LMP Posting plus 14 days | EDS 3 PM | January 28, 2008 |
| EMO5 – Verify ACE performance | EDS-3 LFC Major Milestone Start + 30 days | EDS 3 PM | February 4, 2008 |
| CRR1 – Develop CRR Test Plan | 180 days prior to the first monthly CRR auction | EDS 3 PM | March 3, 2008 |
| CRR2 – Develop TCR to CRR Transition Plan | Go Live Activities less 270 days | CRR PM | March 3, 2008 |
| MO5 – Generate LMPs for 6 months | Second – 6 Month LMP Posting plus 45 days | EDS 3 PM | March 17, 2008 |
| MP16 – MP EDS-4 Trials Participation | EDS 4 Release 9 – DAM, RUC, SASM less 14 days | EDS 4 PM | March 28, 2008 |
| MO5 – Generate LMPs for 6 months | Third – 6 Month LMP Posting plus 90 days | EDS 3 PM | April 10, 2008 |
| MP15 – MP EDS-3 Trials Participation | EDS 3 trials Start plus 14 days | EDS 3 PM | April 29, 2008 |
| E8 – ERCOT Staffed for Texas Nodal Operations | EDS 4 – Full Nodal Functionality 24*7 Operations Major Milestone less 60 days | ERCOT Readiness PM | May 1, 2008 |
| EMO7 – Verify Load Forecast Accuracy | EDS-4 Release 9 Start + 120 days | EDS 4 PM | May 1, 2008 |
| E7 – Validate EDW WEMM Access & Accuracy | EDW 6 FAT Milestone plus 90 days | EDS 4 PM | June 2, 2008 |
| E10 – Validate EDW Commercial Systems Access & Accuracy | EDW 6 FAT Milestone plus 90 days | EDS 4 PM | June 2, 2008 |
| E11 – Validate EDW Compliance Data Access | EDW 6 FAT Milestone plus 90 days | EDS 4 PM | June 2, 2008 |
| EMO6 – QSE Response to Dispatch | EDS-3 Major Milestone LFC Testing + 60 days | EDS 3 PM | June 2, 2008 |
| MP13 – MP Completes EDS-4 Related training | First – EDS 4 – Full Nodal Functionality 24*7 Operations less 20 days Second – Market Open less 30 Days | MP Self Reported | June 5, 2008 |
| MO5 – Generate LMPs for 6 months | Fourth – 6 Month LMP Posting plus 135 days | EDS 3 PM | June 16 2008 |
| CO9 – Verify Financial Transfer and Processing | EDS-4 Full Nodal Functionality Major Milestone | EDS 4 PM | July 1, 2008 |
| E9 – Develop TN Procedures | Go-Live less 60 days | ERCOT Readiness PM | July 1, 2008 |
| EMO2 – Verify Voltage Support Functionality | EDS-4 Full Nodal Functionality Milestone | EDS 4 PM | July 1, 2008 |
| MO3 Verify Supplemental Ancillary Services market (SASM) | Full Nodal Functionality 24*7 Operations | EDS 4 PM | July 1, 2008 |
| MP8 – QSE, AP & RTM MIS and Web Service Transactions | EDS-4 Release 9 – 24*7 Operations plus 7 days | EDS 3 & 4 PM | July 8, 2008 |
| MP9 – QSE, DAM MIS and Web Service Transactions | EDS-4 Release 9 – 24*7 Operations plus 7 days | EDS 4 PM | July 9, 2008 |
| MO5 – Generate LMPs for 6 months | Fifth – 6 Month LMP Posting plus 180 days | EDS 3 PM | July 10, 2008 |
| CO5 Verify RTM Settlement Statements | EDS-4 Release 8 complete plus 14 days | EDS 4 PM | July 14, 2008 |
| CO6 – Verify RTM Settlement Invoices | EDS-4 Release 8 complete plus 14 days | EDS 4 PM | July 14, 2008 |
| CRR3 – Trial operation of Monthly CRR Auction | EDS-3 – Release 7 complete milestone | EDS 3 PM | July 20, 2008 |
| CRR5 – Trial Operation of Annual CRR Auction during Trials | EDS-3 – Release 7 Completion | EDS 3 PM | July 21, 2008 |
| CRR4 – Implement TCR to CRR Transition Plan | Go Live Activities less 120 days | CRR PM | August 1, 2008 |
| CO3 – Verify DAM Settlement Statements | EDS-4 Full Nodal Functionality Major Milestone plus 30 days | EDS 4 PM | August 4, 2008 |
| CO7 – Verify DAM Invoices | EDS-4 Full Nodal Functionality Major Milestone plus 30 days | EDS 4 PM | August 4, 2008 |
| E2 – Verify ERCOT Performance Monitoring Test Plan | EDS 4 - 168 Hour Test major Milestone less 30 days | ERCOT Readiness PM | August 4, 2008 |
| E4 – Price Protection Mechanisms | Go Live Activities less 90 days | ERCOT Readiness PM | August 4, 2008 |
| E12 MIS Compliance Test | EDS-4 Full Nodal Functionality Major Milestone plus 30 | MIS PM | August 4, 2008 |
| E14 – Verify QSE Performance Monitoring Test Plan | EDS 4 – 168 Hour Test Major Milestone less 30 days | ERCOT Readiness PM | August 4, 2008 |
| E15 – Verify TSP Performance Monitoring Test Plan | EDS 4 – 168 Hour Test Major Milestone less 30 days | ERCOT Readiness PM | August 4, 2008 |
| EMO8 – Conduct EECP Test | EDS 4 – 168 Hour Test Major Milestone less 30 days | EDS 2 PM | August 4, 2008 |
| MP17 – MP Qualification Activities | EDS 4 168 Hour Testing Major Milestone less 90 days , less 30 days, less 14 days | ERCOT Manager of Wholesale Client Services | June 2, 2008 August 4, 2008 August 18, 2008 |
| C010 – Verify Credit Calculations | EDS-4 168-Hour Test Major Milestone less 14 days | EDS 4 PM | August 18, 2008 |
| CO8 – Verify CRR Auction Invoices | EDS-3 End of Trial Operations of CRR Major Milestone plus 30 days | EDS 4 PM | August 20, 2008 |
| CO4 – Zonal/Nodal Coordinated Settlement Operations | EDS 4 168 Hour Test Major Milestone | EDS 4 PM | September 1, 2008 |
| MO1 – Operate DA market for 7 Days | Full Nodal Functionality 24*7 Operations plus 60 days | EDS 4 PM | September 1, 2008 |
| MO2 Operate 7 Day Market with RUC | Full Nodal Functionality 24*7 Operations plus 60 days | EDS 4 PM | September 1, 2008 |
| MO6 - Verify DAM Ancillary Services | Full Nodal Functionality 24*7 Operations plus 60 days | EDS 4 PM | September 1, 2008 |
| R2 – Develop Texas Nodal Market Launch Plan | Go Live Activities less 90 days | ERCOT Readiness PM | September 1, 2008 |
| E13 – Standard Form Agreements Executed | Go Live Activities less 120 days | Manager of Wholesale Client Services | September 2, 2008 |
| C1 – Contingency Plan for Weekly, Daily and Hourly RUC Failure | Go Live Activities less 60 days | EDS 4 PM | October 1, 2008 |
| C2 – Contingency Plan for DAM/LMP Failure | Go Live Activities less 60 days | EDS 4 PM | October 1, 2008 |
| C3 – Contingency Plan for ICCP Data Failure | Go Live Activities less 60 days | EDS 2 PM | October 1, 2008 |
| C4 – Contingency Plan for SCED Failure | Go Live Activities less 60 days | EDS 3 PM | October 1, 2008 |
| C5 – Contingency Plans for Key Settlement and Financial Transfer Processes | Go Live Activities less 60 days | EDS 4 PM | October 1, 2008 |
| C6 – Develop Plan for SE Failure | Go Live Activities less 60 days | EDS 2 PM | October 1, 2008 |
| C7 – Contingency Plan for a Backup Facility | Go Live Activities less 60 days | EDS 4 PM | October 1, 2008 |
| C8- Contingency Plan for Portal/API Failure | Go Live Activities less 60 days | EDS 4 PM | October 1, 2008 |
| R1 – Nodal Readiness declaration | Go Live less 60 days | ERCOT NODAL Program Executive Director | October 1, 2008 |
| C9 – Contingency Plan for Site Unavailability | Go Live Activities less 60 days | EDS 4 PM | October 6, 2008 |
| C10 – Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS | Go Live Activities less 60 days | EDS 4 PM | October 6, 2008 |
| E5 – Nodal SAS 70 Preparedness | Go Live Activities less 45 days | ERCOT Readiness PM | October 15, 2008 |
| CO1 – Settle market for 7 Days and provide appropriate extracts | EDS-4 Release 9 Complete | EDS 4 PM | November 3, 2008 |
| CO2 Verify Dispute Process of 168 Hour Test | EDS-4 Release 9 Complete | EDS 4 PM | November 3, 2008 |
| EMO3 – Verify Outage Evaluation System Functionality | EDS-4 Release 9 Complete | EDS 4 PM | November 3, 2008 |
| EMO4 – Run 7 Day Stability Test | Go live Less 30 days | EDS 4 PM | November 3, 2008 |
| IMM1 | EDS 4 – Release 9 Complete | ERCOR PMO PM | November 3, 2008 |
|  | Go Live Activities less 14 days |  | November 17, 2008 |
| EMO1 – Network Security Analysis & Transmission Constraint Management | EDS 2 – Release 3 complete plus 60 days | EDS 2 PM | February 2, 2009 |
| MP10 – Mapping of Resources to Resource Nodes and Resources to Revenue Quality Meters is Complete | Start Go Live Activities less 120 days | ERCOT Manager of Wholesale Client Services | March 2, 2009 |

# Market Participant Metrics

### MP1 - MP Engagement

| Reported By: MP (Accountable Executive) & ERCOT |  |  | EDS: Registration |
| --- | --- | --- | --- |
| Target Completion: Periodic: June 1, TBD, TBD |  |  |  |
| Category: Engagement |  |  |  |
| Metric Description: MP are actively participating in Nodal preparation to include the assignment of an Accountable Executive, a Program Manager,the allocation of a budget, Program Charter and have indicated an intent to participate in the Nodal Market. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants are engaged in Nodal preparations. |  |  |  |
| Criteria: The Readiness Team will review self reporting from each Market Participant indicating their level of engagement in Nodal preparation, mobilization and delivery. Readiness will be achieved when MP Accountable Executives have submitted Completion Review Documents outlining their status related to defined activities. Target 1 – Preparation AE Response Accountable Exec Nominated Project Manager Assigned Project Brief/Initiation Document Completed Project Plan Completed Project Budget Allocated Target 2 Mobilization AE Response Project Staffed and mobilized to meet the EDS Testing Requirements Project Vendor(s) Selected (if Appropriate) Training Plan completed Training Budget allocated Testing Plan completed Business Impact Assessment Completed Target 3 Delivery AE Response Planned Completion Date for Registration <= yyyy/mm/dd Planned Completion Date Qualification <= yyyy/mm/dd Plan Completion Date for Business Requirements <= yyyy/mm/dd Plan Completion Date for Conceptual Systems Designs <= yyyy/mm/dd Plan Completion Date for Detailed Designs <= yyyy/mm/dd Planned Date Systems will be available to test interfaces with ERCOT System <= yyyy/mm/dd |  |  |  |
| Reporting Data Sources: MP Self Reported |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### MP2 – QSE with Resources Connectivity to EDS Environment

| Reported By: QSE with Resource & ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: 6-month LMP posting major milestone less 45 days |  |  |  |
| Category: Connectivity |  |  |  |
| Metric Description: QSEs with resources have confirmed their ability to connect to the MIS and/or an External Web Service in the early Early Delivery System (EDS) environments. |  |  |  |
| Background: The intent of this metric is to ensure that QSEs with Resources can successfully connect to the eEDS allowing ERCOT to provide better support to the MPs facilitating trials completion. |  |  |  |
| Criteria: The Readiness Team will review documentation providing connectivity statistics for the EDS3 environment by Market Participant. Readiness will be met when the MP successfully submits a three part offer, incremental/decremental offer, current operating plan or a output schedule via either web services or the MIS that is logged in the Enterprise Integration Framework (EIF) transaction database as successfully passing the proxy server. EIF entry per QSE with resources >=1 RAG Rules Red – Failure to meet 10/2/07 execution deadline Amber – Failure to sign-up by 8/15/07 Green – Meeting Plan |  |  |  |
| Reporting Data Sources: EIF log table entry in EDS / ERCOT EDS 3 PM EDS 3 team will track registration and execution by QSE with Resources |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### MP3 – QSE with Resources Upload of SCED Offers to EDS

| Reported By: QSE with Resources & ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: 6-month LMP posting major milestone less 45 days |  |  |  |
| Category: Connectivity |  |  |  |
| Metric Description: QSEs with Resources shall demonstrate their ability to successfully submit a 3 part offer and if applicable a dynamic output schedule to the MIS and/or an External Web Service in the Early Delivery System (EDS) environment and successfully pass validation with the MMS system. |  |  |  |
| Background: The intent of this metric is to ensure that QSEs with Resources can successfully submit a 3 part offer and if applicable a dynamic output schedule to the EDS. |  |  |  |
| Criteria: The Readiness Team will review documentation providing transaction statistics by Market Participant. Readiness will be met when the MP successfully submits a request that is logged in the Enterprise Integration Framework (EIF) transaction database. EIF entry with transaction status of Passed per QSE with resources >=1 RAG Rules Red – Failure to meet 10/2/07 execution deadline Amber – Failure to sign-up by 8/15/07 Green – Meeting Plan |  |  |  |
| Reporting Data Sources: EIF log table entry in EDS as verified by the ERCOT EDS Test Team / ERCOT EDS 3 PM EDS 3 team will track SCED offers by QSE with Resources. |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### MP5 – ICCP Point to Point Telemetry Test

| Reported By: QSEs, TDSPs & ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 1 - Release 2 Complete plus 14 days |  |  |  |
| Category: Telemetry |  |  |  |
| Metric Description: ERCOT shall coordinate a test with TSPs and QSEs with resources to verify that the equipment point mapping, value, and status are correctly transmitted within an acceptable scan rate. |  |  |  |
| Background: The intent of this metric is to ensure that TSP, QSE and ERCOT telemetry ICCP representations are in synch with one another. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the accuracy of telemetry points mapping, station topology diagrams, values and status within an acceptable scan rate. Readiness will be achieved when MPs have added all required points to meet Nodal Protocols, Point to Point Verification has occurred, Telemetry issues documented and communicated to MPs, ERCOT has ICCP database under change control and MPs have submitted service requests to resolve ICCP issues. Number of points missing from Nodal Protocol Requirement <= 5% Number of Point to Point Verification = 95% of Points within a 10 second scan rate Number of Telemetry issues identified = Number of Telemetry issues documented and communicated to MPs. Number of MP service request submitted >= 90% of Number of Telemetry issues documented and communicated to MPs RAG Rules Red – Failure to meet above criteria Amber – Behind point to point schedule Green – Meeting above criteria |  |  |  |
| Reporting Data Sources: ICCP Database / Network Operations Model & the EDS 1 status report located on the Nodal Readiness Center: EDS 1 Status MMDDYYYY.xls / ERCOT EDS 2 PM |  |  |  |
| References | TP: 5.4.1 (2)(a) | TNP: 3.10.7, 6.5.7.6.1(8) & 8.1.2.2(6)(b) |  |

### MP6 - QSE and TSP Telemetry/ICCP System Availability

| Reported By: QSE, TSP & ERCOT |  |  | EDS: 1,2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 – Release 3 completion plus 14 days |  |  |  |
| Metric Description: Verify that all MP telemetry availability criteria are met. |  |  |  |
| Category: Telemetry |  |  |  |
| Background: The intent of this metric is to ensure that MP telemetry systems are stable in a redundant state and meet TAC approved telemetry data standards. |  |  |  |
| Criteria: The Readiness Team will verify that telemetry failover thresholds and data availability standards are met by MPs. Readiness will be achieved when the MPs have passed a simulated failover test and proven data availability. These criteria will be kept current with the Texas NODAL Market Telemetry Standards. EDS2 Release 2 Completion Plus 14 Days (October 2007 Measurement): Server Fail Over <=5 Minutes Com Link Failover <= 30 Seconds EDS2 Release 3 Completion Plus 14 Days (January 2008 Measurement): - Critical point (as defined by ERCOT pursuant to Telemetry Standard) availability >= 99.9 percent - Non-Critical point availability >= 99 percent RAG RULES Red – Failure to meet above criteria Amber – Within 10 percent of meeting above criteria Green – Meeting above criteria |  |  |  |
| Reporting Data Sources: ERCOT ICCP EMS Logs / PI Historian / ERCOT EDS 1 & 2 PM |  |  |  |
| References | TP: 5.4.1 (2)(k) | TNP: 3.10.7.4, 6.4.5, 6.5.5, 8.1.2 |  |

### MP8 - QSE Ability to Submit Transactions Via MIS

| Reported By: QSEs & ERCOT |  |  | EDS: 3,4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 3 |  |  |  |
| Metric Description: ERCOT shall verify the ability of QSEs to send transactions via the MIS . |  |  |  |
| Background: The intent of this metric is to ensure that QSEs have the ability to participate in the real time market DA Operations and Adjustment Period Operations. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that market participants can and have successfully sent test real time transactions. Readiness will be met when ERCOT has observed Market Participants successfully sending test real time transactions during the EDS Market Particpant test window. QSEs will be asked to submit transactions via the MIS or External Web Services according to the MMS Explanation of Market Participant Submission Items. MP Transactions Sent = MP Transactions Received at ERCOT during the Market Participant test window MP RAG Rules Green = Complete Amber = Not complete, less than 1 month past due date Red = Not complete, over a month past due |  |  |  |
| Reporting Data Sources: MMS Data Extract / ERCOT EDS 3 & 4 PM |  |  |  |
| References | TP: 5.4.4 & 5.4.7 | TNP: 3.9, 4.3(1), 5.4, 6.4.6 |  |

### MP9 – QSE Ability to Submit Web Service Transactions

| Reported By: QSE & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 9 – 24*7 Operations plus 7 days |  |  |  |
| Metric Description: ERCOT shall verify the ability of QSEs to submit transactions via the Web Services. |  |  |  |
| Background: The intent of this metric is to ensure that QSEs have the ability to participate in the Market. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that the market participants can and have successfully sent test Transactions. Readiness will be met when ERCOT has observed Market Participants successfully sending test transactions during the EDS Market Participant test window. MP Transactions Sent = MP Transactions Received at ERCOT during the Market Participant test Window MP RAG Rules Green – Complete Amber – Not Complete, less than 1 month past due date Red – Not complete, over month past due |  |  |  |
| Reporting Data Sources: MMS Data Extract / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.6 (1) | TNP: 4.3, 4.4, 4.5 |  |

### MP10 - Mapping of Resources to Resource Nodes and Resources to EPS Meters is Complete

| Reported By: QSE with Resource & ERCOT |  |  | EDS: Registration |
| --- | --- | --- | --- |
| Target Completion: EDS 2 Release 4 completion |  |  |  |
| Metric Description: ERCOT shall ensure that all participating Generation Resources in the TN Market have completed their mapping of Resources to Resource Nodes and Resources to EPS Meters at the Generation Facility. |  |  |  |
| Background: It is the intent of this metric to ensure that the settlement of resources involved in a net metering configuration can be executed as specified by the Nodal Protocols. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that all participating resources in the TN Market have completed their mapping of Resources to Resource Nodes and Resources to EPS Meters. Readiness will be achieved when each resource has either mapped their Resources or have accepted the existing default configuration. Resources to Resource Node Mapping = 100% Resources to EPS Meters Mapping = 100% MP RAG Rules Green = Complete Amber = Not complete, less than 1 month past target completion date Red = Not complete, over a month past target completion date |  |  |  |
| Reporting Data Sources: Extract from Registration / ERCOT Manager of Wholesale Client Services |  |  |  |
| References | TP: N/A | TNP: 16.2.3.2(2) |  |

### MP11 - MP Registration Activities

| Reported By: MP & ERCOT |  |  | EDS: Registration |
| --- | --- | --- | --- |
| Target Completion: EDS 3 - Registration EDS Trial Preparation Milestone plus 14 days |  |  |  |
| Category: Registration and Qualification |  |  |  |
| Metric Description: This metric shall measure whether Market Participants have performed the tasks outlined in the Registration & Qualification Guide . |  |  |  |
| Background: The intent of this metric is that ERCOT has all registration related data for all market participants intending to participate in the Nodal Market on record. |  |  |  |
| Criteria: The Readiness Team will review data provided by the Registration and Qualification Coordinator tracking the ERCOT/MP registration activities. MP Readiness will be achieved when the Registration checklist is completed by Client Services and the market participant Accountable Executive and Authorized Representative are notified by ERCOT via email. MP Registration Checklists Completed = Number of MPs Intending to Participate in Nodal Market September 2007 Targets: - measure completion of the Resource Asset Registration Form (RARF) by Resource Entities. - Individual Resource Entities will be measured on their successful completion of the RARF for their generation resources - Market will be measured by percent received % of Generation Participation >= 95% RAG Rules - MPs Red – Failure to submit documentation Amber – Incomplete form Green – All forms received RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria - measure completion of the Ancillary Service Attestation by QSEs with Resources. - Individual QSEs will be measured on their successful completion of the Attestation. Since this is voluntary at this time, QSEs will not be assessed ‘red’ - Market Segment will be measured by percent received % of Ancillary Generation >= 95% RAG Rules - MPs Amber – Incomplete form Green – All forms received RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria Note: additional targets will be added as registration and qualification deadlines arise. These targets will be added via the change control process. |  |  |  |
| Reporting Data Sources: Registration Checklists / ERCOT Manager of Wholesale Client Services |  |  |  |
| References | TP: N/A | TNP: 16.2 thru 16.8 & 3.7.1 |  |

### MP11 - MP Registration Activities – Revised by TPTF on 12/3/07

| Reported By: MP & ERCOT |  |  | EDS: Registration |
| --- | --- | --- | --- |
| Target Completion: EDS 3 - Registration EDS Trial Preparation Milestone plus 14 days |  |  |  |
| Category: Registration and Qualification |  |  |  |
| Metric Description: This metric shall measure whether Market Participants have performed the tasks outlined in the Registration & Qualification Guide . |  |  |  |
| Background: The intent of this metric is that ERCOT has all registration related data for all market participants intending to participate in the Nodal Market on record. |  |  |  |
| Criteria: The Readiness Team will review data provided by the Registration and Qualification Coordinator tracking the ERCOT/MP registration activities. MP Readiness will be achieved when the Registration checklist is completed by Client Services and the market participant Accountable Executive and Authorized Representative are notified by ERCOT via email. MP Registration Checklists Completed = Number of MPs Intending to Participate in Nodal Market September 2007 Targets: - measure completion of the Resource Asset Registration Form (RARF) by Resource Entities. - Individual Resource Entities will be measured on their successful completion of the RARF for their generation resources - Market will be measured by percent received % of Generation Participation >= 95% RAG Rules - MPs Red – Failure to submit documentation Amber – Incomplete form Green – All forms received RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria - measure completion of the Ancillary Service Attestation by QSEs with Resources. - Individual QSEs will be measured on their successful completion of the Attestation. Since this is voluntary at this time, QSEs will not be assessed ‘red’ - Market Segment will be measured by percent received % of Ancillary Generation >= 95% RAG Rules - MPs Amber – Incomplete form Green – All forms received RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria Note: additional targets will be added as registration and qualification deadlines arise. These targets will be added via the change control process. November 2007 Targets measure completion of the Resource Asset Registration Form (RARF) by Resource Entities. - Individual Resource Entities will be measured on their successful completion of the RARF for their generation resources - Market will be measured by percent received % of Generation Participation >= 95% RAG Rules - MPs Red – Failure to submit documentation Amber – Incomplete form Green – All forms received RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria Metric will be updated in tool to reflect these scores beginning 11/16/2007. On 12/21/2007, all incomplete forms will be considered RED. April 2008 Targets measure completion of the Resource Asset Registration Form (RARF) by all Generation and Load Resource Entities. - Individual Resource Entities will be measured on their successful completion of the RARF for their Resources - Market will be measured by percent received % Participation >= 100% RAG Rules - MPs Red – Failure to submit documentation Amber – Incomplete form Green – All forms received RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria Metric will be updated in tool to reflect these scores beginning 3/15/2007. On 5/1/2007, all incomplete forms will be considered RED. |  |  |  |
| Reporting Data Sources: Registration Checklists / ERCOT Manager of Wholesale Client Services |  |  |  |
| References | TP: N/A | TNP: 16.2 thru 16.8 & 3.7.1 |  |

### MP12 - MP Completes EDS-3 Related Training

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: First - EDS 3 - 6 Month LMP Posting Major Milestone less 30 days Second - Market Open less 30 Days |  |  |  |
| Category: Training |  |  |  |
| Metric Description: Market Participants complete the applicable training modules associated with EDS-3. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants participating in EDS-3 and market open have adequate knowledge of the Nodal Market to participate . |  |  |  |
| Criteria: ERCOT Training will dashboard MP training progress against the commitments provided by each Accountable Executive. Progress will be reported to the Accountable Executive and the readiness evaluators (TPTF, TAC, and the ERCOT Board). The Metric will be met for the market when training readiness targets for each Market Participant type as shown below have been met for EDS-3 and market open based on the applicable training for each Market Participant type. The Readiness Team will review the following courses: ERCOT Nodal 101 (The Basics); Basic TrainingProgram; Economics of LMP, Non-Opt in Entity NOIE (QSE) Operations; Load Serving Entity 201. Metric Completion Document Completed and Signed Off by 100 percent of Accountable Executives in accordance with the Market Participant Training Readiness Document RAG Rules Red – Not meeting criteria (<90 percent) Amber – within 10 percent of all criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: Accountable Executive Metric Signoff Document /Training Readiness Document |  |  |  |
| References | TP: 6.1(f) | TNP: N/A |  |

### MP13 - MP Completes EDS-4 Related Training

| Reported By: MP & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: First - EDS 4 – Start of 168 hour test less 20 days Second - Market Open less 30 Days |  |  |  |
| Metric Description: Market Participants complete the applicable training modules associated with EDS-4. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants participating in EDS-4 and market open have adequate knowledge of the Nodal Market to participate . |  |  |  |
| Criteria: ERCOT Training will dashboard MP training progress against the commitments provided by each Accountable Executive. Progress will be reported to the Accountable Executive and the readiness evaluators (TPTF, TAC, and the ERCOT Board). The Metric will be met for the market when training readiness targets for each Market Participant type as shown below has been met for EDS-4 and market open based on the applicable training for each Market Participant type. The Readiness Team will review the following courses: Generation 101, 201, 301; Market Settlements; Transmission 101; CRRs. PCRRs, and Supply Hedging; Network Model Management; Market Information Systems, ERCOT 101 for Wind Generation. Self Reported – Training complete according to MP plan and Signed Off by Accountable Executive in accordance with the Market Participant Training Readiness Document MP RAG Rules Green = Complete according to MP plan Amber = Not complete by 168 hour test start Red = Not complete 30 days prior to market open |  |  |  |
| Reporting Data Sources: Accountable Executive Metric Signoff Document / Training Readiness Document |  |  |  |
| References | TP: 6.1(f) | TNP: N/A |  |

### MP14 - MP EDS-2 Trials Participation

| Reported By: QSE with Resource, TSP & ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 – Start of Release 4 plus 14 days |  |  |  |
| Category: Trials Participation |  |  |  |
| Metric Description: This metric evaluates the level of TSP and QSE market participant participation in the EDS 2 Trial. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants have the ability to access telemetry and State Estimator performance reports and are actively participating in the NOMCR process. |  |  |  |
| Criteria: The Readiness Team will review documentation that an adequate number of MPs by market segment representing an adequate percent of overall load have reviewed performance reports on MIS and confirmed ability to access those reports and submitted modifications through the NOMCR process. # of TSP and QSE MPs Participating in Trial >=95% of TSP and QSE MPs intending to participate in Nodal Market % of Load and Generation Participation >= 95% AND % of Load Serving Entities and Resource Entities Participation >= 95% # of TSP and QSE MPs Participating in Trial accessing Telemetry SE Performance Report >= 75% # of TSP and QSE MPs Participating in Trial participating in the NOMCR process >= 75% RAG Rules - MPs Red - Not participating in trials Amber –Participating, but not in NOMCR Green – Meeting criteria RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: EDS 2 Trials Log / ERCOT EDS 2 PM |  |  |  |
| References | TP: 5.4.1 | TNP: 3.10.8, 3.3.2.1, 3.10.7 |  |

### MP15 - MP EDS-3 Participation

| Reported By: MP & ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: EDS 3 |  |  |  |
| Metric Description: This metric evaluates the level of QSE market participant participation in EDS 3.6 and the level of CRR market participant participation in EDS 3.7. |  |  |  |
| Background: The intent of this metric is to ensure that SCED, LFC and CRR are functional at the market level. |  |  |  |
| Criteria: The Readiness Team will review documentation that all MPs have participated in the CRR auction testing and have participated in Generation Control Testing. # of QSE Participating >representing 98% of Generation Resources intending to participate in Nodal Market AND # of CRR Account Holders Participating participating in CRR Auction Testing >= 90% MP RAG Rules Green = Complete Amber = Participated, but issues exist less than 1 month old Red = Did not complete or outstanding issues over 1 month old |  |  |  |
| Reporting Data Sources: EDS 3 Log / ERCOT EDS 3 PM |  |  |  |
| References | TP: 5.4.8 | TNP: 6.4.4, 6.5.7.1.12, 6.5.7.1.13 |  |

### MP17 - MP Qualification Activities

| Reported By: QSE, CRR Account Holder & ERCOT |  |  | EDS: Registration |
| --- | --- | --- | --- |
| Target Completion: EDS 4 168 Hour Test Major Milestone less 90 days, less 30 days, less 14 days |  |  |  |
| Metric Description: This metric will measure the completion of specified qualification requirements to support EDS Testing Activities and particpate in NODAL market as documented by ERCOT’s Wholesale Client Services team. |  |  |  |
| Background: The intent of this metric is to measure Market Participant ability to perform specific market and operational functions required for qualification approval of all required market-participation. This metric is not intended to be used for final qualification of Market Participants to participate in the market which is provided under a separate ERCOT process. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that market participants are qualified to engage in the market. Target 1; Target 2; Target 3. 90% (90 days); 95% (30 Days); 100% (14 days). MP Qualification = Target % of number of MPs Intending to Participate in the market based on the following timeline: 90 percent 90 days prior to the EDS 4 168 Hour Test Major Milestone 95 percent 30 days prior to the EDS 4 168 Hour Test Major Milestone 100 percent 14 days prior to the EDS 4 168 Hour Test Major Milestone MP RAG Rules Green = Qualified Amber = Qualifying, issues exist Red = Not qualified 14 days prior to 168 hour test |
| Reporting Data Sources: ERCOT Manager of Wholesale Client Services |  |  |  |
| References | TP: N/A | TNP: 16.1, 16.2 |  |

# Commercial Operations Metrics

# Congestion Revenue Rights Metrics

### CRR2 - Develop TCR to CRR Transition Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 270 days |  |  |  |
| Metric Description: ERCOT will provide detailed TCR to CRR plan describing each step of the transition. |  |  |  |
| Background: The intent of this metric is to verify the existence and publication of the TCR to CRR transition Plan. |  |  |  |
| Criteria: The Readiness Team will review, from a public source, the TCR to CRR transition plan including rebate, timing and other CRR details of interest. Readiness will be achieved when the Readiness Team will be provided with documentation that verifies that the TCR to CRR transition plan has been created, updated, and updates approved by TAC. TCR to CRR Transition Plan exists, updated according to schedule, and approved by the TAC |  |  |  |
| Reporting Data Sources: TCR to CRR Transition Plan / ERCOT CRR PM |  |  |  |
| References | TP: N/A | TNP: |  |

### CRR3 –Operation of Monthly CRR Auction and Allocation

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: EDS-3 - Release 7 complete milestone |  |  |  |
| Metric Description: ERCOT shall execute a test monthly allocation and auction of Congestion Revenue Rights for market participants prior to Nodal market launch during Market Trials. |  |  |  |
| Background: This intent of this metric is to verify ERCOT's ability to facilitate, execute and report on a Monthly CRR Auction. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that a Congestion Revenue Rights Monthly auction produced a solution, allocated revenue rights to potential CRR account holders and produced accurate results for statistical sampling of bids as determined by the CRR team.. Readiness will be met when the CRR Monthly auction solves within acceptable timelines and when Monthly CRRs results are distributed to applicable account holders. Monthly CRR Trial Results distributed to auction participants according to schedule defined in CRR Handbook = 100% Allocated Revenue Rights in statistical sample = 100% accurate RAG Rules - Accuracy Green – 100% accuracy Amber – 97% <= accuracy < 100% OR Red – Criteria Not Met (less than 97%) RAG Rules – Schedule Green – Meeting or better than schedule Red – not meeting schedule |  |  |  |
| Reporting Data Sources: Extract from CRR Database / ERCOT EDS 3 PM |  |  |  |
| References | TP: 5.4.5 (1) | TNP: |  |

### CRR4 - Implement TCR to CRR Transition Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 120 days |  |  |  |
| Metric Description: ERCOT shall Implement the approved TCR to CRR Transition Plan to assign rights for the Nodal Market Go-Live. |  |  |  |
| Background: The intent of this metric is to ensure that there is an acceptable TCR to CRR Transition Plan. |  |  |  |
| Criteria: The Readiness Team will be notified of the implementation of the approved TCR to CRR Transition Plan. Readiness will be achieved when the Readiness Team is provided with documentation that verifies that the TCR to CRR transition plan previously described in Metric CRR2, "Develop TCR to CRR TransitionPlan" has been implemented. TCR to CRR Transition Plan Business Procedures have been implemented |  |  |  |
| Reporting Data Sources: Notification of the TCR to CRR Transition Plan Implementation / ERCOT CRR PM |  |  |  |
| References | TP: 6.1 (i) | TNP: |  |

### CRR5 - Operation of Annual CRR Auction and Allocation

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: EDS-3 – Release 7 Completion |  |  |  |
| Metric Description: ERCOT shall execute a test annual allocation and test auction of Congestion Revenue Rights for market participants. |  |  |  |
| Background: This intent of this metric is to prove ERCOT's ability to facilitate, execute and report on an Annual CRR Auction. This metric will correspond to testing defined in the CRR handbook. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that a Congestion Revenue Rights Annual auction produced a reasonably accurate solution, allocated revenue rights to potential CRR account holders and produced accurate results for participants in statistical sample defined by CRR team. Readiness will be met when the CRR Annual Auction solves within acceptable timelines. Readiness will be met when Annual CRRs results are distributed to applicable account holders. Annual CRR Auction produces a reasonably accurate solution within = timeline defined in CRR requirements Annual CRR Trial Results distributed to participants and participants able to view and download results = 100% Auction results in statistical sample are accurate = 100% RAG Rules - Accuracy Green – 100% accuracy Amber – 97% <= accuracy < 100% OR Red – Criteria Not Met (less than 97%) RAG Rules – Schedule Green – Meeting or better than schedule Red – not meeting schedule |  |  |  |
| Reporting Data Sources: Extract from CRR Database / ERCOT EDS 3 PM |  |  |  |
| References | TP: 5.4.5 (1) | TNP: |  |

# ERCOT Internal Metrics

### E0 - ERCOT Engagement

| Reported By: ERCOT |  |  | EDS: 1, 2,3,4 |
| --- | --- | --- | --- |
| Target Completion: Quarterly starting Q3 2007 |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT Transition Sponsors complete the NODAL Self-Reporting Questionnaire for ERCOT. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT is engaged in Nodal preparations. |  |  |  |
| Criteria: The Readiness Team will review self reporting from each ERCOT Transistion Sponsor indicating their level of engagement in Nodal preparation, mobilization and delivery. Readiness will be achieved when ERCOT Transistion Sponsors have submitted Completion Review Documents outlining their status related to defined activities. Questions will be tracked in three categories – Initiation, Mobilization, and Delivery. Questions will target specific areas of concern such as budgets, staffing plan and implementation, training plan and completion, procedure development, and technology. RAG Rules 2007Q3 Red – No Response by deadline Amber – Survey contains negative responses Green – Survey contains all affirmative responses 2007Q4 and beyond Red– Survey contains negative responses Amber – Not Applicable Green – Survey contains all affirmative responses |  |  |  |
| - Reporting Data Sources: ERCOT, inc. Self Reported |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E1 - ERCOT Staff Completes Training

| Reported By: ERCOT |  |  | EDS: 2,3,4 |
| --- | --- | --- | --- |
| Target Completion: Start of EDS 2,3,4, Go Live Activities less 14 days |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT Staff Completes required training modules by area of expertise and job responsibilities. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT staff has the ability to facilitate the Nodal Market. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT Staff have completed the required training. Readiness will be achieved when ERCOT staff have completed required training. Actual Passing Participation by Course for Required Training by EDS/Go Live = 100% - This metric will be measure continuously with updates published in conjunction with planned EDS milestones. - Measurement will include: - Division and Department Head approval of plan - Progress against plan - Division and Department Head sign-off of training accomplishments for each EDS RAG Rules Red – Failure to meet plan Amber – Behind Training Schedule Green – Meeting Plan |  |  |  |
| Reporting Data Sources: Learning Management System / ERCOT Readiness PM - ERCOT will plan which training modules individuals are required to take and will track progress against the plan. - ERCOT will publish accomplishments against the plan. |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E3 - Validate Telemetry/SE EDW/ Data Accuracy

| Reported By: MP & ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 – Release 3 complete |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT shall provide access to accurate operational data via the EDW for both ERCOT Operations and Market Participant. |  |  |  |
| Background: The intent of this metric is to ensure access to accurate data via the EDW. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that operations data access is available via the data warehouse. Readiness will be achieved when source system data is accurately represented and the necessary reports are available in the EDW reports and is accessible by ERCOT Operations and Market Participants. Integration Testing Team attests to the successful completion of all test scripts related to the Operations component of the EDW with no Severity Level 1 defects; and, Operations confirms ability to access EDW reports and Telemetry / SE data accuracy; and Market Participants confirm ability to access EDW/MIS reports and Telemetry / SE data accuracy. RAG Rules Red – Not meeting criteria at end of November 2007 Amber – Not meeting criteria at end of October 2007 Green – meeting criteria |  |  |  |
| Reporting Data Sources: Notification from Integration Test Team Attesting to EDW accuracy / Notification from Operations Attesting EDW Access / ERCOT EDS 2 PM |  |  |  |
| References | TP: N/A | TNP: 17.3.2 |  |

### E5 - Nodal SAS 70

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 45 days |  |  |  |
| Metric Description: ERCOT shall prepare for the transition from current to nodal SAS 70 requirements by identifying those control objectives which must be changed or modified. NODAL shall Meet SAS 70 requirements |  |  |  |
| Background: It is the intent of this metric to ensure that SAS 70 Audits can be accomplished in the Nodal Market by revising the control objectives for Nodal operations. |  |  |  |
| Criteria: The Readiness Team will review documentation that the current to nodal transition SAS 70 control objectives have been updated for nodal operations. Control Objectives Updated = 100% of Control Objectives identified as requiring a Nodal update ERCOT meets SAS 70 Requirements |  |  |  |
| Reporting Data Sources: Control Objectives Log revision history / ERCOT Readiness PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E6 - Develop Nodal Operating Guides

| Reported By: ERCOT |  |  | EDS: 3,4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Less 360 days |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT shall develop Nodal Operating Guides to direct Market Participants on the daily operation of the Texas Nodal Market and Grid. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has provided the Market Participants with the information required to operate the Texas Nodal Market and Grid. |  |  |  |
| Criteria: The Readiness Team will receive documentation that the creation and posting of approved Nodal Operating Guides has occurred. Readiness will be met when the Operating Guides have been posted to the MIS and approved by ROS and TAC. - Traceability of Operating Guidelines to Protocols (50 percent) - Progress against plan (50 percent) - August 22nd – OWG Review of additional comments - September 12th – Impact Analyses due - September 13th – ROS Meeting to consider NOGRR001-017 and IAs - October 5th – TAC Meeting to consider NOGRR001-017 and IAs RAG Rules Red – Failure to Meet Plan and Provide Full Traceability by February, 2008 Amber – Meeting Either Schedule or Traceability, but Not Other Green – On Schedule and Traceability Targets |  |  |  |
| Reporting Data Sources: Operating Guides / ERCOT Readiness PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E8 - ERCOT Staffed for Texas Nodal Operations

| Reported By: ERCOT |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - Full Nodal Functionality 24*7 Operations Major Milestone less 60 days |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT will ensure the appropriate staffing levels required to execute the nodal market. In addition, the roles and responsibilities have been appropriately defined for nodal personnel. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT is appropriately staffed to support Nodal Operations as approved by the PUCT. |  |  |  |
| Criteria: Each impacted Director or VP is responsible for conducting a sizing and alignment analyses for their area as a part of the overall ERT project. Each department will develop their respective supporting documentation and readiness assessment. The Readiness Team will view the analysis results for each department and verify completion of the sizing and alignment analysis and the development of the corresponding staffing plan. Readiness will be achieved upon the completion of Sizing and Alignment Analysis for each Department and Departmental Staffing Plans and the execution of those plans. ERCOT will publish accomplishments against the plan. This metric will be measure continuously with updates published in conjunction with planned EDS milestones. - Sizing and Alignment Analysis completed for each impacted department - Creation of Org. Charts (Q22007) - Division and Department Head approval of deliverables - Allocation of appropriate funding to staff the organization (Q12008) - Staffing to plan (Q42008) |  |  |  |
| Reporting Data Sources: Sizing and Alignment Analysis for each Department / Departmental Staffing Plans / ERCOT Readiness PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E9 - Develop TN Procedures

| Reported By: ERCOT |  |  | EDS: 2,3,4 |
| --- | --- | --- | --- |
| Target Completion: Go-Live less 60 days |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT shall develop it’s internal processes and procedures supporting the Texas Nodal Market. |  |  |  |
| Background: It is the intent of this metric to have ensure that the processes and procedures necessary to run the Nodal market are in place. |  |  |  |
| Criteria: The Readiness Team will review documentation that ERCOT has created the processes and procedures necessary for operating the Texas Nodal Market. Readiness will be achieved when the processes supporting the Nodal Market have been completed. - Traceability of procedures to Protocols (50 percent) - Progress against plan (50 percent) RAG Rules Red – Failure to Meet Plan and Provide Full Traceability Amber – Meeting Either Schedule or Traceability, but Not Other Green – On Schedule and Traceability Targets |  |  |  |
| Reporting Data Sources: ERCOT Process/ Procedure Inventory / ERCOT Readiness PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E12 - MIS Compliance Test

| Reported By: ERCOT |  |  | EDS: |
| --- | --- | --- | --- |
| Target Completion: 168 hour test minus 30 days |  |  |  |
| Metric Description: This metric will measure the completion and implementation of a compliance plan to verify the degree to which protocol requirements for MIS Public, Secure, and Certified areas are met. |  |  |  |
| Background: It is the intent of this metric to ensure the functionality and operability of the Secure, Public and Certified areas of the Market Information System. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT has successfully completed a MIS Compliance Test. Readiness will be met when the completion of the MIS Compliance Test has been accomplished. MIS Compliance Test Successfully Posted according to Protocol Requirements |  |  |  |
| Reporting Data Sources: MIS Compliance Test Plan / MIS Compliance Test Results / ERCOT MIS PM |  |  |  |
| References | TP: 5.4.13 | TNP: 12 & 4.4 & 9.1.3 |  |

# Energy Management Operations Metrics

### EMO1 - Network Security Analysis & Transmission Constraint Management

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 - Release 3 complete plus 60 days |  |  |  |
| Metric Description: ERCOT shall Validate Transmission Constraint Management Functions to include the accurate identification of constraints, the Network Security Analysis Process, the security analysis sequence, operation of Dynamic Ratings processor, Special Protection Scheme (SPS), Remedial Action Plans (RAPs), and Load Rollover. |  |  |  |
| Background: The intent of this metric is to verify the ability of ERCOT manage constraints in a reliable economical manner. |  |  |  |
| Criteria: The Readiness Team shall review documentation that the transmission constraint management functions include the accurate identification of constraints, the Network Security Analysis process, the security analysis sequence and the operation of Dynamic Ratings processor, Special Protection Scheme (SPS), Remedial Action Plans (RAPs), and Load Rollover. Readiness will be achieved when the number of Over Load and Voltage limit alarms are equivalent to the number of actual Over Load and Voltage violations. Readiness will be achieved with the RTCA has been run for every element in system. Number of n-1 contingency violations = Number of Load & Voltage Limit Alarms Sum of N-1 Analyzed = Sum of Elements |  |  |  |
| Reporting Data Sources: SCADA Extract/ EMS Extract / Limit Alarm Log / Extract from Real Time Contingency Analysis Engine (RTCA) / ERCOT EDS 2 PM |  |  |  |
| References | TP: 5.4.3 | TNP: 6.5.7.1 |  |

### EMO2 - Verify Voltage Support Functionality

| Reported By: MP & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Full Nodal Functionality Milestone |  |  |  |
| Metric Description: This metric will verify that ERCOT has a functioning process to manage Voltage Support Services (VSS) in the Nodal Market. |  |  |  |
| Background: It is the intent of this metric to ensure that ERCOT can manage the voltage of the system in the Nodal Market through the use of communicating voltage profile requirements to QSEs and TSPs and monitoring of voltages to assure compliance to Protocols. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the proper functionality of the Voltage Support Service. Readiness will be met when a test of the Voltage Support Service has been completed. Voltage Profiles are created and communicated to QSEs & TSPs Ercot monitors voltage and can confirm compliance to protocols during EDS. |  |  |  |
| Reporting Data Sources: Voltage Profiles by QSE and TSP / EMS Extract of Voltage Telemetry Values corresponding to Voltage Profile Locations / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: 3.15(2) |  |

### EMO5 - Verify ACE Performance

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: EDS-3 LFC Major Milestone Start + 30 days |  |  |  |
| Metric Description: This metric will measure the comparison of the Area Control Error (ACE) calculation between the Nodal control system and existing control system, for accuracy for seven days. |  |  |  |
| Background: It is the intent of this metric to verify that the Nodal ACE Calculation is accurate by comparing it to the existing calculation tool in the Zonal system. |  |  |  |
| Criteria: The Readiness Team will review documentation that the accuracy of calculation of ACE in the TXMACS has been verified. Readiness will be met when the comparison of the Nodal generated raw ACE and processed ACE tracks with the existing (Zonal) ACE for seven consecutive days. TXMACS raw ACE =Current Operations raw ACE for seven consecutive days TXMACS Processed ACE are in control as compared to the Current Operations Processed ACE for seven consecutive days |  |  |  |
| Reporting Data Sources: EMS Extract of existing ACE and Nodal Ace / ERCOT EDS 3 PM |  |  |  |
| References | TP: 5.4.8 (2) | TNP: 6.5.7.6.1 |  |

### EMO6 - QSE Response to Dispatch

| Reported By: MP & ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: EDS-3 Major Milestone LFC Testing + 60 days |  |  |  |
| Metric Description: This metric will ensure that ERCOT can send control signals to QSEs to verify generation control functions, verify that QSEs can receive control signals from LFC for Regulation and Updated Desired Generation from the Generation Sybsystem and that each QSE and its generation can respond to controls. Verify QSEs can operate independently on constant frequency control. |  |  |  |
| Background: It is the intent of this metric that all Generation Resources respond to ERCOT control signals the Generation Sub-system in order to maintain grid reliability. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT can send control signals to QSEs to verify Generation Control, LFC can maintain system frequency by balancing Generation Resources with the system load and that each QSE can respond to the control signals and also run independently on constant frequency control. Readiness will be met when the LFC Testing is complete. LFC Test results in stable frequency demonstrated by meeting NERC CPS1 and CPS2 requriements for the ERCOT System ERCOT can calculate and send correct base point signals QSE providing Regulation Service can successfully run on constant frequency control QSE Resources respond to Regulation Dispatch Instructions QSE Resources respond to Updated Desired Based Point Dispatch Instructions. Verify QSE ability to receive Responsive Reserve Deployment Instructions from ERCOT and their ability to update their Responsive Reserve Schedule RAG Rules Green = frequency in control Red = frequency not in control |  |  |  |
| Reporting Data Sources: Results of LFC Test / Results of Resource Base Point Response Test / Resource Frequency Run Test / ERCOT EDS 3 PM |  |  |  |
| References | TP: 5.4.8 (2) | TNP: 6.5.7.6 & 8.1 |  |

### EMO7 - Verify Load Forecast Accuracy

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 9 Start + 120 days |  |  |  |
| Metric Description: This metric will determine the ability of the Short Term Load Forecast(STLF) and Medium Term Load Forecast(MTLF) to meet accuracy standards. |  |  |  |
| Background: It is the intent of this metric to ensure that the STLF and MTLF meet standard accuracy performance measures in order to determine the amount of required generation required for each hour of the day. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that the Seven-Day Load Forecast and the 36-Month Load Forecast accuracy is within prescribed limits during market trials. Readiness will be met when the Seven-Day Load Forecast is operating to existing standards. Readiness will be met when the 36-Month Load Forecast is operating to existing standards. Seven-Day Load Forecast is within accuracy limit of actual load 36-Month Load Forecast is within accuracy limit of actual load |  |  |  |
| Reporting Data Sources: EMS extract of Actual Load/ EMS extract of STLF / EMS extract of MTLF / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.2(2) | TNP: 3.12, 3.13, 4.2.2 & 8.2(2)© |  |

### EMO9 - Validate Zonal and Nodal Security Analysis Results

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS2 Release 3 plus 14 days |  |  |  |
| Category: Energy Management Operations |  |  |  |
| Metric Description: Verify that Security Analysis Results between the Zonal and Nodal Systems are consistent with one another. |  |  |  |
| Background: The intent of this metric is to provide a litmus test of the Nodal Systems Security Analysis capability. |  |  |  |
| Criteria: The Readiness Team will verify that Zonal and Nodal common constraints are consistent with reasonably comparable results. Readiness will be achieved when constraints are comparable. The set of Zonal Security Violations = The set of Nodal Security Violations Zonal and Nodal Element Security Violations are within 10% of one another as measured monthly RAG Rules Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: SCED / Transmission Constraint Manager (TCM) / ERCOT EDS 2 PM |  |  |  |
| References | TP: 5.4.1 (2)(b) | TNP: N/A |  |

### EMO10 - Network Operations Model and SE Performance

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 - Release 3 complete plus 60 days |  |  |  |
| Metric Description: ERCOT shall verify that all protocol required modeling of Generation and Loads are correctly mapped in the Network Operations Model and that all generation and substation load is either telemetered directly or able to be estimated by the State Estimator. |  |  |  |
| Background: The intent of this metric is to verify the ability of ERCOT construct a network model according to protocols requirements and estimate all genration and load in the ERCOT System. Protocols require minimium SE performance requirements and that SE Performance metrics to be developed and met. |  |  |  |
| Criteria: The Readiness Team shall review documentation that the transmission network operations model is meets protocol requirements. Readiness will be achieved with the TPTF approves the Network Operations Model for nodal go-live. SE meets performance requriements as identified in the State Estimator Standard 100 percent of load is modeled per protocols 100 percent of genration as identified in RARF submissions is modeled per protocol RAG Rules Green - >= 99 percent modeled Yellow – between 90 and 99 percent Red – less than 90 percent |  |  |  |
| Reporting Data Sources: SCADA Extract/ SE Performance logs/ TPTF Approval |  |  |  |
| References | TP: | TNP: 3.10 |  |

### EMO11 – Operating Personnel and Facilities Readiness

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go-Live less 150 days |  |  |  |
| Metric Description: ERCOT dispatch operations personnel are assigned to operate nodal systems 7x24 on site and operater consoles deployed in dispatch control rooms operating nodal systems software 7 x 24 in parallel with current operations. Verification of transmisison and generation parameters with synchronized zonal operations. |  |  |  |
| Background: The intent of this metric is to measure the readiness of ERCOT Energy management system personnel readiness to operate in a nodal environment. |  |  |  |
| Criteria: The Readiness Team shall review documentation that the transmission network operations and generation control functional capability is simliar to or superior to the zonal system. Readiness will be achieved when personnel assigned to man shift work and operating consoles are in place and operational. Dispatch Operations Personnel report by survey that the nodal system provides functionality in grid operations and LFC similar to or superior to the zonal market functionality. EMO Personnel Assigned = 100% required Control Room Operator Consoles in place at Taylor and Austin Control Rooms Affirmative Response from System Operators > 95% RAG Rules Green – Criteria Met Red – Criteria Not Met |  |  |  |
| Reporting Data Sources: Readiness team/ Survey of Control Room Opertors |  |  |  |
| References | TP: 6.0 | TNP: |  |

# Network Model Management Metrics

### N1 - ERCOT Telemetry Alarm Processing

| Reported By: MP & ERCOT(EDS 1 Team) |  |  | EDS: 1 |
| --- | --- | --- | --- |
| Target Completion: EDS 1 - Release 1 Complete plus 14 days |  |  |  |
| Category: Network Model Management |  |  |  |
| Metric Description: ERCOT initiates alarms for Limit Violations,& Status Changes. |  |  |  |
| Background: The intent of this metric is to ensure that control operators are aware of relevant EMS alarms. |  |  |  |
| - Criteria: The Readiness Team will review the results of the Limit, Status and other EMS Alarm Tests. Readiness will be achieved when alarms are generated from the Limit, Status and other EMS Tests and the attributes of the alarms are correct. . Load / Rating > Alarm set point Change of Status inititiates a Status Alarm RAG Rules Red – Failure to meet criteria Amber – Within 10 percent of meeting criteria Green – Meeting criteria |  |  |  |
| Reporting Data Sources: Alarm Log / ERCOT EDS 1 PM |  |  |  |
| References | TP: 5.4.1 (2)(f),(g) | TNP: |  |

### N2 - ERCOT Telemetry/ICCP System Failover

| Reported By: MP & ERCOT |  |  | EDS: 1, 4 |
| --- | --- | --- | --- |
| Target Completion: Local Test - EDS 1 - Release 2 plus 14 days High Availability Test – EDS 4 Release 8 start plus 14 days |  |  |  |
| Category: Network Model Management |  |  |  |
| Metric Description: Verify that all ERCOT telemetry failover criteria are met. |  |  |  |
| Background: The intent of this metric is to ensure that the ERCOT telemetry system is stable in a redundant state. |  |  |  |
| Criteria: The Readiness Team will verify that telemetry failover thresholds are met by ERCOT. Readiness will be achieved when the ERCOT has passed a simulated failover test. Failover testing will occur in two phases. The first test will occur as part of EDS 1 and will be a local failover only. The second test will occur in conjunction with EDS 4 and will test high availability and site-to-site failover. Server Fail Over <=5 Minutes Com Link Failover <= 30 Seconds RAG Rules Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: EDS-1 Dashboard Report / ERCOT ICCP EMS Logs / ERCOT EDS 1 PM / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.1 (2)(k) | TNP: 3.10.7.4, 6.4.5(1) & 8.1.2 |  |

### N3 - Validate SE Performance and Accuracy

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 – Release 3 complete |  |  |  |
| Category: Network Model Management |  |  |  |
| Metric Description: Validate State Estimator performance as the time to reach a valid solution and availability as the percent of time the SE is capable of reaching a solution within accuracy limits defined by TAC approved SE standard. |  |  |  |
| Background: The intent of this metric is to prove the State Estimator meets stated performance criteria for Cold Start and Tracking mode and maintains a sufficient level of availability so as to provide rapid response to changing system conditions. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that the solution time and availability of the state estimator each pass a threshold value. These criteria will be kept current with the Texas NODAL Market State Estimator Standards. RAG Rules Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: State Estimator Statistics from MIS Secure Area / ERCOT EDS 2 PM |  |  |  |
| References | TP: 5.4.2 (2) | TNP: 3.10.9.1, 3.10.9.2 & 8.2(2)(a)(vi) |  |

# Market Operations Metrics

### MO4 - Verify SCED Execution Quality

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: Go Live |  |  |  |
| Category: Market Operations |  |  |  |
| Metric Description: ERCOT will determine the quality of each SCED execution by monitoring model performance (Real Time Duality Gap) and constraints provided by Transmission Constraint Management are managed by SCED. |  |  |  |
| Background: The intent of this metric is to ensure the quality of SCED execution . |  |  |  |
| Criteria: The Readiness Team will review documentation provided by model performance monitoring and constraint management. LMP is Greter than or equal to offer price at maximum limit (HDL) for a Resource which is dispatched at maximum limit (HDL) LMP is less than or equal to offer price at minimum limit (LDL) for a Resource which is dispatched at minimum limit (LDL) LMP is equal to offered price at dispatched MW point for a Resource which is dispatched within minimum limit (LDL) and maximum limit (HDL) (provided the offer price is not mitigated) Shadow Price is zero for a transmission constraint which is not binding Shadow Price is non-zero for a transmission constraint which is binding Base Points are between HDL and LDL RAG Rules Red – Not meeting criteria Amber – LMPs, Base Points, or Shadow Prices are within 3 percent of criteria as measured weekly Green – meeting criteria |  |  |  |
| Reporting Data Sources: Forecast Load / Sum of Base Points / LMPs / Offers of Marginal Resource / ERCOT EDS 3 PM |  |  |  |
| References | TP: 6.1(c.) | TNP: 6.5.7.1.12, 6.5.7.1.13 |  |

### MO5 - Generate LMPs for 6 months

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: – Go Live |  |  |  |
| Category: Market Operations |  |  |  |
| Metric Description: Generate LMPs for a six month period. The six month period commences on January 15, 2008. The metric will measure testing outcomes from November 1, 2007 through January 15, 2008. The LMPs should be calculated daily for each node and posted for Market Participant Access. |  |  |  |
| Background: The intent of this metric is to allow Market Participants and ERCOT to develop experience in the trending, prices and timing of Locational Marginal, Hub, and Zone Prices. |  |  |  |
| Criteria: The Readiness Team will review Publicly posted documentation that demonstrates that ERCOT has generated Nodal LMPs on a daily basis. Readiness will be met when LMPs are produced and posted at regular intervals during EDS 3. Use of price for previous interval will not be considered as a generated LMP and will count against criteria. November 1, 2007 through January 15, 2008 (testing period): - 95 percent SCED execution as evidenced by LMP posting times during testing periods - Consecutive Non Solves per day <=10 RAG Rules Red – Less than 92 percent Amber – Less than 95 percent and greater than or equal to 92 percent Green – Greater than or equal to 95 percent January 15 2008 and Beyond (24 / 7 EDS System Execution): - 100 percent SCED execution as evidenced by LMP posting times RAG Rules Red – Less than 97 percent Amber – Less than 99 percent or greater than or equal to 97 percent Green – Greater than or equal to 99 percent |  |  |  |
| Reporting Data Sources: ERCOT EDS 3 Reporting (Extract from LMP results Database) / EDS 3 PM |  |  |  |
| References | TP: 5.1(4) | TNP: N/A |  |

# Contingency Metrics

# IMM Metrics

# Overall Readiness Metrics